851 SW Sixth Avenue, Suite 260

Portland, Oregon 97204

503/229-0191  Fax 503/229-0443	COORDINATING AND PROMOTING EFFECTIVE PROTECTION AND RESTORATION

www.cbfwa.org	OF FISH, WILDLIFE AND THEIR HABITAT IN THE COLUMBIA RIVER BASIN

| DATE: | December 7, 2005 |
| --- | --- |
| TO: | Members Advisory Group (MAG) |
| FROM: | CBFWA staff |
| SUBJECT: | Update on FY 2006 Within Year Budget Adjustment Process/Quarterly Review Process |

The Budget Oversight Committee (BOG) met today and reviewed all pending within year project modification requests for the first quarterly review for fiscal year 2006.  All requests were sorted into categories.  Several projects were identified as “Reschedules” and will be directly addressed by BPA under the rules identified in the FY 2006 Budget Tracking and Modification Process.  Other projects were removed from the list because they will be addressed using the FY 2006 UPA placeholder identified in the FY 2006 Start of Year Budget or were non-budgetary requests.  The final list of Expense projects eligible for within year modification is included in Table 1.  One Capital project, Sockeye Salmon Captive Broodstock Program, is not included in the list, but is also a UPA project and will be addressed by BPA.

BPA will be identifying the available funds to support these requests on January 11, 2005.  Currently, it appears that BPA may identify as much as $2.5 million be made available for these requests, although no formal identification of funds has been made.  BPA and the NPCC will be seeking public comment on which of these projects should be prioritized to fit within the amount of funding identified in early January.  It is anticipated that the NPCC fish and wildlife committee will discuss these projects at their January meeting, and funding decisions will be made by the full Council in February.

CBFWA and our Members should decide if and how they may comment on this subject.

For questions please call Tom Iverson (503) 229-0191.

(h\w\mag\2005_1208\QtrRevlist.doc)

)

Table 1.  Current Within-Year project modification requests as of December 7, 2005 eligible for Quarterly Review Process approval by Northwest Power and Conservation Council.  For full details for each request see http://www.cbfwa.org/mods.

| Project ID | Project Title | Sponsor | Budget Impact |
| --- | --- | --- | --- |
| 198201301 | Coded Wire Tag Recovery | Pacific States Marine Fisheries Commission | $39,720 |
| 198331900 | New Marking and Monitoring Techniques for Fish | NMFS | $119,235 |
| 198805304 | Hood River Production Program - ODFW M&E | Oregon Department of Fish and Wildlife | $71,219 |
| 198906201 | Fish and Wildlife Program Implementation | CBFWA | $177,223 |
| 198909802 | Idaho Supplementation Studies 198909802 | Nez Perce Tribe | $70,784 |
| 199000500 | Umatilla Hatchery Monitoring and Evaluation | Oregon Department of Fish and Wildlife | $9,536 |
| 199004400 | Coeur d'Alene Tribe Habitat Restoration | Coeur d'Alene Tribe | $193,578 |
| 199104600 | Spokane Tribal Hatchery Operation and Maintenance | Spokane Tribe of Indians | $153,000 |
| 199500100 | Kalispel Resident Fish Project | Kalispel Tribe | $29,392 |
| 199601100 | Walla Walla Juvenile and Adult Passage Improvements | CTUIR | $550,000 |
| 199705100 | Yakima Side Channels | Yakama Nation -YFKP | $1,378,000 |
| 200000100 | Omak Creek Fish Passage | Colville Confederated Tribes | $50,000 |
| 200102900 | FORD HATCHERY O & M | WDFW | $16,933 |
| 200105500 | Assessment of three alternative methods of nutrient enhancement | NOAA | $113,750 |
| 200204500 | Coeur d'Alene Fish Habitat Acquisition | Coeur d'Alene Tribe | $500,000 |
| 200205100 | Crab Creek Subbasin Plan 2006 | Washington Department of Fish and Wildlife | $16,099 |
| 200302200 | Monitor/eval Okanogan Basin Natural Production | Colville Tribes | $174,086 |
| 200600600 | Regional HEP Team | CBFWA | $35,000 |
|  | Evaluation of the NPCC Mainstem Amendment on fisheries near Libby and Hungry Horse Dams, Montana | Montana Fish, Wildlife and Parks | $360,336 |
|  |  |  | $4,057,891 |