## Schedule
FY 2007-2009 Project Selection Processes
| May | June | July | August | September | October
ISRP Review of All Projects | June: Preliminary Review Due June 1; July: Feedback due to ISRP on July 14; August: Final ISRP Report Due August 31
Province Review Groups | June: Final Recommendations Due June 16
NPCC Fish and Wildlife Committee |  | Discuss issues in Rolling Issue Memo | Presentations/Discussion of ISRP and Province Recommendations | Project specific issues, Rolling Issue Memo | Project Recommendations approved
NPCC Full Council | October: Project Recommendations Adopted
CBFWA (potential strategies) | The MAG considers developing a process to guide CBFWA comment in the project selection process in two areas: A) Budget - Use of capital funds, Bridge funding, Remand process B) Prioritization issues - Consistency with the management objectives of agencies and tribes. 1) Should the MAG review the ISRP and provincial groups recommendations/comments and develops separate CBFWA comments? 2) Should the MAG forward a set of questions, following ISRP Review and provincial groups submittals, to the technical committee seeking a response? 3) Should the MAG recommend to the Members that the CBFWA should not engage in a review/comment. | CBFWA Meetings Members - June 6 MAG - June 20 | CBFWA Meetings Members - July 5 MAG - June 18 | CBFWA Meetings Members - August 2 MAG - August 15 Members - August 23-24 | CBFWA comment on NPCC draft recommendations CBFWA Meetings Members - September 6 MAG - September 19
|  |  | MAG 6/20 | MAG 6/20