## Table_i_Budget Summary
Table i_Summary of Funding for Co-manager Involvement
Year Expended
| Table ID | Budget Area | Labor | Travel | Other | Total | 2006 | 2007 / 2008
| 1 and 1A | Involvement of Affiliated HSRG Members
| 2 and 2A | Co-Manager Involvement and Participation, Steering Committee
| 5 and 5A | Co-Manager assistance and review of data and information, NOAA Hatchery Reform and Mitchell Act EIS (Fisheries Analysis) | 200000 | 48157 | 2200 | 250357 | 62926 | 187431
|  | Total | 502925 | 184758 | 10000 | 697683 | 228320.5 | 469362.5
[7 empty] | check | 697683

## Table_5_BudgetSum_ComanagerInvo
Table 5. DRAFT Budget Summary, Data and Information Review
Project Name: |  | NOAA Hatchery Reform and Mitchell Act EIS (Co-manager Involvement)
Contract Period:
Prepared by:
Date: 5/27/06
|  |  | Labor | [47 empty] | Travel | [6 empty] | Supplies / Equipment/ Printing |  |  |  | Budget Totals
| Task ID | Task Title | WDFW Employee 1 | WDFW Employee 2 | ODFW Employee 1 | ODFW Employee 2 | IDFG Employee 1 | IDFG Employee 2 | YN Employee 1 | YN Employee 2 | CTUIR Employee 1 | CTUIR Employee 2 | CTWSR Employee 1 | CTWSR Employee 2 | NPT Employee 1 | NPT Employee 2 | CCT Employee 1 | CCT Employee 2 | SBT Employee 1 | SBT Employee 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours | Labor Cost | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Field/Research Supplies/Equipment | Rent and Utilities | Supplies / Equipment / Printing | Labor | Travel | Supplies, Equip, Printing | TOTALS | 2006 | 2007 / 2008
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task A | HATCHERY REFORM, NEPA, POLICY SUPPORT AND INTERACTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -2000 | 0
| Task B | Implementation Full Project, Project Management, Basic Functions (Scope, Time, Cost, Quality) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task C | Implementation Full Project, Project Management, Facilitating Functions (HR, CIM, Risk, Procurement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | -515 | 0
| Task D | Implementation,Data, Information , Communications System Management (Plan developed in Tasks 4, 4A, 4B, 4C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task E | Implementation, Project Start-up, Kick-off Meeting (Science Group HSRG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task F | Bi-op Remand Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task G | USFWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task H | NPCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task I | Hatchery Review Process (Regions 1 and 2 Lower Columbia, Washington) | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 356 | 980 | 980 | 200 | 2516 | 200 | 0 | 0 | 200 | 8000 | 2516 | 200 | 10716 | 10716
| Task J | Hatchery Review Process (Region 3 Columbia Estuary, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 0 | 980 | 980 | 200 | 2160 | 200 | 0 | 0 | 200 | 8000 | 2160 | 200 | 10360 | 10360
| Task K | Hatchery Review Process (Region 4 and 5 Lower Columbia and Columbia Estuary OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 356 | 980 | 980 | 200 | 2516 | 200 | 0 | 0 | 200 | 8000 | 2516 | 200 | 10716 | 10716
| Task L | Hatchery Review Process (Region 6 Columbia Gorge, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 534 | 1920 | 1715 | 350 | 4519 | 100 | 0 | 0 | 100 | 24000 | 4519 | 100 | 28619 | 28619
| Task M | Prepare Recommendations Report (Regions 1-6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task N | Hatchery Review Process (Region 7 Columbia Gorge, OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 16000 | 0 | 0 | 445 | 640 | 980 | 200 | 2265 | 200 | 0 | 0 | 200 | 16000 | 2265 | 200 | 18465 |  | 18465
| Task O | Hatchery Review Process (Region 8 Columbia Cascade, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 2940 | 600 | 6795 | 300 | 0 | 0 | 300 | 24000 | 6795 | 300 | 31095 |  | 31095
| Task P | Hatchery Review Process (Region 9 Columbia Plateau, OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 2940 | 600 | 6795 | 300 | 0 | 0 | 300 | 24000 | 6795 | 300 | 31095 |  | 31095
| Task Q | Hatchery Review Process (Region 10 Columbia Plateau, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 0 | 0 | 3255 | 0 | 0 | 0 | 0 | 24000 | 3255 | 0 | 27255 |  | 27255
| Task R | Hatchery Review Process (Region 11 and 12 Mountain Snake Salmon and Clearwater, WA) | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 32000 | 1500 | 0 | 1246 | 2560 | 2940 | 600 | 8846 | 300 | 0 | 0 | 300 | 32000 | 8846 | 300 | 41146 |  | 41146
| Task S | Hatchery Review Process (Region 13 Blue Mountain, ID, WA, OR) | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 32000 | 1500 | 0 | 890 | 2560 | 2940 | 600 | 8490 | 400 | 0 | 0 | 400 | 32000 | 8490 | 400 | 40890 |  | 40890
| Task T | Prepare Recommendations Report (Regions 7-13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total Hours | 400 | 400 | 320 | 320 | 160 | 160 | 240 | 240 | 400 | 400 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
|  | Total Dollars | 20000 | 20000 | 16000 | 16000 | 8000 | 8000 | 12000 | 12000 | 20000 | 20000 | 8000 | 8000 | 8000 | 8000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3000 | 0 | 7832 | 16380 | 17395 | 3550 | 48157 | 2200 | 0 | 0 | 2200 | 200000 | 48157 | 2200 | 250357 | 62926 | 187431
[49 empty] | No of trips |  | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Field/Research Supplies/Equipment | Rent and Utilities | Supplies / Equipment / Printing | 700
|  |  | Title |  | Name |  | Rate / Hour | [49 empty] | 0 |  |  |  | 0 | 48157 |  | Check | 250357
|  | 33 | WDFW Employee 1 |  |  |  | 50 | [41 empty] | 20% | WDFW | [6 empty] | 0 |  |  |  | 0 |  |  | Sub detail | 0
|  | 34 | WDFW Employee 2 |  |  |  | 50 | [41 empty] | 16% | ODFW | [6 empty] | 0 |  |  |  | 0 |  |  |  | 250357
|  | 35 | ODFW Employee 1 |  |  |  | 50 | [41 empty] | 8% | IDFG | [6 empty] | 0 |  |  |  | 0
|  | 36 | ODFW Employee 2 |  |  |  | 50 | [41 empty] | 12% | YN | [6 empty] | 0 |  |  |  | 0
|  | 37 | IDFG Employee 1 |  |  |  | 50 | [41 empty] | 16% | CTUIR | [6 empty] | 0 |  |  |  | 0
|  | 38 | IDFG Employee 2 |  |  |  | 50 | [41 empty] | 8% | CTWSR | [6 empty] | 0 |  |  |  | 0
|  | 39 | YN Employee 1 |  |  |  | 50 | [41 empty] | 8% | NPT | [6 empty] | 0 |  |  |  | 0
|  | 40 | YN Employee 2 |  |  |  | 50 | [41 empty] | 4% | CCT | [6 empty] | 0 |  |  |  | 0
|  | 41 | CTUIR Employee 1 |  |  |  | 50 | [41 empty] | 8% | SBT | [6 empty] | 0 |  |  |  | 0
|  | 42 | CTUIR Employee 2 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 43 | CTWSR Employee 1 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 44 | CTWSR Employee 2 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 45 | NPT Employee 1 |  |  |  | 50 | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 46 | NPT Employee 2 |  |  |  | 50
|  | 47 | CCT Employee 1 |  |  |  | 50
|  | 48 | CCT Employee 2 |  |  |  | 50 | [44 empty] | 0
|  | 49 | SBT Employee 1 |  |  |  | 50
|  | 50 | SBT Employee 2 |  |  |  | 50 | [44 empty] | 0
|  | 51 | 0 |  |  |  | 0
|  | 52 | 0 |  |  |  | 0
|  | 53 | 0 |  |  |  | 0
|  | 54 | 0 |  |  |  | 0
|  | 55 | 0 |  |  |  | 0
|  | 56 | 0 |  |  |  | 0
|  | 57 | 0 |  |  |  | 0
|  | 58 | 0 |  |  |  | 0
|  | 59 | 0 |  |  |  | 0
|  | 60 | 0 |  |  |  | 0
|  | 61 | 0 |  |  |  | 0
|  | 62 | 0 |  |  |  | 0
|  | 63 | 0 |  |  |  | 0
|  | 64 | 0 |  |  |  | 0
|  | 65 | 0 |  |  |  | 0
|  | 66 | 0 |  |  |  | 0
|  | 67 | 0 |  |  |  | 0
|  | 68 | 0 |  |  |  | 0
|  | 69 | 0 |  |  |  | 0
|  | 70 | 0 |  |  |  | 0
|  | 71 | 0 |  |  |  | 0
|  | 72 | 0 |  |  |  | 0
|  | 73 | 0 |  |  |  | 0
|  | 74 | 0 |  |  |  | 0
|  | 75 | 0 |  |  |  | 0
|  | 76 | 0 |  |  |  | 0
|  | 77 | 0 |  |  |  | 0
|  | 78 | 0 |  |  |  | 0
[66 empty] | 450889 | 250357
387963

## Table_5A_Budget_Detail_CoManag
Table 5A. DRAFT / Detailed Budget, Data and Information Review
Project Name: |  | NOAA Hatchery Reform and Mitchell Act EIS (Co-manager Involvement)
Contract Period:
Prepared by:
Date: 5/27/06
|  |  | Labor | [47 empty] | Travel | [6 empty] | Supplies / Equipment/ Printing |  |  |  | Budget Totals
| Task ID | Task Title | WDFW Employee 1 | WDFW Employee 2 | ODFW Employee 1 | ODFW Employee 2 | IDFG Employee 1 | IDFG Employee 2 | YN Employee 1 | YN Employee 2 | CTUIR Employee 1 | CTUIR Employee 2 | CTWSR Employee 1 | CTWSR Employee 2 | NPT Employee 1 | NPT Employee 2 | CCT Employee 1 | CCT Employee 2 | SBT Employee 1 | SBT Employee 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Hours | Labor Cost | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Field/Research Supplies/Equipment | Rent and Utilities | Supplies / Equipment / Printing | Labor | Travel | Supplies, Equip, Printing | TOTALS | 2006 | 2007 / 2008
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | HSRG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task A | HATCHERY REFORM, NEPA, POLICY SUPPORT AND INTERACTION | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | -2000 | 0
| Task B | Implementation Full Project, Project Management, Basic Functions (Scope, Time, Cost, Quality) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task C | Implementation Full Project, Project Management, Facilitating Functions (HR, CIM, Risk, Procurement) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | -515 | 0
| Task D | Implementation,Data, Information , Communications System Management (Plan developed in Tasks 4, 4A, 4B, 4C) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task E | Implementation, Project Start-up, Kick-off Meeting (Science Group HSRG) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task F | Bi-op Remand Integration | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task G | USFWS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task H | NPCC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Task I | Hatchery Review Process (Regions 1 and 2 Lower Columbia, Washington) | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 356 | 980 | 980 | 200 | 2516 | 200 | 0 | 0 | 200 | 8000 | 2516 | 200 | 10716 | 10716
| Task J | Hatchery Review Process (Region 3 Columbia Estuary, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 0 | 980 | 980 | 200 | 2160 | 200 | 0 | 0 | 200 | 8000 | 2160 | 200 | 10360 | 10360
| Task K | Hatchery Review Process (Region 4 and 5 Lower Columbia and Columbia Estuary OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 8000 | 0 | 0 | 356 | 980 | 980 | 200 | 2516 | 200 | 0 | 0 | 200 | 8000 | 2516 | 200 | 10716 | 10716
| Task L | Hatchery Review Process (Region 6 Columbia Gorge, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 534 | 1920 | 1715 | 350 | 4519 | 100 | 0 | 0 | 100 | 24000 | 4519 | 100 | 28619 | 28619 |  | 60411
| Task M | Prepare Recommendations Report (Regions 1-6) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| Task N | Hatchery Review Process (Region 7 Columbia Gorge, OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 16000 | 0 | 0 | 445 | 640 | 980 | 200 | 2265 | 200 | 0 | 0 | 200 | 16000 | 2265 | 200 | 18465 |  | 18465
| Task O | Hatchery Review Process (Region 8 Columbia Cascade, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 2940 | 600 | 6795 | 300 | 0 | 0 | 300 | 24000 | 6795 | 300 | 31095 |  | 31095
| Task P | Hatchery Review Process (Region 9 Columbia Plateau, OR) | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 2940 | 600 | 6795 | 300 | 0 | 0 | 300 | 24000 | 6795 | 300 | 31095 |  | 31095
| Task Q | Hatchery Review Process (Region 10 Columbia Plateau, WA) | 80 | 80 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 24000 | 0 | 0 | 1335 | 1920 | 0 | 0 | 3255 | 0 | 0 | 0 | 0 | 24000 | 3255 | 0 | 27255 |  | 27255
| Task R | Hatchery Review Process (Region 11 and 12 Mountain Snake Salmon and Clearwater, WA) | 0 | 0 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 32000 | 1500 | 0 | 1246 | 2560 | 2940 | 600 | 8846 | 300 | 0 | 0 | 300 | 32000 | 8846 | 300 | 41146 |  | 41146
| Task S | Hatchery Review Process (Region 13 Blue Mountain, ID, WA, OR) | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 640 | 32000 | 1500 | 0 | 890 | 2560 | 2940 | 600 | 8490 | 400 | 0 | 0 | 400 | 32000 | 8490 | 400 | 40890 |  | 40890
| Task T | Prepare Recommendations Report (Regions 7-13) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
|  | Total Hours | 400 | 400 | 320 | 320 | 160 | 160 | 240 | 240 | 400 | 400 | 160 | 160 | 160 | 160 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000
|  | Total Dollars | 20000 | 20000 | 16000 | 16000 | 8000 | 8000 | 12000 | 12000 | 20000 | 20000 | 8000 | 8000 | 8000 | 8000 | 4000 | 4000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200000 | 200000 | 3000 | 0 | 7832 | 16380 | 17395 | 3550 | 48157 | 2200 | 0 | 0 | 2200 | 200000 | 48157 | 2200 | 250357 | 62926 | 187431
[49 empty] | No of trips |  | Air | Auto Rental | Auto Mileage | Lodging | Meals | Misc. | Travel Cost | Printing / Copies / Other | Field/Research Supplies/Equipment | Rent and Utilities | Supplies / Equipment / Printing | 700
|  |  | Title |  | Name |  | Rate / Hour | [49 empty] | 0 |  |  |  | 0 | 48157 |  | Check | 250357
|  | 33 | WDFW Employee 1 |  |  |  | 50 | [41 empty] | 20% | WDFW | [6 empty] | 0 |  |  |  | 0 |  |  | Sub detail | 0
|  | 34 | WDFW Employee 2 |  |  |  | 50 | [41 empty] | 16% | ODFW | [6 empty] | 0 |  |  |  | 0 |  |  |  | 250357
|  | 35 | ODFW Employee 1 |  |  |  | 50 | [41 empty] | 8% | IDFG | [6 empty] | 0 |  |  |  | 0
|  | 36 | ODFW Employee 2 |  |  |  | 50 | [41 empty] | 12% | YN | [6 empty] | 0 |  |  |  | 0
|  | 37 | IDFG Employee 1 |  |  |  | 50 | [41 empty] | 16% | CTUIR | [6 empty] | 0 |  |  |  | 0
|  | 38 | IDFG Employee 2 |  |  |  | 50 | [41 empty] | 8% | CTWSR | [6 empty] | 0 |  |  |  | 0
|  | 39 | YN Employee 1 |  |  |  | 50 | [41 empty] | 8% | NPT | [6 empty] | 0 |  |  |  | 0
|  | 40 | YN Employee 2 |  |  |  | 50 | [41 empty] | 4% | CCT | [6 empty] | 0 |  |  |  | 0
|  | 41 | CTUIR Employee 1 |  |  |  | 50 | [41 empty] | 8% | SBT | [6 empty] | 0 |  |  |  | 0
|  | 42 | CTUIR Employee 2 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 43 | CTWSR Employee 1 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 44 | CTWSR Employee 2 |  |  |  | 50 | [49 empty] | 0 |  |  |  | 0
|  | 45 | NPT Employee 1 |  |  |  | 50 | [43 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 46 | NPT Employee 2 |  |  |  | 50
|  | 47 | CCT Employee 1 |  |  |  | 50
|  | 48 | CCT Employee 2 |  |  |  | 50 | [44 empty] | 0
|  | 49 | SBT Employee 1 |  |  |  | 50
|  | 50 | SBT Employee 2 |  |  |  | 50 | [44 empty] | 0
|  | 51 | 0 |  |  |  | 0
|  | 52 | 0 |  |  |  | 0
|  | 53 | 0 |  |  |  | 0
|  | 54 | 0 |  |  |  | 0
|  | 55 | 0 |  |  |  | 0
|  | 56 | 0 |  |  |  | 0
|  | 57 | 0 |  |  |  | 0
|  | 58 | 0 |  |  |  | 0
|  | 59 | 0 |  |  |  | 0
|  | 60 | 0 |  |  |  | 0
|  | 61 | 0 |  |  |  | 0
|  | 62 | 0 |  |  |  | 0
|  | 63 | 0 |  |  |  | 0
|  | 64 | 0 |  |  |  | 0
|  | 65 | 0 |  |  |  | 0
|  | 66 | 0 |  |  |  | 0
|  | 67 | 0 |  |  |  | 0
|  | 68 | 0 |  |  |  | 0
|  | 69 | 0 |  |  |  | 0
|  | 70 | 0 |  |  |  | 0
|  | 71 | 0 |  |  |  | 0
|  | 72 | 0 |  |  |  | 0
|  | 73 | 0 |  |  |  | 0
|  | 74 | 0 |  |  |  | 0
|  | 75 | 0 |  |  |  | 0
|  | 76 | 0 |  |  |  | 0
|  | 77 | 0 |  |  |  | 0
|  | 78 | 0 |  |  |  | 0
[66 empty] | 450889 | 250357
387963

## Table 6_ Summary Program List
Table 6: Hatchery Review Regions and Co-manager Involvement
Group No | Region No. | Region Name | Natural | Hatchery | Total | Mitchell Act | Difference | WDFW | ODFW | IDFG | YN | CTUIR | CTWSR | NPT | CCT | SBT
1 | 1 | Lower Columbia , WA Cowlitz/Washougal | 4 | 19 | 23 | 10 | 9 | bar: WDFW to SBT
| 2 | Lower Columbia , WA Kalama/Lewis | 7 | 16 | 23 | 16 | 0
2 | 3 | Columbia Estuary,WA | 5 | 16 | 21 | 9 | 7 | bar: WDFW
3 | 4 | Lower Columbia, OR | 21 | 18 | 39 | 5 | 13 | bar: WDFW to SBT
| 5 | Columbia Estuary, OR | 4 | 7 | 11 | 2 | 5
4 | 6 | Columbia,. Gorge, WA | 12 | 16 | 28 | 12 | 4 | bar: WDFW; YN to CTUIR
5 | 7 | Columbia, Gorge, OR | 6 | 4 | 10 | 3 | 1 | bar: WDFW to SBT
6 | 8 | Columbia, Cascade | 3 | 21 | 24 | 0 | 21 | bar: WDFW; YN; CCT
7 | 9 | Columbia, Plateau, OR | 3 | 8 | 11 | 0 | 8 | bar: WDFW to SBT
8 | 10 | Columbia, Plateau, WA | 7 | 12 | 19 | 6 | 6 | bar: WDFW; YN
9 | 11 | Mountain Snake -Clearwater | 5 | 12 | 17 | 0 | 12 | bar: WDFW to SBT
| 12 | Mountain Snake -Salmon | 6 | 38 | 44 | 0 | 38
10 | 13 | Blue Mountain. | 9 | 24 | 33 | 7 | 17 | bar: ODFW to IDFG; CTUIR; NPT; SBT
|  | Total | 92 | 211 | 303 | 70 | 141
293
|  |  |  | Areas Involved in |  |  |  | 5 | 4 | 2 | 3 | 4 | 2 | 2 | 1 | 2 | 25
|  |  |  | % of Travel | 100% |  |  | 20% | 16% | 8% | 12% | 16% | 8% | 8% | 4% | 8%
Note: Budget is based on Co-manager assistance in review of data and information in 10 Group Areas ( 13 regions) where the manager has responsibility for programs