## Timeline
CBFWA Amendment Strategy Implementation |  |  | April | May | June | July | August
Assignment to Technical Committees
Define and Clarify terms (i.e., focal populations, objectives, how to express limiting factors, etc.)
|  | May 9 Workshop - reach agreement on definitions and terms |  | X
Confirm population level biological objectives
|  | April 10-11 RFAC meeting to prepare population ID and existing objectives | √
|  | April 23 and May 8 AFAC meeting to prepare population ID and existing objectives | √
|  | April 25-26 WAC meeting to develop strategies for establishing biological objectives | √
|  | May 9 Workshop - present population, objectives, and metrics to MAG |  | X
Validate current limiting factors including out-of-basin affects
|  | April 10-11 RFAC meeting to prepare expression of limiting factors and threats | √
|  | April 23 and May 8 AFAC meeting to prepare expression of limiting factors and threats | √
|  | May 9 Workshop - present limiting factors and threats to MAG |  | X
Review and build on strategies and actions necessary to reduce the limiting factors.
|  | May 9 Workshop - discuss process and protocols for developing strategies and actions |  | X
Assignment to MAG
Link subbasin population objectives to regional Program goals
|  | May 9 Workshop to discuss linkage of subbasin objectives to BPA obligations |  | X
Develop a comprehensive management coordination strategy
|  | Coordination Project Sponsors meet to develop coordination strategy | √ | √ | √ | √ | √
|  | MAG updates on workgroup discussions | √ | √ | √ | √ | √
Interact with the Council and regional communities
|  | Ad-Hoc Objectives Workgroup discussing development of objectives for BPA obligations | √ | √ | √ | √ | √
Other activities:
DMFS developing data management strategy
|  | Data management framework and FY08-09 project recommendations? |  | √ | √
|  | Data management strategies and actions for amendment |  |  | √ | √ | √
Science/Policy Oversight Workgroup
|  | Possible CBFWA workshops |  |  | √ | √ | √
|  | Council staff evaluations |  |  | √ | √ | √
|  | Science/Policy Exchange September 11-12, 2007 |  |  |  |  | X