## FY07_09 Summary
Task | Total Costs | % of Budget
1. Develop Work Plans / Interact w Prog. Entities (all tasks) | 217874.7075 | 22.83%
2. Inventory existing data relevant to questions | 44099.9377 | 4.622%
3. Organize subset of data into accessible form | 32843.3179 | 3.442%
4. Evaluate ability to answer key questions with existing data | 87287.8642 | 9.148%
5. Collaborative monitoring program design | 450856.8892 | 47.25%
6. Multi-agency implementation of monitoring programs. | 87241.3383 | 9.143%
7. Multi-agency evaluation of results of new monitoring pgms. | 33949.1626 | 3.558%
Total | 954153.2173 | 100%
| Fees | Disbursements | Total | % of Budget
ESSA | 187746.2 | 19923 | 207669.2 | 21.76%
ODFW | 86132.25 | 7590.192 | 93722.442 | 9.822%
IDFG | 94568.4629 | 9134.616 | 103703.0789 | 10.87%
WDFW | 75290.85 | 7590.192 | 82881.042 | 8.686%
MDFW | 0 | 0 | 0 | 0%
CRITFC | 104311.12 | 0 | 104311.12 | 10.93%
Umatilla | 12800 | 4618.272 | 17418.272 | 1.825%
Yakima | 12800 | 4618.272 | 17418.272 | 1.825%
Nez Perce | 92349.2 | 9134.616 | 101483.816 | 10.64%
Colville | 22902.4 | 4618.272 | 27520.672 | 2.884%
Nick Bouwes, Ecological Research | 23199.56 | 3629 | 26828.56 | 2.812%
Lyman MacDonald, WEST | 18000 | 3975.168 | 21975.168 | 2.303%
Kim Hyatt, DFO | 7200 | 3408.798 | 10608.798 | 1.112%
Charlie Paulsen, PER | 10200 | 0 | 10200 | 1.069%
CBFWA Meeting Costs | 0 | 12738 | 12738 | 1.335%
CBFWA Travel | 0 | 10000 | 10000 | 1.048%
Subtotal | 747500.0429 | 100978.398 | 848478.4409
Indirect Charges (CBFWA 12.8% of non CBFWA costs) | 95680.0055 | 10014.7709 | 105694.7764 | 11.08%
Total Contract | 843180.0484 | 110993.1689 | 954173.2173 | 100%

## FY07_09 Detailed Budget
CSMEP |  |  |  | 0 |  |  | Disbursements calculated with IDFG Overhead @ 0.218 | [24 empty] | 1 person-week = 5 days + 2 days contingency = 7 days (1.75 days each)
December 13 2005 | Funded by this proposal |  |  |  |  | Tom Rien | Sam Sharr | Pete Hahn | Phil Roger | Gary James | Dave Fast | Dave Stadtler | Jerry Marco | Lyman MacDonald | Charlie Paulsen | Kim Hyatt, M. Stockwell |  | Bruce Schmidt | John Palensky | Kim Hyatt DFO | Frank Young | Howard Schaller | Michele DeHart | Jim Gieselman | Total Cost Share Days | Total | Total Fees | Total | Total Fees |  | Total for
| ESSA |  |  |  |  | ODFW | IDFG | WDFW | CRITFC | Umatilla | Yakama Nation | Nez Perce [3] | Colville |  |  |  | Eco Logical Research | StreamNet Cost Share | NMFS Cost Share | DFO Cost Share | CBFWA Cost Share | USFWS Cost Share | FPC Cost Share | BPA cost share |  | Funded Days | by task | Expenses by task | Plus Expenses |  | fy05 & fy06
| Marmorek | Parnell | Porter | Pickard | Abraham | Eric Tinus, T. Dalton | C. Petrosky; Tim Copeland; Claire McGrath | Kristin Ryder; Pete Hahn; Dick O'Connor | E. Weber, S.Y. Hyun, P. Galbreath, J. Fryer | Jesse Schwartz | D. Fast; Bill Bosch | P. Kucera; C. Beasley; J. Hesse; C. Rabe | K. Wolf |  |  |  | Nick Bouwes; Robert Al-Chokhachy | K. Wegner; M. Grosbeck; E. Brown | Chris Jordan + ??? | Kim Hyatt & M. Stockwell DFO | J. Eckman, F. Young, K. Titzler | P. Wilson | M. Filardo, T. Berggren, H. Franzoni | Charlie Paulsen |  |  |  |  | by task | % of total budget |  | Notes on time estimates for ESSA
Daily Rate | 1100 | 683 | 615 | 615 | 400 | 450 | 349.7122 | 430 | 430 | 400 | 400 | 400 | 400 | 900 | 680 | 600 | 680 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Hourly Rate | 146.6667 | 91.0667 | 82 | 82 | 53.3333
Computed FTEs | 0.25218 | 0.019231 | 0.41154 | 0.28269 | 0.011538 | 0.73617 | 1.0401 | 0.67344 | 0.93302 | 0.12308 | 0.12308 | 0.88797 | 0.22022 |  | 0.057692 |  | 0.13122 | 0.78462 | 0.53077 |  | 0.74231 | 0.31154 | 0.48077 | 0.099038 | 2.85
Agreed upon FTEs | [17 empty] | ? | 1.125 |  | 0.75 | 0.5 | 0.5 |  |  |  |  | subcontract administration +
FTE Split between $'s and Agency Cost share | [27 empty] | communication + reporting costs spread
Objectives and Tasks | [27 empty] | across tasks according to fraction of total days
1. Develop Work Plans / Interact w Prog. Entities (all tasks)
1.1 Develop CSMEP Quarterly Workplans [1] | 4 |  | 5 | 0 |  | 4 | 4 | 4 | 4 |  |  | 4 | 4 |  |  |  |  | 4 |  |  | 10 | 4 | 4 | 0 | 22 | 33 | 17313.8486 | 2739.5114 | 20053.3601 |  | 40106.7201
1.2 Quarterly Progress Reports | 1 |  | 4 | 0 |  | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 |  |  |  |  | 2 |  |  | 5 | 2 | 2 | 0 | 11 | 19 | 9279.4243 | 1577.2945 | 10856.7188 |  | 21713.4376
1.3 Preparation of Draft and Final Annual Reports | 2 |  | 7 | 2 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 3 |  |  |  | 2 | 3 | 3 |  | 15 | 3 | 3 | 1 | 27 | 36 | 18474.1365 | 2988.5579 | 21462.6944 |  | 42925.3888
1.4 CSMEP conference calls, meetings and workshops | 8 |  | 10 | 6 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  |  | 5 | 8 | 8 |  | 20 | 8 | 8 | 1.5 | 52 | 93 | 48117.6973 | 7720.4413 | 55838.1386 |  | 111676.2772
1.5 Coordination w PNAMP on joint activities and work products | 4 |  | 3 | 0 |  | 3 | 3 | 3 | 3 | 2 | 2 | 3 | 8 |  |  |  |  | 3 |  |  | 20 |  | 3 | 0 | 26 | 34 | 17224.1365 | 2822.5269 | 20046.6634 |  | 40093.3268
1.6 Present CSMEP progress at various Columbia Basin forums [2] | 4 |  | 2 | 0 |  | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 |  |  |  |  | 2 | 2 |  | 20 |  |  | 0 | 24 | 20 | 11349.4243 | 1660.31 | 13009.7343 |  | 26019.4686
0
Total days for Objective 1 | 23 | 0 | 31 | 8 | 1 | 22 | 22 | 22 | 22 | 14 | 14 | 22 | 27 | 0 | 0 | 0 | 7 | 22 | 13 | 0 | 90 | 17 | 20 | 2.5 | 162 | 235 | 121758.6675 | 96116.04 | 217874.7075 | 22.83% | 435749.415 |  | 0
2. Inventory existing data relevant to questions | ESSA mostly acting in review capacity
2.1 QA on StreamNet Inventory Work prepatory to ID, WA, OR pilot designs | 2 |  | 2 | 0 |  | 15 | 10 | 10 |  |  |  | 10 | [5 empty] | 132 | 10 |  |  |  |  | 0 | 142 | 49 | 21977.1216 | 4067.7594 | 26044.881 |  | 52089.762
2.2 Sockeye Data Inventory |  |  |  | 0 |  |  | 5 | 5 | 10 | [6 empty] | 12 |  |  |  | 30 |  |  | 10 | 0 | 40 | 32 | 15398.5608 | 2656.4959 | 18055.0567 |  | 36110.1135
[21 empty] | 5 |  |  | 0 | 5 | [5 empty] | 0
Total days for Objective 2 | 2 | 0 | 2 | 0 | 0 | 15 | 15 | 15 | 10 | 0 | 0 | 10 | 0 | 0 | 0 | 12 | 0 | 132 | 10 | 30 | 5 | 0 | 10 | 0 | 187 | 81 | 37375.6824 | 6724.2553 | 44099.9377 | 4.622% | 88199.8754
3. Organize subset of data into accessible form | ESSA mostly acting in review capacity
3.1 Continue to improve web-based metadata system, links to data | 1 |  | 2 | 0 |  | 10 | 10 | 10 | 5 |  | 10 | 10 | [5 empty] | 35 |  | 20 | 10 |  |  | 0 | 65 | 58 | 24777.1216 | 4814.8989 | 29592.0205 |  | 59184.0409
3.2 CSMEP website improvement | 0.5 |  | 1 | 0 |  | 1 | 1 | 1 |  |  |  | 1 | [8 empty] | 30 |  |  | 0 | 30 | 5.5 | 2794.7122 | 456.5852 | 3251.2974 |  | 6502.5948
[21 empty] | 5 |  | 5 | 0 | 10 | [5 empty] | 0
Total days for Objective 3 | 1.5 | 0 | 3 | 0 | 0 | 11 | 11 | 11 | 5 | 0 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 20 | 45 | 0 | 5 | 0 | 105 | 63.5 | 27571.8338 | 5271.4841 | 32843.3179 | 3.442% | 65686.6357
4. Evaluate ability to answer key questions with existing data
4.1 Organization of existing data for Snake Basin pilot design |  |  | 5 | 0 |  |  | 30 |  |  |  |  | 20 | [5 empty] | 5 | 5 |  | 2 |  | 5 | 0.25 | 17 | 55 | 21566.3648 | 4565.8524 | 26132.2172 |  | 52264.4344
4.2 Organization of existing data for OR pilot design |  |  | 5 | 0 |  | 30 |  |  | 10 | 3 |  | 10 | [5 empty] | 5 | 5 |  | 2 |  | 5 | 0.25 | 17 | 58 | 26075 | 4814.8989 | 30889.8989 |  | 61779.7977
4.3 Organization of existing data for WA pilot design |  |  | 5 | 0 |  |  |  | 30 | 10 |  | 2.95 | 10 | [5 empty] | 5 | 5 |  | 2 |  | 5 | 0.25 | 17 | 57.95 | 25455 | 4810.7481 | 30265.7481 |  | 60531.4962
0
Total days for Objective 4 | 0 | 0 | 15 | 0 | 0 | 30 | 30 | 30 | 20 | 3 | 3 | 40 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 6 | 0 | 15 | 0.75 | 51 | 170.95 | 73096.3648 | 14191.4994 | 87287.8642 | 9.148% | 174575.7283
5. Collaborative monitoring program design
5.1 Consolidate Snake River Pilot M&E design and PrOACT tradeoff analysis | 5 |  | 13 | 13.5 | 0 | 20 | 30 | 15 | 25 |  |  | 20 |  | 5 | 5 |  | 10 |  | 20 |  | 5 | 15 | 15 | 5 | 55 | 161.5 | 81188.8648 | 13407.0029 | 94595.8677 |  | 189191.7354
5.2 Convert SRB into practical plan for Salmon basin pilot (later OR and WA) | 5 |  | 15 | 15.5 | 1 | 20 | 45 | 20 | 30 |  |  | 20 | [6 empty] | 20 |  | 5 | 15 | 15 | 5.5 | 55 | 171.5 | 78894.5472 | 14237.1579 | 93131.7051 |  | 186263.4102
5.3 DQO work -> M&E Tools for other subbasins in CRB / Marketing | 10 | 5 | 5 | 30 | 1 | 20 | 60 | 15 | 70 | 10 |  | 50 | 10 | 15 | 10 |  | 10 |  | 20 |  | 5 | 15 | 15 | 7.5 | 55 | 321 | 157972.7296 | 26647.9748 | 184620.7044 |  | 369241.4088
5.4 Feed M&E results into NPCC Rolling Provincial Review Process | 3 |  | 5 | 1.5 | 0 | 10 | 20 | 10 | 10 |  |  | 10 | 6 | [7 empty] | 5 | 15 | 15 | 1.5 | 35 | 75.5 | 33791.7432 | 6267.6701 | 40059.4133 |  | 80118.8266
5.5 Get feedback from CRB entities on various M&E designs | 4 |  | 4 | 1.5 | 0 | 10 | 10 | 10 | 20 |  |  | 10 | [8 empty] | 5 |  | 15 | 1.5 | 20 | 69.5 | 32679.6216 | 5769.5771 | 38449.1987 |  | 76898.3974
Total days for Objective 5 | 27 | 5 | 42 | 62 | 2 | 80 | 165 | 70 | 155 | 10 | 0 | 110 | 16 | 20 | 15 | 0 | 20 | 0 | 60 | 0 | 25 | 60 | 75 | 21 | 220 | 799 | 384527.5064 | 66329.3828 | 450856.8892 | 47.25% | 901713.7783
6. Multi-agency implementation of monitoring programs.
6.1 Develop broad conceptual plan for M&E implementation across CRB | 10 |  | 10 | 3.5 |  | 20 | 20 | 20 | 20 | 5 | 5 | 30 | 10.8 |  |  |  | 2.117 |  | 20 |  | 10 |  |  | 1.5 | 30 | 156.417 | 74256.3032 | 12985.0351 | 87241.3383 |  | 174482.6766
Total days for Objective 6 | 10 | 0 | 10 | 3.5 | 0 | 20 | 20 | 20 | 20 | 5 | 5 | 30 | 10.8 | 0 | 0 | 0 | 2.117 | 0 | 20 | 0 | 10 | 0 | 0 | 1.5 | 30 | 156.417 | 74256.3032 | 12985.0351 | 87241.3383 | 9.143% | 174482.6766
7. Multi-agency evaluation of results of new monitoring pgms.
7.1 Collaborative review of federal RME projects, WA SRFB Effectiveness Monitoring Projects, and other recent pilot projects | [24 empty] | 0
| 2.067 |  | 4 | 0 |  | 13.405 | 7.418 | 7.095 | 10.584 |  |  | 7.873 | 3.456 |  |  |  | 5 |  | 20 |  | 12 | 4 |  |  | 36 | 60.898 | 28893.6848 | 5055.4778 | 33949.1626 |  | 67898.3252
Total days for Objective 7 | 2.067 | 0 | 4 | 0 | 0 | 13.405 | 7.418 | 7.095 | 10.584 | 0 | 0 | 7.873 | 3.456 | 0 | 0 | 0 | 5 | 0 | 20 | 0 | 12 | 4 | 0 | 0 | 36 | 60.898 | 28893.6848 | 5055.4778 | 33949.1626 | 3.558% | 67898.3252
Totals for Project | 65.567 | 5 | 107 | 73.5 | 3 | 191.405 | 270.418 | 175.095 | 242.584 | 32 | 32 | 230.873 | 57.256 | 20 | 15 | 12 | 34.117 | 204 | 138 | 50 | 193 | 81 | 125 | 25.75 | 791 | 1566.765 | 747480.0429 | 206673.1744 | 954153.2173 |  | 1908306.4346
Total Fees | 72123.7 | 3415 | 65805 | 45202.5 | 1200 | 86132.25 | 94568.4629 | 75290.85 | 104311.12 | 12800 | 12800 | 92349.2 | 22902.4 | 18000 | 10200 | 7200 | 23199.56 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 747500.0429
days/month | 5.4639 |  | 8.9167 | 6.125 | [24 empty] | 968802 | fy06 budget
Change in fees from fy06 budget | 19.07% |  | 13.83% | 25.64% |  | -22.32% | 12.48% | -22.21% | -4.117% |  | -49.94% | 0% | -49.98% | n.a. | n.a. | n.a. | -22.67% | [11 empty] | -1.51% | % change from fy06
Disbursements (billed at cost)
Travel | 4662 | 0 | 4662 | 4389 |  | 5778.192 | 7322.616 | 5778.192 | 0 | 2806.272 | 2806.272 | 7322.616 | 2806.272 | 2163.168 |  | 1596.798 | 1776 |  |  |  | 10000 |  |  |  |  | 63869.398
Communication | 1000 |  | 1500 | 1000 | 960 | 1812 | 1812 | 1812 |  | 1812 | 1812 | 1812 | 1812 | 1812 |  | 1812 | 1853 | [8 empty] | 22621
Report Production, Printing, Photocopying | 500 |  | 500 | 500 | 250 | [20 empty] | 1750
Workshop Expenses & Subcontracts for Specialists | [20 empty] | 12738 |  |  |  |  | 12738 |  | Disb + Contract Admin
Total Disbursements | 6162 | 0 | 6662 | 5889 | 1210 | 7590.192 | 9134.616 | 7590.192 | 0 | 4618.272 | 4618.272 | 9134.616 | 4618.272 | 3975.168 | 0 | 3408.798 | 3629 |  |  |  | 22738 |  |  |  |  | 100978.398 |  | 206673.1744
Change in disbursements from fy06 budget | 0% |  | 0% | 0% | 0% | -16.91% | 0% | -16.91% | -100% |  | -49.44% | 0% | -49.44% |  |  |  | -28.01%
Total Fees + Disbursements | 78285.7 | 3415 | 72467 | 51091.5 | 2410 | 93722.442 | 103703.0789 | 82881.042 | 104311.12 | 17418.272 | 17418.272 | 101483.816 | 27520.672 | 21975.168 | 10200 | 10608.798 | 26828.56 |  |  |  | 22738 | [5 empty] | 848478.4409
CBFWA Contract Administration (12.8%) | 10020.5696 | 437.12 | 9275.776 | 6539.712 | 308.48 | 11996.4726 | 13273.9941 | 10608.7734 | 13351.8234 | 2229.5388 | 2229.5388 | 12989.9284 | 3522.646 | 2812.8215 | 1305.6 | 1357.9261 | 3434.0557 | [9 empty] | 105694.7764
Total Fees + Disbursements + Contract Administration | 88306.2696 | 3852.12 | 81742.776 | 57631.212 | 2718.48 | 105718.9146 | 116977.073 | 93489.8154 | 117662.9434 | 19647.8108 | 19647.8108 | 114473.7444 | 31043.318 | 24787.9895 | 11505.6 | 11966.7241 | 30262.6157 |  |  |  | 22738 |  |  |  | 954173.2173 |  | 954173.2173
Travel Details…
# flights | 6 | 0 | 6 | 6 |  | 7 | 9 | 7 | 0 | 3 | 3 | 9 | 3 | 2 |  | 2 | 2
cost / flight including ground transportation | 600 | 600 | 600 | 600 |  | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 620 |  | 500 | 620
# days per diem | 12 |  | 12 | 12 |  | 12 | 14 | 12 | 0 | 6 | 6 | 14 | 6 | 4 |  | 3 | 4
cost / per diem | 43 | 43 | 43 | 43 |  | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 |  | 43 | 43
# nights hotel accomodation | 6 | 0 | 6 | 3 |  | 8 | 10 | 8 | 0 | 6 | 6 | 10 | 6 | 4 |  | 2 | 4
cost / hotel night | 91 | 91 | 91 | 91 |  | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 |  | 91 | 91
Cost of travel without overhead | 4662 | 0 | 4662 | 4389 |  | 4744 | 6012 | 4744 | 0 | 2304 | 2304 | 6012 | 2304 | 1776 |  | 1311 | 1776
Markup on travel costs | 0 | 0 | 0 | 0 |  | 1034.192 | 1310.616 | 1034.192 | 0 | 502.272 | 502.272 | 1310.616 | 502.272 | 387.168 |  | 285.798 | 0
Total Cost of Travel | 4662 | 0 | 4662 | 4389 |  | 5778.192 | 7322.616 | 5778.192 | 0 | 2806.272 | 2806.272 | 7322.616 | 2806.272 | 2163.168 |  | 1596.798 | 1776
Notes: | ESSA Total Fees |  | 187746.2
| % change from fy06 |  | 20.69%
[1] to be coordinated w StreamNet, PNAMP and other entities | $ change from fy06 |  | 32185 | this equals actual overbudget in FY05
[2] examples would include NWPCC, TRTs, PNAMP, WA DOE, AFS NPIC
[3] Nez Perce amount includes allocation for Chris Beasley (% dependent on ability of NP to hire biometrician)
Note on A10: Ian Parnell: Constant multiplier across tasks, works of days entered in column the multiplier is entered in.
Note on A49: David Marmorek: Generalizing results of DQO process into newsletters, etc.
Note on C42: David Marmorek: ESSA acting to 'coach' CSMEP staff in identifying these opportunities
Note on I26: David Marmorek: Need to know SK guy from WDFW
Note on J26: David Marmorek: Jeff Fryer working together with Kim Hyatt on this
Note on J39: David Marmorek: Will be handled by Nez Perce
Note on J40: David Marmorek: This involves getting Warm Springs data
Note on J51: David Marmorek: Consult w harvest mgrs and tribes
Note on K40: David Marmorek: Provide Umatilla data for OR pilot
Note on K56: David Marmorek: Acting in review capacity
Note on L32: David Marmorek: Link in Yakima data
Note on L56: David Marmorek: Acting in review capacity
Note on M5: David Marmorek: Need a firm commitment of Chris + Jay's time for this to work
Note on N5: David Marmorek: Keith's role here is to become thoroughly familiar w CSMEP products so as to market them well through PNAMP
Note on P3: David Marmorek: To cover costs not paid for by BPA
Note on R6: David Marmorek: Blended rate for Robert and Nick
Note on R47: David Marmorek: Robert to work on bull trout component of design
Note on R49: David Marmorek: Nick to provide summary of question clarification approach
Note on R62: David Marmorek: Nick / Robert to bring in lessons from John Day project
Note on T5: David Marmorek: This is unofficial cost shsring, not to be listed in proposal as cost share
Note on W26: David Marmorek: Assist states in getting access to bull trout information
Note on X26: David Marmorek: Assist states in getting access to mainstem information

## Work Product Description
CSMEP FY07-09: Overview of Objectives, Work Elements and Work Products
Objectives and Work Elements | Description of Work Products | Timing | Entities Collaborating w CSMEP Members [5] | Enter comments here by task
1. Develop Work Plans / Interact with Programmatic Entities (all tasks)
1.1 Develop CSMEP Quarterly Workplans | Collaboratively prepared quarterly workplans to maximize integration and efficiency, avoid duplication of effort. | quarterly | PNAMP, BPA, NPCC, StreamNet
1.2 Quarterly Progress Reports | Quarterly reports by objective and work element to ensure close contract monitoring. | quarterly | BPA
1.3 Preparation of Draft and Final Annual Reports | 3-level annual reports: 2-pg. exec. Summary; ~25-pg. overview w ~75-pg. appendices; hyperlinked detailed reports | annual | internal
1.4 CSMEP conference calls, meetings and workshops | Calls: Track progress, review products, coordinate efforts. Workshops: Present results, get technical/programmatic feedback, brainstorm next steps in subgroups | biweekly calls 3-4 workshops/yr | Calls: internal Workshops: Programmatic and Policy Feedback for part of meeting
1.5 Coordination w PNAMP on joint activities and work products | Joint PNAMP/CSMEP workshop in spring each year; Annual work planning; Synthesis of work products | annual workshop plan mtgs twice/yr | PNAMP Steering Committee
1.6 Present CSMEP progress at various Columbia Basin forums | Give presentations to inform region CSMEP outcomes and products, and to integrate with others' efforts | 2-3 times / yr | NPCC, TRTs, PNAMP, WA DOE, AFS, EPA
2. Inventory existing data relevant to questions
2.1 QA on StreamNet Inventory Work prepatory to ID, WA, OR pilot designs | Review StreamNet's metadata inventories (priority subbasins are CSMEP pilot designs in ID, WA and OR) [1] | fy07-fy09 | StreamNet (separate contract); fed/state/tribal agencies with data
2.2 Sockeye Data Inventory | Update metadata inventory of Okanagan sockeye, add Wenatchee and Redfish Lake stocks | fy07 | DFO, Okanagan Nation Alliance
3. Organize subset of data into accessible form
3.1 Continue to improve CSMEP web-based metadata application [2] | Add hyper links from CSMEP database to on-line databases housed by agencies collecting/maintaining data | fy07-fy09 | StreamNet (separate contract); fed/state/tribal agencies with data
3.2 CSMEP website improvement [3] | Provide user-friendly summaries of CSMEP products in hierarchical form to communicate to multiple audiences | fy07-fy09 | CBFWA web master Amy Langston
4. Evaluate ability to answer key questions with existing data
4.1 Organization of existing data for Snake Basin pilot design [4] | Detailed review of CSMEP inventories and strengths & weaknesses assessments; GIS overlays of existing sampling sites with EMAP master sample to refine sampling designs for status & trend | mostly in fy06; some work in fy07 | USFS, BLM, OR Aquatic Inventory, OWEB, ID DEQ, PCSRF, BoR, EPA, others
4.2 Organization of existing data for OR pilot design | As above for work element 4.1. Area of OR pilot to be defined (e.g. Willamette, Deschutes). | fy07 and fy08 | USFS, BLM, OR Aquatic Inventory, OWEB, OR DEQ, PCSRF, BoR, EPA, others
4.3 Organization of existing data for WA pilot design | As above for work element 4.1. Area of WA pilot to be defined (e.g. Lower Snake, Lower Columbia). | fy07 and fy08 | USFS, BLM, WA SRFB, WA DEQ, PCSRF, BoR, EPA, DFO, others
5. Collaborative monitoring program design
5.1 Consolidate Snake River Pilot M&E design and PrOACT tradeoff analysis | Demonstrate cost-precision and other tradeoffs associated with alternative integrated designs that attempt to meet information needs for key decisions in recovery assessment and 4 H's. | mostly in fy06; some work in fy07 | Interact with programmatic/policy entities with responsibiilty for decisions in recovery assessment and 4 H's to fine tune design, costs.
5.2 Convert pilot M&E designs into practical plans for provincial / ESU scale areas in ID, OR, WA | Develop and present three provincial scale fish and habitat M&E plans that integrate across issues, questions, species and agencies to meet identified priorities. Work towards implementation of these plans . | ID (fy06-07); OR (fy07-09); WA (fy07-09) | as for work element 5.1. Build on insights gained from NOAA-AA pilot projects, policy survey
5.3 DQO work -> M&E Tools for other subbasins in CRB / Marketing | Generalize qualitative and quantitative tools developed in CSMEP DQO process for use throughout CRB. Present general implications to managers and scientists. | fy07-09 | Market existence of tools and methods through CBFWA, PNAMP, NPCC websites and newsletters
5.3a Status & Trends | Extend tools for assessing M&E designs to detect recovery status (more VSP criteria, species); publish/present results. | fy07-09 | Technical Recovery Teams, ISRP/ISAB
5.3b Hydro | Complete DQO steps 6-7 for hydrosystem decisions and publish/present results for feedback. Extend findings to other regions (i.e. Mid/Upper Columbia). | fy07-09 | AFEP, NOAA-Hydro, PUDs, ISRP/ISAB
5.3c Habitat | Work with restoration managers across multiple watersheds on implementation / M&E methods that will maximize learning on restoration effectiveness at various scales. | fy07-09 | PNAMP entities, restoration managers, NOAA-AA pilot projects, ISRP/ISAB
5.3d Hatchery | Complete M&E designs for large scale hatchery / supplementation questions (i.e. hatchery straying into wild populations, relative reproductive success) and present recommended plans | fy07-09 | Hatchery managers, ISRP/ISAB
5.3e Harvest | Complete M&E designs for improving data for harvest pre-season and in-season decisions | fy07-09 | Harvest managers (e.g. TAC, US v. OR, PST, CTC), ISRP/ISAB
5.4 Feed M&E results into NPCC Rolling Provincial Review Process | Interact with CBFWA / NPCC managers to provide insights for project approval and M&E guidelines | fy07-09 | NPCC, CBFWA
5.5 Get feedback from CRB entities on various M&E designs | As described above under 5.2 and 5.3, but beyond immediate areas of pilot studies | fy07-09 | As for work element 5.1.
6. Multi-agency implementation of monitoring programs.
6.1 Develop broad conceptual plan for M&E implementation across CRB | Update plan developed in fy06 as new knowledge developed from CSMEP and NOAA-AA pilot projects. | fy07-09 | As for work element 5.1.
7. Multi-agency evaluation of results of new monitoring pgms.
7.1 Collaborative review of federal RME projects, WA SRFB Effectiveness Monitoring Projects, and other recent pilot projects | Review results of Wenatchee, John Day and Salmon pilot projects as they are made available and incorporate into next set of designs. | fy07-09 | NOAA-AA pilot projects
Notes:
[1] Inventories for salmon, steelhead, bull trout and other high priority resident fish. This assumes separate funding of StreamNet data inventory work. Twelve subbasins already have metadata inventories from StreamNet/CSMEP work in fy04 and fy05.
[2] CSMEP Metadata Application located at https://nrimp.dfw.state.or.us/csmep/ . Other possibilities for improvements include georeferenced displays of data locations (also dependent on StreamNet funding).
[3] CSMEP main website for work products is http://www.cbfwa.org/committees/csmep/
[4] Snake Basin pilot study to expand focus from spring/summer chinook to include more detail on steelhead, bull trout and other resident fish, as well as considering habitat monitoring. Focus is on Mountain Snake and Blue Mountain province, including Salmon, Clearwater, Grande Ronde, Imnaha, and Asotin subbasins (and their associated subbasin plans).
[5] Agencies involved in CSMEP: CBFWA, NOAA Fisheries, USFWS, CRITFC, BPA, ODFW, WDFW, IDFG, Fish Passage Center (FPC), StreamNet, Nez Perce Tribe, Confederated Tribes of the Colville Reservation, Yakama Indian Nation

## FY06 Budget
CSMEP |  |  |  | -0.056653 |  |  | Disbursements calculated with IDFG Overhead @ 0.218 | [20 empty] | 1 person-week = 5 days + 2 days contingency = 7 days (1.75 days each)
July 6 2005 | Funded by this proposal |  |  |  |  | Tom Rien | Sam Sharr | Pete Hahn | Larry Peterman; Chris Hunter | Rob Lothrop | Dave Fast | Dave Stadtler | Jerry Marco |  | Bruce Schmidt | John Palensky | Frank Young | Howard Schaller | Michele DeHart | Jim Gieselman | Total Cost Share Days | Total | Total Fees | Total | Total Fees |  | Total for
| ESSA |  |  |  |  | ODFW | IDFG | WDFW | MDFWP | CRITFC | Yakama Nation | Nez Perce [3] | Colville | Eco Logical Research | StreamNet Cost Share | NMFS Cost Share | CBFWA Cost Share | USFWS Cost Share | FPC Cost Share | BPA cost share |  | Funded Days | by task | Expenses by task | Plus Expenses |  | fy05 & fy06
| Marmorek | Parnell | Porter | Pickard | Abraham | Eric Tinus, K. Kostow | C. Petrosky; Tim Copeland; Claire McGrath | Annette Hoffman; Dick O'Connor | TBA | E. Weber, R. Sharma, J. Fryer, P. Roger | D. Fast; Bill Bosch | P. Kucera; C. Beasley; J. Hesse; C. Rabe | K. Wolf; J. Marco | Nick Bouwes | K. Wegner; M. Grosbeck; E. Brown | Steve Katz, Chris Jordan, Tom Cooney | J. Eckman, F. Young, K. Titzler | P. Wilson | M. Filardo, T. Berggren, H. Franzoni | Charlie Paulsen |  |  |  |  | by task | % of total budget |  | Notes on time estimates for ESSA
Daily Rate | 1100 | 683 | 615 | 615 | 400 | 450 | 349.7122 | 430 | 385 | 430 | 400 | 400 | 400 | 680 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hourly Rate | 146.6667 | 91.0667 | 82 | 82 | 53.3333
Computed FTEs | 0.2118 | 0 | 0.36154 | 0.225 | 0.011538 | 0.94771 | 0.92468 | 0.86575 | 0 | 0.97308 | 0.24587 | 0.88797 | 0.44022 | 0.16968 | 0.78462 | 1.1038 | 0.75 | 0.31154 | 0.5 | 0.1 | 3.45
Agreed upon FTEs | [14 empty] | ? | 1.125 | 0.75 | 0.5 | 0.5 |  |  |  |  | subcontract administration +
FTE Split between $'s and Agency Cost share | [23 empty] | communication + reporting costs spread
Objectives and Tasks | [23 empty] | across tasks according to fraction of total days
1. Develop Work Plans / Interact w Prog. Entities (all tasks)
1.1 Develop CSMEP Quarterly Workplans [1] | 4 |  | 5 | 0 |  | 4 | 4 | 4 |  | 4 |  | 4 | 4 |  | 4 | 4 | 10 | 4 | 4 | 0 | 26 | 33 | 17313.8486 | 2595.2916 | 19909.1403 |  | 39818.2806
1.2 Quarterly Progress Reports | 1 |  | 4 | 0 |  | 2 | 2 | 2 |  | 2 | 1 | 2 | 2 |  | 2 | 2 | 5 | 2 | 2 | 0 | 13 | 18 | 8879.4243 | 1415.6136 | 10295.0379 |  | 20590.0759
1.3 Preparation of Draft and Final Annual Report for FY05 | 2 |  | 7 | 2 | 1 | 3 | 3 | 3 |  | 3 | 2 | 3 | 3 | 2 | 3 | 3 | 15 | 3 | 3 | 1 | 27 | 34 | 17674.1365 | 2673.9368 | 20348.0733 |  | 40696.1466
1.4 CSMEP conference calls and meetings | 8 |  | 10 | 6 |  | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 5 | 8 | 8 | 20 | 8 | 8 | 1.5 | 52 | 85 | 44917.6973 | 6684.8421 | 51602.5394 |  | 103205.0788
1.5 Coordination w PNAMP on joint activities and work products | 4 |  | 3 | 0 |  | 3 | 3 | 3 |  | 3 | 2 | 3 | 8 | 2 | 3 | 3 | 20 |  | 3 | 0 | 29 | 34 | 17784.1365 | 2673.9368 | 20458.0733 |  | 40916.1466
1.6 Present CSMEP progress at various Columbia Basin forums [2] | 4 |  | 2 | 0 |  | 2 | 2 | 2 |  | 2 | 1 | 2 | 2 |  | 2 | 2 | 20 |  |  | 0 | 24 | 19 | 10949.4243 | 1494.2588 | 12443.6831 |  | 24887.3663
Total days for Objective 1 | 23 | 0 | 31 | 8 | 1 | 22 | 22 | 22 | 0 | 22 | 14 | 22 | 27 | 9 | 22 | 22 | 90 | 17 | 20 | 2.5 | 171 | 223 | 117518.6675 | 108435.1919 | 225953.8594 | 23.32% | 451907.7188 |  | 0
2. Inventory existing data relevant to questions | ESSA mostly acting in review capacity
2.1 Inventory Tier 1 information | 0.5 |  | 7 | 0 |  | 15 | 15 | 15 |  | 15 |  | 10 |  | 7 |  | 10 |  |  |  | 0 | 10 | 84.5 | 38510.6824 | 6645.5195 | 45156.2019 |  | 90312.4038
2.2 Complete data inventory for second and third set of subbasins | 0.5 |  | 2 | 0 |  | 25 | 25 | 25 |  | 25 | 20 | 25 | 25 |  | 132 |  |  |  | 10 | 0 | 142 | 172.5 | 71272.804 | 13566.2972 | 84839.1012 |  | 169678.2024
2.3 Report on the Inventory process | 0.5 |  | 2 | 0 |  | 5 | 5 | 5 |  | 5 |  | 5 | 5 |  | 5 | 5 | 5 |  |  | 0 | 15 | 32.5 | 14078.5608 | 2555.969 | 16634.5298 |  | 33269.0597
Total days for Objective 2 | 1.5 | 0 | 11 | 0 | 0 | 45 | 45 | 45 | 0 | 45 | 20 | 40 | 30 | 7 | 137 | 15 | 5 | 0 | 10 | 0 | 167 | 289.5 | 123862.0472 | 22767.7858 | 146629.833 | 15.14% | 293259.6659
3. Organize subset of data into accessible form | ESSA mostly acting in review capacity
3.1 Continue to develop web-based data inventory system | 0.5 |  | 1 | 0 |  | 5 | 5 | 5 |  | 2 |  | 5 | 3 |  | 25 |  | 10 |  |  | 0 | 35 | 26.5 | 11373.5608 | 2084.0978 | 13457.6586 |  | 26915.3173
3.2 CSMEP website improvement | 0.5 |  | 1 | 0 |  | 1 | 1 | 1 |  | 2 |  | 1 |  |  |  |  | 30 |  |  | 0 | 30 | 7.5 | 3654.7122 | 589.839 | 4244.5512 |  | 8489.1023
3.3 Develop protocol for making data available to CSMEP analysts | 0.5 |  | 1 | 0 |  | 5 | 5 | 5 |  | 5 | 2 | 5 | 3 |  | 10 |  | 5 |  | 5 | 0 | 20 | 31.5 | 13463.5608 | 2477.3238 | 15940.8846 |  | 31881.7693
Total days for Objective 3 | 1.5 | 0 | 3 | 0 | 0 | 11 | 11 | 11 | 0 | 9 | 2 | 11 | 6 | 0 | 35 | 0 | 45 | 0 | 5 | 0 | 85 | 65.5 | 28491.8338 | 5151.2607 | 33643.0944 | 3.473% | 67286.1889
4. Evaluate ability to answer key questions with existing data
4.1 Assess strengths & weaknesses of data for Tier 1 questions | 1 |  | 2 | 0 |  | 10 | 10 | 10 |  | 10 |  | 5 | 5 | 3 |  | 5 | 2 |  | 5 | 0.25 | 12 | 56 | 24967.1216 | 4404.1313 | 29371.2529 |  | 58742.5057
4.2 Complete Tier 2 S&W Assessment for 2nd set of subbasins | 1 |  | 2 | 0 |  | 15 | 15 | 15 |  | 15 | 12 | 15 | 10 |  | 5 | 5 | 2 |  | 5 | 0.25 | 17 | 100 | 42025.6824 | 7864.5201 | 49890.2025 |  | 99780.405
4.3 Complete Tier 2 S&W Assessment for 3rd set of subbasins | 1 |  | 2 | 0 |  | 15 | 15 | 15 |  | 15 |  | 15 | 10 |  | 5 | 5 | 2 |  | 5 | 0.25 | 17 | 88 | 37225.6824 | 6920.7777 | 44146.4601 |  | 88292.9202
4.4 Identify opportunities for Tier 3 Evaluations (C4 tables and beyond) | 1 |  | 2 | 0 |  | 15 | 15 | 15 |  | 15 | 5 | 15 | 10 |  |  | 20 | 2 |  | 5 | 0.25 | 27 | 93 | 39225.6824 | 7314.0037 | 46539.6861 |  | 93079.3722
Total days for Objective 4 | 4 | 0 | 8 | 0 | 0 | 55 | 55 | 55 | 0 | 55 | 17 | 50 | 35 | 3 | 10 | 35 | 8 | 0 | 20 | 1 | 73 | 337 | 143444.1688 | 26503.4328 | 169947.6016 | 17.54% | 339895.2032
5. Collaborative monitoring program design
5.1 Consolidate Snake River Pilot M&E design and PrOACT tradeoff analysis | 5 |  | 13 | 13.5 | 0 | 20 | 20 | 20 |  | 20 | 5 | 20 | 5 | 5 |  | 35 | 5 | 15 | 15 | 5 | 70 | 146.5 | 70391.7432 | 11521.522 | 81913.2652 |  | 163826.5304
5.2 Convert SRB into practical plan for Salmon basin pilot | 3 |  | 5 | 15.5 | 1 | 20 | 20 | 15 |  | 20 | 4.926 | 20 | 5 | 6 |  | 35 | 5 | 15 | 15 | 5.5 | 70 | 135.426 | 63402.1432 | 10650.605 | 74052.7482 |  | 148105.4964
5.3 M&E Recommendations for other subbasins in CRB | 3 |  | 5 | 15 | 1 | 20 | 20 | 15 |  | 20 |  | 20 |  | 6 |  | 35 | 5 | 15 | 15 | 7.5 | 70 | 125 | 59124.2432 | 9830.6502 | 68954.8934 |  | 137909.7867
5.4 Feed M&E results into NPCC Rolling Provincial Review Process | 3 |  | 5 | 1.5 | 0 | 20 | 20 | 15 |  | 20 |  | 20 |  | 6 |  | 35 | 5 | 15 | 15 | 1.5 | 70 | 110.5 | 50421.7432 | 8690.2947 | 59112.0379 |  | 118224.0759
5.5 Get feedback from CRB entities on various M&E designs | 4 |  | 4 | 1.5 | 0 | 10 | 10 | 10 |  | 20 |  | 10 |  |  |  | 35 | 5 |  | 15 | 1.5 | 55 | 69.5 | 32679.6216 | 5465.8415 | 38145.4631 |  | 76290.9262
Total days for Objective 5 | 18 | 0 | 32 | 47 | 2 | 90 | 90 | 75 | 0 | 100 | 9.926 | 90 | 10 | 23 | 0 | 175 | 25 | 60 | 75 | 21 | 335 | 586.926 | 276019.4944 | 46158.9134 | 322178.4078 | 33.26% | 644356.8156
6. Multi-agency implementation of monitoring programs.
6.1 Develop broad conceptual plan for M&E implementation across CRB | 5 |  | 5 | 3.5 |  | 10 | 10 | 10 |  | 10 | 1 | 10 | 3 | 2.117 |  | 20 | 10 |  |  | 1.5 | 30 | 69.617 | 34364.1816 | 5475.043 | 39839.2246 |  | 79678.4492
Total days for Objective 6 | 5 | 0 | 5 | 3.5 | 0 | 10 | 10 | 10 | 0 | 10 | 1 | 10 | 3 | 2.117 | 0 | 20 | 10 | 0 | 0 | 1.5 | 30 | 69.617 | 34364.1816 | 5475.043 | 39839.2246 | 4.112% | 79678.4492
7. Multi-agency evaluation of results of new monitoring pgms.
7.1 Collaborative review of federal RME projects, WA SRFB Effectiveness Monitoring Projects, and other recent pilot projects | [20 empty] | 0
| 2.067 |  | 4 | 0 |  | 13.405 | 7.418 | 7.095 |  | 12 |  | 7.873 | 3.456 |  |  | 20 | 12 | 4 |  |  | 36 | 57.314 | 26102.5648 | 4507.4711 | 30610.0359 |  | 61220.0717
Total days for Objective 7 | 2.067 | 0 | 4 | 0 | 0 | 13.405 | 7.418 | 7.095 | 0 | 12 | 0 | 7.873 | 3.456 | 0 | 0 | 20 | 12 | 4 | 0 | 0 | 36 | 57.314 | 26102.5648 | 4507.4711 | 30610.0359 | 3.16% | 61220.0717
Totals for Project | 55.067 | 0 | 94 | 58.5 | 3 | 246.405 | 240.418 | 225.095 | 0 | 253 | 63.926 | 230.873 | 114.456 | 44.117 | 204 | 287 | 195 | 81 | 130 | 26 | 897 | 1628.857 | 749802.9581 | 218999.0986 | 968802.0567 |  | 1937604.1133
Total Fees | 60573.7 | 0 | 57810 | 35977.5 | 1200 | 110882.25 | 84077.0981 | 96790.85 | 0 | 108790 | 25570.4 | 92349.2 | 45782.4 | 29999.56 | 0 | 0 | 0 | 0 | 0 |  |  | 749802.9581
days/month | 4.5889 |  | 7.8333 | 4.875 | [20 empty] | 968802 |  | Council Approved
Disbursements (billed at cost)
Travel | 4662 | 0 | 4662 | 4389 |  | 7322.616 | 7322.616 | 7322.616 | 0 | 7322.616 | 7322.616 | 7322.616 | 7322.616 | 3188 |  |  | 10000 |  |  |  |  | 78159.312 |  |  | -0.056653 | : Difference between budgeted and approved
Communication | 1000 |  | 1500 | 1000 | 960 | 1812 | 1812 | 1812 |  | 1812 | 1812 | 1812 | 1812 | 1853 | [7 empty] | 18997 |  |  | -5.848e-06%
Report Production, Printing, Photocopying | 500 |  | 500 | 500 | 250 | [16 empty] | 1750
Workshop Expenses & Subcontracts for Specialists | [16 empty] | 12738 |  |  |  |  | 12738 |  | Disb + Contract Admin
Total Disbursements | 6162 | 0 | 6662 | 5889 | 1210 | 9134.616 | 9134.616 | 9134.616 | 0 | 9134.616 | 9134.616 | 9134.616 | 9134.616 | 5041 |  |  | 22738 |  |  |  | 111644.312 | 111644.312 |  | 218999.0986
Total Fees + Disbursements | 66735.7 | 0 | 64472 | 41866.5 | 2410 | 120016.866 | 93211.7141 | 105925.466 | 0 | 117924.616 | 34705.016 | 101483.816 | 54917.016 | 35040.56 |  |  | 22738 | [5 empty] | 861447.2701
CBFWA Contract Administration (12.8%) | 8542.1696 | 0 | 8252.416 | 5358.912 | 308.48 | 15362.1588 | 11931.0994 | 13558.4596 | 0 | 15094.3508 | 4442.242 | 12989.9284 | 7029.378 | 4485.1917 | [8 empty] | 107354.7866
Total Fees + Disbursements + Contract Administration | 75277.8696 | 0 | 72724.416 | 47225.412 | 2718.48 | 135379.0248 | 105142.8135 | 119483.9256 | 0 | 133018.9668 | 39147.258 | 114473.7444 | 61946.394 | 39525.7517 |  |  | 22738 |  |  |  | 968802.0567 |  | 968802.0567
131207.7
Travel Details…
# flights | 6 | 0 | 6 | 6 |  | 9 | 9 | 9 | 0 | 9 | 9 | 9 | 9 | 4
cost / flight including ground transportation | 600 | 600 | 600 | 600 |  | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 620
# days per diem | 12 |  | 12 | 12 |  | 14 | 14 | 14 | 0 | 14 | 14 | 14 | 14 | 8
cost / per diem | 43 | 43 | 43 | 43 |  | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43 | 43
# nights hotel accomodation | 6 | 0 | 6 | 3 |  | 10 | 10 | 10 | 0 | 10 | 10 | 10 | 10 | 4
cost / hotel night | 91 | 91 | 91 | 91 |  | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91 | 91
Cost of travel without overhead | 4662 | 0 | 4662 | 4389 |  | 6012 | 6012 | 6012 | 0 | 6012 | 6012 | 6012 | 6012 | 3188
Markup on travel costs | 0 | 0 | 0 | 0 |  | 1310.616 | 1310.616 | 1310.616 | 0 | 1310.616 | 1310.616 | 1310.616 | 1310.616 | 0
Total Cost of Travel | 4662 | 0 | 4662 | 4389 |  | 7322.616 | 7322.616 | 7322.616 | 0 | 7322.616 | 7322.616 | 7322.616 | 7322.616 | 3188
ESSA Total Fees + Disbursements in July 6 budget | 64522.5 | 42189.6498 | 43804 | 22808 | 2160 | 175484.1498
ESSA Total Fees + Disbursements in current budget | 66735.7 | 0 | 64472 | 41866.5 | 2410 | 175484.2
Notes: | ESSA Total Fees |  | 155561.2
[1] to be coordinated w StreamNet, PNAMP and other entities
[2] examples would include NWPCC, TRTs, PNAMP, WA DOE, AFS NPIC
[3] Nez Perce amount includes 55,679 for NP + 45,788 for Chris Beasley
Note on A10: Ian Parnell: Constant multiplier across tasks, works of days entered in column the multiplier is entered in.
Note on C42: David Marmorek: ESSA acting to 'coach' CSMEP staff in identifying these opportunities
Note on D25: maps of existing habitat sampling sites as part of design work. Other tier 1 review work.
Note on S26: David Marmorek: Assist states in getting access to bull trout information
Note on T26: David Marmorek: Assist states in getting access to mainstem information

## Schedule FY07
CSMEP Schedule FY07 - NOT DONE YET
Fraction of task occurring in each month
| 2005 | [7 empty] | 2006
Task | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Sum
1. Develop Work Plans / Interact w Prog. Entities (all tasks) | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.2 | 0.2 | 1
1.1 Develop CSMEP Quarterly Workplans [1] | [12 empty] | 0
1.2 Quarterly Progress Reports | [12 empty] | 0
1.3 Preparation of Draft and Final Annual Report for fy05 | [12 empty] | 0
1.4 CSMEP conference calls and meetings | [12 empty] | 0
1.5 Coordination w PNAMP on joint activities and work products | [12 empty] | 0
1.6 Present CSMEP progress at various Columbia Basin forums [2] | [12 empty] | 0
Total days for Objective 1 | [12 empty] | 0
2. Inventory existing data relevant to questions
2.1 QA on StreamNet Inventory Work prepatory to ID, WA, OR pilot designs | 2005 Oct: 0.33; 2005 Nov: 0.33; 2005 Dec: 0.34 | 1
2.2 Sockeye Data Inventory | 2005 Oct: 0.2; 2005 Nov: 0.2; 2005 Dec: 0.2; 2005 Jan: 0.1; 2005 Feb: 0.1; 2005 Mar: 0.1; 2005 Apr: 0.1 | 1
0 | 2005 Mar: 0.33; 2005 Apr: 0.33; 2005 May: 0.34 | 1
Total days for Objective 2
3. Organize subset of data into accessible form
3.1 Continue to improve web-based metadata system, links to data | 0.1 | 0.1 | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 1
3.2 CSMEP website improvement | 2005 Oct: 0.25; 2005 Jan: 0.25; 2005 Apr: 0.25; 2006 Jul: 0.25 | 1
0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 1
Total days for Objective 3 | [12 empty] | 0
4. Evaluate ability to answer key questions with existing data
4.1 Organization of existing data for Snake Basin pilot design | 0.13 | 0.1 | 0.06 | 0.205 | 0.205 | 0.1 | 0.1 | 0.1 |  |  |  |  | 1
4.2 Organization of existing data for OR pilot design | 0.13 | 0.1 | 0.06 | 0.205 | 0.205 | 0.1 | 0.1 | 0.1 |  |  |  |  | 1
4.3 Organization of existing data for WA pilot design | 0.13 | 0.1 | 0.06 | 0.205 | 0.205 | 0.1 | 0.1 | 0.1 |  |  |  |  | 1
0 | 0.13 | 0.1 | 0.06 | 0.205 | 0.205 | 0.1 | 0.1 | 0.1 |  |  |  |  | 1
Total days for Objective 4 | [12 empty] | 0
5. Collaborative monitoring program design
5.1 Consolidate Snake River Pilot M&E design and PrOACT tradeoff analysis | 2005 Oct: 0.2; 2005 Nov: 0.2; 2005 Dec: 0.2; 2005 Jan: 0.2; 2005 Feb: 0.2 | 1
5.2 Convert SRB into practical plan for Salmon basin pilot (later OR and WA) | 2005 Jan: 0.2; 2005 Feb: 0.2; 2005 Mar: 0.2; 2005 Apr: 0.2; 2005 May: 0.05; 2006 Jun: 0.05; 2006 Jul: 0.1 | 1
5.3 DQO work -> M&E Tools for other subbasins in CRB / Marketing |  |  |  |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.2 | 0.2 | 1
5.4 Feed M&E results into NPCC Rolling Provincial Review Process | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 |  |  | 1
5.5 Get feedback from CRB entities on various M&E designs | 0.05 | 0.1 | 0.05 | 0.1 | 0.05 | 0.1 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1
Total days for Objective 5 | [12 empty] | 0
6. Multi-agency implementation of monitoring programs.
6.1 Develop broad conceptual plan for M&E implementation across CRB | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 1
Total days for Objective 6 | [12 empty] | 0
7. Multi-agency evaluation of results of new monitoring pgms.
7.1 Collaborative review of federal RME projects, WA SRFB Effectiveness Monitoring Projects, and other recent pilot projects | 0.05 | 0.05 | 0.05 | 0.1 | 0.2 | 0.1 | 0.1 | 0.05 | 0.05 | 0.05 | 0.1 | 0.1 | 1
0
Total days for Objective 7 | [12 empty] | 0
Total | [12 empty] | 0

## Billings FY 07
CSMEP Billings FY07 - NOT DONE YET
Projected $ billed per task per month
| 2005 | [7 empty] | 2006 |  |  |  |  | Total / task
Task | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Sum | in budget | Diff (should be zero)
1. Develop Work Plans / Interact w Prog. Entities (all tasks) | 10893.7354 | 10893.7354 | 10893.7354 | 10893.7354 | 10893.7354 | 10893.7354 | 10893.7354 | 10893.7354 | 21787.4708 | 21787.4708 | 43574.9415 | 43574.9415 | 217874.7075
1.1 Develop CSMEP Quarterly Workplans [1] | [12 empty] | 0
1.2 Quarterly Progress Reports | [12 empty] | 0
1.3 Preparation of Draft and Final Annual Report for FY05 | [12 empty] | 0
1.4 CSMEP conference calls and meetings | [12 empty] | 0
1.5 Coordination w PNAMP on joint activities and work products | [12 empty] | 0 |  | Task # | FY06 $'s | % $'s | Days | % Days
1.6 Present CSMEP progress at various Columbia Basin forums [2] | [12 empty] | 0 |  | Task 1 | 217874.7075 | 23.14% | 171 | 19.06%
[13 empty] | 0 |  |  |  | 0% |  | 0% | 968000
Total days for Objective 1 | [12 empty] | 0 |  |  |  | 0% |  | 0%
[13 empty] | 0 |  | Task 2 | 44099.9377 | 15.1% | 167 | 18.62%
2. Inventory existing data relevant to questions | [12 empty] | 0 |  | Task 3 | 32843.3179 | 3.925% | 85 | 9.476%
2.1 Inventory Tier 1 information [3] | 8594.8107 | 8594.8107 | 8855.2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26044.881 |  | Task 4 | 87287.8642 | 18.52% | 73 | 8.138%
2.2 Complete data inventory for second and third set of subbasins | 3611.0113 | 3611.0113 | 3611.0113 | 1805.5057 | 1805.5057 | 1805.5057 | 1805.5057 | 0 | 0 | 0 | 0 | 0 | 18055.0567 |  | Task 5 | 450856.8892 | 32.27% | 335 | 37.35%
2.3 Identify a third set of subbasins to inventory | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Task 6 | 87241.3383 | 3.885% | 30 | 3.344%
[13 empty] | 0 |  |  |  | 0% |  | 0%
Total days for Objective 2 | [12 empty] | 0 |  |  |  | 0% |  | 0%
[13 empty] | 0 |  | Task 7 | 33949.1626 | 3.159% | 36 | 4.013%
3. Organize subset of data into accessible form | [12 empty] | 0 |  | Total | 954153.2173 |  | 897
3.1 Continue to develop web-based data inventory system | 2959.202 | 2959.202 | 2959.202 | 2959.202 | 1479.601 | 1479.601 | 1479.601 | 1479.601 | 2959.202 | 2959.202 | 2959.202 | 2959.202 | 29592.0205
3.2 CSMEP website improvement | 812.8243 | 0 | 0 | 812.8243 | 0 | 0 | 812.8243 | 0 | 0 | 812.8243 | 0 | 0 | 3251.2974
3.3 Develop protocol for making data available to CSMEP analysts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total days for Objective 3 | [12 empty] | 0
0
4. Evaluate ability to answer key questions with existing data | [12 empty] | 0
4.1 Assess strengths & weaknesses of data for Tier 1 questions | 3397.1882 | 2613.2217 | 1567.933 | 5357.1045 | 5357.1045 | 2613.2217 | 2613.2217 | 2613.2217 | 0 | 0 | 0 | 0 | 26132.2172
4.2 Complete Tier 2 S&W Assessment for 2nd set of subbasins | 4015.6869 | 3088.9899 | 1853.3939 | 6332.4293 | 6332.4293 | 3088.9899 | 3088.9899 | 3088.9899 | 0 | 0 | 0 | 0 | 30889.8989
4.3 Complete Tier 2 S&W Assessment for 3rd set of subbasins | 3934.5473 | 3026.5748 | 1815.9449 | 6204.4784 | 6204.4784 | 3026.5748 | 3026.5748 | 3026.5748 | 0 | 0 | 0 | 0 | 30265.7481
4.4 Identify opportunities for Tier 3 Evaluations (C4 tables and beyond) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Total days for Objective 4 | [12 empty] | 0
0
5. Collaborative monitoring program design | [12 empty] | 0
5.1 Continue to develop Tier 1 & 2 sampling and response design options | 18919.1735 | 18919.1735 | 18919.1735 | 18919.1735 | 18919.1735 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94595.8677
5.2 Test and revise Tier 1 & 2 design options / template [4] | 0 | 0 | 0 | 18626.341 | 18626.341 | 18626.341 | 18626.341 | 4656.5853 | 4656.5853 | 9313.1705 | 0 | 0 | 93131.7051
5.3 Develop & evaluate Tier 3 design template [5] | 0 | 0 | 0 | 0 | 18462.0704 | 18462.0704 | 18462.0704 | 18462.0704 | 18462.0704 | 18462.0704 | 36924.1409 | 36924.1409 | 184620.7044
5.4 Improve mainstem Tier 3 monitoring framework [6] | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 4005.9413 | 0 | 0 | 40059.4133
5.5 Get feedback from CRB entities on various M&E designs | 1922.4599 | 3844.9199 | 1922.4599 | 3844.9199 | 1922.4599 | 3844.9199 | 1922.4599 | 3844.9199 | 3844.9199 | 3844.9199 | 3844.9199 | 3844.9199 | 38449.1987
0
Total days for Objective 5 | [12 empty] | 0
0
6. Multi-agency implementation of monitoring programs. | 8724.1338 | 8724.1338 | 4362.0669 | 4362.0669 | 4362.0669 | 4362.0669 | 8724.1338 | 8724.1338 | 8724.1338 | 8724.1338 | 8724.1338 | 8724.1338 | 87241.3383
6.1 Develop broad conceptual plan for M&E implementation across CRB | [12 empty] | 0
0
Total days for Objective 6 | [12 empty] | 0
0
7. Multi-agency evaluation of results of new monitoring pgms. | 1697.4581 | 1697.4581 | 1697.4581 | 3394.9163 | 6789.8325 | 3394.9163 | 3394.9163 | 1697.4581 | 1697.4581 | 1697.4581 | 3394.9163 | 3394.9163 | 33949.1626
7.1 Collaborative review of federal RME projects and WA SRB Effectiveness Monitoring Projects, and other recent pilot projects | [12 empty] | 0
0
0
Total days for Objective 7 | [12 empty] | 0
0
Total | [12 empty] | 954153.2173
Estimated total billings per month | 73488.1729 | 71979.1726 | 62463.58 | 87518.6385 | 105160.7399 | 75603.8843 | 78856.3156 | 62493.2317 | 66137.7817 | 71607.1913 | 99422.2544 | 99422.2544 | 954153.2173
% of annual billings/month | 7.702% | 7.544% | 6.546% | 9.172% | 11.02% | 7.924% | 8.265% | 6.55% | 6.932% | 7.505% | 10.42% | 10.42% | 8.333% | 79512.7681
Estimated total billings per quarter | 2005 Dec: 207930.9256; 2005 Mar: 268283.2628; 2006 Jun: 207487.329; 2006 Sept: 270451.7
% of annual billings/quarter | 2005 Dec: 21.79%; 2005 Mar: 28.12%; 2006 Jun: 21.75%; 2006 Sept: 28.34%