Developing a Columbia Basin White Sturgeon Monitoring Strategy: Sub-regional Workshop Process and Sideboards

For the Sub-Regional Workshops to Establish a Basin-wide Strategic Plan

GOAL

- Develop a monitoring framework and project specific implementation strategy for white sturgeon monitoring based on population metrics and hatchery effectiveness monitoring within the Columbia River Basin that meets the needs of the Northwest Power and Conservation Council’s (NPCC) Fish and Wildlife Program (Program) and regional fisheries management objectives.

- Prioritize white sturgeon population specific monitoring needs.

- Confirm inventories of existing white sturgeon monitoring work.

- Identify potential changes to existing projects to meet regional monitoring needs and identify and prioritize remaining gaps that need to be filled.

- Provide information in a well documented format for use in a workshop that will produce, based upon the recommendations received, a monitoring framework and project specific implementation strategy for white sturgeon.

## SIDEBOARDS

- The scope is limited to white sturgeon populations. Projects monitoring white sturgeon that also address other resident fish will be noted and potentially a given higher value.

- The strategy must be legal (i.e., the outcome must comply with legal obligations such as under the Power Act, ESA, NEPA, etc.). Also, the strategy must be consistent with entities’ statutory obligations.

- The strategy must be consistent with the NPCC’s Program which includes the Accord commitments.

- The framework and strategy should support, in-part, management goals/needs.

- The monitoring strategy will use existing monitoring guidance to the extent practicable.

- Recommendations of all existing white sturgeon workgroups will be considered when developing the monitoring framework and strategy.

- Discussions will not include hatchery facility specific monitoring such as spawner ratios, disease, and other monitoring specific to an HGMP.

- The strategy must be implementable (e.g., within BPA's contracting process where applicable).

- The strategy must respect previous Accord agreements, though outcomes from this process could involve recommendations for changes in some Accord M&E projects. Any suggested changes to Accord projects will need to be agreed-upon by the Accord party.

## WORKSHOP TASKS AND OUTPUTS

- For each population, verify the current white sturgeon monitoring projects listed in the inventory tables. The population metrics and hatchery effectiveness inventory should identify monitoring projects from all funding sources. Also, identify if the project is important for other fish species monitoring.

Output A. Updated and verified Comparison Table

- Verify or agree on population specific monitoring needs and strategies for population metrics and hatchery effectiveness within the Comparison Table based on:

  - Management plan monitoring guidance

  - NPCC monitoring objectives

Output B - Verify or agree on monitoring strategies or design for each population that addresses population metrics and hatchery effectiveness within the sideboards and as expressed in the verified Comparison Table.

- Identify GAPS between A & B

Output C –Further update the Comparison Tables that clearly identify GAPS and come to agreement on the priority GAPS that will be addressed during the development of alternative monitoring strategies.

- Develop three alternative integrated monitoring strategies specific to your regional fish population monitoring needs :

  - Alternative 1: Increased Efficiencies under Existing Level of Funding

- Develop an efficient, integrated monitoring strategy to fill GAPS based on current project funding. This alternative aims to fill the GAPS through increased efficiencies under the existing by:

    - Re-structuring current projects such as modifying scope,

    - Work with Accord parties to focus/modify scope of some of the new projects to address GAPS,

    - Eliminating redundancies by coordinating among projects,

    - Eliminating projects that do not meet the sideboards above and that are not critical for other monitoring needs. Identify consequences associated with elimination of projects.

    - Identify any cost savings resulting from changes to existing projects, such as combining projects to reduce overhead cost, which can be used to address gaps - hence resulting in a net zero budget change.

    - Identify consequences of GAPS that cannot be addressed given this budget limitation.

    - Identify non-BPA funded projects that are contributing to implementing the strategy. This will assist in focusing BPA funds to other aspects of the monitoring strategy currently not funded by any other entity.

  - Alternative 2: Increased Efficiencies and Increased Regional Funding

- Develop an efficient strategy using Alternative 1, but allow for new projects funded from additional regional funding to cover costs needed to fill remaining GAPS not covered under Alternative 1.

    - Clearly identify benefits of implementing the strategy proposed under Alternative 2 compared to Alternative 1

  - Alternative 3: Increased Efficiencies and Reduced RM&E Funding

- Develop an efficient monitoring strategy based on Alternative 1 from above less 10% of the current BPA funding.

    - Clearly identify consequences of implementing Alternative 3 compared to Alternative 1

Output D – Three alternative monitoring scenarios with prioritized projects