# Bonneville Power Administration

# Fish and Wildlife Program FY99 Proposal

# Section 1.  General administrative information

Yakima Phase II Screens - Construction

Bonneville project number, if an ongoing project	9107500

Business name of agency, institution or organization requesting funding

US Bureau of Reclamation

Business acronym (if appropriate)	USBOR

Proposal contact person or principal investigator:

Name	R. Dennis Hudson

Mailing Address	1150 N. Curtis Rd. - Suite 100

City, ST Zip	Boise ID  83706-1234

Phone	(208) 378-5250

Fax	(208) 378-5171

Email address	rhudson@pn.usbr.gov

Subcontractors.

| Organization | Mailing Address | City, ST Zip | Contact Name |
| --- | --- | --- | --- |
| Washington Department of Fish and Wildlife | PO Box 9155 | Yakima WA 98909 | John Easterbrooks |

NPPC Program Measure Number(s) which this project addresses.

7.11B.1

NMFS Biological Opinion Number(s) which this project addresses.

Other planning document references.

Subbasin.

Yakima

Short description.

Install new fish screens at all significant diversions in the Yakima River Basin to keep juvenile salmon and steelhead from being diverted and lost in canals during outmigration.  Improve adult upstream passage at selected sites.

# Section 2.  Key words

| Mark | Programmatic Categories | Mark | Activities | Mark | Project Types |
| --- | --- | --- | --- | --- | --- |
| X | Anadromous fish | X | Construction | X | Watershed |
| + | Resident fish |  | O & M |  | Biodiversity/genetics |
|  | Wildlife |  | Production |  | Population dynamics |
|  | Oceans/estuaries |  | Research |  | Ecosystems |
|  | Climate |  | Monitoring/eval. |  | Flow/survival |
|  | Other |  | Resource mgmt |  | Fish disease |
|  |  |  | Planning/admin. |  | Supplementation |
|  |  |  | Enforcement |  | Wildlife habitat en- |
|  |  |  | Acquisitions |  | hancement/restoration |

Other keywords.

passage facilities

# Section 3.  Relationships to other Bonneville projects

| Project # | Project title/description | Nature of relationship |
| --- | --- | --- |
| 9503300 | O&M of Yakima Fish Protection, Mitigation & Enhancement Facilities. | Provides on-going operation and maintenance activities at completed screens. |
| 9200900 | Yakima Screens - Phase II - O&M | Provides on-going operation and maintenance activities at completed screens. |
| 9105700 | Yakima Phase II Screen Fabrication | Provides fabrication and installation of screens and other mechanical and metalwork items at Phase II screen sites. |

# Section 4.  Objectives, tasks and schedules

## Objectives and tasks

| Obj 1,2,3 | Objective | Task a,b,c | Task |
| --- | --- | --- | --- |
| 1 | Provide screens at all Phase II diversion sites that will meet current agency design criteria for effective fish protection and passage. | a | Develop schedules and budgets and coordinate project implementation |
|  |  | b | Develop conceptual plans and obtain consensus of all interested parties at each site |
|  |  | c | Prepare designs and specifications |
|  |  | d | Award construction contracts and supervise and administer construction. |

## Objective schedules and costs

| Objective # | Start Date mm/yyyy | End Date mm/yyyy | Cost % |
| --- | --- | --- | --- |
| 1 | 10/1992 | 5/2001 | 99.99% |
|  |  |  | TOTAL 99.99% |

Schedule constraints.

Canal system consolidation proposals must be implemented by January 1999 or else we must proceed to screen existing diversions.  Water rights uncertainties must be resolved  by Jan 1999 or else we will proceed with sizing based on historical diversions.

Completion date.

2001

# Section 5.  Budget

## FY99 budget by line item

| Item | Note | FY99 |
| --- | --- | --- |
| Personnel | Direct labor for project coordination, design, contract administration, construction supervision | $400,000 |
| Fringe benefits |  | $140,000 |
| Supplies, materials, non-expendable property |  | $5,000 |
| Operations & maintenance |  |  |
| Capital acquisitions or improvements (e.g. land, buildings, major equip.) |  |  |
| PIT tags | # of tags: |  |
| Travel |  | $50,000 |
| Indirect costs | 19.5% of direct labor + benefits | $105,000 |
| Subcontracts | Construction contracts | $780,000 |
| Other |  | $20,000 |
| TOTAL |  | $1,500,000 |

## Outyear costs

| Outyear costs | FY2000 | FY01 | FY02 | FY03 |
| --- | --- | --- | --- | --- |
| Total budget | $1,000,000 | $1,000,000 |  |  |
| O&M as % of total |  |  |  |  |

# Section 6.  Abstract

All Phase II diversion sites will be screened to meet current agency design criteria for effective fish protection and fish passage by the year 2001.  The target objectives of adequate juvenile fish passage are designed to meet three criteria which will: (1) reduce delay to a degree approaching zero; (2) reduce the possibility of injury to a degree approaching zero; and (3) allow fish to pass with little additional expenditure of energy.  Selected Phase II screens  have been (and others will be) monitored and evaluated using live fish to determine effectiveness of the new screens.

This program directly relates to measure 7.11B.1 of the  1994 Columbia Basin Fish and Wildlife Program as amended in 1995.

# Section 7.  Project description

a.	Technical and/or scientific background.

b.	Proposal objectives.

c.	Rationale and significance to Regional Programs.

d.	Project history

Planning Report completed in FY1990.  Preliminary and final design initiated in FY1990-91.  First construction initiated in FY1992.  As of the end of FY1997, construction of screens, consolidation of ditches, elimination of diversions or other corrective measures are complete on about 80% (55) of the Phase II diversions.  About 40% of the sites have been eliminated due to non-use or have been screened by the Washington Department of Fish and Wildlife using small prefabricated modular screen units.  Data collection, preliminary and final design is underway on the remaining 15 sites.  Uncertainties in the consolidation process continue to delay construction of some new screens until final consolidation plans are made and funding is secured.  Water rights ajudication has delayed construction at some sites because of uncertainties in selecting appropriate design flows.  Difficulties in securing rights-of-way at some sites (particularly on the YIN reservation) has delayed and may continue to delay construction at some sites.  We are proceeding with preliminary design work at all sites so that there will be enough lead time to prepare final designs and award contracts for construction once consolidation and water rights decisions are firmed up.

e.	Methods.

f.	Facilities and equipment.

g.	References.

# Section 8.  Relationships to other projects

The Phase II program is facilitated by  the Yakima Fish Passage Technical Work Group.  This group consists of representatives from BPA, BOR, NMFS, WDFW, CBFWA, CRITFC, Yakama Indian Nation, Yakima River Basin Association of Irrigation Districts, and other state, Federal and local agencies and interested individuals.

# Section 9.  Key personnel

# Section 10.  Information/technology transfer

Design standards and criteria are updated frequently to reflect lessons learned at earlier sites.  We participate in the Annual Fish Screen Workshop to share information with others working on fish passage issues in the western U.S.