# Bonneville Power Administration

# Fish and Wildlife Program FY99 Proposal

# Section 1.  General administrative information

Yakima Basin Environmental Education

Bonneville project number, if an ongoing project	9405900

Business name of agency, institution or organization requesting funding

Educational Service District 105

Business acronym (if appropriate)	ESD 105

Proposal contact person or principal investigator:

Name	Julie Bradley

Mailing Address	33 South Second Ave.

City, ST Zip	Yakima, WA. 98902

Phone	509-575-2885

Fax	509-575-2918

Email address	julieb@destiny.esd105.wednet.edu

Subcontractors.

| Organization | Mailing Address | City, ST Zip | Contact Name |
| --- | --- | --- | --- |
| EcoNorthwest | 270 Westridge Rd | Selah, WA. 98942 | Bob Tuck |
| ––––– | ––––– | ––––– | ––––– |
| ––––– | ––––– | ––––– | ––––– |
| ––––– | ––––– | ––––– | ––––– |

NPPC Program Measure Number(s) which this project addresses.

7.6B.6

NMFS Biological Opinion Number(s) which this project addresses.

7.6B6

Other planning document references.

–––––

Subbasin.

Yakima

Short description.

Provides training for teachers and students which allows them the opportunity to participate in the maintainance and restoration of their local watershed through integrated, hands-on curriculum that meets the essential learnings mandated by the state.

# Section 2.  Key words

| Mark | Programmatic Categories | Mark | Activities | Mark | Project Types |
| --- | --- | --- | --- | --- | --- |
| X | Anadromous fish | – | Construction | – | Watershed |
| – | Resident fish | – | O & M | – | Biodiversity/genetics |
| – | Wildlife | – | Production | – | Population dynamics |
| – | Oceans/estuaries | – | Research | X | Ecosystems |
| – | Climate | – | Monitoring/eval. | – | Flow/survival |
| X | Other | – | Resource mgmt | – | Fish disease |
|  |  | – | Planning/admin. | – | Supplementation |
|  |  | – | Enforcement | * | Wildlife habitat en- |
|  |  | – | Acquisitions |  | hancement/restoration |

Other keywords.

Education, teacher training, salmon life cycle, raisins salmon in the classroom, water quality monitoring, riparian restoration, stream inventories, community service projects, curriculum  integration, essential learnings alignment

# Section 3.  Relationships to other Bonneville projects

| Project # |  | Nature of relationship |
| --- | --- | --- |
| ––––– |  | ––––– |
| ––––– | ––––– | ––––– |
| ––––– | ––––– | ––––– |
| ––––– | ––––– | ––––– |

# Section 4.  Objectives, tasks and schedules

## Objectives and tasks

| Obj 1,2,3 | Objective | Task a,b,c | Task |
| --- | --- | --- | --- |
| 1 | To provide relevant, hands-on curriculum to all participating teachers and their students | a | develop communications links with local research projects that have the potential for student involvement |
| –– | ––––– | b | involve students in community problem solving related to local environmental issues, and arrange for area scientists to participate in teacher training sessions and student presentations |
| 2 | Provide teachers and students with necessary equipment and materials to participate in local environmenatal education activities | a | identify, purchase, and maintain equipment related to field trip topics |
| –– | ––––– | b | organize a check-out system for the equipment |
| 3 | Continue to support teachers and students who have participated in the program over the years | a | provide updated information and access to newly acquired resources |
| –– | ––––– | b | provide resources for ongoing student projects |
| 4 | Foster community partnerships to improve both education and the environment | a | involve various community agencies and organizations in active participation in classroom activities |
| –– | ––––– | b | involve students in presenting possible solutions to problems they have identified to appropriate agencies or organizations |
| 5 | Stimulate student interest in science and the environment as possible career choices | a | arrange for local biologists and other scientists to participate in field trip trainings and classroom presentations |
| –– | ––––– | b | offer opportunities for student involvement in various area research projects |
| 6 | Protect and rehabilitate local habitat | a | arrange partnerships with local agencies and organizations to involve students in relevant projects |
| –– | ––––– | b | provide a curriculum with appropriate information aimed at creating positive attitudes about the environment among future decision makers |

## Objective schedules and costs

| Objective # | Start Date mm/yyyy | End Date mm/yyyy | Cost % |
| --- | --- | --- | --- |
| 1 | 8/1999 | 7/2000 | 69.00% |
| 2 | 8/1999 | 7/2000 | 6.00% |
| 3 | 8/1999 | 7/2000 | 5.00% |
| 4 | 8/1999 | 7/2000 | 5.00% |
| 5 | 8/1999 | 7/2000 | 5.00% |
| 6 | 8/1999 | 7/2000 | 10.00% |
|  |  |  | TOTAL 100.00% |

Schedule constraints.

–––––

Completion date.

2010

# Section 5.  Budget

## FY99 budget by line item

| Item | Note | FY99 |
| --- | --- | --- |
| Personnel | 180 days @ $240.00/day | $43,200 |
| Fringe benefits | ––––– | $14,256 |
| Supplies, materials, non-expendable property | supplies and instructional materials | $2,500 |
| Operations & maintenance | ESD 105 office costs | $7,600 |
| Capital acquisitions or improvements (e.g. land, buildings, major equip.) | ––––– | ––––– |
| PIT tags | # of tags: ––––– | ––––– |
| Travel | Teacher field trip transportation @ $500/trip X 4 trips | $3,000 |
| Indirect costs | 9.00% | $9,860 |
| Subcontracts | EcoNorthwest | $15,000 |
| Other | 50 substitutes @ $120/sub X 4 trips | $24,000 |
| TOTAL |  | $119,416 |

## Outyear costs

| Outyear costs | FY2000 | FY01 | FY02 | FY03 |
| --- | --- | --- | --- | --- |
| Total budget | $119,416 | $123,000 | $126,000 | $130,000 |
| O&M as % of total | ––––– | ––––– | ––––– | ––––– |

# Section 6.  Abstract

The Environmental Education Training Program offers teachers throughout the Yakima Valley the opportunity to become involved with their students in real life projects to protect, enhance, analyze and provide solutions to water resource problems in their community.  This ongoing program is in sixth year of operation.  In excess of 200 teachers throughout the region have been involved and annually over 2000 students are actively involved in hands-on activities related to understanding the on-going stewartship of our watershed.  Activities range from math and science investigations to language arts, journal writing, historical investigations of the watershed, civics, economics, and responsible citizenship through knowledge of water issues like water quality monitoring, salmon life cycle needs, stream hydrology, riparian habitat functions, wetlands, etc.

Students have developed community partnerships to monitor water quality, restore riparian corridors, raise salmon in their classroom for release into various tributaries, monitor storm run-off, collect data annually on salmon redds in the upper Yakima River.  Each year additional teachers will be trained adding additional schools and students to the evergrowing number of involved participants.  An independent evaluation of the program was conducted in 1998 and will be an on-going part of the program documenting program outcomes, teacher reaction, and community involvement as well as the long term impact of the program on teaching best practices.

# Section 7.  Project description

a.	Technical and/or scientific background.

Water conservation and the maintenance of high water quality are priority issues in the Yakima River watershed.  The increasing concern for potential salmon recovery is also of high interest to many in the Yakima Valley.  Approximately 80% of the mainstream Yakima River flows are diverted and re-diverted for agricultural irrigation.  Return flows are serioulsy polluted and, as a result, the lower Yakima River exceeds permissible state standards for DDT, ammoniea and other nutrients, temperature and turbidity.  Because of these conditions, the Yakima River has been listed as ÒimpairedÓ under the Federal Clean Water Act.  Once abundant salmon and steelhead populations have dwindled to precariously low levels and other beneficial uses of Yakima River waters are in jeopardy.  In addition to agriculture, grazing, logging, mining and urban development have contributed to water problems in the Yakima River Basin

This created a local social and political climate with a high potential for controversy.  This also created a great need for education about the importance of water conservation, water quality, and caring for out watershed ecosystem.

In the area of education reform the Washington Office of the Superintendent of Public Instruction has issued a mandate requiring that all Washington schools teach environmental education K-12 in an intefrated curriculum.  A great deal of research points to the success of an interactive curriculum whereby students are actively engaged in problem identification, investigation, data collection and analysis, and synthesis.  Environmental understanding, not just environmental awareness, is an important componet of an educated and literate individual and therefore, environmental education has a very important role to play.  It provides great opportunities for inter disciplinary work that allows students to link together hands-on science investigations with real world solutions to local issues and problems.

This program plays a significant role in teacher training.  Science education reform requires that teachers need to teach in different ways.  This program allows teachers to opportunity to create innovative curriculum that leads students toward an understanding of important local themes and concepts related to our watershed.  With genuine understanding of the natural world comes an appreciation and concern that will hopefully lead to sustainable actions, attitudes, and values.

This program has provided the opportunity for over 2000 student each year to observe spawning salmon on the upper Yakima River.  Several long term school projects have developed with the help of partnerships with the North Yakima Conservation District, Washington State Department of Fish & Wildlife, and the city of Yakima Parks Department resulting in the construction of two nature trails along local streams.

Several schools raise salmon in their classrooms for release into three local streams.  This activity over the past five years resulted in confirmed returns of adult coho into Wide Hollos Creek last year. The governor commended the students involved in this effort during his 1998 state of the state address.  Other successful program activities include water quality monitoring by several schools along the Yakima River, monitoring of suspended solitds in local drains, and K-12 curriculum activities related to salmon life cycle needs.

b.	Proposal objectives.

1. To provide relevant, hands-on curriculum to all participating teachers and their students by

a) developing communication links with local research projects that have the potentail for student involvement,

b) involving students in community problem solving related to local environmental issues, and arranging for area scientists to participate in teacher training sessions and student presentations.

2. To provide teachers and students with necessary equipment, by

a) identifying, purchasing and maintaining equipment related to field trip topics and

b) organizing a check-out system for the equipment

3. To continue supporting teachers and students who have participated in the program during the last six years by,

a) providing updated information and access to newly acquired resources,

b) provide resources for ongoing student projects

4. Tp foster community partnerships to improve both education and the environment by,

a) involving various community agencies and organizations in active participation in classroom activities, and

b) involving students in presenting possible solutions to problems they have identified to appropriate agencies or organizations

5. To stimulate student interest in science and the environment as possible career choices by,

a) arranging for local biologists and other scientists to participate in field trip trainings and classroom presentations, abd

b) offering opportunities for student involvement in various area research projects

6. To protect and rehabilitate local habitat by

a) arranging partnerships with local agencies and organizations to involve students in relevant projects, and

b) provid a curriculum with appropriate information aimed at creating positive attitudes about the environment among future decision makers

c.	Rationale and significance to Regional Programs.

The Environmental Education Program specifically addresses Section 76B.6 of the Fish and Wildlife Program by:

providing educational training, materials, and support for teachers

providing relevant, hands-on field oriented environmental education opportunities for students, focusing on water, salmon life cycle, and watershed management

forming partnerships with teachers and students with scientific and technical profressionals across a broad spectrum of resource activities and interests involved in watershed and resource management

providing opportunities for real world project involvement by students, including water quality, riparian restoration, salmon life cycle, and related items

providing the opportunity for students to share the results of their field work and observations with other students both in and outside the Yakima Basin through such means as science fairs and the world wide web

The Environmental Education Program supports the entire concept of salmon recovery through watershed restoration embodied in Section 7 of the Fish and Wildlife Program.  This program provides teachers and students a grounding in integgrated resouce management, the importance of water to all phases of human existence, the need to consider various human communities when addressing water and related resources, the manner in which all resources are connected, and the need for an open and inclusive process when making resource management decisions.

Through this program, students obtain a broad understanding of the complexities with respect to natural resource management and are better equiped to make informed decisions when addressing resource issues as an adult.  By involving professional scientists and resource managers from a broad specturm of agencies and user groups, teachers and students not only gain knowledge and insights into resource management and access to resource professionals, but students are exposed to potential career opportunities in natural resource management.

There are a number of education programs offered by various resource agencies in the Columbia Basis, but this is the only program that provides hands-on training for participating teachers, continuing support for participating teachers after they have completed the program and provides substitute teachers for the teachers on the training days.  Materials from other resource training and education efforts are utilized when appropriate.

The scope and extent of student projects and work products produced as a reslut of this program are only limited by the imagination of the teachers and students.  Teachers have integrated natural resources and related issues into math and science lessons, english papers, history term papers, and art projects such as mural and paper macheÕ

d.	Project history

The Yakima Basin Environmental Education Program (9405900) has received $99,992 in 1997, $97,681 in 1996, $94,701 in 1995, $94,701 in 1994.

The success of the program is indicated in the attached independent evaluation.  To date the program has trained 150 teachers that continue to sustain curriculum and activities.  Over 2000 students each year are actively involved in related projects, field trips, and classroom activities related to our local watershed restoration.

e.	Methods.

Objective 1:  To provide relevant, hands-on curriculum to all participating teachers and their students

In each two year program cycle, teachers take part in eight field trip training experiences covering such topics as understanding water needs and uses, stream hydrology, the value of wetlands, riparian habitat functions, monitoring and maintaining water quality, and salmon life cycle and spawning requirements.  The training allows teachers to become confident in and competent about these issues.

Teachers, after each training session, are given relevant materials and equipment.  They are then able to replicate their experiences with their students.  Students are involved in hands-on activites about crucial environmental issues in an interdisciplinary context.

Objective 2:  Provide teachers and students with necessary equipment and materials to participate in local environmental education activities

This program provides teachers with necessary equipment required to do project work in the field with their students including water quality testing kits, waders, kick nets, measuring tapes, emhoff cones, etc.  These items are maintained and available on a check-out basis through the Educational Service District 105 (ESD 105)

Additional items for classroom demonstration and instruction are also provided.  These include groundwater models, watershed demonstration models, curriculum guides, maps posters, and field study guides acquired through the program budget and provided for teachers on request.

Objective 3:  To continue to support teachers and student who have participaed in the program during previous training cycles

Each fall all present participating teachers and students as well as all past participating teachers and students are encouraged to visit the spawning salmon in the upper Yakima River by arranging a scheduled guided field trip with expert biologists on hand at the site to provide information and instruction.  IN this way over 2000 students observe spawning salmon each year.

Additionally, every teacher who has participated in the training program can arrange for classroom speakers or specific classroom presentations provided by this program with the cooperation of the several partnerships involved throughtout the program training.

Objective 4:  To foster community partnerships to improve both education and the envrionment

Through the school year teachers and students are advised of various opportunities to become actively involved with specific projects funded by various local, state, federal and tribal programs.  These communtity agencies and environmental organizations allow imput and participation of various classrooms on riparian restoration, water quality monitoring, nature mapping and inventory, etc.

Through suggested classroom activities in the training program, teachers are encouraged to involve their students in student identifies projects related to the local watershed.  Students identify a problem, test their hypothesis, and then present their findings to the appropriate agency or organization. (Example: Selah Middle School students presented their water quality monitoring data to City of Selah Treatment Plant)

Objective 5: To stimulate student interest in science and the environment as possible career choices

This program provides many opportunities for students to observe local scientists, biologists and technicians in the field.  Partnerships with local agencies have allowed students to participate in field work in water quality monitoring, soil sampling, wetland management, fisheries, forestry, and wildlife.

Objective 6: To protect and rehabilitate local habitat

The program actively provides teachers with classroom activities and curriculum with approprate information aimed at creating positive attitudes about the local environment among future decision makers

This program arranges partnerships with local agencies and organizations to involve students in relevant projects that improve and protect habitat.  Some of these have included the development and maintainance of a nature trail along Wide Hollow Creek, monitoring water quality and clean up of the creek in Randall Park, monitoring salmon redds in the upp Cle Elum River, monitoring wetland in Sportsman Park .

f.	Facilities and equipment.

Facilities for the operation of the Environmental Education Training Program include office space at the Educational Service District office including the following:

space

support staff

computer services and networking

copying

phone

Equipment for the operation of the Environmental Education Training Program includes:

charter bus for each of the teacher training field trips (4 trips each year)

replacement chemicals and equipment for water quality test kits

replacement waders, kick nets, buckets, measuring tapes, etc.

field study guides, curriculum packets, posters, etc.

g.	References.

# Section 8.  Relationships to other projects

It is the goal of the Environmental Education Training Program to involve the teachers and students in active research projects sponsored by local, state, federal and tribal programs, as well as cultivate community service project relationships with a number of local businesses and environmental organizations.  Twelve organizations actually took part in conducting training activities for teachers and making field trip and classroom presentations.  The were:  Boise Cascade, Bureau of Reclamation, City of Yakima, Nature Conservancy, North Yakima Conservation District, Pacific Power & Light, Tree Top, Washington State Fish and Wildlife Department, Washington State Parks, Yakama Indian Nation Fisheries Department, Yakama Indian Nation Wildlife Department.

These organizations made substantial contributions, in both time and resource, to the program.  Each saw the program as valuable to the students, to the community, and to their agency.  Some of the reasons they gave for taking part in the program were that it promotes understanding of environmental issues and allowed them to network with the schools giving the organization a way of reaching future decision makers in an ongoing and positive way.  Carrying on educational activities in cooperation with the schools results in positive public exposure for the organization and provides educational opportunities for students enabling the agency and its employees to fulfill an important civic responsiblity.

# Section 9.  Key personnel

# Section 10.  Information/technology transfer