Proposal ID 20025

PART II - NARRATIVE

Section 7.  Abstract

The average number of wild summer steelhead escaping to the Deschutes River has declined dramatically since the 1980's, prompting the proposed listing of the population as a threatened species by National Marine Fisheries Service (NMFS).  Although a number of factors could potentially be contributing to this population decline, the Oregon Department of Fish and Wildlife (ODFW) believes one possible cause could be the loss of reproductive capacity as a result of indigenous steelhead spawning with out-of-basin stray hatchery steelhead.  Hatchery stray steelhead have dominated steelhead runs in the Deschutes River in recent years.  In 1994 stray hatchery steelhead comprised 76% of the steelhead run monitored at Sherars Falls (river mile 43).  Wild steelhead escapements to the Deschutes River have declined from 6,715 in 1984 to 1,719 in 1997 (Annual Reports, Mid-Columbia Fish District).  It also appears possible that a portion of the “wild” escapement may also be stray fish.

This project would compile and analize existing Columbia Basin summer steelhead data to determine the magnitude and cause of the straying problem in the Deschutes River.

Section 8.  Project description

a.	Technical and/or scientific background

The Oregon Fish and Wildlife Commission, in an October 21, 1997 letter to NMFS, requested that NMFS and ODFW work cooperatively to conduct a joint review of available Columbia Basin steelhead data to determine the magnitude and causes of summer steelhead straying into the Deschutes River.  In December 1997, ODFW convened a multi-agency work group, including representation from the Steelhead Management agencies and conservation groups, to address this stray issue.  Initial major findings of the work group include the following: (1) the proportion of hatchery steelhead strays in the Deschutes River has increased dramatically since the mid 1980's and currently dominates the run;  (2) in

addition to hatchery strays, it is possible that a significant portion of the wild origin fish in the Deschutes River may be strays; (3) a 1996 radio telemetry study indicates tha a substantial percentage of Columbia Basin steelhead not only migrated into the Deschutes River, but stayed in the river and presumably spawned; (4) a comparison of limited coded wire tag recoveries seemed to indicate several upper Columbia Basin fish hatcheries had high stray indices; (5) more detailed coded wire tag data analysis indicated that broodstock source and smolt release location are potential factors influencing straying; and (6) preliminary findings have shown no obvious correlation between straying and transported smolts.

b.	Rationale and significance to Regional Programs

Hatchery summer steelhead production in the upper Columbia River / Snake River basins, and/or downstream smolt transportation may be contributing to the proliferation of stray steelhead entering the Deschutes River.  It is apparent that many of these stray steelhead are remaining in the Deschutes River to spawn.

The spawning of stray steelhead with the indigenous Deschutes River summer steelhead may be posing significant genetic risk to the Deschutes population.  The wild Deschutes population has declined from 6,715 in 1984 to 1,719 in 1997.  The decline in the number of wild (naturally produced) adults had occurred despite near record numbers of spawning steelhead in the Deschutes River in the last decade.

The Deschutes River has long been one of Oregon’s premiere summer steelhead streams.  The declining numbers of wild steelhead could result in the listing of this population, as well as restrictions on a popular sport and tribal subsistence fishery.

c.	Relationships to other projects

There is a potential that other BPA funded steelhead projects in the Columbia River Basin are threatening the exinction of the indigenous Deschutes River population.  The Deschutes River population is proposed for listing as a Threatened Species, under the Endangered Species Act.

Benefits from BPA funded Deschutes subbasin fish habitat restoration projects could be in jeopardy if stray steelhead spawning with indigenous fish is reducing genetic fitness and smolt to adult survival.  There are a number of other non-BPA funded programs underway in the subbasin that are attempting to improve watershed conditions, stream habitat, and ultimately steelhead production.  These complimentary projects are being implemented by the Bureau of Land Management (BLM), ODFW, CTWSRO, Natural Resources Conservation Service (NRCS), Farm Services Administration (FSA), watershed councils, and soil and water conservation districts.

d.	Project history (for ongoing projects)

This is a new project proposal.  However, a multi-agency work group has met to discuss the stray steelhead issue and review some preliminary steelhead data.  This work group has agreed there is a significant problem with stray steelhead entering and remaining in the Deschutes River.  The work group supports a project that will specifically identify the magnitude and cause of the straying phenomina, as well as identify potential remedial measures that could be implemented to reduce or eliminate the problem.

e.	Proposal objectives

The primary objectives of this project proposal are to (1) assess the magnitude of straying summer steelhead into the Deschutes River, (2) determine the causes of adult summer steelhead straying into the Deschutes River, and (3) report findings and the conclusions of the data analized.

Specific proposal objectives include:

Objective 1.	Assess the magnitude of straying summer steelhead into the Deschutes River.

Performance Measures:	(1) A report summarizing the numbers and proportion of hatchery and wild stray steelhead in the Deschutes River.

Purpose:	This objective is intended to evaluate the trends, from 1977 to present, in hatchery strays compared to Deschutes hatchery origin and wild steelhead numbers based on data collected annually at Sherars Falls, the Pelton Trap, the Warm Springs National Fish Hatchery trap, and the sport and tribal in-river fisheries based on fin marks and coded wire tag recoveries.

Objective 2.	Determine the causes of adult summer steelhead straying into the Deschutes River.

Performance Measures:	A report summarizing the cause of hatchery and wild steelhead straying into the Deschutes River.

Purpose:	This objective is intended to provide for the analysis of steelhead data from Columbia Basin fish hatcheries, as well as data on smolt migration monitoring, the transportation program, river conditions, and environmental factors that could help provide the answers for the stray problem.

Objective 3.	 Report findings and the conclusions of the data analized.

Performance Measures:	A report summarizing the magnitude and cause of hatchery and wild steelhead straying into the Deschutes River.

Purpose:	This report would present the information, including the causes for the steelhead straying problem.  The report would include an analysis of data that will help to identify remedial measures that can be implemented to minimize or eliminate the steelhead stray problem.

f.	Methods

The Deschutes River Stray Summer Steelhead Assessment will be implemented with the following tasks listed with the specific project objective presented in Section 4 of this proposal.

Objective 1.	Assess the magnitude of straying summer steelhead into the Deschutes River.

Task 1.	Evaluate time trends from 1977 to present (numbers and proportion of the run) of hatchery strays, compared to Deschutes hatchery origin and wild steelhead returns at Sherars Falls (Rm 43), sport and tribal fisheries, Pelton fish trap(Rm 100), and the Warm Springs National Fish Hatchery trap based on fin clips and coded wire tag recoveries.

Task 2.	Determine the origin of hatchery strays at each Deschutes River sampling location based on coded wire tags.

Task 3.	Determine the stray rate (proportion of coded wire tags recovered in the Deschutes) by origin at each location.

Task 4.	Determine the origin of steelhead that do not stray into the Deschutes River.

Task 5.	Quantify the number of wild strays at each location based on radio telemetry data and tagging at Sherars Falls.

Task 6.	Characterize spatial and temporal distribution and fallout characteristics of steelhead strays into the Deschutes River based on 1996 and 1997 radio telemetry data.

Objective 2.	Determine the causes of straying of adult steelhead into the Deschutes River.

Task 1.	Determine the effects of widescale stock (A and B steelhead) and geographic (Snake vs upper and lower Columbia) differences.

Task 2.	Determine the effects of hatchery practices (broodstock selection, rearing method, size and time of release, release location and method) and experimental treatments.

Task 3.	Determine the effects of juvenile migration timing and migration conditions (flow, temperature, and other environmental factors).

Task 4.	Determine the effects of the juvenile fish transportation and transportation method (truck vs barge).

Task 5.	Determine the effects of adult migration timing and migration conditions (flow, temperature, and other environmental factors).

Objective 3.	Report the findings and the conclusions of the data analysis.

Task 1.	Write a report summarizing findings and conclusions on the magnitude and causes of steelhead straying into the Deschutes River.

Task 2.	Prepare a list of remedial measures that could be expected to reduce or eliminate steelhead straying into the Deschutes River.

g.	Facilities and equipment

This project would operate from an existing ODFW office.  Project personnel would have the use of a computer, and other office equipment, including communications.  The project would require the use of a leased vehicle to access some of the data sources.

h.	Budget

The proposal budget (presented in detail in Section 5) is primarily directed at funding the personnel required to gather and analize the steelhead data that is available in the Columbia River Basin.  There are small budget items that specifically deal with miscellaneous office supplies, utility costs, and travel expences.

Section 9.  Key personnel

This project will utilize an experienced Natural Resource Specialist 2 or 3.  This position will remain open until funding is available for the position.

Section 10.  Information/technology transfer

Information collected and conclusions made will be included in the final project report, which will then be disseminated to the NPPC, BPA, fishery managers and other interested entities.