# Bonneville Power Administration

# FY 2001 Innovative Project Proposal Review

# PART 2 of 2. Narrative

Title:	Evaluate The Use of Small (Nano)Radio Tags to Determine Subadult Bull Trout Usage In Dworshak Reservoir, N.F. Clearwater River Drainage, ID

# Section 3. Project description

Provide project detail for headings a through g.

a. Abstract

- Little information is known about bull trout Salvelinus confluentus in the North Fork Clearwater River drainage.  Surveys conducted by the Idaho Department of Fish and Game, Nez Perce Tribe and other agencies have documented these fish in several streams and in Dworshak Reservoir.  Historically, prior to the construction of Dworshak Dam, bull trout interfaced with bull trout from other streams within the Clearwater River system, perpetuating genetic interchange throughout the drainage.  The role Dworshak Dam and reservoir play in the life history of bull trout in the North Fork is relatively unknown.  This study, in concert with ongoing Idaho Department of Fish and Game research, is designed to address life history in the North Fork Clearwater River and how, when and where bull trout use Dworshak Reservoir.  Entrainment of bull trout through Dworshak Dam will be assessed by monitoring radio-tagged fish and PIT tags.  Recent studies in southern Idaho reservoirs have documented movement of bull trout downstream past dams.  The significance of these losses is unknown, but could be important to viability of  the population.  Nano-radio transmitters (small) will be inserted into subadult bull trout captured in the reservoir and movement of these fish will be monitored throughout the life of the transmitters to determine distribution and habitat usage in the reservoir and drainage.  Because smaller, long-lived, nano-tags are just now becoming commercially available for fisheries investigations, this project will be one of the first to use the tags on bull trout in reservoir situations.  The information collected will not only provide important biological data, but will also provide information as to the feasibility of using radio tags on small fish in reservoir environments.

b. Technical and/or scientific background

In 1971 the construction of Dworshak Dam was completed near the mouth of the North Fork Clearwater River.  The 218 m high dam inundates >100 km of riverine habitat on the mainstem of the North Fork Clearwater River and it’s tributaries.  With no passage for fish migration the impacts to anadromous fish have been significant.  It is estimated that approximately 33 percent of the spring Chinook Oncorhynchus tschawytscha and steelhead trout Oncorhynchus mykiss and 20 percent of the fall Chinook production in the Clearwater Basin have been lost as a direct result of the construction and operation of Dworshak Dam (Cramer, Huntington, and Steward 1993).  Impacts on other native species in the basin are not as clear.

Bull trout exhibit a number of life history forms (i.e., resident, fluvial and adfluvial).  All life history forms can coexist within a basin.  Resident bull trout spend their entire life cycle within a single headwater tributary stream and, relative to fluvial and adfluvial forms, are small in size.  Fluvial and adfluvial bull trout move extensive distances, sometimes exceeding 200 miles (Bjornn and Mallet 1964).  Juvenile adfluvial fish spend one to three years in the tributaries before moving to lakes where they reside for one to three years before they return to natal streams to spawn (Pratt 1992).  Fluvial forms are similar to adfluvial fish, but grow and mature in large streams and rivers.  Both adfluvial and fluvial forms can attain lengths up to 700 mm (Shepard et al. 1984).  We hypothesize that fluvial populations in the basin may either use the large mainstem river or reservoir and that populations closer to the reservoir may be more affected by the alteration of the riverine habitat than populations farther away

Prior to construction of Dworshak Dam, bull trout had the opportunity to interchange with other bull trout populations in the Clearwater River drainage. Rieman and McIntyre (1993) indicate that characteristics of bull trout populations are consistent with the metapopulation concept that purports the need to protect genetic variation available for adaptation to change.  The maintenance of adequate migratory corridors throughout the Clearwater River drainage may be an important feature to ensure the genetic interchange suggested.   With construction of Dworshak Dam near the mouth of the North Fork Clearwater River, movement of bull trout is limited to downstream passage only as there is no avenue by which bull trout can move upstream past Dworshak Dam. Similarly, bull trout that move downstream of the dam can no longer return to the North Fork Clearwater River.  Again, Rieman and McIntyre suggest that isolated populations face serious risk of extinction, even with no further loss of habitat.

Ratliff and Howell (1992) found that where bull trout evolved with large populations of juvenile salmon, the fish declined when salmon declined.  Bull trout in rivers may parallel the distribution of potential prey (Carl 1985; Shepard and others1984b).  Because Dworshak Dam effectively blocks the migration of anadromous fish into the North Fork Clearwater River drainage, the abundance of potential prey (juvenile salmon and steelhead) has been diminished.  Bull trout in the drainage may seek alternate prey in Dworshak Reservoir as kokanee salmon populations have prospered in the reservoir.

Bull trout inhabiting the reservoir are at risk of moving through the reservoir and out of

the North Fork Clearwater River drainage past Dworshak Dam.  Idaho Department of

Fish and Game studies in the Boise River system have found bull trout captured and

tagged in reservoirs have moved past dams (Flatter 1998).  Similar movements of bull

trout may be occurring in the North Fork Clearwater River system.

The impact of severing the migratory corridor up the North Fork Clearwater River could

be critical in sustaining bull trout upstream of Dworshak Dam.  Bull trout

populations are prone to habitat disruption and fragmentation (Rieman and

McIntyre 1993).  Without more information the disruption of this migratory

corridor can only be viewed as a threat to the persistence of the North Fork Clearwater

River bull trout population.

It is assumed that the construction of Dworshak Dam has significantly reduced the distribution, abundance, and population viability of native fish populations in Dworshak Reservoir and its upstream tributaries (CBFWA 1997).  Information that is needed to assess this assumption however does not exist.

While bull trout have been documented throughout the N.F. Clearwater River basin and Dworshak Reservoir, little information is available on their life history or distribution (Cannon 1970, Lindland 1987, Statler 1989, Schriever and Cochnauer 1996, Weigel unpublished data ).  More importantly, other than documenting presence or absence, no information was available regarding the role Dworshak Reservoir plays in the life history and distribution of bull trout in the drainage.  In 2000, the Idaho Department of Fish and Game in cooperation with the Clearwater National Forest initiated a study to determine status of bull trout in the N.F. Clearwater River drainage as well as Dworshak Reservoir.  Bull trout were captured at the head end of Dworshak Reservoir during April and May.  Because of limitations on minimum body weight for placement of radio tags, only fish over 400 g were tagged with radio transmitters.  Over one half of the bull trout collected were less than this minimum size.   Of the 21 fish tagged all but two moved into the N.F. Clearwater River drainage.  An important element of data needs for bull trout in the drainage is the reservoir usage of bull trout that do not make a spawning migration.  To obtain this information smaller (nano-) tags will have to be utilized.  Small radio transmitters with longevity of up to one year have not been commericially available until recently and none have been evaluated on fish inhabiting large reservoirs.  The project is designed to test small radio transmitters in large reservoir environments.  The need to obtain information on subadults (<400 g) is critical to fully understand the role Dworshak Reservoir plays in the life history of bull trout in the N.F. Clearwater River drainage.

c. Rationale and significance to Regional Programs

The Northwest Power Council Fish and Wildlife Program acknowledges the impacts of hydropower development on anadromous and native fish populations in the Columbia River Basin (NPPC 1995).  The Council’s program identifies the needed to: 1) protect, mitigate and enhance resident fish populations to the extent they were or are affected by construction and operation of dams, and 2) protect, mitigate and enhance resident fish in hydropower system storage projects to the fullest extent practicable from negative impacts associated with water releases.  A priority of the Council’s program is to rebuild to sustainable levels weak, but recoverable, native populations injured by the hydropower system, when such populations are identified by the resident fish managers.

The resident fish managers have specifically identified the need to assess the impacts of the construction and operation of Dworshak Dam on native species (e.g., bull trout, cutthroat trout) in the Lower Snake Subregion (CBFWA 1997).  Section 6.6.5.3.of the Resident Fish Multi-Year Implementation Plan identifies the need to: 1) maintain and restore bull trout and cutthroat trout population productivity reduced by the development and operation of Dworshak Dam to healthy levels, and 2) ensure that native populations are above minimum viable population sizes which maintain adaptability and genetic diversity, and maximum probability of survival (CBFWA 1997).

The Council and the resident fish managers have included specific measures and strategies in their programs to maintain, protect and restore resident fish populations impacted by hydropower.  Section 10.1C of the Councils Fish and Wildlife Program (NPPC 1995) empowers fisheries managers to complete assessments of resident fish losses and gains related to the construction of each hydropower facility throughout the Columbia River Basin.  And, to fund the completion of these resident fish assessments and identify the need for mitigation actions with prompt action forestalling Endangered Species Act listing for several species including bull trout and westslope cutthroat (NPPC 1995).

For native fish species (bull trout and cutthroat trout) in Dworshak and the associated upstream North Fork Clearwater River watershed, the resident fish managers program identifies the need to: 1) identify and estimate the status of populations and groups of populations 2) identify factors limiting each population, critical habitat or conditions which limit life stages, and population sizes, and 3) select and implement measures based on distribution, status, and limiting factor assessments to improve habitat conditions, restore genetic integrity and connectivity between isolated subpopulation.

Although the Council and the resident fish managers agree that basinwide reviews of resident fish populations are needed these reviews have not yet been initiated in most basins.  Baseline inventory information on native fish stocks in the Columbia Basin is lacking in most basins.  Basinwide inventories of remaining native fish populations and their status are needed to identify opportunities to restore and rebuild native resident fish populations and to set priorities (Bisson 1998).

- In 1998, bull trout was listed as endangered.  The Nez Perce Tribe and

- Idaho Department of Fish and Game have identified the need to assess the losses and/or

- gains of bull trout in the North Fork Clearwater River related to the construction of

- Dworshak Dam. The baseline information on bull trout populations in the North Fork

- Clearwater River that is needed to assess the effects of the construction and operation of

- Dworshak Dam and Reservoir and develop strategies to protect and perpetuate the

- population does not exist.  General information describing the movement of bull trout in

- the North Fork Clearwater River drainage, and their life history relationship to Dworshak

- Reservoir is critical in assessing the need to: 1) maintain and/or restore complex

- interacting groups of bull trout populations throughout the drainage, 2)maintain the

- conditions of those areas presently supporting critical bull trout habitat, and 3)institute

- recovery strategies that produce measurable improvement in the status, abundance, and

- habitats of bull trout that have been adversely affected by the construction and operation

- of Dworshak Dam.

d. Relationships to other projects

In the North Fork Clearwater River little work has been done to quantify the impacts of the construction and operations of Dworshak Dam on resident fish. While BPA is funding projects on Dworshak Reservoir addressing the impacts to resident fish species, no work has been directed to bull trout.

In 1995, the Nez Perce Tribe began documenting the extent of hybridization between native westslope cutthroat trout and hatchery rainbow trout stocked in Dworshak Reservoir (9501600).  Hybridization with exotic trout is considered the greatest threat to the conservation of the native westslope cutthroat trout in northern Idaho (Allendorf and Leary 1988).  Distributions of pure and hybridized westslope cutthroat trout have been identified using nuclear DNA analysis in the North Fork Clearwater basin.  Information on habitat use and spawning locations of westslope cutthroat has also been recorded.  Incidental observation of habitat use and spawning locations, along with genetic samples have also been recorded and collected for bull trout during this study.  This information will be used to identify study populations of bull trout and critical habitat areas.  This project will also complement two other ongoing BPA sponsored projects, Dworshak Dam Impacts Assessment and Fisheries Investigation (8709900) and Dworshak Impacts/M&E Biological-Integrated Rule Curves (8740700) which are assessing the effects of Dworshak operations on reservoir production and the fishery.  In 2000, the Idaho Department of Fish and Game in cooperation with the Clearwater National Forest initiated a project to address bull trout status in the N.F. Clearwater River drainage, including usage and status in Dworshak Reservoir.  At the start of the project only radio tags suitable for larger bull trout (>400 g) were available.  Although a number of smaller (<400 g) bull trout were captured none were outfitted with radio tags.  Only recently have small radio tags became available for use in this project.  This proposed project will fill the life history gaps necessary to fully understand bull trout usage and status in Dworshak Reservoir.  Strategies for reservoir operations should not be considered without a full understanding of risks to endangered species present.  Data collected on effects of Dworshak operations on bull trout viability should be considered in the development of rule curves and strategies to minimize entrainment losses from the reservoir.

e. Proposal objectives, tasks and methods

Objectives

- Objective 1:	Characterize basic biology of bull trout in Dworshak Reservoir.

Assumptions: Reservoir use by bull trout varies seasonally among age classes and subpopulations.  Use of the reservoir may effect (either positive or negative) the viability of bull trout subpopulations within the subbasin (HUC 4).

Task 1: 	Collect bull trout, measure individual parameters, and mark as appropriate.

Task 2: 	From data collected in task 1, determine age, growth rate, condition factor, length-weight relationship, and mortality.

Objective 2:	Determine bull trout temporal and spatial distributions within Dworshak Reservoir project area.

Task 1:	Establish and implement a radio telemetry tracking protocol utilizing aerial, boat, and ground tracking methods.  Determine distribution in reservoir.

Tasks and Methods

  - Bull trout will be captured within the reservoir using hook-and-line sampling, boat electrofishing, and nets. All fish will be initially held in recirculating tanks and anesthetized prior to tagging and measurements taken.  We will take measurement of total length, fork length and total weight for all fish captured. A scale sample for ageing will be removed posteriorly to the dorsal fin and stored.  Also the adipose fin will be removed and stored in a 95% ethanol solution for genetic analysis under the ongoing Idaho Fish and Game study.  We will concentrate sampling efforts in  the upper section of Dworshak Reservoir near the mouths of the Little North Fork Clearwater River and mainstem North Fork Clearwater River.  Random sampling for bull trout will occur throughout the reservoir during the months of March-May.  Bull trout between 200 g and 400 g will be considered for tagging with nano-radio transmitters.  The transmitters will be inserted in the abdominal cavity.  We anticipate inserting transmitters in a maximum of 60 bull trout in 2001.  We will individually mark all captured bull trout with PIT tags.  Bull trout larger than 400 g will be marked (approximately 30 radio tags) under the ongoing IDFG study.  All bull trout captured throughout the drainage will be observed for tags.  Similar tagging investigation conducted by IDFG indicates that direct mortality due to handling will be less than 10%.

Surgical implantation of the radio transmitters requires anesthetizing the fish for not more than 10 minutes, which allows for the surgical procedure and data collection.  Bull trout will be anesthetized in a MS222 solution ranging between 60 and 80 mg/l.  All surgical tools and transmitters will be disinfected before each surgery.  Radio transmitter implantation will include the following steps.  The transmitter will be placed in the abdominal cavity and the excess antenna wire will be pulled out the exit hole.  The incision will be closed using three interrupted sutures evenly spaced across the incision.  Iodine solution will again be applied to the incision and antenna exit.  The antenna wire will be clipped at a length even with the caudal peduncle concluding the surgery. The fish will then be transferred to fresh water for not less than 15 minutes or until fully recovered from the anesthesia.

  - From information collected in Task 1.1  we will develop length-frequency, length and weight at age, and age at maturity relationships.

2.1	 The radio tagged individuals will be monitored at a minimum of twice every two weeks.  This will be accomplished by boat or fixed-wing aircraft on Dworshak Reservoir, vehicle on the roaded sections of the N.F. Clearwater River and fixed-wing aircraft in remote areas.  PIT tagged individuals will be monitored through continual netting, angling and electroshocking within the reservoir and associated spillway and selected streams above the reservoir.  This will be accomplished by either boat on Dworshak Reservoir, vehicle on the roaded sections of the N.F. Clearwater River and fixed-wing aircraft.  We will monitor all marked bull trout by netting and angling in the reservoir, and by electroshocking the river below Dworshak Dam and selected streams above the reservoir. In Dworshak Reservoir we will define habitat at each capture or observation site by measuring, water depth, temperature, and light penetration.

We will develop bull trout usage maps of the reservoir by season and reservoir elevation.  In coordination with the ongoing Idaho Department of Fish and Game study, we will be able to determine the importance of bull trout utilization of the reservoir and whether Dworshak Dam operations impact that population.

At the end of this project, we will coordinate with the Nez Perce Tribe, U.S. Forest Service and U.S. Army Corps of Engineers to develop relative risks to achieving our biological objectives.  As part of the N.F. Clearwater River bull trout project (funded by Idaho Department of Fish and Game and Clearwater National Forest), appropriate managers will develop strategies to minimize risks.

f. Facilities and equipment

The project’s field crew will be stationed at IDFG’s Clearwater Region Office in Lewiston, ID.  At the Lewiston facility, the necessary clerical staff, office space, computers, etc., are available.  IDFG will provide a boat suitable for use on Dworshak Reservoir.  IDFG also has electroshocking equipment suitable for the sampling work required.

g. References

Bisson, P.A. and others. 1998. Report of the Independent Scientific Review Panel. ISRP 98-1. Report to Northwest Power Planning Council. Portland, OR

Bjornn, T.C., and J. Mallet. 1964. Movement of planted and wild trout in an Idaho river system. Transactions of the American Fisheries Society 93:70-76.

Carl, L. 1985. Management plan for bull trout in Alberta. In:MacDonald, D.D., ed. Proceedings of the Flathead River basin bull trout biology and population dynamics modeling information exchange.  Cranbrook, BC: British Columbia Ministry of Environment.

Cannon, W. 1970.  Dworshak Fisheries Study.  Idaho Department of Fish and Game. Annnual Report DSS 29. Lewiston, ID

Columbia River Basin Fish and Wildlife Authority. 1997. Draft multi-year implementation plan for resident fish protection, enhancement, and mitigation in the Columbia River Basin. CBFWA Tech. Planning Document. Portland, OR

Cramer, S.P., C.W. Huntington, and C.R. Steward. 1993. Harvest of Anadromous Fisheries Lost by the Nez Perce Indian Tribe as a Result of the Lewiston and Harpster Dams in the Clearwater Basin. S.P. Cramer and Associates. Gresham, OR.

Lindland, R.L.  1987. Idaho Department of Fish and Game Regional Fish Management Investigations. F-71-11. Lewiston, ID.

Pratt, K.L. 1992. A review of bull trout life history. In: Howell, P.J. and D.V. Buchanan eds. Proceedings of the Gearhart Mountain bull trout workshop. (August) Oregon Chapter, American Fisheries Society, Corvallis, OR

Ratliff, D.E., and Howell, P.J. 1992. The status of bull trout  populations in Oregon. In: Howell, P.J.; Buchanan, D.V., eds. Proceedings of the Gearhart Mountain bull trout workshops; 1992 August; Gearhart Mountain, OR. Corvallis, OR.

Schriever, E. and T. Cochnauer. 1996.  Idaho Department of Fish and Game Regional Fish Management Investigations. F-71-R-17.  Lewiston, ID

Shepard, B.; Pratt, K.; Graham, P. 1984b. Life histories of westslope cutthroat and bull trout in the upper Flathead River basin, Montana. Kalispell, MT: Montana Department of Fish and Wildlife, and Parks. 85 p.

Statler, D.P.  1988.  Dworshak Reservoir investigations – Trout, bass and forage species.  Annual Report to BPA, Contract No. De-A179-87B35165. Nez Perce Department of Fisheries Resource Management. Orofino, ID

Rieman, B.E.; McIntyre, J.D. 1993. Demographic and habitat requirements for conservation of bull trout. Gen. Tech. Rep. IN-302. Ogden, UT: U.S. Department of Agriculture, Forest Service, Intermountain Research Station. 38 p.

# Section 4. Key personnel

The primary personnel involved in this project will be the project manager and a fishery biologist as the principal investigator.  The project manager, Tim Cochnauer, is the Idaho Department of  Fish and Game Clearwater Region fishery manager.  This position is funded by sources outside of the BPA process and will serve as the administrator and supervisor of this project

Project Manager:  Tim Cochnauer, PhD

Postion:  Regional Fish Manager, Idaho Department of Fish and Game, Clearwater Region, Lewiston, ID  83501

Address:  Idaho Department of Fish and Game

Clearwater Region

1540 Warner

Lewiston, ID  83501

Phone:  208-799-5010

FAX:  208-799-5012

e-mail:  tcochnau@idfg.state.id.us

Education:  Doctorate in Fishery Resources, 1983, University of Idaho, Moscow, ID

MS in Zoology, 1973,  University of Oklahoma, Norman, OK

BS in Zoology, 1967, University of Oklahoma, Norman, OK

Current responsibilities:

As regional fish manager, the project manager has responsibility for both anadromous and resident fish populations and fisheries within the Clearwater Region of north central Idaho.  The area encompasses the entire Clearwater River drainage, the Snake River drainage upstream to Hells Canyon Dam, the Palouse River drainage, and the Salmon River drainage (north side) from its mouth upstream to Horse Creek (rkm 300).  The IDFG Clearwater Region has a staff of four fishery scientists conducting a variety of activities including data collection, creel census, fish management decisions, establishing and implementing fishing seasons, etc., throughout the region.  The staff has responsibility for the FWP funded Idaho Supplementation Study and Natural Production Monitoring and Evaluation projects within the region.

The project manager has over twenty-five years experience with Idaho Department of Fish and Game working in fish research, fish management  and the hatchery system.  Experience includes radio-tagging and monitoring a variety of fish species found in Idaho;  marking and monitoring chinook salmon and steelhead trout juveniles and adults during the rearing, spawning and migratory phases of their lives; and, the use of a variety of techniques for capturing different life history phases of different species of fish.  These techniques have including, electroshocking, netting, angling, rotary screen traps, weirs, and seining.

Publications:

Cochnauer, T., E. Schriever, and J. Brostrom. 1993.  River and Stream Investigations.    F-71-R-17.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Cochnauer, T., E. Schriever, and J. Brostrom. 1994.  River and Stream Investigations.    F-71-R-18.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Cochnauer, T., E. Schriever, and J. Brostrom. 1995.  River and Stream Investigations.    F-71-R-19.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Cochnauer, T., E. Schriever, and J. Brostrom. 1996.  River and Stream Investigations.    F-71-R-20.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Cochnauer, T., E. Schriever, and J. Brostrom. 1997.  River and Stream Investigations.    F-71-R-21.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Cochnauer, T., E. Schriever, and J. Brostrom. 1998.  River and Stream Investigations.    F-71-R-22.  Federal Aid in Sport Fish Restoration. Idaho Department of Fish and Game.

Principal Investigator:  Danielle Schiff, BS Fishery Resources, University of Idaho;  Presently graduate student at University of Idaho

Danielle Schiff has extensive experience with radio tagging projects.  For two years, the Idaho Department of Fish and Game radio-tagged bull trout in the S.F. Clearwater River drainage and monitored their movements by road vehicle and aircraft for the duration of tag life.  In 1998, the Department used radio tags to monitor steelhead trout movements in the Selway River  drainage.  Ms. Schiff was the principal investigator for both projects.  Ms. Schiff has been the principal investigator in the N.F. Clearwater River drainage where radio tagged bull trout have been monitored for the past seven months.  She has monitored these fish through fixed radio receivers, roaded vehicles, and aircraft.