# Bonneville Power Administration

# FY 2001 Innovative Project Proposal Review

# PART 2 of 2. Narrative

Title:	   Evaluation of Two Captive Rearing Methods for Assisting with Recovery of  Naturally Spawning Populations of Steelhead and Coho Salmon

# Section 3. Project description

a. Abstract

We propose to evaluate two hatchery methodologies for steelhead (Oncorhynchus mykiss) and coho salmon (O. kisutch) that can potentially contribute to recovery of naturally spawning populations.

(1) We propose to develop an experimental hatchery broodstock of steelhead at the Abernathy Fish Technology Center (AFTC) by trapping wild or natural–origin (NOR) juveniles from Abernathy Creek and raising those fish in situ to sexual maturity (Phase I).  We will collect 500 age 0+ steelhead from Abernathy Creek in each of five years and then rear those fish to sexual maturity at the AFTC.  Specifically, we will assess captive-rearing of juveniles as an alternative to trapping sexually mature adults for developing new, native broodstocks of steelhead. The National Marine Fisheries Service (NMFS), through its Biological Opinions, is requiring the development of native steelhead broodstocks as a reasonable and prudent alternative to maintaining existing, non-native hatchery broodstocks that may jeopardize ESA-listed populations in the Columbia River Basin (CRB).  However, trapping adult steelhead for native broodstocks may be logistically unfeasible and may also pose unacceptable biological risks to depressed or ESA-listed populations.  Our short-term goal is to develop protocols and operational guidelines for developing new hatchery broodstocks of steelhead (i.e. from juvenile fish) that can be applied to listed populations elsewhere in the CRB.   We will then, in future years, spawn those captively-reared fish, release their progeny as smolts, monitor the return of their progeny as adults, and then evaluate - through DNA markers – the ability of those returning adults to reproduce naturally and contribute genetically (via supplementation) to the steelhead population in Abernathy Creek (Phase II).   Our future goal is to assess supplementation success of a “native” broodstock in a small, intensively-studied stream (i.e. Abernathy Creek) and compare demographic changes in abundance over time to control populations in two adjacent watersheds (Germany and Mill creeks).  Steelhead in the three watersheds are not listed under the ESA but are described as depressed but stable by the Washington Department of Fish & Wildlife (WDFW).  Those populations and the AFTC thus offer a significant, if not unique, opportunity to experimentally assess potential restoration and supplementation strategies in a small, test stream (Abernathy Creek) relative to two, natural population controls.  We have already initiated Phase I of this project by electrofishing Abernathy Creek during September of the past two years (1999 and 2000) and transferring 500 age 0+ steelhead of each brood year to each of two raceways equipped with covers and automatic feeders.  Initial survivals and preliminary results through October 2000 have been very promising (>80% survival of BY1999 fish after one year).  However, at the present time, we have no funding for this project and will not be able to continue unless funding is obtained.

(2)  While collecting age 0+ steelhead from Abernathy Creek during the past two Septembers (1999 and 2000), we discovered substantial numbers of NOR (unclipped) subyearling coho salmon in pools throughout the watershed (steelhead occur primarily in the riffle areas).   The observed number of subyearling coho was surprising because of the very poor status of coho salmon in the lower Columbia River.  The very few adults that have been observed incidentally have mostly been hatchery-origin adults with clipped adipose fins.    If those fish are spawning successfully, then overwinter survival of subyearling coho salmon may be very low because of high-velocity stream flows after major storms in the late autumn and winter.   The Abernathy Creek watershed is still recovering from historical (pre-1960) logging practices, and stream flows after major storms are sometimes very high.  We propose to collect 2,000 subyearling coho salmon from Abernathy Creek during September 2001and maintain those fish in an outdoor raceway at the AFTC prior to release as smolts the following spring (April-May 2002).   Our goal is to assess this strategy as a potential method to increase overwinter survival of pre-smolt juveniles and overall production of NOR smolts.  This innovative approach could also be a potential strategy for collecting NOR coho from remnant source populations for reintroduction programs elsewhere.   For our studies, we will PIT-tag all pre-smolt coho prior to release.  At the time of release, a subsample of 30 fish will be retained to assess gill Na+K+-ATPase activity, seawater tolerance, plasma cortisol, prolactin, and thyroid hormone levels.  We will then trap, with a rotary screw trap, outmigrating smolts in Abernathy Creek approximately 3 kms downstream from the AFTC.  The proportion of tagged to untagged smolts will be used to estimate the total number of coho (and steelhead) smolts outmigrating from Abernathy Creek after trap efficiency is calibrated.  We will estimate mean lengths, weights, and condition factors of the tagged and untagged smolts to evaluate the growth effects of overwintering coho salmon in a hatchery raceway versus those that overwinter in the creek.  Subsamples of 30 tagged and 30 untagged smolts will be retained from the smolt trap for physiological analyses (as described above) to compare indices of smolt quality for the two groups of fish.  A companion proposal by Zydlewski et al. (submitted for this RFP)  would use a new type of  extended-range PIT tag and within-stream antennas to estimate overwinter survivals of NOR coho salmon and steelhead in Abernathy Creek. We will also operate an electric weir during the fall, winter, and early spring to enumerate upstream-migrating adult coho salmon and steelhead.   Returns of PIT-tagged adults will be monitored in future years at the AFTC to assess return rates of all experimental fish (this proposal and the companion proposal of Zydlewski et al.).  We also invite state, tribal, and other federal biologists as collaborators on these projects.

b. Technical and/or scientific background

Development of the hydropower system in the Columbia River Basin included federal legislation (e.g. Mitchell Act, Lower Snake River Compensation Plan) requiring that fishery losses associated with those hydropower facilities be mitigated or compensated by hatcheries and artificial propagation  (NWPPC 1999).  At the present time, nearly 100 hatcheries and satellite facilities exist in the Columbia River Basin.   More than 85% of all adult salmon and steelhead  returning to the Columbia River Basin are of hatchery origin, and these hatchery-origin fish contribute significantly to commercial, sport and tribal fisheries.  However, recent ESA listings throughout the Columbia River Basin have forced fishery biologists and managers to reexamine the mandates and priorities of hatcheries with an increasing emphasis on potentially using hatcheries as tools to help recover naturally spawning populations as opposed to simply providing fish for harvest.

The work proposed here will investigate two hatchery methodologies that can potentially assist with recovery of naturally spawning populations: (1) development of native broodstocks of steelhead via captive rearing of natural-origin (NOR) juveniles (age 0+ fish) and (2) short-term (6-7mos.) rearing of pre-smolt, NOR coho salmon in hatchery raceways prior to release at smoltification to increase overwinter survival and total smolt production, and to assess this approach as a potential strategy for collecting NOR juveniles for reintroduction programs in the Columbia River Basin.

Steelhead

Hatchery programs for steelhead have been managed primarily to support sport and tribal fisheries, purposes for which those programs have been quite successful.   Many of the existing hatchery programs use non-native stocks to provide fishery opportunities.  For example, the Wallowa Hatchery stock of steelhead in the Grande Ronde River was developed from adults trapped at Lower Granite Dam and not from fish trapped in the Grande Ronde River.   Biologists and managers now recognize the potential negative effects that can occur when non-native hatchery fish interact biologically with native populations (Hindar et al. 1991; Waples 1991; Campton 1995).  Not only do non-native stocks pose genetic and ecological risks to naturally spawning populations in the target watersheds, but non-native fish stray as returning adults at a much higher rate than do native fish (Quinn 1993).  Biologists and managers also recognize the need to maintain the genetic resources associated with naturally spawning populations, and to recover or restore those populations wherever possible.   As a consequence, the U.S. Fish & Wildlife Service (USFWS) and the National Marine Fisheries Service (NMFS) have been recommending a general policy that discourages the use of non-native hatchery stocks and encourages native broodstocks.  There are two primary motivations for these recommendations: (1) reduce or minimize potential negative biological effects resulting from genetic or ecological interactions between hatchery-origin and naturally-produced fish and (2) potentially use native broodstocks as genetic reserves or resources to enhance naturally spawning populations when necessary or desired.   Recently, NMFS has declared, in a  Biological Opinion on Artificial Propagation in the Columbia River Basin , that non-native hatchery steelhead jeopardize the continued existence of listed, naturally spawning populations in watersheds where the two groups of fish may interbreed or interact ecologically.  As a consequence, NMFS is requiring, as a reasonable and prudent alternative, that federal and state agencies phase out non-native broodstocks of steelhead and replace them with native broodstocks.

The development of new, native broodstocks of hatchery-propagated steelhead is hampered significantly by the threatened or endangered status of the naturally spawning populations where the new broodstocks are required.   The traditional method of initiating broodstocks by trapping adults may not be biologically acceptable because such activities may pose significant risks (i.e. via broodstock mining) to naturally spawning populations that are already depressed or listed under the ESA.  In addition, the trapping of adult steelhead may be logistically unfeasible in many subbasins because of high water flows in the spring when steelhead spawn.  As a result, alternative methods for collecting and developing native broodstocks may be necessary or desirable.

One alternative for developing native broodstocks, particularly when the collection of adults is unfeasible or biologically unacceptable, is the captive rearing to sexual maturity of naturally-produced juveniles.   The concept is relatively simple: collect pre-smolt juveniles from the streams or watershed for which a native broodstock is desired and then raise those juveniles to sexual maturity in the hatchery to initiate the hatchery program .  Hatchery-reared adults then become the broodstock source for gametes and initial progeny releases.  Such a captive rearing program for developing native broodstocks has many potential advantages over traditional programs initiated by trapping sexually-maturing adults:  (1) large numbers of juveniles can be collected from the wild with only minimal impacts to naturally spawning populations because juvenile-to-adult survivals are typically very small (<1-3%) under natural conditions; (2)  the genetic base of the broodstock (i.e. genetic effective population size) can be substantially larger for juveniles than adults because juveniles can theoretically represent the offspring of all adults that spawned successfully within a stream or watershed, as opposed to trapping only a small portion of those returning adults for broodstock, and this factor will - in turn -  (3) substantially reduce the risk of  genetically “swamping” naturally spawning populations with hatchery-origin fish as can occur when those hatchery-released fish represent the progeny of a relatively small number of adults.(Ryman and Laikre 1991; Ryman et al. 1995).   On the other hand,  initiating broodstocks from captively-reared juveniles, compared to trapping adults, has the following disadvantages: (1) three years of captive rearing are necessary to obtain sexually mature adults;  (2) major uncertainties exist regarding the survival of juvenile steelhead to sexual maturity in captivity; (3) the biological effects of captive rearing on sexual maturation, fertilization success, and subsequent progeny development are largely unknown for steelhead; and (4) domestication selection effects in captivity can be significant if overall survival to adulthood is low (e.g. <20%).  Consequently, captive-rearing methods for steelhead should be field-tested if they are to be used as a low-risk method for developing new, native broodstocks in the Columbia River Basin.

Coho salmon

Naturally spawning populations of coho salmon throughout the Columbia River Basin are severely depressed.  Native populations are considered extinct in the Snake River and in the Columbia River upstream from Bonneville Dam except in the Hood River (Nehlsen et al. 1991; Johnson et al. 1991).   Populations throughout the lower Columbia River (LCR) below Bonneville Dam were severely impacted by logging practices and were overfished to near extirpation after the development of an extensive hatchery program in the 1960’s (Flagg et al. 1995).   Indeed, a biological review team for  NMFS concluded that they could not find evidence for any remaining native populations of coho salmon in the LCR except in the Clackamas River (Johnson et al. 1991).   NMFS concluded that native populations may be largely extinct because of severe overfishing and extensive straying and natural spawning  by transplanted (or outplanted) hatchery-origin fish.   In addition, much of the critical freshwater habitat for coho salmon in the LCR has not fully recovered since old-growth forests were logged and  splash dams were used to transport felled trees.  Coho salmon juveniles are highly dependent on deep pool areas and large woody debris in small streams for refuge and feeding (Cedarholm et al. 1997), and these types of freshwater habitats may require many decades to fully recover naturally to their historical levels of productivity.

Salmon managers are testing various hatchery strategies to reintroduce and enhance naturally spawning populations of coho salmon throughout the Columbia River Basin.  These methods include the  outplanting of eggs, fry, and smolts from existing hatchery populations.  However, those attempted methods at enhancing or restoring naturally spawning populations of coho salmon may be severely inhibited by (a) the ancestry of the outplanted fish which may include several continuous generations of hatchery propagation without any natural reproduction and (b) the compromised state of the freshwater habitats on which coho salmon juveniles are highly dependent.  For example, attempts to enhance naturally spawning populations of coho salmon in the lower Columbia River with large outplants of hatchery-origin pre-smolts, smolts, and adults appear to have been unsuccessful; most of those populations appeared to go extinct in the late 1980’s (Johnson et al. 1991; Chilcote 2000).   Nevertheless, remnant populations of juvenile coho salmon still exist throughout the lower Columbia River, although those natural-origin fish may largely represent the offspring of hatchey-origin adults that have spawned successfully.  Regardless of their ancestry, natural-origin juveniles in lower Columbia River streams would clearly represent the product of successful spawning and natural selection in a stream environment and thus could serve as a potential source of fish for restoration and recovery of naturally spawning populations.   One approach would be to collect subyearling, natural-origin coho salmon (age 0+) from streams during their first summer, maintain those fish in hatchery raceways during the autumn and winter, and then release those fish as smolts in the same streams or other target streams the following spring.  This strategy may increase overall fry-to-smolt survival in streams particularly susceptible to high-velocity “flashing” following major, winter storms.  It could also provide a potential source of NOR smolts for restocking extirpated populations in streams comparable to the source stream.  To our knowledge, this potentially innovative strategy to help restore or enhance naturally spawning populations of coho salmon has not yet been tested or evaluated.

###### Supplementation

The ability of hatchery-origin adults to reproduce successfully and contribute genetically, via supplementation, to the rebuilding or recovery of naturally spawning populations is a major uncertainty confronting salmon comanagers in the Pacific Northwest.   This question has been debated intensively throughout the Columbia River Basin for over 10 years but remains unresolved.   Indeed, a major symposium was conducted in June, 2000 to specifically address these uncertainties and identify future research and comanager needs (IMST 2000).

Much of the uncertainty associated with supplementation is due to the absence of detailed studies on a small, experimental scale.  Virtually all evaluations to date have either been at large watershed levels (i.e. on a production scale) or have failed to incorporate appropriate control populations to which the supplemented populations could be directly compared (IMST 2000).   Even in those instances where supplementation is currently being evaluated with control populations, most of those studies will be unable to determine the relative reproductive success of individual hatchery-origin and natural-origin adults.  Such information is critical to understanding why supplementation is successful or unsuccessful.  To achieve this latter objective, nearly all upstream-migrating adults need to be genotyped with a battery of DNA markers, and then samples of their naturally-produced offspring (e.g. parr or smolts) similarly genotyped to identify, via the statistical methods of maximum likelihood, the specific male and female parents of each juvenile fish.  Appropriate streams for these types of experimental studies are extremely difficult to locate.  A basin-wide need exists to identify such experimental streams where the parents of naturally-produced progeny can by identified genetically and supplementation evaluated in a controlled, scientific manner.

###### Abernathy Fish Technology Center

The  U.S. Fish & Wildlife Service’s Abernathy Fish Technology Center (AFTC) has a unique opportunity to investigate the aforementioned hatchery methodologies and associated supplementation questions.  The AFTC is located at stream mile 3.4 on Abernathy Creek, a tributary to the lower Columbia River approximately 10 miles west of Longview, Washington.  The AFTC  was originally built as a “mitigation” hatchery in the 1950's, and from 1957 through 1997, non-native tule fall chinook salmon were propagated and released as part of the Mitchell Act mitigation in the Columbia River.  However, this propagation program and associated mitigation responsibilities have been terminated.  The AFTC  is now refocusing as a research hatchery to investigate new propagation strategies and technologies that can contribute to the recovery of anadromous fishes in the Columbia River Basin.   The AFTC is equipped with all the components necessary for a self-sufficient salmon/steelhead hatchery including an electric weir and holding pond for trapping and enumerating upstream-migrating adults.  The existence of such a facility devoted strictly to research purposes is unique among hatcheries in the Pacific Northwest.  In this context, the AFTC has a long history of testing and developing new hatchery technologies in the Pacific Northwest, particularly in the areas nutrition, diet, and feed development.

Abernathy Creek is an ideal location to address new recovery strategies for anadromous salmonid fishes. Abernathy Creek is a small, 3rd order stream with a drainage area of approximately 110 km2 that is particularly amenable to intensive, scientific study of salmonid fishes.  Like most streams in the lower Columbia River, Abernathy Creek historically supported abundant runs of steelhead and coho salmon.  Other native species include coastal cutthroat trout (O. clarki clarki) and chum salmon (O. keta).  The Washington Department of Fish and Wildlife (WDFW) now considers the steelhead population in Abernathy Creek to be “depressed” with an estimate of only 100-150 adult spawners per year based on expanded redd counts (Dan Rawding, WDFW, pers comm.).  The status of coho salmon is largely unknown, although we have found significant numbers of subyearling coho juveniles during electrofishing activities during the past two Septembers (see below).  In addition, two neighboring streams of approximately the same size, Germany and Mill Creeks, enter the Columbia River immediately upstream (approx. two miles) and downstream (approx. one mile), respectively, from the mouth of Abernathy Creek, and those other two streams can potentially serve as “controls” for research activities on Abernathy Creek.   Lastly, Abernathy Creek and the two adjacent streams are located approximately 160 km downstream from Bonneville Dam in a rural area of Cowlitz County.  The opportunity of the AFTC to test new culture and recovery strategies in a natural stream without the constraints imposed by dams, mitigation responsibilities, and urban impacts is unique among artificial propagation facilities in the Pacific Northwest.

###### Proposed research

(1) We propose to develop an experimental hatchery broodstock of steelhead at the Abernathy Fish Technology Center (AFTC) by trapping wild or natural–origin (NOR) juveniles from Abernathy Creek and raising those fish in situ to sexual maturity (Phase I). Specifically, we will assess the captive-rearing of juveniles to sexual maturity as an alternative to trapping sexually mature adults for developing native or endemic broodstocks.  In future years (Phase II), we will spawn those captively-reared adults, release their progeny as smolts, monitor the return of their progeny as adults, and then evaluate - through DNA markers – the ability of those returning adults to reproduce successfully and contribute genetically (via supplementation) to the naturally spawning population of steelhead in Abernathy Creek.   Our long-term goal is to assess supplementation spawning in Abernathy Creek of hatchery-origin steelhead representing a “native” broodstock and compare demographic changes in abundance over time to control populations in Germany and Mill creeks.  (2)  We propose also, for FY2001, to collect subyearling coho salmon from Abernathy Creek during September 2001and maintain  those fish in an outdoor raceway at the AFTC prior to release as smolts the following spring (April-May 2002).  The goal of this latter project is to assess this latter strategy as (a) a potential method to increase overwinter survival of pre-smolt juveniles and increase overall smolt production in the source stream and (b) as a method of potentially collecting NOR fish for restoring severely depressed or extirpated populations.   Our proposed work includes trapping outmigrating smolts in Abernathy Creek with a rotary screw trap approximately 3 kms downstream from the AFTC and them comparing physiological indices of smolt quality between tagged (AFTC-released) and untagged (NOR-released) fish.

c. Rationale and significance to Regional Programs

The rationale for our proposed work is largely described in the preceding section.   As noted above, testing the ability to develop native broodstocks of steelhead from wild-caught, NOR juveniles is motivated by recent Biological Opinions of NMFS and the need to develop native broodstocks without “mining” naturally spawning populations that are already listed or severely depressed.  Our proposed work with coho salmon investigates a hatchery strategy that can potentially be used to help recover or restore severely-depleted  - or extirpated - naturally spawning populations in the Columbia River Basin.

The work proposed here addresses the following goals and objectives of the 1994 Fish and Wildlife Program of the Northwest Power Planning Council:

2.2A 	Support Native Species in Native Habitat.

2.2H 	The Need to Learn from Implementation.

  - Salmon and Steelhead Research and Evaluation.

7.1B	Conserve Genetic Diversity.

7.1H	Reprogramming of Existing Hatchery Stocks and Facilities.

7.2D	Improve Propagation at Existing Facilities.

7.4A	Identify, Evaluate, and Implement New Production Initiatives.

7.4D	Captive Brood Stocks.

7.5C	Lower Columbia River Coho Salmon.

d. Relationships to other projects

Our porposed work with steelhead will complement ongoing captive broodstock work currently conducted with sockeye and chinook salmon by the National Marine Fisheries Service and comanaging state agencies (Conrad Mahnken, NMFS, Manchester, WA).    Those programs by NMFS are primarily emergency captive broodstock programs to help protect endangered populations from extinction in the Snake River and elsewhere in the CRB.   In contrast, our proposed work with steelhead will investigate the potential use of  NOR juveniles for developing native broodstocks that can be used both for conservation AND mitigation (i.e. harvest augmentation) purposes.   The ability to collect NOR juveniles at will from Abernathy Creek, raise them to sexual maturity on creek water in the AFTC (see methods below), and then evaluate the natural spawning success of their progeny in future years are major strengths of our proposed work.   We (USFWS) have genetic concerns regarding the desire of the state agencies to develop native broodstocks of steelhead by trapping adults from ESA-listed or depressed populations, and our proposed work  would investigate a low-risk alternative to traditional methods of broodstock development.

The work proposed here for steelhead would also complement ongoing work by the Washington State Department of Fish & Wildlife (WDFW0 in the Kalama River.   WDFW has been investigating genetic interactions between hatchery and natural-origin steelhead in the Kalama River since the mid-1970’s.   Until recently, those studies have focused on introduced hatchery steelhead from two non-native stocks:  Skamania summer-run steelhead and Beaver Creek (Elochoman R., Chambers Creek)  winter-run steelehead.   Research with those two introduced stocks is now complete, and WDFW is now developing a native hatchery broodstock on the Kalama River by trapping wild or NOR adults (Pat Hulett, WDFW, pers. comm.).  WDFW will, in future years, assess the natural spawning success of hatchery-produced progeny of  NOR parents in the Kalama River by current DNA methodologies.   Our future goals with steelhead are similar to those of WDFW, but we want to first investigate the feasibility of developing native broodstocks by captively rearing NOR juveniles to sexual maturity.   We believe the opportunities for capturing large amounts of genetic diversity in hatchery broodstocks is much greater with juveniles than with adults, particularly considering the threatened and endangered status of steelhead throughout various segments in the Columbia River Basin that may preclude trapping sufficient numbers of adults for achieving desired effective population sizes.  We believe also that Abernathy Creek, and the two adjacent control streams (Germany and Mill Creeks), offer excellent experimental control conditions for future evaluations of supplementation success and hatchery-wild fish interactions.

We are unaware of other studies of coho salmon where the principal goal is to capture NOR juveniles and attempt to assess their ability to overwinter successfully in hatchery raceways.   The work proposed here would complement transplantation studies conducted elsewhere (e.g. Yakima River, Wenatchee River) where hatchery-origin smolts from lower-mid Columbia River hatcheries are released in an attempt to reestablish runs to the mid-upper Columbia River.

e. Proposal objectives, tasks and methods

Long term goals:

- Develop a native hatchery broodstock of steelhead for Abernathy Creek at the AFTC to (a) develop, test, and evaluate new strategies for developing native broodstocks of steelhead via captive rearing to sexual maturity of natural-origin juvenile fish as an alternative to trapping wild adults for developing new broodstocks (this proposal) and (b) evaluate the natural spawning success of hatchery-produced steelhead from a native broodstock that is as similar as possible genetically to the naturally spawning population from which it was derived (future proposals).  This long term goal includes the following objectives:  (a) determine the genetic and environmental effects of hatchery rearing on phenotypic fitness and subsequent reproductive success under natural conditions; (b) test the concept of genetically integrating hatchery and naturally-reproducing populations to maintain the genetic characteristics of natural populations among hatchery-origin fish; and (c) evaluate the ability of  artificial propagation and supplementation to assist with rebuilding naturally spawning populations or maintaining them at carrying capacity levels when habitats or environmental conditions are not optimum.

- Rebuild and restore naturally spawning populations of coho salmon in the lower Columbia River and elsewhere in the Columbia River Basin.  Can natural-origin juveniles residing in lower Columbia River tributaries serve as a potential broodstock or population source for restoration and recovery of naturally spawning populations?

- Develop the Abernathy Fish Technology Center (USFWS) into a cooperative research hatchery with Abernathy Creek serving as a natural population test stream for evaluating new hatchery concepts and innovative strategies for recoverying naturally spawning populations in the Columbia River Basin.

Objectives

###### Steelhead.   Short-term goal: Develop a native hatchery broodstock from natural-origin juveniles in Abernathy Creek and evaluate this methodology as a potential alternative to trapping natural-origin adults for developing new hatchery broodstocks.

FY2001

- Collect, via stratified sampling, 500 age 0+ steelhead from a 10 km section of Abernathy Creek in September 2001.

- Transfer 500 age 0+ steelhead to a raceway supplied with covers and Abernathy Creek water at the AFTC.

- Stimulate natural-origin steelhead juveniles to feed on artificial hatchery diets.

- Estimate the mean and variance in growth, and determine overall survival of captively-reared steelhead every four months (January, May, September 2002).

- Maximize survival and mean growth rate, and minimize the variance in growth rate, of  captively-reared steelhead.

- Estimate allele frequencies at 20 nuclear DNA loci for NOR steelhead from Abernathy Creek.

- Monitor and enumerate upstream-migrating adult steelhead and exclude hatchery-origin (adipose clip) from migrating upstream past the AFTC in Abernathy Creek (November 2001 – April 2002)

- Produce a handbook and protocol manual for developing native broodstocks of steelhead by captively rearing natural-origin juveniles to sexual maturity.

Future years

- Maintain natural-origin steelhead in captivity for 2-3 years with the goal of producing a minimum of 50 sexually mature-males and females, respectively.

- Repeat 1-7 for a minimum of five consecutive years.

- Assess the effects of captive rearing on overall survival, body morphology, physiology, sexual maturation, and gamete quality.

- Spawn sexually mature adults by crossing mature males of one brood year with mature females of the another brood year to yield a minimum effective population size of 100 breeders per year.

Coho salmon.  Short term goal:  Assess the ability to maintain natural-origin, pre-smolt juveniles in hatchery raceways prior to release into streams where natural populations may be severely depressed or extirpated.

FY2001

- Collect 2,000 subyearling coho salmon from Abernathy Creek in September, 2001.

- Transfer 2,000 subyearling coho salmon to a raceway supplied with covers and Abernathy Creek water.

- Stimulate natural-origin coho juveniles to feed on artificial hatchery diets.

- PIT-tag all coho juveniles and estimate mean and variance in size (January 2002).

- Estimate gill Na+ K+ ATPase activity, seawater tolerance, plasma cortisol, prolactin, and thyroid hormone levels for a random sample of 30 coho immediately prior to release.  Estimate overall survival of natural-origin coho salmon durng the preceding 6-7 months of captivity at the AFTC (April 2002).

- Release PIT-tagged coho smolts into Abernathy Creek from the AFTC (April-May 2002).

- Set-up a rotary screw smolt trap in Abernathy Creek approximately 2.5 miles downstream from the AFTC, calibrate the catch efficiency of the trap, and trap downstream migrating coho and steelhead smolts (February-June, 2002).

- Estimate the total number of natural-origin coho and steelhead smolts from the ratio of marked (PIT-tagged coho) to unmarked fish.  Incidentally monitor cutthroat trout smolts.  Retain 30 PIT-tagged and 30 non-tagged coho smolts for physiological assays as described under 5.   Test the null hypotheses that mean size and smolt quality are equal for stream-reared (untagged) and hatchery-reared (tagged) coho salmon.

- Monitor and enumerate upstream-migrating adult coho salmon and determine the ratio of hatchery-origin (adipose clip) to natural-origin (unclipped) adults migrating past the AFTC in Abernathy Creek (October 2001 – January 2002).

Future years

- Repeat 1-9 in FY2002 and FY2003.

- Monitor and enumerate upstream migrating coho salmon adults, Fall 2003, 2004, 2005, 2006, and 2007.  Estimate smolt-adult survival and return rates of PIT-tagged adults returning to the AFTC.

Tasks and Methods

## Steelhead

- Collect, via stratified sampling, 500 age 0+ steelhead from a 10 km section of Abernathy Creek in September 2001.   We have identified five sample site locations in Abernathy Creek over a 6.6 mile stretch of stream immediately upstream from the AFTC (stream miles 3.4 to 10.0).   These five stream sections are approximately 1 mile apart.  During the 3rd and 4th weeks of September in 2000 and 1999, respectively, we used a backpack electroshocker to collect 75-125 age 0+ steelhead from each of those five stream areas for a total of 500 age 0+ fish of each brood year.   These fish were transferred to a holding tank supplied with oxygen in the back of a pick-up truck where they are maintained for up to four hours prior to transfer to the AFTC (see below).  Our sampling has been stratified by sample site to maximize the number of parents potentially contributing to the fish we have collected.    Mortalities associated with these collections have been extremely low; we have observed less than 10 dead fish during the first 24 hours after collection during the past two years.   If funded, we will continue this collection of age 0+ steelhead in September 2001.

- Transfer 500 age 0+ steelhead to a raceway supplied with covers and Abernathy Creek water at the AFTC.    Age 0+ steelhead will be transferred to 8’x 80’ raceways at the AFTC within four hours after capture from Abernathy Creek.  We have constructed low-hanging covers that are approximately three feet above the raceways to provide shade and partial refuge.  These raceways are supplied with Abernathy Creek water and automatic feeders.

- Stimulate natural-origin steelhead juveniles to feed on artificial hatchery diets.   Fish will initially be fed starter diets coated with krill hydrolysate to stimulate initial feeding on salmonid feeds.    We had some initial difficulties getting BY1999 age 0+ steelhead to start feeding on artificial feeds when those fish were first captured in September, 1999.  We were able to stimulate their conversion to artificial feeds by coating the feed pellets with a krill hydolysate.   These oils exude into the water, stimulating the olfactory senses and feeding response of the fish.   Feeding protocols will follow standard hatchery practices for steelhead and rainbow trout after hatchery growth is initiated.  At  2-3 years of age, depending on growth rate and size, the fish will be switched over to a  broodstock diet (e.g. Bio-OregonTM  BioDiet Brood) to stimulate sexual maturation and proper gamete development.

- Estimate the mean and variance in growth, and determine overall survival of captively-reared steelhead every four months (January, May, September 2002).   Fish will be crowded in a raceway, removed by dip net, and anesthetized with MS-222.   All fish will be counted to determine overall survival to each four-month time interval.  A subsample of 50 fish will be measured and weighed to estimate the mean size and associated variance among all fish in each raceway.

- Maximize survival and mean growth rate, and minimize the variance in growth rate, of  captively-reared steelhead.    Fish will be fed by automatic feeders and supplemented by hand as necessary to ensure optimum growth.   At one of the four-month intervals, fish will be graded and raceways subdivided, if necessary, to minimize the variance in growth and size among fish of a given brood year.  The goal here is not to raise “wild fish” per se, but rather to optimize growth and survival to sexual maturity to maximize the total number of adults available for spawning 2.5-3.5 years after collection.  Ideally, 200-300 fish of each brood year would survive and be available as sexually mature adults.

- Estimate allele frequencies at 10-20 nuclear DNA loci for NOR steelhead from Abernathy Creek.   We will collect fin clips from 100 fish x three brood years (1999, 2000, 2001; 300 fish total) during one of the four-month sampling periods when fish are crowded and measured.   These clips will be placed in small vials with 100% ethanol for DNA extraction.   We will obtain microsatellite nuclear DNA allele frequencies for Abernathy Creek steelhead in order to compare the genetic background of this population to the Beaver Creek Hatchery population and other steelhead populations in the Columbia River Basin.   One of us (DEC) recently conducted a workshop in Portland among salmon geneticists in Oregon, Washington, and Idaho to standardize nuclear DNA methods region-wide.  The goal is to develop a basin-wide genetic database for steelhead.  We plan to contract the DNA work for steelhead from Abernathy Creek to the National Marine Fisheries Service (Paul Moran, NMFS).   The NMFS lab in Seattle is currently performing similar contract work for the USFWS on steelhead from the Eagle Creek National Fish Hatchery.

- Monitor and enumerate upstream-migrating adult steelhead and exclude hatchery-origin (adipose clip) fish from migrating upstream past the AFTC in Abernathy Creek (November 2001 – April 2002).   The Washington Department of Fish & Wildlife has historically released 6,500-10,000 steelhead smolts from the Beaver Creek Hatchery into the lower reaches of Abernathy Creek.  The last year of these releases was 1999.   A few of these hatchery origin fish migrate past the AFTC when they return in the late Fall and early Winter as adults.   The AFTC is equipped with an electric weir and pond for diverting and trapping upstream-migrating fish.  We will keep this weir turned on from November through early March to exclude any hatchery origin steelhead from migrating past the AFTC and potentially spawning in Abernathy Creek upstream from our facility.   As noted above, age 0+ steelhead are collected for captive rearing upstream of the AFTC.

- Produce a handbook and protocol manual for developing native broodstocks of steelhead by captively rearing natural-origin juveniles to sexual maturity.   We will document successes and failures with the goal of producing a protocol manual for captively rearing NOR steelhead juveniles to sexual maturity.

## Coho Salmon

- Collect 2,000 subyearling coho salmon from Abernathy Creek in September, 2001.   We will use a backpack electroshocker to collect 2,000 subyearling coho salmon from the same sample site areas that we collect age 0+ steelhead.  These fish will be retained as described above for steelhead.

- Transfer 2,000 subyearling coho salmon to a raceway supplied with covers and Abernathy Creek water.  These methods will follow those described for steelhead above.

- Stimulate natural-origin coho juveniles to feed on artificial hatchery diets.   These methods will follow those described above for steelhead.

- PIT-tag all coho juveniles and estimate mean and variance in size (January 2002).   We will PIT tag all coho juveniles prior to release in the Spring of 2002.   If the companion proposal by Zydlewski et al. is funded, we will use the new long-range PIT tags so that within-stream movements can be monitored by remote antennas.

- Estimate gill Na+ K+ ATPase activity, seawater tolerance, plasma cortisol, prolactin, and thyroid hormone levels for a random sample of 30 coho immediately prior to release.  Estimate overall survival of natural-origin coho salmon durng the preceding 6-7 months of captivity at the AFTC (April 2002).    The developmental process of smolting is measurable via seasonal examination of physiological condition.  Predictable physiological changes associated with smolting include increases in gill Na+ K+ ATPase activity, plasma cortisol, thyroid hormone, and decreases in prolactin levels (Zaugg 1981; Dickhoff et al. 1982; Prunet and Boeuf 1985).   These physiological parameters will be measured on a sample of 30 coho salmon immediately prior to release.   ATPase activity, plasma cortisol, thyroid hormone, and prolactin will be measured by the methods of McCormick (1993), Carey and McCormick (1998), Dickoff et al. (1982), and Prunet and Boeuf (1985), respectively.

- Release PIT-tagged coho smolts into Abernathy Creek from the AFTC (April-May 2002).   We will open up the downstream trap of our raceway by April 1 and allow coho salmon to exit volitionally into Abernathy Creek.  Any fish remaining after June 1 will be flushed out into Abernathy Creek.

- Set-up a rotary screw smolt trap in Abernathy Creek approximately 2.5 miles downstream from the AFTC, calibrate the catch efficiency of the trap, and trap downstream migrating coho and steelhead smolts (February-June, 2002).   Downstream migrating smolts will be enumerated and released.  A subsample of smolts will be marked with a dye tattoo and released upstream of the trap to calibrate catch efficiency.

- Estimate the total number of natural-origin coho and steelhead smolts from the ratio of marked (PIT-tagged coho) to unmarked fish.  Incidentally monitor cutthroat trout smolts.  Retain 30 PIT-tagged and 30 non-tagged coho smolts for physiological assays as described under 5.   Test the null hypotheses that mean size and smolt quality are equal for stream-reared (untagged) and hatchery-reared (tagged) coho salmon.   Physiological assays comparing stream-reared versus hatchery-reared smolts will follow the methods outlined under objective 5 above.   An additonal 15 fish of each group will be retained for saltwater challenge experiments to test the null hypothesis that survival and osmoregulatory ability are equal between stream-reared and hatchery-reared smolts.

- Monitor and enumerate upstream-migrating adult coho salmon and determine the ratio of hatchery-origin (adipose clip) to natural-origin (unclipped) adults migrating past the AFTC in Abernathy Creek (October 2001 – January 2002).    We will turn on our electric weir by October 1, or whenever the first fall freshet begins.  Although coho salmon are not currently released into Abernathy Creek, staff at the AFTC have observed a few adipose-clipped, adult coho salmon (presumably hatchery strays) migrating upstream past the AFTC in the past couple years.  We will trap and enumerate adult coho salmon and then determine the proportion of hatchery and natural-origin fish migrating upstream.

- Prepare a final report and manuscript for publication.   In addition to our reporting requirements to BPA, we will prepare a manuscript for publication in a scientific journal where we evaluate temporary hatchery rearing of natural-origin, subyearling coho salmon as a potential method of obtaining fish for recovery activities.

f. Facilities and equipment

Existing facilities and equipment

The Abernathy Fish Technology Center is a complete salmonid hatchery with approximately 1200 Heath incubator trays, 95 4-ft. circular tanks inside the hatchery building for performing controlled, experimental trials (e.g. nutrition and physiology studies), and 12, 8’ x 80’ concrete raceways supplied with both Abernathy Creek water and well water. For the work described here, all fish will be maintained on creek water after transfer to the raceways, although raceways holding steelhead may have to be supplemented with well water during the late summer if drought conditions develop before fall freshets.   A new well with a pump capacity of 2,500 gpm is available.   A diesel-powered, back-up generator provides electrical power to all pumps and electronic monitoring devices in the advent of a power outage.   A fish pathologist, Dr. Pete Taylor, works on site and monitors fish health for the AFTC.

The AFTC is located immediately adjacent to Abernathy Creek with an electric weir and holding pond for diverting and enumerating upstream-migrating fish.   This weir is scheduled to be replaced with a new, variable-field  weir during the summer of 2001, and this updated design will ensure 100% diversion of upstream-migrating fish.   A weir of identical design was recently installed at the USFWS’ Quilcene National Fish Hatchery (Little Quilcene River, Hood Canal, Washington) with outstanding results (Larry Telles, Quilcene NFH, pers. comm.).

The AFTC is also equipped with a fish feed extruder for developing new test diets, and we are developing a physiology laboratory for performing the smoltification assays described above.   We have all the laboratory equipment necessary for performing the physiological assays described above except for a microplate reader (see below).  As noted above, one of our long-term goals is to develop the AFTC into a complete research hatchery with support laboratories in nutrition, physiology, pathology, and genetics.   All four principal investigators are permanent employees of the U.S Fish & Wildlife Service.  We all have pentium-level personal computers with all the necessary software (e.g. SAS, SYSTAT, MS-Excel, etc.) necessary for maintaining and analyzing the data to be collected for the project.

###### Requested equipment

We are requesting FY2001 funds from BPA to purchase the major equipment described below.

Backpack electroshocker.   We are requesting $5,000 to purchase a Smith-Root, Inc. (Vancouver, WA)  backpack electroshocker (Model 12-B P.O.W. 24V) and accessories.   This shocker will be used to collect subyearling coho salmon and steelhead from Abernathy Creek.

Rotary screw smolt trap and trailer.	This trap will be used to collect downstream-migrating smolts in Abernathy Creek.    We are requesting $14,600 to purchase a five-foot trap ($12,600) and trailer ($2,000) from the manufacturer (E.G. Solutions, Inc., Corvallis, Oregon).

Microplate reader.  We are requesting $14,000 to purchase a laboratory, microplate reader (Manufacturer to be decided at purchase).   This reader is necessary for performing some of the physiological assays described above.   It is the only piece of laboratory equipment needed for the work described in this proposal.

g. References

Campton, D.E. 1995. Genetic effects of hatchery fish on wild populations of Pacific salmon and steelhead: What do we really know? Edited by H.L.Jr. Schramm and R.G. Piper. American Fisheries Society, Bethesda, Maryland pp. 337-353.

Carey, J.B. and McCormick, S.D. 1998. Atlantic salmon smolts are more responsive to handling and confinement stress than parr. Aquaculture 168: 237-253.

Cedarholm, C.J. and seven coauthors. 1997. Response of juvenile coho salmon and steelhead to placement of large woody debris in a coastal Washington stream. N. Am. J. Fish. Managment 17: 947-963.

Dickhoff, W.W., Folmar, L.C., Mighell, J.L., and Mahnken, C.V.W. 1982. Plasma thryoid hormones during smolfication of yearling and underyearling coho salmon and yearling chinook salmon and steelhead trout. Aquaculture 28: 39-48.

Flagg, T.A., Waknitz, F.W., Maynard, D.J., Milner, G.B., and Mahnken, C.V.W. 1995. The effect of hatcheries on native coho salmon populations in the lower Columbia River. Am. Fish. Soc. Symp. 15: 366-375.

Hindar, K., Ryman, N., and Utter, F. 1991. Genetic Effects of cultured fish on natural fish populations. Canadian Journal of Fisheries and Aquatic Sciences 48: 945-957.

IMST (Independent Multidisciplinary Science Team) 2000. Conservation Hatcheries and Supplementation Strategies for Recovery of Wild Stocks of Salmonids: Report of a Workshop. IMST, Portland, OR.

Johnson, O.W. and and several other authors In prep. Status review of west coast cutthroat trout (Oncorhynchus clarki clarki) from Washington, Oregon, and California. National Marine Fisheries Service, NOAA, U.S. Dept. of Commerce, Seattle, WA.

McCormick, S.D. 1993. Methods for non-lethal gill biopsy and measurement of Na+, K+ - ATPase activity. Can. J. Fish. Aquat. Sci. 50: 656-658.

Nehlsen, W., Willams, J.E., and Lichatowich, J.A. 1991. Pacific salmon at the crossroads: stocks at risk from California, Oregon, Idaho, and Washington. Fisheries 16: 4-21.

NWWPC (Northwest Power Planning Council) 1999. Artificial Production Review, Council Document 99-15. Northwest Power Planning Council, Portland, OR.

Prunet, P. and Boeuf, G. 1985. Plasma prolactin level during transfer of rainbow trout and Atlantic salmon from fresh water to sea water. Aquaculture 45: 167-176.

Quinn, T.P. 1993. A Review of Homing and Straying of Wild and Hatchery-Produced Salmon. Fisheries Research 18: 29-44.

Ryman, N., Jorde, P.E., and Laikre, L. 1995. Supportive breeding and variance effective population size. Conservation Biology 9: 1619-1628.

Ryman, N. and Laikre, L. 1991. Effects of supportive breeding on the genetically effective population size. Conservation Biology 5: 325-329.

Waples, R.S. 1991. a)Genetic interactions between hatchery and wild salmonids: lessons from the Pacific Northwest. Canadian Journal of Fisheries and Aquatic Sciences 48: 124-133.

# Section 4. Key personnel

Please see the attached one-page C.V.’s for each of the Principal Investigators.

Principal investigators:

Donald E. Campton, Fish Geneticist

Email:  Don_Campton@fws.gov

Address:

U.S. Fish & Wildlife Service

Abernathy Fish Technology Center

1440 Abernathy Creek Road

Longview, WA.  98632

TEL:  360-425-6072

FAX:  360-636-1855

Responsibilities (0.1 FTE):  Will serve as Project Manager and co-P.I., and will assume primary responsibility for this project, including preparation of progress and annual reports.  Will supervise the GS-9 Fishery Biologist (to be funded by this project) and will delegate field and hatchery responsibilities to that person.

Gayle Barbin, Behavioral Physiologist

Email:  Gail_Barbin@fws.gov

Address:

U.S. Fish & Wildlife Service

Abernathy Fish Technology Center

1440 Abernathy Creek Road

Longview, WA.  98632

TEL:  360-425-6072

FAX:  360-636-1855

Responsibilities (0.1 FTE):   Will serve as co-P.I. and be responsible for performing the physiological analyses described in this proposal.

Ann Gannam, Fish Nutritionist

Email:  Ann_Gannam@fws.gov

Address:

U.S. Fish & Wildlife Service

Abernathy Fish Technology Center

1440 Abernathy Creek Road

Longview, WA.  98632

TEL:  360-425-6072

FAX:  360-636-1855

Responsibilities (0.05 FTE):  Will serve as co-P.I. and will be responsible for evaluating feed and diet needs of all fish, and preparing or modifying specific feeds to ensure optimum and growth and survival of all fish raised at the AFTC.

Principal investigators (cont.):

Travis Coley, Fishery Biologist/Ecologist

Email:  Travis_Coley@fws.gov

Address:

U.S. Fish & Wildlife Service

Columbia River Fisheries Program Office

9317 Highway 99, Suite I

Vancouver, WA 98665

TEL:  360-696-7605

FAX:  360-696-7968

Responsibilities (0.05 FTE):  Will serve as co-P.I. and will provide field expertise and training to project staff as needed.  Will assist DEC with directing field activities of the GS-9 Fishery Biologist.

### Personell to be hired with BPA funds:

### GS-9 Fishery Biologist (1.0 FTE)

This person will be hired with the BPA funds requested here and will be responsible for performing all field, hatchery, and data collection activities associated with collection, transfer, care, and maintenance of the fish studied for this project.   This person will supervise two GS-5 Fishery Biologists on this project.

GS-5 Fishery Biologist (1.0 FTE)

This person will assist the GS-9 Fishery Biologist will all aspects of the field and hatchery work, including data collecting, including associated duties assigned by the GS-9 Fishery Biologist.

GS-5 Fishery Biologist (0.5 FTE)

This person will assist the GS-9 Fishery Biologist will all aspects of the field and hatchery work, including data collecting, including associated duties assigned by the GS-9 Fishery Biologist.   The 1.0 FTE time of this GS-5 Fishery Biologist will be split 50:50 between the project proposed here and BPA Project #20106 (P.I. : D.E. Campton) which was funded with FY2000 funds.

- DONALD E. CAMPTON

- E-mail: Don_Campton@fws.gov

- Position:  Fish Geneticist, U.S. Fish & Wildlife Service, Longview, WA

- Education:

Ph.D., Genetics, University of California, Davis, 1986.

M.S., Fisheries, University of Washington, Seattle, 1981.

B.S., Genetics, University of California, Berkeley, 1974.

- Recent employment:

1997-present:	Regional Geneticist, U.S. Fish & Wildlife Service, Region 1, Longview, Washington.

1986-1997: Assistant/Associate Professor, Department of Fisheries and Aquatic Sciences, University of Florida, Gainesville, Florida.

- Expertise:

Population and quantitative genetics of fish with applications to fisheries management, conservation, and artificial propagation; use of molecular genetic markers for studying population structures and relationships.

Relevant publications:

Campton, D.E. and F.M. Utter.  1985.  Natural hybridization between steelhead trout (Salmo gairdneri) and coastal cutthroat trout (Salmo clarki clarki) in two Puget Sound streams.  Can. J. Fish. Aquat. Sci. 42:110-119.

Campton, D.E. and J.M. Johnston.  1985.  Electrophoretic evidence for a genetic admixture of native and nonnative rainbow trout in the Yakima River, Washington.  Trans. Am. Fish. Soc. 114:782-793.

Campton, D.E. and F.M. Utter.  1987.  Genetic structure of anadromous cutthroat trout (Salmo clarki clarki) populations in the Puget Sound area: evidence for restricted gene flow.  Can. J. Fish. Aquat. Sci. 44:573-582.

Campton, D.E.  1987.  Natural hybridization and introgression in fishes: methods of detection and genetic interpretations, p.161-192.  IN: N. Ryman and F. Utter (eds.), Population Genetics and Fishery Management.  Washington Sea Grant College Program and University of Washington Press, Seattle, Washington.

Campton, D.E., F.W. Allendorf, R.J. Behnke, and F.M. Utter; M.W. Chilcote, S.A. Leider, and J.J. Loch.  1991.  Reproductive success of hatchery and wild steelhead.  Trans. Am. Fish. Soc. 120: 816-827.

Campton, D.E.  1995.  Genetic effects of hatchery fish on wild populations of Pacific salmon and steelhead: What do we really know?, p. 337-353.  IN: H.L. Schramm, Jr., and R.G. Piper (eds), Uses and Effects of Cultured Fishes in Aquatic Ecosystems,  American Fisheries Society Symposium 15, American Fisheries Society, Bethesda, Maryland.

Burger, C.V., K.T. Scribner, W.J. Spearman, C.O. Swanton, and D.E. Campton.   2000.   Genetic contribution of three introduced life history forms of sockeye salmon to colonization of Frazer Lake, Alaska.  Can. J. Fish. Aquat. Sci.  57: in press.

Gayle Barbin Zydlewski,  Behavioral Physiologist

Experience

1999-Present:  Research Fish Biologist, USFWS, Abernathy Fish Technology Center,

Longview, WA

Develop innovative fish culture methods in support of restoration and recovery initiatives; investigate relationships between juvenile rearing strategies and adult return rates at Regional fish hatcheries; develop new approaches to investigate the extent of interactions between hatchery-reared and wild fish; and evaluate restoration and recovery strategies for certain populations in decline.  These duties revolve around the use of behavioral (assessment of downstream movements of smolts) and physiological (biochemical and endocrine) techniques to assess the above listed strategies.

1997-1999:  Postdoctoral Research Associate, USGS/BRD, Conte Anadromous Fish

Research Center, Turners Falls, MA
Conducted research to determine whether environmental factors which control the physiology of smolting also affect downstream migratory behavior of Atlantic salmon smolts. I also worked to determine the influence of endocrine changes (exogenous thyroid hormones, cortisol, growth hormone, prolactin) throughout smolting and the initiation of downstream migration.  This research involved maintenance of Atlantic salmon parr and smolts for experimental studies, technical training in fish physiology.

Education:     School                                     			Degree and Date Received

Southeastern Massachusetts University 		B.S., 1990
 	          University of Rhode Island					M.S., 1992

University of Maine							Ph.D., 1996

Expertise:

Physiology and behavior of migration of diadromous fishes.  Nonlethal gill biopsies for gill Na+-K+ ATPase activity assays.  Conduct and develop biochemical assays for determination of endocrine parameters.  Development of passive integrative transponder (PIT) systems for quantifying behavior in the laboratory and field

Publications:

Zydlewski, G.B., A.J. Haro, K.G. Whalen, & S.D. McCormick.  Accepted with revisions.  Performance of stationary and portable Passive Transponder (PIT tag) detection systems for monitoring fish movements in streams and rivers.  Journal of Fish Biology.

Zydlewski, G.B., S.D. McCormick, & A.J. Haro. in review. The role of temperature in downstream migratory behavior of Atlantic salmon smolts.

Barbin, G.P., S.J. Parker, & J.D. McCleave. 1998. Olfactory clues play a critical role in the estuarine migration of silver-phase American eels. Environmental Biology of Fishes 53: 283-291.

Barbin, G.P. 1998. The role of olfaction in homing and estuarine migratory behavior of yellow-phase American eels. Canadian Journal of Fisheries and Aquatic Sciences 55: 564-575.

Barbin, G.P. & J.D. McCleave. 1997. Fecundity of the American eel at 45°N in Maine, U.S.A. Journal of Fish Biology 51(4): 840-847.

Ann L. Gannam

Fish Nutritionist

Abernathy Fish Technology Center

Longview, WA   98632

Education

1988	Ph.D. in Fish Nutrition /Aquaculture, Auburn University, Auburn, Alabama.

1980	Masters of Science in Biology, University of Southern Mississippi, Hattiesburg, 				Mississippi.

1976	Bachelor of Science in Zoology, University of Georgia, Athens, Georgia.

Related Experience

1992-present	Nutritionist, USFWS, Abernathy Salmon Culture Technology Center.  Responsibilities include developing new diets, conducting feeding trials and working on feed problems at the federal hatcheries in Region 1.  Am also responsible for feed mill inspections (fish feed quality control) to insure compliance with specifications for feeds made for the federal government in Region 1.

1989-1992	Assistant Professor, Fisheries, University of Arkansas Pine Bluff, Department of Agriculture.  Was an adjunct assistant professor at the University of Arkansas Fayetteville. Responsibilities included teaching fisheries courses as well as conducting fish nutrition research.  Conducted nutrition studies addressing alternative protein options for channel catfish, lipid concerns in hybrid striped bass, cost effective feed for golden shiners and the effects of temperature on growth in tilapia.

9/1988-2/1989	Research Associate in fish nutrition at the University of Arkansas Pine Bluff.  Responsibilities included equipping and maintaining the nutrition laboratory.  Did preliminary studies to determine the feasibility of using sunflower seed meal as a substitute for soybean meal in catfish diets.  Consulted with catfish and baitfish farmers about problems concerning fish feeding and nutrition.

Selected Publications

Webster, C. D., L. G. Tui, A. M. Morgan and A. Gannam.  2000.  Differences in growth in blue catfish Ictalurus furcatus and channel catfish I. punctatus fed low-protein diets with and without supplemental methionine and/or lysine.  Journal of the World Aquaculture Society 31: 195-205.

Webster, C. D., K. R. Thompson, A. M. Morgan, E. J. Grisby, A. L. Gannam.  2000.  Use of hempseed meal, poultry by-product meal, and canola meal in practical diets without fish meal for sunshine bass (Morone chrysops x M. saxatilis).  Aquaculture 188: 299-309.

Pirhonen, J., C. B. Schreck and A. Gannam.  2000.  Appetite of chinook salmon (Oncorhynchus tshawytscha) naturally infected with bacterial kidney disease.  Aquaculture 189: 1-10.

Gannam, A. L. and R. M. Schrock.  1999. Immunostimulants in fish diets.  Journal of Applied

Aquaculture 9:53-70

Webster, C. D., L. G. Tui, A. M. Morgan and A. Gannam. 1999.  Effect of partial and total replacement of fish meal on growth and body composition of sunshine bass Morone chrysops x M. saxatilis fed practical diets.  Journal of World Aquaculture Society 30:443-453.

## Travis C. Coley

- Columbia River Fisheries Program Office

U. S. Fish and Wildlife Service

9317 Highway 99, Suite I

Vancouver, Washington 98665

360-696-7605

travis_coley@fws.gov

Education:

B.S.  (1976) Fisheries Science (zoology minor), Mississippi State University

M.S.  (1979) Fisheries Resources, University of Idaho

- Experience:

1991- present:  Team Leader, Habitat and Natural Production Team, Columbia River Fisheries Program Office, U.S. Fish and Wildlife Service.  Supervise a staff of 12 biologists and technicians working primarily on habitat assessment, habitat restoration, and fish population assessment and monitoring. Principal investigator on the following studies: 1) Factors Limiting Chum Salmon Populations in the Columbia River Gorge; 2) Habitat Use and Population Dynamics of Lamprey in Cedar Creek; 3) Biological Verification of the Rosgen Stream Restoration Method.

1986 – 1991:  Assistant Project Leader, Idaho Fisheries Resources Office, U.S. Fish and Wildlife Service, Ahsahka, Idaho.  Principle duties consisted of hatchery evaluations, supplementation and natural production investigations.

1978 – 1986:  National Marine Fisheries Service, Northwest and Alaska Fisheries Center, Hammond, Oregon.  Conducted fisheries research in the Columbia River estuary and Pacific Ocean.

- Pertinent Publications:

Muir, W.D. and T.C. Coley. 1996. Diet of yearling chinook salmon and feeding success during downstream migration in the Snake and Columbia Rivers. Northwest Science 70: (298-305).

Muir, W.D., A.E. Giorgi, and T.C. Coley. 1994. Behavioral and physiological changes in yearling chinook salmon during hatchery residence and downstream migration. Aquaculture: 127(69-82).

Miller, W.H., T.C. Coley, H.L. Burge, and T.T. Kisanuki.  1990.  Analysis of salmon and steelhead supplementation: emphasis on unpublished reports and present programs.  Part I.  Technical Report 1990 to Bonneville Power Administration.  Portland, Oregon.

Giorgi, A.E., G.A. Swan, W.S. Zaugg, T.C. Coley, and T.Y. Barila.  1988.  Susceptibility of chinook salmon smolts to bypass systems at hydroelectric dams. North American Journal of Fisheries Management 8:25-29.

McCabe, G.T., Jr., R.L. Emmett, T.C. Coley, and R.J. McConnell.  1988.  Distribution, density and size class structure of Dungeness crab in the river-dominated Columbia River estuary.  Northwest Science 62(5):254-262.

McCabe, G.T., Jr., R.L. Emmett, T.C. Coley, and R.J. McConnell.  1987.  Effect of a river dominated estuary on the prevalence of Crinonemertes errans, an egg predator of the Dungeness crab, Cancer magister.  Fishery Bulletin 85:140-142.

Coley, T.C., A.J. Chacko, and G.W. Klontz.  1983.  Development of a lavage technique for sampling Ceratomyxa shasta in adult salmonids.  Journal of Fish Diseases 6:317-319.

ITEMIZED BUDGET

Personnel

Campton, D.E. (P.I., 0.1 FTE, GS-12-8) . . . . . . . . . . . . . . . . . . . . . . . . . . . . $  6,412

Zydlewski, G. (Co-P.I., 0.1 FTE, GS-12-1) . . . . . . . . . . . . . . . . . . . . . . . .	     5,199

Gannam, A.L. (Co-P.I., 0.05 FTE, GS-12-6) . . . . . . . . . . . . . . . . . . . . . . . .		3,033

Coley, T.C  (Co-P.I., 0.05 FTE, GS-12-8) . . . . . . . . . . . . . . . . . . . . . . . . . .	     3,206

Fishery Biologist (GS-9, 1.0 FTE) . . . . . . . . . . . .. . . . . . . . . . . . . . . . . . . . .     35,854

Fishery Biologist (GS-5, 1.0 FTE)  . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .   23,663

Fishery Biologist (GS-5, 0.5 FTE)  . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .   11,832

Subtotal salaries  . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .   89,199

Fringe benefits (35%)  . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .  . 31,220

Total, personnel   . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .  120,419

Major equipment

Smolt screw trap + trailer . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . 	14,600

Backpack electroshocker + accessories . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . 	  5,000

Microplate reader . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .	14,000

Expendable supplies

Laboratory chemicals/supplies for physiological assays . . . . . . . . . . . . . . . . . . .	3,000

Subcontract to NMFS for genetic assays (300 fish @ $60/fish) . . . . . . . . . . . . .   18,000

PIT tags (3,500 @ $2.40 each) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .	     6,000

Other

Fish food, electricity, misc. hatchery costs ($1,000/mo x 12 mos.) . . . . . . . . . . .  12,000

Labor, PIT-tagging fish (3,500 fish @ $1.25/fish) . . . . . . . . . . . . . . . . . . . . . . .	 3,750

Subtotal . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .	  196,769

Indirect costs (34.2 %) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .	    67,295

Total requested funds . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . .	$264,064