Project ID:	199800702

Title:	Grande Ronde Supplementation: Lostine River O&M and M&E

# Section 9 of 10. Project description

a. Abstract

Activities performed under this project involve the operation and maintenance of adult collection and juvenile acclimation and release facilities and the monitoring and evaluation of a supplementation program on the Lostine River (tributary to the Grande Ronde River) in Northeast Oregon.  These activities are an integral component of the Grande Ronde Basin Endemic Spring Chinook Supplementation Program (GRESP) which is a cooperative project between the NPT, ODFW, CTUIR, and USFWS.  This program was initiated in 1994 as a conservation measure in response to severely decining runs of chinook salmon in the Grande Ronde Subbasin.  The GRESP utilizes supplementation with conventional and captive broodstock techniques to prevent extirpation and begin rebuilding of ESA listed spring chinook.  This project is an integral part of achieving the overall goal of the GRESP, "to prevent extinction, provide a future basis to reverse the decline in stock abundance, and ensure a high probability of populations persistence."  The Nez Perce Tribe is responsible for implementation, coordination, and facilitation of the Lostine River component of the GRESP.

We have operated the adult trapping facility since 1997 for the collection of broodstock and baseline data on adult escapement to the Lostine River prior to supplementation.  In 1999, we released 12,000 conventionally produced smolts from the acclimation facility (the first artificially produced endemic Grande Ronde spring chinook).  The first releases of captive broodstock progeny were 35,000 smolts in 2000 and 133,000 smolts in 2001.

Daily monitoring of the adult weir coincides with its operation along with the collection of environmental data. Juvenile in-hatchery performance and emigration from the acclimation facility is also monitored. In addition, the Nez Perce Tribe conducts spawning ground surveys with co-managers. Therefore, the performance of adult and juvenile hatchery fish can be evaluated against the standards set by natural production.

b. Technical and/or scientific background

### Study Site

The Lostine River is located within the Grande Ronde Subbasin in northeast Oregon. The river is a fourth order stream and a major tributary to the Wallowa River. Its confluence with the Wallowa River lies between the towns of Lostine and Wallowa. The headwaters of the Lostine River are found in the Eagle Cap Wilderness Area of the Wallowa-Whitman National Forest. The West Fork of the river originates at the outlet of Minam Lake and the East Fork originates at the outlet of Upper Lake, both at an elevation of approximately 7300 ft.  The Lostine watershed encompasses an area of 70.9 sq. miles and the river itself is approximately 30 miles long (USGS, 1999). The upper section of the river within the national forest is designated as a National Wild and Scenic River (Palmer, 1993). It flows through a canyon bounded by steep ridge topography. The lower section of the river flows through an open agricultural valley characterized by floodplain geography.

The hydrology of the Lostine River is largely dependent upon seasonal patterns of snowmelt and rainfall. Mean annual flow is 200 cfs. Peak flows occur in late spring and early summer and average 800cfs. Low flows occur in August and September and correspond to the latter part of the dry season. Average low flow is 50 cfs. Water quality in the Lostine River is considered good to excellent. Nutrient levels are low typical of an oligotrophic watershed. The Department of Environmental Quality (ODEQ) establishes water standards for streams in Oregon and identifies steams in violation in its 303(d) list. Nitrate and phosphorus concentrations are consistently below the 0.3mg/L and 0.1mg/L standards set by ODEQ. E-Coli counts are also not out of compliance. The lower portion of the Lostine River is presently on the 303(d) list because of stream flow, habitat channelization and sediment impacts (GRESP 1998).

Fish resources in the Lostine River are representative of northeast Oregon. The drainage supports anadromous species including spring chinook salmon Oncorhynchus tshawytscha, summer steelhead trout O. mykiss and perhaps early fall chinook. The Lostine River historically produced coho salmon O. kisutch, however, this species was extirpated in the Grande Ronde basin by 1979 (Witty 1997). Resident fish species that reside in the Lostine River watershed include, rainbow trout Oncorhynchus mykiss, bull trout Salvelinus confluentus, mountain whitefish Prosopium williamsoni, longnose dace Rhinichthys cataractae, sucker Catostomus spp and sculpin Cottus spp. Introduced fish species in this system include brook trout S. fontinalis, and golden trout Oncorhynchus aguabonita.

### Statement of Problem

Prior to the 1900s, returning adult chinook salmon were estimated to number more than 1.5 million in the Snake River Basin (NMFS 1995). However, numerous stock assessments and review literature have documented the contemporary demise of these Snake River populations (Horner and Bjornn 1979; Howell et al. 1985; Nehlsen et al. 1991). In recognition of this decline, the National Marine Fisheries Service (NMFS 1992) listed Snake River spring and summer chinook as threatened under the federal Endangered Species Act (ESA) in 1992. As have other Snake River stocks, spring chinook populations in the Lostine River also experienced drastic declines in recent decades (Ashe et al. 200). At current escapement levels this stock faces demographic risk and imminent extirpation (Mundy 1999).

In 1994, fisheries co-managers, ODFW, NPT, CTUIR, and USFWS implemented the Grande Ronde Basin Endemic Spring Chinook Supplementation Program in the Lostine River, Catherine Creek and the upper Grande Ronde River.  The goal of this program is to prevent extinction of spring chinook in the three tributaries, provide a future basis to reverse the decline in stock abundance, and ensure a high probability of population persistence. The GRESP proposes to increase the survival of spring chinook salmon in the Grande Ronde River by increasing egg to smolt survival through hatchery incubation and rearing (80% survival as compared to 12% survival for wild/natural).  An increase in adult returns and natural spawners would likewise increase the number of listed offspring.  Artificial propagation under this program utilizes conventional and captive broodstock sources.  Alternative actions considered by co-managers and the NEPA process to restore and rebuild Grande Ronde River spring chinook included: 1) restoration of Snake and Columbia River mainstem habitat and passage (dam removal/breaching) and 2) supplementation with Rapid River (non-native) hatchery stock.

The NPT is primarily responsible for operating supplementation facilities (adult collection and holding and juvenile acclimation and release) on the Lostine River, while the CTUIR is responsible for operating supplementation facilities on the upper Grande Ronde River and Catherine Creek.  ODFW is responsible, in coordination with the Tribes, NMFS, and USFWS for production and activities occurring at Lookingglass SFH, Irrigon SFH, Bonneville SFH, and Manchester Marine Laboratory.

In addition to the potential benefits, the co-managers acknowledge that supplementation programs also have potential risks associated with them (Cuenco et al. 1993, Waples 1995).  A comprehensive monitoring and evaluation program to assess effectiveness and provide information to manage associated risks of the supplementation program is an integral part of the GRESP.  The Nez Perce Tribe, in coordination with ODFW is responsible for monitoring and evaluation of activities in the Lostine River.

c. Rationale and significance to Regional Programs

The Grande Ronde Endemic Spring Chinook Supplementation Program is based on recommendations of an Independent Scientific Panel (Currens et al. 1996) which was convened under the U.S. v. Oregon dispute resolution process to review the Grande Ronde spring chinook status and hatchery program and make recommendations on the most appropriate course of action.  Additionally, this program has undergone intense scrutiny and review through the NMFS ESA Section 10 Application process and an Independent Scientific Review through the NPPC 3-Step Process.

The facilities and activities associated with the GRESP have been authorized under ESA Section 10 and Section 7 Permits and Biological Opinions.  These documents include ESA Section 10 Permit No. 973, Permit No. 1011 (ODFW 1996), Modification of Permit No. 1011 and Permit No. 1164, FWS Section 7 Biological Opinion 501.1100,1-4-98-F4 (bull trout), ESA Section 10 Applications (ODFW 1998, BIA 1998), and NMFS Section 10 Biological Opinion (1998).

Production occurring under the GRESP is completely integrated with the Lower Snake River Compensation Plan (LSRCP) Program.  LSRCP currently provides the facilities, equipment, and personnel to assist production, evaluations, and fish health monitoring of juveniles produced for release in the acclimation facilities funded by this project.

## The goals and objectives of this monitoring and evaluation proposal are consistent with and/or recommended by the Columbia River Basin Fish and Wildlife Program (NPPC 1994 and 2000), Grande Ronde Subbasin Summary (Nowak et al. 2001), Federal Columbia River Power System  Biological Opinion (NMFS 2000), Wy-Kan-Ush-Mi-Wa-Kish-Wit (Nez Perce Tribe et al. 1995) and NMFS Recovery Plan for Snake River Salmon (NMFS 1995).

## Relationship to the Columbia River Basin Fish and Wildlife Program

The intended goals of the 2000 Fish and Wildlife Program (NPPC 2000) are furthered with the initiation of this project: 1) “Halt declining trends in salmon populations above Bonneville Dam by 2005” 2) “Restore the widest possible set of healthy naturally reproducing populations of salmon in each relevant province by 2012” 3) “Increase total adult salmon runs above Bonneville Dam by 2025”.

The Fish and Wildlife Program (FWP) calls for artificial production strategies that are implemented within an experimental, adaptive management approach and use monitoring and evaluation to resolve key program uncertainties. The proposed objectives of the project relate specifically to Section 4 “Artificial Production Strategies” and to Section 9 “Research, Monitoring and Evaluation”. Finally, proposals must also plan for the dissemination of collected data, proven technology and project results (NPPC 2000). Therefore, supplementation technology as described in this proposal falls within the conceptual framework and strategy established in the FWP.

The Lostine component of the GRESP also addresses many of the measures identified in the 1994 version of the Columbia River Basin Fish and Wildlife program (NPPC 1994).  Measure 7.2D.1, encourages incorporating effective husbandry practices and Measure 7.2D.3 includes the investigation of hatchery rearing operations and release strategies to improve survival of propagated fish.  In addition, this project furthers development of FWP Measure 7.4D (Captive Brood Stocks), 7.4F (Portable Facilities for Adult Salmon Collection and Holding, and for Juvenile Salmon Acclimation), and 7.4O (Small-Scale Production Projects).  The monitoring and evaluation research outlined in this proposal is consistent with FWP Measure 7.1C (baseline data collection from naturally spawning populations), Measure 7.2A.6 which stresses the need for evaluating the genetic and ecological impacts of outplanting hatchery fish on wild populations, Measure 7.4L.1, which mandates evaluation of supplementation projects to increase production. Finally, Measure 7.4D.3 encourages the study of hatchery rearing and release strategies to improve survival and adaptation of cultured fish.

## Relationship to the Grande Ronde Subbasin Summary

Many of the goals, objectives, needs, strategies and action items detailed in the Grande Ronde Subbasin Summary (Nowak et al. 2001) are addressed by the Lostine component. Fish hatchery and fisheries research needs outlined in the Summary that relate specifically to spring chinook populations in the basin are as follows:

Hatchery Needs

1. 	Need to continue implementation of Grande Ronde Conventional and Captive

Broodstock Hatchery Programs.

2.	Need to continue to participate in planning, consultation and ESA permitting

activities pertaining to Grande Ronde Basin chinook salmon populations.

3.	Need to develop Annual Operating Plans and write annual reports for all projects.

4.	Need to develop adult collection weirs on the Lostine, upper Grande Ronde rivers

and Catherine Creek that are effective across the entire potential hydrograph.

Monitoring and Evaluation Needs

- Continue and expand efforts to monitor the effectiveness of the chinook salmon captive broodstock, LSRCP and NEOH artificial production programs.

- Need to determine smolt-to-adult survival, survival factors, spawning escapement and life history characteristics of natural and hatchery origin spawning populations.

- Need to evaluate the success of Captive and Conventional broodstock programs for restoring fisheries and increasing endemic stocks of spring chinook salmon in Catherine Creek, Lostine River, and upper Grande Ronde River.

- Need to determine reproductive success of hatchery fish spawning in nature.

The Summary presents strategies and action items needed to meet these needs. The table below lists the strategies and actions identified in the Grande Ronde Subbasin Summary (Nowak et al.  2001) that are specifically addressed through this project.

Grande Ronde Subbasin Summary Strategy and Action Items

Strategy 1 Use artificial propagation to enhance natural production and fisheries in the Grande Ronde Subbasin Action 1.3 Collect returning adult spring chinook salmon at weirs on Catherine Creek, Lostine River and Grande Ronde River. Action 1.9 Acclimate juveniles at sites located on the home stream of each stock and release as smolts. Action 1.11 Develop Annual Operation Plans for captive and conventional broodstock programs Action 1.12 Evaluate programs at each life history stage: spawning, incubation, parr-smolt, smolt release and adult returns for captive and conventional broodstock programs; parr collection, post smolt rearing and maturation for the captive broodstock program. Action 1.13 Coordinate ESA permit activities and participate in program planning and oversight. Action 1.14 Summarize data and prepare and submit annual reports

Strategy 2 Implement monitoring and evaluation to assess health, status and productivity of natural populations. Action 2.1 Conduct spawning ground surveys of streams within the Grande Ronde river Basin: Count number of redds, live and dead adult salmon, examine carcasses for marks and collect coded wire tags, collect scales, determine age of maturity, prespawn mortality, spawner distribution and hatchery:wild ratio. Action 2.4 Monitor run size and develop run size estimate models based on previous years escapement, spawning ground information and other available data. Action 2.5 Evaluate ability to estimate escapement and straying and to characterize the spawning populations in the system. Action 2.8 Estimate and compare smolt detection rates at mainstem Columbia and Snake river dams for fall and spring migrating spring chinook salmon from tributary populations in the upper Grande Ronde river, Catherine Creek and the Lostine River. Action 2.9 Document the annual migration patterns for spring chinook salmon in the Grandse Ronde Subbasin

Strategy 3 Implement monitoring and evaluation to assess health, status and productivity of hatchery fish and effectiveness of hatcheries to accomplish objectives. Action 3.6 Evaluate effectiveness of captive and conventional broodstock programs to restore endemic stocks of spring chinook salmon in the upper Grande Ronde river, Catherine Creek and the Lostine River and maintain their genetic diversity. Examine various indices (e.g., egg-to-fry and fry-to-smolt survival, growth and health, fecundity, progeny:parent ratio) at specific life stages (incubation, fry-smolt rearing, post-smolt rearing and maturation) of all fish raised at hatcheries. Action 3.7 Develop and maintain a database for Captive and Conventional broodstock programs

Strategy 6 Use artificial propagation for supplementation and/or reintroduction of endemic stock spring chinook into the Grande Ronde subbasin tributaries to provide natural production and harvest.

Strategy 9 Monitor and evaluate hatchery programs to ensure they are successful and minimize adverse effects on listed or other indigenous species.

Strategy 10 Implement artificial propagation practices to maintain the genetic and biological integrity of supplemented stocks

## Relationship to the FCRPS Biological Opinion

The objectives of this proposal are specifically related to the Reasonable and Prudent Actions (RPA) identified in the Federal Columbia River Power System (FCRPS) Biological Opinion (NMFS 2000). Co-managers, such as the Nez Perce Tribe, are expected to develop monitoring techniques to help resolve a wide range of uncertainties related to supplementation and “reform existing hatcheries and artificial production programs”. Many of the monitoring and evaluation activities related to supplementation programs and designated in Actions 1, 9, 174, 180 and 182 of the Biological Opinion will be executed in part through the objectives of this proposal. The table below lists the proposed objectives and tasks associated with the actions recommended in NMFS Biological Opinion.

FCRPS Biological Opinion Action Items

Action #1 – implement specific measures in research and monitoring needed to meet and evaluate the performance standards contained in this biological opinion

Action # 8 – develop plans for hatchery and harvest measures that provide offsite mitigation.

Action # 9 – develop plans for monitoring and evaluation to determine the effectiveness of the suite of actions in this RPA.

Action #174 – collaborate with the regional, state, Tribal and Federal fish managers and the Pacific States Marine Fisheries Commission to enable the development and implementation of a comprehensive marking plan.

Action # 176 – develop HGMP’s for the Grande Ronde and Tucannon spring/summer chinook safety net programs.

Action # 177 – BPA shall implement and sustain NMFS-approved safety-net projects.

Action #180 – develop program collaboratively with appropriate regional agencies and determine population status and allow ground truthing of regional databases

Action #182 – determine the reproductive success of hatchery fish relative to wild fish.

## Relationship to Wy-Kan-Ush-Mi-Wa-Kish-Wit

Wy-Kan-Ush-Mi Wa-Kish-Wit (CRITFC 1995) recommends,  AImplement supplementation projects that have met the screening criteria of RASP (1992) and Cuenco et al (1993)”, which includes the proposed Imnaha and Grande Ronde River projects.  “Establish additional programs for each of the subbasin tributary systems to monitor adult escapement and resulting smolt production, and to evaluate (by measuring the number of adults returning) the ability of managers to meet goals set by the Columbia River Management Plan.”

## Relationship to the NMFS Recovery Plan for Snake River Salmon

This project relates to the Snake River Recovery Plan (NMFS 1995): 4.1.b, 4.4c. A...develop and implement management plans for Snake River spring/summer chinook salmon conservation hatchery programs…” and “The fisheries agencies and Tribes should design and carry out production-scale experiments at appropriate Columbia River Basin hatcheries to test individual release strategies and evaluate smolt quality indices believed to improve smolt quality.  The fisheries agencies and the Tribes should develop methods of achieving high quality fish…using acclimation ponds and volitional release strategies”.  The Recovery Plan also calls for genetic studies, evaluations of release strategies, and the development of smolt quality indices, all of which should accompany supplementation projects. These recommendations are addressed in the monitoring and evaluation objectives outlined in this proposal

d. Relationships to other projects

The GRESP is a cooperative project between NPT, ODFW, CTUIR, and USFWS composed of several different BPA contracts with each participating entity.

- Funding for development of new facilities in the Grande Ronde subbasin to implement the GRESP are through:  198805301 - Northeast Oregon Hatchery (NPT), 198805303 – Northeast Oregon Hatchery (CTUIR), and 198805305 - Northeast Oregon Hatchery (ODFW).

- Funding for operation and maintenance of Grande Ronde subbasin adult collection and juvenile acclimate and release facilities are through:  199800702 – Grande Ronde Supplementation (NPT) and 199800703 – Grande Ronde Supplementation (CTUIR).

- Funding for operation and maintenance of the captive broodstock production is through 199801001 - Grande Ronde Captive Broodstock O&M, M&E, Fish Health Monitoring (ODFW).

- Funding for cryopreservation, storage and reconstitution of semen utilized in the program is through:  199703800 - Listed Stock Gamete Preservation (NPT).

- Funding for monitoring and evaluation of the GRESP is through:  199801006 - Captive Broodstock Artificial Propagation (NPT), 199202604 - Early Life History of Spring Chinook Salmon in the Grande Ronde Basin (ODFW), 199800702, 199800703, and 199801001.

The Lower Snake River Compensation Plan program directly affects the success of the GRESP by providing the facilities, equipment, and personnel to facilitate production, evaluations, and fish health monitoring.

Other monitoring and evaluation projects funded under the Columbia River Basin Fish and Wildlife Program that will complement the Lostine plan are: 198712700 – Smolt Monitoring by Non-Federal Entities (ODFW) and 199202604 – Life History of Spring Chinook Salmon and Steelhead (ODFW). These two projects provide wild smolt emigration information that is used to compare hatchery smolt performance. Projects 199703800 - Listed Stock Gamete Preservation (NPT) and 198909600 - Monitor and Evaluate Genetic Characteristics of Supplemented Salmon and Steelhead (NMFS) provide genetic analysis of Lostine origin fish.

The Nez Perce Tribe recognizes the necessary connection between supplementation as a recovery tool and habitat. Habitat condition is a major limiting factor influencing salmon abundance in the Grande Ronde Basin. Indeed, it is the current limitation of habitat that necessitates such a drastic measure as a captive broodstock program. Although it is beyond the scope of this and other localized projects to investigate mainstem and ocean habitat conditions as survival variables, many efforts are directed towards local habitat conditions in the Grande Ronde system. These efforts relate directly to this proposal in that they influence the quality of the aquatic habitat inhabited by endangered salmon. Habitat improvement projects identified in the FWP that will enhance survival of Lostine hatchery fish monitored under this proposal are: 199608300 - Grande Ronde Subbasin Watershed Restoration (CTUIR), 199402700 – Grande Ronde Model Watershed Habitat Projects (GRMWP), 199702500 - Wallowa County/NPT Salmon Habitat Recovery (NPT), 19943900 – Wallowa Basin Project Planner (NPT) and 198402500 - Grande Ronde Habitat Enhancement (ODFW).

Reduced streamflow is identified in the Grande Ronde Subbasin Summary as one of the most serious environmental problems in the Lostine River. Adult upstream passage is a concern in late summer due to irrigation withdrawals. In addition to the projects listed above the following projects address river flows specifically: Larabee Irrigation Improvement – convert from flood to sprinkler (NRCS/BOR/GWEB), Lostine River Hydrology Study (BOR), Westside and Clearwater Ditch Lining (BOR), Carman, Imsland and Attebury Ranch Irrigation Improvement – convert from flood to sprinkler (BOR). Two new proposals that will increase flows in the Lostine River are the Wallowa Dam Rehabilitation Project (ADC) and the Lostine River Water Right Acquisition Proposal (NPT).

e. Project history (for ongoing projects)

Until 1998, the NPT portion of this project was funded under NEOH Master Plan, project 198805301, which developed planning and design documents for adult trapping and juvenile acclimation facilities.  Operation of the adult trapping facility in 1997 also occurred under 198805301.

### Program Progress and Preliminary Results

1997

Preliminary planning and design and environmental assessment (NEPA) documents were completed for the adult trapping/holding and juvenile acclimation/release facilities.  Land acquisition agreements were also obtained for the trapping facility site.  We operated the Lostine River adult weir/trap facility from July 17 to October 1and captured a total of 27 adult spring. Daily monitoring of potential impacts of the weir on spring chinook or other fish species coincided with its operation.  Seven of the adults collected were selected as broodstock and transported to Lookingglass Hatchery for spawning.  Two chinook were adipose fin-clipped, indicating they were hatchery reared strays, and were transported to Lookingglass Hatchery and euthanized.

The adult return, in 1997, was comprised of a nearly equal proportion of age 4 and 5 fish ( 52% four-years-old; 48% five-years-old).  The total sample was comprised of 12 females and 13 males (F/M = 0.92).  The female component had a greater proportion of age 5 fish (58%), whereas males were predominately age 4 fish (62%).  Fork-lengths ranged between 715 mm – 870 mm for the total sample.

The 1997 spawning population was compared to the immigrant population with data collected from 52 recovered carcasses.  Carcasses were comprised predominately of age 4 fish (87%).  Age 5 and age 3 fish comprised 4% and 8% of the sample, respectively.  The age of approximately 2% of the sample could not be determined.  Age determination by scale analysis differed from length frequency criteria on 13 occasions.  All discrepancies were determined to be 1 year younger by scale analysis than if their ages were determined by length criteria.  Females comprised the majority of the carcasses recovered (F/M = 1.6; 62% of the total sample).  Females were recovered at ages 3 (6%), 4 (84%), and 5 (6%); the ages of 3% of the female sample could not be determined.  Males were recovered at ages 3 and 4, with age 4 fish comprising 90% of the male sample.  Fork-lengths, for the total sample, ranged from 560mm – 910 mm.  Fork-length distributions of sampled carcasses were not significantly different from weir sampled fish (chi-square P = 1.00).

In 1997, 17 opercle punched fish were released above the weir to spawn.  Five of the 53 carcasses recovered during spawning surveys had an opercle punch.  This results in a mark-recapture estimate of 147 + 103 (95% CI) adults above the weir.  Forty seven redds were located above the weir, giving a 3.13 fish:redd ratio.  Extrapolating this data to the 49 redds found in the entire Lostine River results in a total return estimate of 162 fish.

The resultant hatchery production of the adults collected for broodstock was approximately 12,000 smolts that was acclimated and released from the Lostine juvenile facility in April 1999.  Adult returns from the 1997 release occurred as 27 jacks in 2000 and 40 four year olds as of July 13, 2001.

1998

Planning, design and the NEPA process for the collection and release facilities were completed.  The project was then evaluated by an Independent Science Review through the Northwest Power Planning Council’s 3-Step Review Process.  The NPPC approved funding for the construction of the facilities in June.  Land acquisition agreements for the acclimation facility site and access road were accomplished through the BPA Lands Division.  Construction of the Lostine Acclimation Facility began in December, 1998.

A comprehensive management plan was developed by the NPT and ODFW for the Lostine River which integrated conventional and captivebrood production.  An ESA Section 10 Permit Application was submitted to NMFS in April that reflected the management plan and requested authorization to operate the collection and release facilities described in this proposal.  We operated the adult weir from June 17 to October 1 and captured a total of 23 adult spring chinook. No fish were observed with external marks or fin clips.  Trapping was interrupted several times during high spring flows.  Broodstock collected for conventional production were returned to the Lostine River to spawn naturally due to fish health concerns at Lookingglass Hatchery.

Adults collected at the weir were predominately at age 4 and 5 (96%), with five-year-olds comprising the majority of the total sample (70%).  One three-year-old was sampled, comprising 4% of the total sample. The total sample was comprised of 12 females and 11 males     (F/M = 1.09).  The female component of the sample was comprised of four and five-year-old fish, with 67% of the females returning at 5 years old.  Males returned at age 3, 4, and 5, with 73% of the males returning at 5 years old. Fork-lengths of immigrants ranged from 560 mm to 1,020 mm.  The length frequencies describing 1998 immigrants were distributed normally. Although the length frequency distribution from the 1997 immigrants was truncated as compared to that of the 1998 run, there was no significant difference between fork-length frequencies from 1997 and 1998 immigrants (chi-square P = 0. 99).

Thirty-five chinook salmon carcasses were recovered during spawning ground surveys in 1998.  Carcasses were comprised of predominately age 5 fish (80%).  Age 4 and age 3 fish comprised 17% and 3% of the sample, respectively.  Age determination by scale analysis differed from length frequency criteria on 4 occasions.  All discrepancies were females, 3 of which were determined to be one year older than if they were estimated by length frequency.  Females comprised the majority of the sample (F/M = 2.8; 71% of total sample).  Females were recovered at ages 4 (20%) and 5 (80%).  Males were recovered at ages 3, 4, and 5.  Sampled males were predominately comprised of five-year-olds (78%).  Fork-lengths, for the total sample, ranged from 555 mm – 1,022 mm.  Length frequencies were distributed normally, and were not significantly different from those of immigrants sampled at the weir in 1998 (Chi-square P = 0.96).

In 1998, 19 opercle punched fish were released above the weir to spawn.  Three of the 28 carcasses recovered during spawning surveys had an opercle punch.  The mark recapture estimate is 138 + 114 (95%CI) fish above the weir.  Twenty eight redds were located above the weir, resulting in a fish:redd ratio of 4.92.  Extrapolating this to the total number of redds (35) found above and below the weir results in a total return estimate of 172.

Hatchery parr were significantly larger than wild parr in the Lostine River (P < 0.0001; Fig 8).  Fork lengths of the 1997 cohort sampled at LGH on November 4, 1998 were distributed normally, ranging from 69 mm – 180 mm with a mean of 122.3 mm.  Weights ranged from 1.4 – 40.4 g, with a mean weight of 20.4 g.  Hatchery parr had a mean relative condition factor (K) of 1.17 + 0.12 and a mean Fulton’s condition factor (Kn) of 1.00 + 0.04.

1999

In February 1999, construction of the Lostine Acclimation Facility was completed and tested for a week prior to delivery of chinook smolts from Lookingglass Hatchery.  On March 1, 12,000 hatchery-reared smolts (BY 97) were transported and released into the acclimation facility.  Acclimation occurred from March 1 to April 1.  During acclimation, the natural rearing environment concept was implemented at this facility in several ways; low rearing densities, natural coloration, natural structures and cover/shading and natural foods.  Fish health and genetic samples were collected on March 29.  Volitional release of fish began on April 1 and fish remaining on April 15 were force released into the Lostine River.

Fork lengths of the 1997 cohort were distributed normally with no bimodal growth pattern, ranging from 105 mm – 148 mm with a mean of 128.0 mm.  Weights ranged from 15.4 -33.8 g, with a mean weight of 23.7 g.  The hatchery smolts had a mean relative condition factor (K) of 1.00 + 0.02 and a mean Fulton’s condition factor (Kn) of 1.13 + 0.05.

Video tapes indicated volitional smolt departure and overall activity were influenced by water temperature. The majority of smolts leaving volitionally departed only on 2 days (4/11 and 4/13) during the afternoon hours when the water temperature reached 41 F.  NPT staff worked with ODFW crews on the Lostine and Wallowa smolt traps during spring emigration. The first hatchery smolt was captured by the Lostine trap on April 3. Based on trap efficiencies, an estimated 2,098 hatchery smolts passed the trap site prior to the forced release on April 15. Hatchery smolt movement through the Lostine trap generally paralleled that of the wild smolts. The diel pattern of hatchery smolts observed at the Wallowa trap was also strongly correlated with the pattern seen in the wild smolts

Preliminary PITAGIS data indicated over 50% (2508) of the pit tagged hatchery fish were interrogated at one or more of the three monitored lower Snake River dams or at McNary Dam. Detections came primarily from the facility at Little Goose Dam. Travel time to Lower Granite Dam ranged from 17 to 60 days. Survival as modeled by SURPH 62.7% (0.13 SE) to Lower Granite Dam. No significant difference was observed between length frequency at tagging and the length frequency at tagging of fish detected at the dams (chi-square, p > 0.05). The length frequencies appeared virtually identical suggesting that smolt size had no effect on downstream mortality.

Fork lengths of the 1999 cohort sampled at LGH on October 26-27, 1999 were distributed normally with no bimodal growth pattern observed, ranging from 64 mm – 173 mm with a mean of 112.5mm.  Weights ranged from 4 – 60 g, with a mean weight of 19.1 g.  Hatchery parr had a mean relative condition factor (K) of 0.99 + 0.04 and a mean Fulton’s condition factor (Kn) of 1.31 + 0.13.

In 1999, sampling of adult salmon at the chinook salmon weir/trap proceeded from April 19 – October 1. Trapping was interrupted several times during high spring flows.  Thirteen adult chinook salmon immigrants were sampled at the Lostine River chinook salmon weir/trap.  One fish was observed with and AD fin clip.  Due to an insufficient adult return those fish collected for broodstock were returned to the Lostine River.

Adults returned predominately at age 4 and 5 (96%), with four-year-olds comprising the majority of the total sample (62%).  Two three-year-old were sampled, comprising 15% of the total sample. The total sample was comprised of 7 females and 6 males (M:F = 1:1.7).  The female component of the sample was comprised of four and five-year-old fish, with 86% of the females returning at 4 years old.  Males returned at age 3, 4, and 5, with 33% of the males returning at each age class. Fork-lengths of immigrants ranged from 560 mm to 813 mm.  The length frequencies describing 1999 immigrants were not distributed normally primarily because of the very small sample size.

2000

A total of 35,039 hatchery-reared smolts (BY 98) were transported and released into the Lostine Acclimation Facility between February 29 and March 1, 2000. These fish constituted the first group of captive broodstock progeny (F1) juveniles released in the Lostine River.   The  natural-type rearing environment was implemented by providing natural in-pond structures, cover, and shading in addition to the natural foods.  Fish health and genetic samples were collected on March 27.  Volitional release of fish began on April 1 and fish remaining on April 18 were force released into the Lostine River at dusk.

In May 2000, an auxillary trap/weir was installed on the Lostine River slightly upstream from the picket weir site that was fished from 1997-1999.  This weir was associated with the Clearwater Diversion and was installed in an attempt to fish during high flows.  The weir was operated from May 5 to June 20th with several interruptions due to record high flows.  No chinook salmon were captured in the auxillary trap during it’s operation, however, two bull trout were captured and released, one on May 7 and one on May 26.

On June 21, installation of the picket weir was completed and fished until October 1, 2000.  Beginning in early July, project staff (O&M and M&E) identified several migration barriers (irrigation diversions) and sections of the river where fish passage was questionable due to the extremely low flow conditions.  Beginning July 14, fish that were identified to be passed above the weir were transported by project staff around the “de-watered” zone and released upstream.  From July 14 to July 23rd, eight fish were transported and released at RM 7.  From July 24th to September 13th, 35 fish were transported and released at RM 13.  Increased flows were observed in mid-September due to the cessation of irrigation activities and some rain events, and fish were no longer transported after September 13th.

A total of 91 adults were trapped from June 22 to September 20, 2000.  Thirty-three of these were retained for broodstock and transported by NPT personnel for conventional program egg source, which produced approximately 32,000 green eggs.

Program results are now available in quarterly reports, AOP documents and ESA Annual Reports.  However, the ultimate utility of the supplementation programs will be demonstrated in the ensuing years when hatchery cohorts begin to return to the natal streams. Only then will evaluation be complete. Therefore, the continuation of this demonstration project will allow a comprehensive review of supplementation technologies. And if successful it will provide time for the region to address factors that limit recovery, restoration and mitigation of Pacific salmon in the Grande Ronde Subbasin.

## Past Costs

Planning, design and construction costs for adult trapping/holding and juvenile acclimation/release on the Lostine River was approximately $350,000 when completed.  In 2002, the adult trapping facility will be in its sixth year of operation, and the acclimation facility will be in its fourth year of operation.  Annual costs for operation and maintenance and monitoring and evaluation are contained in the following table.

| Year | O&M | M&E | Total |
| --- | --- | --- | --- |
| 1998 |  |  | $327,125 |
| 1999 | $336,333 | $124,097 | $460,430 |
| 2000 | $233,113 | $151,686 | $384,799 |
| 2001 | $340,319 | $201,802 | $542,121 |

f. Proposal objectives, tasks and methods

## Project Goals

In light of the present status of the resource, the primary goal of the Lostine River supplementation program is to re-establish and supplement the natural population without a phenotypic or genetic change occurring.

## O&M Goal

Operate and maintain adult collection and juvenile acclimation and release facilities necessary to implement the Lostine River portion of the Grande Ronde Endemic Spring Chinook Salmon Supplementation Program and achieve the overall program goal of increasing adult returns.

## M&E Goal

Because of the underlying uncertainties and necessary management questions concerning this program, monitoring and evaluation is critical. The principal monitoring and evaluation goal is threefold; 1) to establish baseline information on the Lostine River spring chinook salmon population prior to supplementation; 2) to monitor and evaluate the effectiveness of supplementation under the Grande Ronde Basin Endemic Spring Chinook Salmon Supplementation Program; 3) and to provide science-based recommendations for management and policy consideration.

- Objectives, Methods & Associated tasks

After establishing program goals, managers should choose objectives that will define progress towards achievement of those goals and provide a measurable definition of project success (Krueger and Decker 1993). The following objectives were formulated to meet the above goals, management needs and to address program uncertainty. Detailed methodologies and procedures are available in the Annual Operation Plan (AOP). This document is updated and revised each year by the co-managers.

Objective 1:  Coordinate and develop Grande Ronde Endemic Spring Chinook Supplementation Program.

The GRESP was developed cooperatively by the fisheries co-managers, the Nez Perce Tribe, Oregon Department of Fish and Wildlife and the Confederated Tribes of the Umatilla Indian Reservation. All activities involving the GRESP (operation and monitoring and evaluation), i.e, spawning ground surveys, adult trapping, spawning, incubation, juvenile rearing, juvenile tagging and marking, and smolt release will be coordinated among the co-managers.  Documents cooperatively prepared describing program operations include: ESA Section 10 permit applications (ODFW1996, ODFW 1998, BIA 1998) and LSRCP Annual Operating Plans (AOP).  Forums that the co-managers participate in to coordinate operations are LSRCP Evaluation Coordination Committee, Columbia Basin Fish and Wildlife Authority, Conservation Planning Oversight Committee, Captive/Conventional Broodstock Technical Oversight Team, and the U.S. v. Oregon Production and Policy Committees.  All activities are permitted under the ESA Section 10 Permit process.  Funding and program oversight is through BPA.  Other entities involved in the project include USFWS, NMFS, NPPC, CBFWA.  Coordination also occurs with landowners leasing property for facilities and cultural resource, construction and engineer consultants involved in developing and operating the adult and juvenile facilities.

Task 1.1	Coordinate all aspects of the Grande Ronde Basin chinook conventional and captive broodstock project production planning, implementation and monitoring and evaluation with ODFW, NMFS, FWS, and CTUIR.

Task 1.2	Attend TOT and AOP meetings to represent the interest of and to provide information for the Nez Perce Tribe.

Task 1.3	Cooperatively develop appropriate permit applications and biological assessments for implementation of the GRESP.

Task 1.4	Coordinate with private landowners for operation and maintenance of adult and juvenile facilities.

Task 1.5	Coordinate with cultural resource, construction and engineer consultants for operation and maintenance of adult and juvenile facilities.

Task 1.6	Coordinate with other co-managers, regarding relevant management issues, through U.S. v. Oregon Production Advisory Committee and Technical Advisory Committee forums.

Task 1.7	Facilitate the use of collected data with co-managers.

Objective 2:  Operate and maintain a portable weir/trap facility on the Lostine River to collect spring chinook adults.

Protocols for operation of the Lostine River trapping facility will follow basic adult trapping and handling procedures consistent with IHOT guidelines (1995) and the LSRCP Annual Operating Plan.  Adults selected for broodstock will be transferred to a transportation vehicle and transported to Lookingglass Hatchery.  Adults for natural spawning will be released upstream of the weir following recovery from anesthetic.  Only a portion of adults of natural or conventional hatchery origin from across the run will be retained for broodstock.  All captive broodstock origin adults will be released to spawn naturally.  The level of take or number of adults necessary to implement the conventional production component is based on a sliding scale developed by the co-managers (BIA 1998) and permitted by NMFS ESA Section 10 permit.  Adult collection, transportation, and holding details are worked out annually by co-managers through the Annual Operation Plan process.

Task 2.1	Set up auxillary trapping facility structure to fish during high flows - April through June.

Task 2.2	Set up main trapping facility as soon as flows allow to fish during lower flows - July through September.

Task 2.3	Staff facility 24 hours a day providing routine trap checks.  Collect spring chinook adults for a broodstock source and assessment of adult escapement.  Pass fish not selected for broodstock above the weir.

Task 2.4	Sample adults at least daily, collect mark, length, sex, spawning maturation information, and biological samples from adults trapped and opercle punch all adults released upstream of weir.  Provide data to monitoring and evaluation project.

Task 2.5	Deliver necessary injections to those adults selected for broodstock.

Task 2.6	Transport adults selected for broodstock to Lookingglass Hatchery or other holding facility.   Provide transportation of adults back to the Lostine River if necessary.

Task 2.7	Provide transportation of adults from weir to spawning grounds (around dewatered sections) should extreme low flow conditions exist in the Lostine River.

Task 2.8	Collect biological data on incidentally caught species (bull trout and steelhead) and provide data to monitoring and evaluation project.

Task 2.9	Disassemble facilities and equipment on or about October 1.

Task 2.10	Provide security and maintenance of living quarters, facilities and equipment.

Task 2.11	Perform maintenance of facility property as required by agreement with landowner (e.g., fence repairs, irrigation of trees, knoxious weed control).

Task 2.12	Update facility operations manual and routine maintenance journal.

Objective 3:  Operate and maintain a juvenile acclimation and release facility on the Lostine River.

The Lostine River acclimation facility is located approximately twelve miles upstream from the mouth.  Facility capacity is approximately 250,000 fish at 20 fish/lb.  The facility consists of a water supply intake, supply pipeline, four raceways, and drain/release pipes.  Water will be pumped from the Lostine River into the facility.  Protocols for operation of the Lostine River acclimation facility will follow basic juvenile acclimation procedures consistent with IHOT guidelines (1995) and the LSRCP Annual Operating Plan.

Task 3.1	Set up/assemble and test facility in February prior to bringing fish on station.

Task 3.2	Provide pumps, generators, fuel supply, maintenance and emergency service for water supply to acclimation facility.

Task 3.3	Coordinate fish delivery, fish health inspections, and release with co-managers.

Task 3.4	Staff facility 24 hours a days to perform necessary fish culture activities (i.e., feeding, cleaning, monitoring flows, temperatures, DO) and provide final rearing regime and acclimation for up to 250,000 smolts.

Task 3.5	Provide natural type rearing by providing adaptations to rearing containers (e.g., trees for structure, natural foods, shading).

Task 3.6	Facilitate and assist with necessary fish health, genetic, tagging sampling activities.

Task 3.7	Provide volitional release opportunity followed by forced release on appropriate dates.

Task 3.8	Disassemble facilities and equipment following release of fish, on or about April 15.

Task 3.9	Provide security and maintenance of living quarters, facility and equipment.

Task 3.10	Perform maintenance of facility property as required by agreement with landowner (e.g., fence repairs, irrigation of trees, knoxious weed control).

Task 3.11	Update facility operations and routine maintenance journal.

Objective 4: Monitor and evaluate juvenile hatchery  production and performance.

The importance of evaluating hatchery fish performance in the natural environment is stated repeatedly in both the Grande Ronde Subbasin Summary and the Columbia River Basin Fish and Wildlife Program. The critical uncertainty for the region is whether supplementation can help rebuild naturally spawning populations. Therefore, Objective 4 is essential for the proper assessment of supplementation and its utility for restoring chinook salmon in the Grande Ronde subbasin.

Methods:

Monitoring of in-hatchery production reared under the conservation hatchery approach allows for a measure of comparison across years. Collection of biological data during the rearing process assists proper evaluation of the hatchery product used in supplementation. An identifying group mark is required of hatchery fish by US vs Oregon. Mark type will be coordinated by co-managers to ensure compatibility with other programs. A visual implant elastamer (VIE) will be used to distinguish conventional and captive progeny when they return as adults. In addition, a percentage of the total production will be PIT tagged to monitor the volitional departure from the acclimation facility and to examine downstream migration.

Sample size requirements for determining survival to Lower Granite and McNary dams are estimated using SURPH SAMPLE-SIZE program. Using observed survival and detection probability rates from recent hatchery releases, estimated minimum release groups of 800 (Lower Grannite Dam) to 7,500 (McNary Dam) smolts will be required.

Rearing and release strategies can then be evaluated according to smolt emigration survival and adult return. Their post release performance is compared against the standards set by their wild counterparts. Projects198712700 – Smolt Monitoring by Non-Federal Entities (ODFW) and 199202604 – Life History of Spring Chinook Salmon and Steelhead (ODFW).monitored wild smolt performance.

An FS 1001 PIT tag monitoring system operates at the Lostine River Acclimation Facility to aid in evaluation efforts. Software designed with time-stamp capabilities makes this system particularly appealing for volitional release applications. Action codes for each raceway combined with fish movement data according to day and hour allow for proper analysis of rearing and acclimation strategies. Calculating the number of fish remaining after the volitional period is possible without the handling stress of a mark and recapture estimate. Because of the time-stamp feature, accurate migration timing through the hydrosystem is also possible for each fish from a volitional release. Negative travel times are no longer be recorded.

Once in river, smolt survival is determined with Program SURPH.2. The model is a statistical survival analysis package used in fish and wildlife tagging studies. It was designed to analyze release-recapture data for survival estimates (Skalski et al. 1994). For the purpose of this study, SURPH methodology is combined with PIT-tag technology to help quantify survival relationships through the Columbia River Basin. Wild and/or hatchery juveniles from the Lostine River are PIT-tagged, released and potentially detected at multiple dams as they migrate to the ocean. PIT-tag interrogation data is retrieved from the PTAGIS database and processed for SURPH through the program called CAPHIST. CAPHIST was designed by the University of Washington to arrange “comma separated values” (CSV) lists obtained from PTAGIS into SURPH data files. The result is the collection of capture data that can be analyzed to estimate survival and covariates that might influence survival (Skalski et al. 1994).

Task 4.1	Contract for the VIE marking of the conventional F1 smolts.

Task 4.2	Cooperatively PIT tag  with  ODFW  a subsample (7,500) of parr at LFH .

Task 4.3	Sub sample hatchery juveniles for biological characteristics and determine marking efficiencies/retention prior to release.

Null hypothesis: Mean length, weight and condition factors are not significantly different between stocks, cohorts or rearing strategies.

Task 4.4	Monitor the volitional release of the captive and conventional F1 smolts at the acclimation facility.

Null hypothesis: Volitional departure is not significantly different between cohorts or rearing strategies.

Task 4.5	Assist ODFW with the operation of the Lostine screw trap during hatchery 		release periods to monitor the migration of the hatchery smolts and 			compare with wild smolt emigration performance collected by projects 			198712700 – Smolt Monitoring by Non-Federal Entities (ODFW) and 			199202604 – Life History of Spring Chinook Salmon and Steelhead 			(ODFW).

Null hypothesis: Diel and daily movement patterns not significantly different between wild and hatchery smolts.

Task 4.6	Estimate arrival timing, detection rate and survival of released 				conventional smolts to Lower Granite, Little Goose, Lower Monumental 			and McNary Dams Survival and compare with wild smolt 					emigration performance collected by projects 198712700 – Smolt 				Monitoring by Non-Federal Entities (ODFW) and 199202604 – Life 			History of Spring Chinook Salmon and Steelhead (ODFW). Survival is 			estimated with the SURPH.2 model.

Null hypothesis: Arrival timing and downstream survival are not significantly different between wild and hatchery smolts.

.		Null hypothesis: Survival is not correlated with smolt size.

OBJECTIVE 5:  Collect baseline information on environmental conditions in the Lostine River. Habitat information is a stated need in the Grande Ronde Subbasin Summary. Objective 1 Strategy 2 calls for the collection of this data. The Columbia River Basin Fish and Wildlife Program. also identifies the need to “collect current condition and biological potential of the habitat”.

Methods:

Chinook salmon stock status and performance can be evaluated only with respect to the properties of the natural environment in which the population is found.  Understanding interactions between abiotic and biotic components of the ecosystem is important for accurate assessment of a population. Physical processes are known to affect habitat carrying capacity and other biological factors regulating salmon abundance (Major and Mighell 1967; Becker et al. 1983). For this reason, information on the environment is a priority need addressed through monitoring and evaluation. We investigate temperature and discharge data and link these habitat conditions with juvenile and adult chinook salmon in the Lostine River. Water temperature and river flow are monitored to correlate performance variables such as migration timing with the physical conditions of the river.

Task 5.1	Monitor a constant recording thermograph to collect water temperature information near the adult trapping facility and smolt acclimation and release facility. Evaluate according to adult and juvenile movement.

Null hypothesis: Emigration and immigration are not correlated with stream temperature.

Task 5.2	Monitor staff gauge to determine water flows near the adult trapping facility and smolt acclimation and release facility. Evaluate according to adult and juvenile movement.

Null hypothesis: Emigration and immigration are not correlated with stream flow and discharge.

Task 5.3	Use on-line stream discharge information to evaluate  adult and juvenile movement according to flow.

Null hypothesis: Emigration and immigration are not correlated with stream flow and discharge.

OBJECTIVE 6:  Collect and analyze information on abundance, genetic and life history characteristics of the Lostine River wild spring chinook salmon population and compare with that of the returning hatchery fish. The importance of evaluating hatchery fish performance in the natural environment is stated repeatedly in both the Grande Ronde Subbasin Summary and the Columbia River Basin Fish and Wildlife Program. The critical uncertainty for the region is whether supplementation can help rebuild naturally spawning populations. Therefore, Objective 6 is also essential for the proper assessment of supplementation and its utility for restoring chinook salmon in the Grande Ronde subbasin.

Methods:

If a supplementation program is to be successful, the phenotypes and the underlying genetic characteristics of hatchery fish should mimic those of the locally adapted wild chinook. It is through life history traits and genetic variability that salmon populations are able to exploit unique habitats (Gharrett and Smoker 1993). Therefore, the Nez Perce Tribe will monitor both genetic and life history diversity in the wild population. Once this diversity is measured it will be used as a performance standard against which hatchery fish will be compared. Accurate estimates of abundance are also needed to assess whether the population is responding to supplementation.

Smolt to adult survival rates (SARs) will be calculated as the percentage of the minimum number of smolts from one brood year (BY) that pass Lower Granite Dam and the number of adults produced by those smolts that return to Lower Granite Dam (number adults return LGD/number smolts pass LGD).  Recruit per spawner (R/S) ratios will be calculated as the number of adults from one brood year that return to a stream divided by the number of spawners that produced them (number of adults from brood year/number of spawners of brood year).  The return of adults from one brood year may include one-ocean (three year old) to four-ocean (six year old) fish.

The weir facility on the Lostine River is a monitoring tool for biological data as well as a method for broodstock collection. Information collected from this facility assists in developing baseline information on the abundance and biological characteristics of Both wild and hatchery adult salmon returning to the Lostine River.

Information on adult size and age composition of the run will also be obtained from salmon carcasses collected on the spawning grounds in a cooperative effort with ODFW.

Multiple pass spawning ground surveys are conducted with standard methodologies.

Abundance is indexed by adult escapement and estimated via redd counts and enumeration at the weir. Escapement is estimated using two methods of assessment, mark-recapture estimates and redd counts.  A mark-recapture study is initiated each migration year when immigrating are intercepted at the weir, marked with an opercle punch, and released above the weir.  Recaptures are sampled as carcasses found during spawning ground surveys.  Mark-recapture population estimates are calculated using the Bailey modification (1951) of the Petersen Index. Fish per redd ratio are calculated by dividing the number of redds found above the weir by the population estimate.  Total return to the river is then estimated by extrapolating the fish per redd ratio to the total number of redds in the Lostine River (above/below weir).

Task 6.1	Utilize information collected from operation of the adult fish weir and trapping structure on the Lostine River (Objective 2).  Assist with weir installation and/or removal, operation and collection of information from adult salmon as needed.

Task 6.2	Calculate the SARS survival for adult escapement to LGD and to the 																																			Lostine weir.

Task 6.3	Coordinate and gather information collected on abundance and timing of the adult salmon spawner migration into the Lostine River.

Task 6.4	Collect mark, length, sex, and spawning maturation information from adults trapped and opercle punch all adults released upstream of the weir.

Task 6.5	Determine the abundance, age-at-maturity, mean length-at-age, sex ratio and timing of wild adult salmon and compare with the hatchery contribution to the chinook run in the Lostine River.

Null hypothesis: Smolt-to adult survival, sex ratios, age structure and migration timing are not significantly different between wild and hatchery adults.

Task 6.6	Collect genetic samples from adults collected and passed at the weir, from carcasses and juvenile production in the hatchery.

Task 6.7	Contract for the genetic analysis of collected tissues.

Null hypothesis: Genetic structure and diversity are not significantly different between wild and hatchery adults.

Null hypothesis: Genetic structure and diversity are not significantly affected by supplementation.

Task 6.8	Collect life history characteristics, and migration information on steelhead and bull trout incidentally captured at the weir.

Task 6.9	Cooperatively conduct annual chinook salmon spawning ground surveys with ODFW to collect adult size, age composition, stray rates and female egg retention from carcasses sampled in the Lostine River and compare adult wild and captive progeny.

Null hypothesis: Mean length, age-at-maturity and egg retention are not significantly different between wild and hatchery adults.

Task 6.10	Determine hatchery to wild fish ratios based on marked and unmarked carcass recoveries.

Task 6.12	Calculate the fish per redd ratio above the weir.

Task 6.12	Determine total escapement above the weir based on number of adults released above the weir and mark to unmarked ratios.

Null hypothesis: Supplementation does not significantly increase total escapement into the Lostine River.

OBJECTIVE 7:    Monitor and evaluate the operation of adult collection (weir and trap) for adverse impacts to resident and/or anadromous fish populations in the Lostine River. Objective 1 strategy 4 in the Grande Ronde Subbasin Summary stipulates that weirs should be monitored for harmful effects to fisheries resources.

Methods:

Vertical picket weirs are the most common type of weir for trapping adult anadromous fish. In Oregon and Idaho, vertical picket weirs have been used to sample steelhead (Lindsay et al 1994, Sen et al. 1984) and chinook salmon (Messmer et al. 1992, Schrader and Petrosky 1993). The weir facility on the Lostine River is a monitoring tool for biological data as well as a method for broodstock collection. The picket style weir guides fish to the trap at a 45 angle. Pickets are spaced to allow juvenile passage.

To evaluate the effect of the weir/trap on migration of chinook salmon, in-season

monitoring is used to identify any impediments to immigration.  Although our primary concern is chinook salmon immigration, we also evaluate the effect of the facility on non-target species, namely rainbow (steelhead), bull trout, mountain whitefish, and largescale suckers.  Observational sampling is the primary method used to assess the effect of the weir on migration.  Twenty-four hour monitoring in the immediate vicinity of the weir is used to determine weir integrity and any visible negative effects of the weir.  Weir staff note observations in a daily on-site log.  Observations are summarized by day, and totaled for areas above and below  the weir. Stream bank surveys are performed upstream and downstream of the weir. Daily monitoring of the facility coincides with its operation.

Task 7.1	Monitor upstream and downstream of the weir at regular intervals by stream side surveys to determine the presence and species composition of fish on both sides of the weir. Special attention will be given to monitoring whether spring chinook spawning migration is impeded.

Task 7.2	Determine the number of chinook redds and fish in the stream reach below the weir and compare with historical records.

OBJECTIVE 8:  Technology Transfer. Disseminating project information is specifically called for in the Columbia River Basin Fish and Wildlife Program. The Grande Ronde Subbasin Summary also promotes the transfer of monitoring and evaluation information in Objective 2-Strategy 5 and Strategy 1-Action 1.14.

Methods:

Communication of results is essential for practical adaptive management in the Grand Ronde Subbasin. Information shared between all stakeholders regarding the Lostine River Monitoring and Evaluation project increases our collective knowledge of supplementation. That knowledge will lead us to effective salmon management in the Lostine River and other salmon streams.

Task 8.1	Prepare and provide quarterly reports summarizing activities accomplished during the quarter associated with the captive broodstock program. Reports will be submitted 15 days after the end of the quarter.

Task 8.2	Compile, analyze and present results in annual reports summarizing activities associated with supplementation and compare to similar work proceeding in the Columbia River Basin. Provide reports and/or data electronically via BPA and other public access outlets.

Task 8.3	Present reports on project activities and findings at Annual BPA/CBFWA Project Review and other forums (i.e., AFS, NAFWS, LSRCP Annual Review).

We compute mean length of adult spawners and the mean length of juveniles at various life stages to develop growth trajectories with respect to sex, cohort and origin. Mean age-at-maturity is also calculated by sex, cohort and origin. Descriptive statistics such as mean length, mean weight and mean age-at-maturity and their associated variation, standard deviation, degrees of freedom, and confidence intervals are estimated using standard procedures described in Snedecor and Cochran (1980). We calculate indices of condition according to the Fulton and Relative methods.

We utilize inferential statistics for hypothesis testing in which to compare treatment groups (cohorts, sex, origins, etc.).Two way analysis of variance examines year and origin effects on salmon length and age. Independent t-Tests are used to compare group means of length according to sex and cohort. Various distributions are examined with Chi-square tests. Median dates of capture are compared according to life stage and origin with nonparametric median tests (Snedecor and Cochran 1980). The following is a cursory and preliminary examination of some of the collected data. Results were taken from the 2000 ESA Annual Report (NPT 2001), BPA quarterly and draft annual reports.

g. Facilities and equipment

Lostine Adult Trapping Facility

This facility was constructed in 1997 and consists of a portable, picket style weir/trap is located on the Lostine River about a mile upstream from the mouth.  It spans approximately 200 feet, is constructed of aluminum and steel, and is installed at a 45 degree angle to stream flow.  It was designed, engineered, and constructed by River Masters Engineers and Montgomery Watson to ensure optimal fish passage performance.  The weir/trap requires 24-hour monitoring by NPT personnel. To facilitate this a travel trailer and three GSA fleet pick-ups are necessary.

## Lostine Acclimation Facility

The facility consists of a water supply intake, supply pipeline, four raceways, and drain/release pipes.  Water will be pumped from the Lostine River into the facility.  The intakes are provided with stoplog slots and fish screens, which are designed to provide up to 1.9 cfs with a maximum approach velocity of 0.4 fps (consistent with NMFS protocols).  The raceways are constructed of steel and are 8 ft. wide by 80 ft. long, 4.5 ft. high with a 3.5 ft. water depth.  The raceways are fabricated in 20 foot sections and joints are flanged with a rubber gasket to minimize leakage.  This facility has the potential to be portable if necessary.

Fish Transport

The transport of the adults retained for broodstock is accomplished with fish transportation units purchased through this project.  Fish are transported from the Lostine River weir to Lookingglass Hatchery and also around the dewatered zone in the Lostine River during the months of July and August.

## Office space

The Nez Perce Tribe reserves office space at the Enterprise Field Office (Oregon). As part of the field office, a fenced compound is available for parking of vehicles and storage of equipment.  Administrative and fisheries management offices providing support for the project are located in Lapwai, Idaho.

## Technical Equipment

Three desktop computers and two laptop computers are dedicated in part to the project’s needs. Field equipment suitable for field and monitoring activities resides at the Enterprise Office. An FS 2002 PIT tag loop detector is used to interrogate PIT tagged smolts at the Lostine River  screw trap. A stationary FS 1001 PIT detection system was installed at the Lostine River Acclimation Facility to monitor volitional departure of F1 smolts. PIT tags, syringes and needles are used to tag program fish at Lookingglass Fish Hatchery.

## Vehicles

The project leases one GSA vehicle for M&E activities and two GSA vehicles for O&M activities .

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Anders, P.J. 1998. Conservation aquaculture and endangered species: can objective science prevail over risk anxiety?. Fisheries, 23(11):28. |  |
| Ashe, B., K. Concannon, D.B. Johnson, R.L. Zollman, D. Bryson, G.Alley. 2000. Northeast Oregon hatchery spring chinook master plan. Bonneville Power Administration. Project No. 198805305, April 2000. DOE/BP-3267. Bailey, N.J.J/ 1951. On estimating the size of mobile populations from recapture data. Biometrika 38:293-306. Becker, C.D., D.A. Neitzel and C.S. Abernethy. 1983. Effects of dewatering on chinook salmon redds: tolerance of four development phases to daily dewaterings. North American Journal of Fisheries Management 3: 373-382. Botkin, D.B., D.L. Peterson, and J.M. Calhoun (technical editors). 2000. The scientific basis for validation monitoring of salmon for conservation and restoration plans. Olympic Natural Resources Technical Report. University of Washington, Olympic Natural Resources Center, Forks, Washington, USA. Carmichael, R.W., and R.T. Messmer. 1995. Status of supplementing chinook salmon natural production in the Imnaha River Basin. Pages 284-291 in H.L. Schramm, Jr., and R.G. Piper, editors. Uses and effects of cultured fishes in aquatic ecosystems. American Fisheries Society, Bethesda, Maryland. Chilcote, M.W., Leider, S.A., and J.J. Loch. 1986. Differential reproductive success of hatchery and wild summer-run steelhead under natural conditions. Trans. Am. Fish. Soc. 115:726-735. CRITFC (Columbia River Intertribal Fish Commission). 1995. Wy-Kan-Ush-Me Wa-Kush-Wit, Spirit of the Salmon. The Columbia River Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Springs and Yakim Tribes. Columbia River Intertribal Fish Commission, Portland, OR. Dauble, D.D. and D.G. Watson. 1990. Spawning and abundance of fall chinook salmon (Oncorhynchus tshwaytscha) in the Hanford Reach of the Columbia River, 1948 – 1988. PNL – 7289, Pacific Northwest Laboratory, Richland, Washington. Gharrett, A.J., and W.W. Smoker. 1993. Genetic components in life history traits contribute to population structure. Pages 197-202 in J.G. Cloud and G.H. Thorgaard (ed). Genetic conservation of salmonid fishes. Plenum Press, New York. GRESP. 1998. Grande Ronde Basin endemic spring chinook salmon supplementation program: Preliminary Environmental Assessment (DOE/EA – 1173). Bonneville Power Administration, Portland, Oregon. February 1998. Horner, N. and T.C. Bjornn. 1979. Status of upper Columbia and Snake River spring chinook salmon in relation to the Endangered Species Act. A report prepared for the U.S. Fish and Wildlife Service. Idaho Cooperative Fishery Research Unit, University of Idaho, Moscow, Idaho. 60 pages. Howell, P., K. Jones, D. Scarnecchia, L. Lavoy, W. Kendra and D. Ortmann. 1985. Stock assessment of Columbia river anadromous salmonids, Volume 1: Chinook, coho, chum and sockeye salmon stock summaries. Final Report, Project No. 83-335. Bonneville Power Administration, Portland, Oregon. Independent Scientific Group. 1996. Return to the river: Restoration of salmonid fishes in the Columbia river ecosystem. Northwest Power Planning Council, Portland, Oregon. Krueger, C.C. and Daniel J. Decker. 1993. The process of fisheries management. Pages 33-54 in C.C. Kohler and W.A. Hubert (ed.). Inland Fisheries Management in North America. American Fisheries Society, Bethesda, Maryland. Lichatowich, J.A., and J.D. McIntyre. 1987. Use of hatcheries in the management of Pacific salmonids. American Fisheries Society Symposium 1:131-136. Lindsay, R.B., R.K. Schroeder, and K.R. Kenaston. 1994. Steelhead production factors. Oregon Department of Fish and Wildlife, Fish Research Project F-120-R-10, Annual Progress Report, Portland. Major, R.L. and J.L. Mighell. 1967. Influence of Rocky Reach Dam and the temperature of the Okanagan River on the upstream migration of sockeye salmon. Fishery Bulletin 66:131-147. Messmer, R.T., R.W. Carmichael, M.W. Flesher and T.A. Whitesel. 1992. Evaluation of Lower Snake River Compensation Plan facilities in Oregon. Oregon Department of Fish and Wildlife, Fish Research Project AFF1-LSR-94-06, Annual Progress report, Portland. Miller, W.H. (Editor). 1990. Analysis of salmon and steelhead supplementation. Report to Bonneville Power Administration, Contract DE-A179-88BP92663, 119 p. (Available from Bonneville Power Administration, Box 3621, Portland, OR 97208.) Mundy, P.R.. 1999. Status and expected time to extinction for Snake River spring and summer chinook stocks: the doomsday clock and salmon recovery index models applied to the Snake River Basin. Tout Unlimited, Portland, Oregon. 29p. Nehlsen W., J.E. Williams and J.A. Lichatowich. 1991. Pacific salmon at the crossroads: stocks at risk from California, Oregon, Idaho and Washington. Fisheries 16 (3): 4-21. National Research Council. 1996. Upstream: salmon and society in the Pacific Northwest. National Academy Press, Washington D.C. NMFS. 1992. Endangered and threatened species; threatened status for Snake River spring/summer chinook salmon, threatened status for Snake River fall chinook salmon. Federal Register [Docket No. 910647-2043, 22 April 1992] 57 (78): 14,653 – 14,662. NMFS. 1995. Proposed recovery plan for Snake River salmon. U.S. Department of Commerce. National Oceanic and Atmospheric Administration, NMFS, Seattle Washington. March 1995. NMFS. 2000. Biological Opinion: Operation of the federal Columbia River power system including the juvenile fish transportation program and the Bureau of Reclamation’s 31 projects, including the entire Columbia Basin Project. July 27, 2000. Nowak, M.C. and 25 co-authoring agencies. 2001. Draft Grande Ronde Subbasin summary. 256 pp. NPPC. 1994. Columbia River Basin Fish and Wildlife Program. Northwest Power Planning Council. Portland, OR. NPPC. 1999. Multi-species framework – conceptual foundation of the framework process. Northwest Power Planning Council, Portland, Oregon. NPPC. 2000. Columbia River Basin Fish and Wildlife Program. Northwest Power Planning Council. Portland, OR. NPT. 2001. Grande Ronde supplementation program annual ESA report. Endanger Species Permit No. 1011. June, 2001, 56 pp. Olson, D.E., B.C. Cates and D.H. Diggs. 1995. Use of a national fish hatchery to complement wild salmon and steelhead production in an Oregon stream. American Fisheries Society Symposium 15:317-328. Palmer, T. 1993. The Wild and Scenic Rivers of America. Island Press, Washington, D.C. Ptolemy, R.A. 1986. Assessment of highway construction impacts and fisheries mitigation in the Coquihalla River near Hope, British Columbia: progress in 1985. BC Fisheries Project Report No. FIU – 04. RASP (Regional Assessment of Supplementation Project). Summary report series. December 1992. Reisenbichler, R.R.. 1988. Relation between distance transferred from natal stream and recovery rate for hatchery coho salmon. North American Journal of Fisheries Management 8: 172-174. Schrader, W.C., and C.E. Petrosky. 1993. Idaho habitat/natural production monitoring: Part III. Idaho Department of Fish and Game 1993 Annual Report to the U.S. Department of Energy, Bonneville Power Administration, Contract No. DE-B179-81BP21182, Project Sen, H., J. Mack and L. Rothfus. 1984. Compendium of low cost Pacific salmon and steelhead trout production facilities and practices in the Pacific Northwest. Bonneville Power Administration, Division of Fish and Wildlife, Project 83-353, Portland, Oregon. Skalski, J.R., S.G. Smith, S.G., J.W. Schlechte, A. Hoffmann and V.Cassen. 1994. SURPH.1 Manual. Statistical survival analysis of fish and wildlife tagging studies. Report to Bonneville Power Administration. Contract DE-B179-90BP02341, Project 89-107. 268 p. Snedecor, G.W. and W.G. Cochran. 1980. Statistical methods, 7th edition. Iowa State university Press, Ames, Iowa. Soule´, M.E.. 1991. Conservation tactics for a constant crisis. Science 253: 744-750. USGS. 1998. Oregon current stream flow conditions. Internet web page. Http://wwworegon.wr.usgs.gov/rt-cgi/gen_tbl_pg. Vincent, E.R. 1987. Effects of stocking catchable-size hatchery rainbow trout on two wild trout species in the Madison River and O’Dell Crek, Montana. North American Journal of Fisheries Management 7:91-105. Witty, K.L. 1997. Wallowa County anadromous fish restoration plan: Northeast Oregon hatchery coho salmon master plan. S.P. Cramer and Associates. Gresham, Oregon. |  |

# Section 10 of 10. Key personnel

Becky Ashe, Production Project Leader

Nez Perce Tribe Department Fisheries Resource Management, Lapwai, ID office

General management, operations, and coordination.

EDUCATION:

M.S. in Biology with Fisheries emphasis, Eastern Washington University, 1991

B.S. in Biology, EWU, 1989

PROFESSIONAL EXPERIENCE:

Project Leader, Nez Perce Tribe, Lapwai, ID, Jan. 1997 - Present

Northeast Oregon Hatchery Master Plan

Lostine Supplementation Project

Imnaha Steelhead Supplementation

Project Leader, Nez Perce Tribe, Lapwai, ID, April 1997 - Present

Grande Ronde River Supplementation Project - Lostine River

Project Leader, Nez Perce Tribe, Lapwai, ID, May 1994 - 1997

Integrated Hatchery Operations Team

Assistant Project Leader, Columbia River Inter-Tribal Fish Commission, Lewiston, ID, July 1991 - Feb. 1993

Project: Managed CRITFC field office, manage and coordinate northern squawfish predation project on Snake and Columbia River mainstem dams.

Developed Nez Perce Tribe Fish Health Policy and Kalispel Tribe Fisheries Management Plan, primary author of four other publications, co-authored over 10 other publications regarding Integrated Hatchery Operations Team Policies and Procedures Manual, reintroduction of coho salmon in the Clearwater River, predation by northern squawfish, assessment of thermomechanical pulp mill, and baseline fisheries investigations.

RECENT PUBLICATIONS:

Primary Author:

2000.	Northeast Oregon Hatchery Spring Chinook Master Plan.  Bonneville Power Administration, Portland, OR. (Ashe, B., K. Concannon, D.B. Johnson, R. Zollman, D. Bryson, and G. Alley).

1996.  Nez Perce Tribe 1994 Annual Production Report, Sweetwater Springs Hatchery, Spring Chinook Salmon.  Nez Perce Tribe Department of Fisheries Resource Management, Lapwai, ID.  (Ashe, B.L, R.E. Larson, G.W. Walker, and D.B. Johnson.)

### James R. Harbeck, Project Leader

Nez Perce Tribe

Department of Fisheries Resource Management

EDUCATION:

M.S. in Fisheries, Michigan State University, 1998

B.A. in Aquatic Biology, Grand Valley State University, 1994

EMS in Emergency Medical Technology, Davenport College, 1983

DUTIES:

Project implementation for the captive broodstock program and the Lostine River monitoring and evaluation component of the Grand Ronde Basin Supplementation project. Specific duties include coordinating captive brood activities with ODFW, the collection and analysis of data associated with the program, representing the Nez Perce Tribe in meetings with co-managers, personnel supervision, and proposal development.

PROFESSIONAL EXPERIENCE:

Fisheries Biologist, Nez Perce Tribe – 7/98 to Present

Captive Broodstock Project Leader

Lostine River Monitoring and Evaluation Project Leader

Research Assistant, MSU Department of Fisheries and Wildlife –- 1995 -1998

Primary investigator for a steelhead trout evaluation study

Estimated the wild and hatchery composition and determined life history characteristics

Fisheries Creel Clerk, MDNR Fisheries Division –  1994-1995

Collected biological and sociological data from commercial and recreational catch

Evaluated instream habitat structures

Fisheries Aide, District 9, MDNR Fisheries Division – 1993-1995

Conducted lake and stream assessments and surveys

Assisted in stream rehabilitation projects

Environmental Consultant, Applied Ecology Group – 1993

Collected and identified aquatic invertebrates

Conducted literature searches for research projects

Zoology Lab Instructor, Cornerstone College – 1993

Presented stream and habitat evaluation techniques

Prepared lab exercises

SKILLS:

Fish Sampling: electrofishing (backpack, stream barge shocker, and boat units), trap netting, seining, fyke netting, gill netting, minnow traps, hook & line, snorkel surveys, temporary weir and trap, boat handling, and commercial and recreational creel sampling. Population Dynamics: fish identification, Peterson mark-and recapture and DeLury removal methods, spawning ground surveys, Catch-at-Age analysis, and growth relationships. Life History Evaluation: scale pattern analysis (age composition, origin, and smolt size influence), radio telemetry, and bio-data interpretation. Habitat Evaluation: riparian and instream scoring, stream rehabilitation, and macroinvertebrate indices (collection, identification and interpretation). Fish Culture: salmonid and percid spawning, fish outplanting. Computer Proficiency: OPTIMAS (image-processing software), DISBCAL(back-calculation and regression statistics), MS Word, WordPerfect, Excel, and Powerpoint.

ADDITIONAL

SKILLS:

Certified open water diver(PADI), Licensed airframe & powerplant mechanic

(FAA), Licensed emergency medical technician (Michigan Department of                                                                                      Public Health)

TECHNICAL PAPERS AND PRESENTATIONS:

Hesse, J A. and J.R. Harbeck. 2000. Northeast Oregon hatchery spring/summer chinook salmon conceptual monitoring and evaluation plan. Pages 1-26 in Ashe et al. Northeast Oregon hatchery project: spring chinook master plan. Bonneville Power Administran, Portland, OR. DOE/BP-3267.

Harbeck, J.R. 1998. Contribution and Comparative Life History Characteristics of Hatchery and Naturalized Steelhead in the Betsie River, Michigan. Master Thesis, Michigan State University, Lansing MI.

Harbeck, J.R., T.J. Newcomb, and T.G. Coon. 1997. Production and Survival of Juvenile Steelhead in the Betsie River Watershed. Paper presented to the Michigan Chapter of the American Fisheries Society, Aug. 7, 1997, Grand Rapids, Michigan.

Harbeck, J.R. and T.G. Coon. 1997. Contribution and Comparative Life History Characteristics of Hatchery and Naturalized Steelhead in the Betsie River, Michigan. Paper presented at the 59th Midwest Fish and Wildlife Conference, Dec. 7-10, 1997, Milwaukee, Wisconsin.

Harbeck, J.R. and T.G. Coon. 1997. Contribution and Comparative Life History Characteristics of Hatchery and Naturalized Steelhead in the Betsie River, Michigan. Paper presented to the Michigan Academy of Science, Arts, and Letters, Feb. 27-28, 1998, Alma, Michigan.

Rick Zollman, NEOH Assistant Project Leader

Nez Perce Tribe Department of Fisheries Resource Management, Enterprise, OR office

EDUCATION:

A.S. Fisheries Science from Mt. Hood Community College

B.S. in Biology from Shelbourne University, 2001

DUTIES:

Manager of facility operation and maintenance, production and monitoring and evaluation coordination.

PROFESSIONAL EXPERIENCE:

Acting Manager, Eagle Creek National Fish Hatchery,USFWS, 1993-1996

Acting Assistant Manager, Eagle Creek National Fish Hatchery, USFWS, 1990-1993

Work Leader, Eagle Creek National Fish Hatchery, USFWS, 1987-1990

Fish Culturist, Eagle Creek/Dworshak National Fish Hatchery, USFWS, 1981 - 1987

SKILLS:

Management and operation of major anadromous hatchery program (2.5 million smolts), associated structures, and basin co-management.  Experience with all life stages of culturing spring chinook salmon, coho salmon, and winter steelhead.  Management and training of hatchery staff : four FTE fish culturists, maintenance personnel, and temporary helpers that ranged from 2 to 12 depending on work loads.  Experience with communication and coordination involving federal, state, tribal, and private entities.

TRAINING:

Training was implemented by USFWS and included disease short courses, work force management and cross training at other federal hatcheries. The most recently competed training was Fish Genetics in February 1997.

AWARDS:

USFWS Special Achievement Award, several Quality Performance Awards, and Fish Culturist of the Year in 1987.

# Jay Hesse, Research Coordinator

Nez Perce Tribe

Department of Fisheries Resource Management

EDUCATION:

M.S. in Fisheries, Michigan State University, 1994

B.S. in Fisheries and Wildlife, Michigan State University, 1992

DUTIES:

Technical direction and supervision of fisheries research projects, research coordination, Nez Perce Tribe LSRCP project implementation, report writing, monitoring and evaluation plan and  proposal development, tribal fisheries research representation at federal and state meetings, budget preparation, personnel supervision.

PROFESSIONAL EXPERIENCE:

Project Leader, Idaho Salmon Supplementation Study.  Nez Perce Tribe. July 1994 - October 1997.

PUBLICATIONS:

Hesse, J.A. and S.P. Cramer. 2000. Monitoring and evaluation plan for the Nez Perce Tribal Hatchery: Phase 1 Action Plan. Prepared for Bonneville Power Adminstration, Project 8335000. Nez Perce Tribe, Lapwai, Idaho.

Hesse, J A. and J.R. Harbeck. 2000. Northeast Oregon hatchery spring/summer chinook salmon conceptual monitoring and evaluation plan. Pages 1-26 in Ashe et 	al. Northeast Oregon hatchery project: spring chinook master plan. Bonneville Power Administration, Portland, OR. DOE/BP-3267

Hesse, J. 1997.  A-run steelhead status in tributaries of the lower Clearwater River, Idaho.  In Interactions of hatchery and wild steelhead in the Clearwater River of Idaho. 1995 Progress Report, Fisheries Stewardship Project, USFWS Report.  November 1997.

Hesse, J.A., P.J. Cleary, and B.D. Arnsberg.  1995.  Salmon Supplementation Studies in Idaho Rivers.  Annual Report - 1994.  U.S. Department of Energy - Bonneville Power Administration.  Portland, Oregon.

Hesse, J.A. and B.D. Arnsberg 1994.  Salmon Supplementation Studies in Idaho Rivers.  Annual Report - 1993.  U.S. Department of Energy - Bonneville Power Administration.  Portland, Oregon.

Hesse, J.A. 1994.  Contribution of hatchery and natural chinook salmon to the eastern Lake Michigan fishery, 1992-1993.  Masters Thesis, Michigan State University.

# Paul Kucera, Director of Biological Services

Nez Perce Tribe

Department of Fisheries Resource Management

EDUCATION:

M.S. in Fisheries Management, University of Idaho 1990

B.S. in Fisheries Management , Utah State University ,1975.

PROFESSIONAL EXPERIENCE:

1991-present		Director of Biological Services with the Nez Perce Tribe Department of Fisheries Resources Management.  Responsible for technical program direction and administration of the Fisheries Research Division.

1988-1991		Senior Fisheries Biologist with the Nez Perce Tribe Fisheries Department.

1987-1988		Acting Fisheries Program Manager with the Nez Perce Tribe Fisheries Department. Responsible for fisheries program management and direction.

1984-1986		Senior Fisheries Biologist with the Nez Perce Tribe Fisheries Department.  Conducted research on juvenile steelhead trout  life history characteristics and abundance in relation to physical habitat parameters on five streams.

1982-1983		Project fisheries biologist with the Nez Perce Tribe Fisheries Department.  Responsible for conduct of a physical and biological inventory of streams on the reservation proper with emphasis on anadromous salmonids.

1978-1980		Fisheries biologist with the Colville Confederated Tribes Fish and Wildlife Department.  Developed fishery management programs for the Colville Tribe on their 1.3 million acre reservation and the 1.7 million acre ceded area.

1975-1978		Fisheries research biologist with W.F. Sigler and Associates, Environmental Consulting Firm. Ecological and fish life history research on 110,000 acre Pyramid Lake, Nevada.

PUBLICATIONS:

Kucera, P.A. and M.L. Blenden. 1996. Summary report of 1996 project activities relating to endangered chinook salmon populations listed under the Endangered Species Act. Nez Perce Tribe Department of Fisheries Resources Management, Lapwai, Idaho. 60 pp.

Kucera, P.A.  1989.  Nez Perce Tribal review of the Imnaha River Lower Snake River Compensation Plan.  AFF1/LSR-89-08, Tech. Rep. 89-7.   Annual project report to the U.S. Fish and Wildlife Service.  Nez Perce Tribe Fisheries Dept., Lapwai, ID. 49 pp.

Kucera, P.A., D.L. Koch and G.F. Marco.  1985.  Introductions of Lahontan cutthroat trout into Omak Lake, Washington.  North Amer. Jrnl. Of Fish. Mngt. 5(2): 296-301.

Johnson, J.H. and P.A. Kucera.  1985.  Summer-autumn habitat utilization of subyearling steelhead trout in tributaries of the Clearwater River, Idaho.  Can. Jrnl. Zool.  Vol, 63:2283-2290.

Sigler, W.F., W.T. Helm, P. A. Kucera, S. Vigg and G. W. Workman.  1983.  Life history of the Lahontan cutthroat trout, Salmo clarki henshawi, in Pyramid Lake, Nevada.  Great Basin Naturalist 43(1): 1-29.