# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID: 199800704

Title:	Northeast Oregon Hatcheries Implementation (ODFW)

# Section 9 of 10. Project description

a. Abstract

This project was initiated as one of the Northeast Oregon Hatchery Projects to improve fish production in the Hood, Umatilla, Imnaha, Grande Ronde and Walla Walla basins via hatchery and satellite facility development. Originally this project focused on contributing to the council’s doubling goal. With the listing of Snake River chinook and steelhead under the federal Endangered Species Act, efforts in the Grande Ronde and Imnaha have been refocused on contributing to recovery.  Specially, the current objective is to contribute to an upward trend in spawning ground counts. This will be accomplished through increased outmigration of smolts using hatchery production while avoiding unintended changes to population structure, fitness and genetics. Without intervention, loss of biodiversity and inbreeding depression due to small population size may put these stocks further at risk.  Long-term project implementation is expected to result in the return of increased numbers of wild adults, reducing those risks and hastening recovery. We expect recovery of these weak populations over the next 5+ generations (20+ years), to population sizes supporting ESA de-listing. This project is responsible for integrating Northeast Hatchery Operations (NEOH) with the spring chinook master plan submitted by the Nez Perce Tribe (Ashe et al. 2000).  The Draft Grande Ronde Subbasin Summary (Nowak 2001), Draft Imnaha Subbasin Summary (Saul et al. 2001), and NPT spring chinook master plan calls for development of new conservation facilities and modifications to Lookingglass Hatchery to implement salmon recovery programs in the Imnaha and Grande Ronde subbasins. This proposal covers Oregon Dept. of Fish and Wildlife implementation of the conventional supplementation component of the Grande Ronde Endemic Spring Chinook Supplementation Program (GRESCSP). The program is a cooperative effort among ODFW, USFWS, NPT, and CTUIR to develop endemic broodstocks. NPT is primarily responsible for operating adult trapping and smolt acclimation facilities on the Lostine River. CTUIR is primarily responsible for operating adult trapping and smolt acclimation facilities on upper Grande Ronde River and Catherine Creek. This project is also responsible for integrating the GRESCSP with existing USFWS artificial propagation activities at Lookingglass Hatchery.  Specially, this proposal is to supplement existing programs to implement the short-term goal of producing 360k endemic (conventional) smolt spring chinook (120k each for Catherine Creek, upper Grande Ronde, and Lostine River), monitor adult returns, and evaluate conventional to captive brood recovery approaches, and monitor fish health.  The long-term goal for Lookingglass Hatchery is to return 5,800 adults by producing 900k endemic smolt spring chinook for Grande Ronde Subbasin.

b. Technical and/or scientific background

Construction of four Lower Snake dams were authorized by Congress in 1945 with no mitigation identified for anadromous fish.  Nine years later, funding was appropriated for construction of the four dams with funding for adult fish ladders and other facilities for salmon and steelhead mitigation.  However, no artificial propagation measures for compensating for unmitigated fish losses were specified at that time.

In the mid-1960’s, after Ice Harbor had been constructed and Lower Monumental and Little Goose were underway, the Fish and Wildlife Service, National Marine Fisheries Service, and state fisheries agencies began to assess mitigation for project-related fish and wildlife losses under the Fish and Wildlife Coordination Act.  A joint 1972 FWS/NMFS Coordination Act Report provided to the Corps described the short and long term impacts of all four Lower Snake dams and recommended mitigation and compensation for both fish and wildlife.  That report provided the basis for the Corp’s 1975 Lower Snake River Fish and Wildlife Compensation Plan (LSRCP) to Congress.  A year later, the LSRCP was authorized by Congress as part of the Water Resources Development Act of 1976.

The basis for the anadromous fish compensation was a 15% loss of emigrating smolts passing through the turbines at each of the four Lower Snake facilities.  The cumulative losses were estimated to total 48% of the pre-dam Snake River chinook salmon and steelhead runs.  The plan called for creation of hatcheries to produce sufficient juveniles to compensate for the this loss with two additional goals of replacing the adult returns “in-kind” and “in-place.”  The other 52% of the run was expected to be maintained or increased through natural production.  The compensation was focused on replacing adult spring/summer and fall chinook and summer steelhead, despite the fact that there were other anadromous species, such as coho and sockeye, still returning to the basin at that time of dam construction.  Congress authorized the Corps to construct the facilities, BPA to repay the treasury for the cost of this program from revenues generated by power sales, and FWS or NMFS to administer of operations.  In 1976 the Corps, FWS, NMFS agreed that the FWS would administer the program.

The adult return goals contained in the compensation plan were based on the Snake River runs between 1959 and 1961.  The overall goals of the LSRCP include returning adults above Lower Granite Dam.  The fall chinook goal is 18,300, the spring/summer chinook 58,700, and the summer steelhead 55,100.  The plan also calls for resident trout production to compensate for the loss of angler days when the dams inundated about 140 miles of spawning habitat.  Specifically in the Grande Ronde subbasin, the LSRCP goals are 5,820 spring chinook and 9,184 steelhead.

The USFWS LSRCP Program must comply with the federal Endangered Species Act (ESA), meet federal tribal trust responsibilities, adhere to federal laws and agreements and court orders, and to pursue FWS Mission and Vision.  Under the ESA, we are to ensure that LSRCP actions do not jeopardize listed species whenever possible.  Tribal responsibilities require that FWS provide technical assistance, consult with tribes as co-managers, help fulfill restoration or mitigation needs as determined by co-managers, and recognize tribal management decisions on resources under direct jurisdiction (i.e. on reservations).  Agreements and court orders that impact the LSCRP Program directly are the U.S.-Canada Treaty and US vs. Oregon (the Columbia River Fish Management Plan).

The rationale of the NEOH implementation process is to integrate existing programs (e.g. LSRCP and NEOH) and to restore Grande Ronde basin endemic spring chinook as directed by the National Marine Fisheries Service (NMFS). To implement the NMFS directions, Lookingglass Hatchery program has been modified and the operations and maintenance of Lookingglass Hatchery is more complex.  The current program consists of four endemic stocks (Imnaha, Lostine, Catherine, and Grande Ronde), two captive brood components (wild parr and F1 smolts), and bacterial kidney disease rearing segregation, as well as adult holding, spawning, and smolt acclimation of the three endemic and Imnaha spring chinook stocks.

Modifications to the well water delivery system and chillers were made to Lookingglass Hatchery to provide a “disease free” water source for incubation and early rearing for endemic program, and captive brood wild parr rearing (BPA 198801006).  These modifications were not successful.  Modifications resulted in limited chilled well water enough for either wild parr rearing or egg incubation.  Currently, wild parr are reared at Lookingglass and all green eggs are transferred to either Irrigon or Oxbow hatcheries.  Eggs are incubated, hatched, and reared to 150 to 250 fpp before transferring back to Lookingglass.

c. Rationale and significance to Regional Programs

The rationale of this proposal integrates two recovery approaches, captive brood supplementation and conventional enhancement, to LSRCP mitigation and is tied to recovery subbasin plans (Ashe et al. 2000; Nowak et al. 2001). The ODFW recent NEOH efforts have focused on planning and implementation of the Grande Ronde Endemic Spring Chinook Supplementation Project (GRESCSP) to support recovery of these populations as directed by the National Marine Fisheries Service (NMFS).  The GRESCSP incorporates a number of components including setting aside the Wenaha and Minam basins as natural production reserves, supplementing Lostine, Catherine Creek and upper Grande Ronde chinook populations using captive and conventional hatchery broodstock techniques.  The GRESCSP serves as the umbrella integrating existing programs (e.g. Lower Snake River Compensation Plan, NEOH, etc) to limit duplication.

In addition, the captive brood program was initiated in 1995 as a conservation measure in response to severely declining endemic stocks of chinook salmon in the Grande Ronde Subbasin. Our goals are to help prevent extinction of the three populations (Lostine, Catherine Creek and upper Grande Ronde) and to ensure a high probability of population persistence well into the future once the causes of basin wide population declines have been addressed. The program is designed to produce a minimum of 150 adults to the river of parent origin and to ensure threshold escapement levels are met. Management strategies for the Grande Ronde River subbasin incorporate objectives derived from recommendations made by the Columbia Basin Fish and Wildlife program, NMFS Draft Recovery Plan, Tribal Recovery Plan, Columbia River Fisheries Management Plan, as well as draft Imnaha Subbasin Summary and the draft Grande Ronde Subbasin Summary (Nowak et al. 20001).

This proposal also addresses the objectives outlined by ODFW in the draft Grande Ronde Subbasin Summary.  Objectives include:

Objective 1:  Achieve a sufficient spawner numbers and productivity of Grande Ronde Basin spring chinook salmon, by restoring and maintaining natural spawning populations, to will allow de-listing.

Objective 2:  Reduce the demographic risks associated with the low productivity and decline of native spring chinook salmon populations in Catherine Creek, Lostine River and Grande Ronde River.

Objective 3:  Maintain artificial production programs for spring chinook salmon and steelhead, using locally-adapted broodstocks to meet recovery, conservation and harvest goals, and mitigate for fish losses associated with construction and operation of lower Snake River dams.

Objective 4:  Establish an annual supply of steelhead and spring chinook salmon brood fish capable of meeting annual production goals.

This proposal also addresses the objectives outlined by NPT in the draft Grande Ronde Subbasin Summary. Objectives include:

Objective 1.  Restore and recover historically present fish species.

Objective 2.  Provide for harvestable, self-sustaining populations of anadromous and resident fish species in their native habitat.

Objective 3.  Manage salmon and steelhead for long-term population persistence.

Objective 11.  Meet federal fisheries mitigation responsibilities for LSRCP program.

Objective 12.  Provide for Tribal hatchery production needs in federal and state managed facilities.

Objective 14.  Coordinate with the National Marine Fisheries Service and U.S. Fish and Wildlife Service to fund and implement actions identified in the Biological Opinions, and to implement other emergency actions that address imminent risk to listed salmon, steelhead, and bull trout populations.

This proposal also addresses the objective outlined by CTUIR in the draft Grande Ronde Subbasin Summary.

Objective 1.  Achieve and maintain an average run of 16,400 spring chinook to the Grand Ronde River mouth for purposes of natural production, fisheries, and broodstock.

d. Relationships to other projects

The implementation efforts of this proposal are associated with LSRCP operation and maintenance of Lookingglass Hatchery, fish health inspections, and monitoring and evaluation activities under the conventional broodstock strategy, and coordination with NPT and CTUIR operations of hatchery facilities.  NPT is primarily responsible for developing and operating adult trapping and smolt acclimation facilities on the Lostine River. CTUIR is primarily responsible for developing and operating adult trapping and smolt acclimation facilities on upper Grande Ronde River and Catherine Creek. ODFW is primarily responsible for transportation, spawning, rearing, and pathology activities. Co-managers cooperate to develop annual operating plans and conduct monitoring and evaluation activities.

The projects related to the NEOH implementation of the GRESCSP include (Figure 1):

Grande Ronde Subbasin Fisheries Restoration Programs

LSRCP AOP ODFW

NEOH Master Plan NPT

BPA Captive Brood (TOT) ODFW, CTUIR, NPT, NMFS

BPA Captive Brood (AOP) ODFW, CTUIR, NPT, NMFS

Planning and Coordination

NEOH Planning ODFW

GRMWSP

Lookingglass Hatchery O&M ODFW

Hatcheries M&E ODFW/NPT

Salmon Life History ODFW

Fish Passage

Lostine Facility NPT

Catherine Cr. U. Grande Ronde Facilities CTUIR

Outmigration/

Survival M&E  ODFDW/NPT

Irrigon Hatchery O&M ODFW

Hatchery Operations

Research Monitoring and Evaluations

Captive Brood ODFW/CTUIR/NPT/NMFS

Bull Trout Life History ODFW

Habitat Enhancement

Oxbow Hatchery ODFW

Fish Liberations ODFW

Fish Health ODFW

Cyrogenetic Preservation NPT

Figure 1.  Project interactions between Coordination and Planning, Research Monitoring and Evaluation, and Hatchery Operations in the Grande Ronde Subbasin.

- LSRCP (USFWS).  Administration.  Plan, develop, and integrate O&M and M&E activities of tribal and federal agencies into an annual operation plan (LSRCP AOP).

- LSRCP (USFWS).  Hatchery and Satellite Maintenance and Operations.

- LSRCP (USFWS).  Hatchery Monitoring and Evaluations including smolt passage and survival.

- LSRCP (USFWS).  Fish Health.

- LSRCP (USFWS).  Liberations.

- The Northeast Oregon Hatchery Master Plan (198805301).  Plan and develop conservation production facilities in the Imnaha and Grande Ronde rivers necessary to implement salmon recovery programs for native, ESA listed salmon.  Development of a comprehensive monitoring and evaluation program that allows adaptive management to optimize hatchery and natural production, sustain harvest, and minimize ecological impacts.  Complete activities and sub-activities designed to provide data for resolving management questions and critical uncertainties relating to supplementation of chinook salmon.

- Grande Ronde Model Watershed Project (199202601).  Selected in 1992 by the NPPC as the model watershed project in Oregon (includes the Grande Ronde and Imnaha subbasins).  Completed a basin wide assessment in 1993.  Completed an Operations-Action Plan in 1994. The 14 member Board represents a broad constituency. Subcommittees include a Standing Committee and a Technical Commmittee (which reviews all project proposals).  The Program provides coordination of efforts in the Grande Ronde and Imnaha subbasins.  The planner associated with the program writes project proposals and completes BA’s and NEPA for the projects.

- Captive Brood Artifical Progation (199801001).  Implements the captive broodstock project through the collection of juvenile salmon from the wild and maintaining them in captivity. The founding generation is spawned at maturity and the resulting F1 generation is released back to the parental stream.

- Grande Ronde Basin Spring Chinook Captive Broodstock Program (198801006).  Implement captive broodstock programs and associated research, monitoring, evaluation, and fish health for spring chinook salmon populations in Catherine Creek, upper Grande Ronde and Lostine rivers, to conserve genetic diversity and assist in recovery.

- Preserve Salmonid Gametes (199703800). Preserve male salmonid gametes through cryogenic techniques in order to maintain genetic diversity in populations with low levels of abundance and at high risk of localized extinction. Strives to ensure availability of a genetic sample of the existing male population through preservation in a salmonid germplasm repository.  Our approach is to sample and cryopreserve gametes thereby preserving salmonid genetic diversity within the major subbasins in the Snake River basin.

- Life History of Spring Chinook Salmon and Summer Steelhead (199202604). Investigate the abundance, migration patterns, survival, and alternate life history strategies exhibited by spring chinook salmon and summer steelhead from distinct populations in the Grande Ronde and Imnaha River basins

- Bull Trout Genetics, Habitat Needs, Life History, etc. in Central and N.E. Oregon (199405400). The goal of the project is to provide scientific information that will help develop a protection and recovery plan for bull trout in Oregon’s proportion of the Columbia Basin.  Specially, monitor and enumerate bull trout at LSRCP adult collection facilities.

- Grande Ronde Supplementation: Lostine River O&M and M&E (199800702).  Operate adult trapping and juvenile acclimation facilities and conduct monitoring and evaluation in the Lostine River to implement the Lostine component of the Grande Ronde Basin Endemic Spring Chinook Supplementation Program (GRESCSP).

- Facility O&M And Program M&E For Grande Ronde Anadromous Salmonids (199800703).  Operate adult trapping and juvenile acclimation facilities and conduct monitoring and evaluation in the Upper Grande Ronde and Catherine Creek to implement the Upper Grande Ronde and Catherine Creek component of the Grande Ronde Basin Endemic Spring Chinook Supplementation Program (GRESP).

- The Habitat Enhancement Project (8402500) establishes long term riparian, fish habitat and tributary passage improvements on private lands through riparian leases, cooperative agreements and easements of 15 years in length.  Individual projects contribute to ecosystem and subbasin wide watershed restoration and management efforts underway by state, federal and tribal agencies.  The project provides off-site mitigation for mainstem fisheries losses caused by Bonneville, The Dalles and John Day hydroelectric dams.

e. Project history

This project was initiated as one of the Northeast Oregon Hatchery Projects to improve fish production in the Hood, Umatilla, Imnaha, Grande Ronde and Walla Walla basins via hatchery and weir development. Originally this project focused on facility planning to contribute to the council’s doubling goal. In 2001, this proposal was divided into planning and implementation. With the listing of Snake River chinook and steelhead under the federal Endangered Species Act, efforts have been refocused on contributing to recovery before attempting to meet the Council’s doubling goal.  This project focused on the implementing the Currently Permitted Program (CCP) of 900k endemic smolts: 250k Lostine, 250k Catherine, 250k Grande Ronde, 150k Lookingglass Creek.

In 1997, Comanagers installed temporary adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River and began collecting adult chinook. ODFW spawned and reared progeny of adults collected from Lostine River.

In 1998, Comanagers operated temporary adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River. Too few adult chinook were collected for spawning. Adults were returned to spawn naturally.

In 1999, Comanagers operated temporary adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River. Too few adult chinook were collected for spawning. Adults were returned to spawn naturally.  First release Lostine river release of 12k endemic ChS smolts.

In 2000, Comanagers operated acclimation and adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River. Acclimated and released 1.5K GR, 38K CC, and 35K LR captive brood produced smolts. Comanagers operated adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River. Eight females from Lostine were collected and spawned (33,546 green eggs taken). Grande Ronde and Catherine Creek adults were returned to spawn naturally. Spawning ground surveys recorded 34 redds Catherine Creek, 20 redds Grande Ronde, 64 redds Lostine, 139 redds Minam, and 138 redds Wenaha.

In 2001, Comanagers operated acclimation facilities in upper Grande Ronde River, Catherine Creek, and Lostine River. Acclimated and released 2.5 GR, 138K CC, and 134K LR captive brood produced smolts. Comanagers operated adult collection facilities in upper Grande Ronde River, Catherine Creek, and Lostine River.  As of July 6, 262 adults were trapped at Lostine (55 retained for brood), and as of July 13, 85 adults have been trapped at CC (22 retained for brood), and 44 adults have been trapped at GR (14 retained for brood).  In addition, jacks from Captive Brood program have been recovered: Catherine Creek-27, Grande Ronde-0, Lostine-1.  Co-mangers agreed to maintain the captive brood propagation component at least through 2004 with M&E through 2009; Therefore reducing target (short-term) of endemic production to 360k smolt spring chinook, 120K each for Catherine Creek, upper Grande Ronde, and Lostine River.  .

f. Proposal objectives, tasks and methods

Objective 1. Assist LSRCP artificial propagation program with implementation of the endemic broodstocks to reduce the decline and contribute to recovery Grande Ronde basin spring chinook by coordinating with NPT, CTUIR, and USFWS.

Task 1.a	Work with GRESCSP cooperators to develop annual operating plan implementing provisions of NMFS permits covering the GRESCSP.

Task 1.b	Participate in monthly Captive Brood Technical Oversight Team meeting with cooperators to coordinate activities under the annual operating plan.

Task 1.c	Update GRESCSP planning documents as required by NMFS permit modifications, NWPPC program requirements, LSRCP and BPA contract provisions.

Objective 2.  Short-term, produce 360k endemic (conventional) smolt spring chinook, 120K each for Catherine Creek, upper Grande Ronde, and Lostine River.  Long term, produce 900k endemic smolt spring chinook for Catherine Creek, upper Grande Ronde, Lostine River, and Lookingglass Creek. (All tasks are short term)

Task 2.a	The broodstock goal is 100 adults each from Lostine River, upper Grande Ronde, and Catherine Creek.  Broodstock is collected at each tributary from May through September according to ESA Section 10 permits on adult sliding scales and co-management agreements.  Fish are transferred to Lookingglass for holding and spawning.

Formalin or Hydrogen peroxide treatments will be administered three to five days per week beginning in June under prescription protocols developed and implemented by ODFW personnel.

Task 2.b	Spawning will be conducted at Lookingglass Hatchery August through September.  A spawning matrix will be utilized whenever possible.  Only naturally produced (unmarked) fish will be used.  Captive Brood F1 adults will not be used for broodstock, but released to spawn naturally.  Approximately 176,000 green eggs are collected and transferred to either Irrigon or Oxbow hatcheries.

After adult fish are spawned, the progeny are reared under funding agreements with the USFWS (LSRCP).

Objective 3.  Assist LSRCP Fish Health Pathologist to monitor fish health at all stages in the Grande Ronde Endemic Spring Chinook Supplementation Program.

Task 3.a	Monitor adult mortalities and spawned adults for presence of viral, bacterial, fungal, and parasitic agents.

Task 3.b	Conduct monthly monitoring of hatchery reared juveniles to assess presence of viral, bacterial, fungal, and parasitic agents.

Task 3.c	Conduct examinations at all life stages when unusual loss occurs to determine cause of loss and recommend preventative and therapeutic treatment.

Objective 4.  Assist ongoing LSRCP M&E to evaluate the success of the Grande Ronde Endemic Spring Chinook Supplementation Program.

Task 4.a	Compare performance of natural, conventional hatchery, and captive broodstock components of the program by comparisons of progeny-to-parent ratios, survival rates among life stages, and survival to mainstem dams.

Task 4.b	Utilize data collected from other projects (e.g. Early Life History Study) for evaluations of program success.

Task 4.c	Conduct multiple spawning surveys in supplemented and non-supplemented streams in the basin to evaluate: effects of the program on spawner distribution, survival, and behavior; contribution of hatchery adults to spawning; and, progeny-to-parent ratios.

Task 4.d	Monitor genetic and life history characteristics of supplemented and non-supplemented populations in the basin and hatchery and natural chinook in supplemented sub-basins.

g. Facilities and equipment

The LSRCP facilities and equipment are essential to the endemic implementation programs.  The BPA endemic implementation proposal would not be functional without the LSRCP capital investments.  The NEOH planning efforts address short falls and capital investments in Northeast Oregon.

### LSRCP-Lookingglass Hatchery

The main water source for Lookingglass Hatchery is Lookingglass Creek (50 CFS water right).  Water temperatures fluctuate daily and seasonally with mean temperatures ranging between 34 o and 61oF.  Additional water source include 2 wells that are capable of pumping 5 CFS of 58oF.

The Lookingglass Hatchery consists of one Hatchery building complex (11,588 ft.2) that includes an office, spawning room, incubation, rearing, cold storage, shop, lab, visitor center and dormitory.  Support buildings include:  one storage (2,240 ft.2), one intake  (1,920 ft.2), three residence of equal size (1,500 ft.2), one BPA/endemic (adult holding) (3,710 ft.2), one generator (792 ft.2), one CTUIR/BPA storage (502 ft.2), and one pump station (261 ft.2).

Outside rearing containers include 18 raceways with rearing volume 3500 ft.3 (10’x100’x3.5’), 2 adult holding raceways 6,400 ft.3 (20’x80’x4’), three adult circular holding tanks 942 ft.3 (20’x3’).  Inside rearing containers include 32 troughs and 288 incubation trays in 36 stacks.

LSRCP-Essential equipment includes:

3-vechiles (1994 ¾ ton 4 X 4, 1995, ½ ton 4 X 4, 1997 1-ton 4 X 4 Club Cab Pickup)

1-Electric Fish Pump

1-John Deere Tractor with Snow Blower

1-Hyster Forklift 6000 lb. capacity

2-walk behind snow blowers

1-Caterpillar Road Grader

1-1986 Chevy Dump truck (5 yd.)

1-John Deere 310B Backhoe

2 trailers-20 ft low Boy equipment trailer and snowmobile

2-pressure washers, electric

13-radios (base station, vehicles, hand held)

3-computers (1 laptop), monitors, printers, scanner

1-egg counter

Misc. Fish culture equipment

2-portable generators 15 kW

4-portable trash pumps

Misc. shop tools

1-Snowmobile

2-65 ton chiller (170gpm of 43F)

1-15 ton chiller  (30gpm of 40F)

1-Heat Exchanger Unit

8-pumps (~20 hp)

1-walk in freezer

3-200 hp electric pumps

1-right angle drive unit

1-450hp-diesel turbo charged engine

1-180KW backup generator

1-50 kW backup electric generator

### Fish Liberations and Administration

### Essential Equipment includes:

BPA

Ford F-450 1 ½ ton flatbed

550-gallon transfer tank

250-gallon portable transfer tank

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| CRITFC (Columbia River Intertribal Fish Commission). 1996. Wy-Kan-Ush-Mi Wa-Kish-Wit: Spirit of the Salmon. The Columbia River anadromous fish restoration plan of the Nez Perce, Umatilla, Warm Springs, and Yakama Tribes. Vols. I and II. Portland, Oregon | N |
| Currens, K., J. Lannan, B. Riddell, D. Tave, and C. Wood. 1996. Responses of the independent scientific panel to questions about the interpretation of genetic data for spring chinook salmon in the Grande Ronde basin. US v. OR Dispute Resolution, 1996 | N |
| Groberg, W. J., S. T. Onjukka, K. A. Brown, and R. A. Holt. 1999. A Report of Infectious Disease Epidemiology among Spring Chinook Salmon at Lookingglass Hatchery. Oregon Dept. of Fish and Wildlife, Fish Pathology. | N |
| Herrig, D. 1998. Lower Snake River Compensation Plan Background. Pages 14-19 in: Lower Snake River Compensation Plan Status Review Symposium. US Fish and Wildlife Service, Boise, Idaho. | N |
| Maynard, D.J., T.A. Flagg, and C.V.W. Mahnken (editors). 1996. Development of a natural rearing system to improve supplemental fish quality, 1991-1995. Report to Bonneville Power Administration, Contract DE-AI79-91BP20651, 231pp. | N |
| Montgomery Watson. 1999. Lookingglass Hatchery Review Final Report. BPA Report to Bonneville Power Administration, Project No. 88-053-01. Bellevue, WA. 64p. | N |
| Nehlsen, W.J., J.E. Williams, and J.A. Lichatowich. 1991. Pacific salmon at the crossroads: stocks at risk from California, Oregon, Idaho, and Washington. Fisheries 16(2):4-21. | N |
| National Marine Fishery Service 2000. Endangered Species Act – Section 7 Consultation. Draft Biological Opinion of the Federal Columbia River Power System Including the Juvenile Fish Transportation Program and the Bureau of Reclamations 31 Projects, Including the Entire Columbia Basin Project. | N |
| NMFS (National Marine Fisheries Service) 1997. Snake River Salmon Recovery Plan, August 8, 1997 Draft. National Marine Fisheries Service, Portland, Oregon. | N |
| NPPC (Northwest Power Planning Council) 1987. 1987 Columbia River Basin Fish and Wildlife Program. NPPC, Portland, Oregon. | N |
| NPPC (Northwest Power Planning Council) 1994. 1994 Columbia River Basin Fish and Wildlife Program. NPPC, Portland, Oregon. | N |
| ODFW (Oregon Department of Fish and Wildlife) 1996. Application For An Emergency Permit For Scientific Purposes And To Enhance The Propagation Or Survival Of Endangered Grande Ronde River Basin Spring Chinook Salmon Under The ESA. ODFW, Portland, Oregon. | N |
| ODFW (Oregon Department of Fish and Wildlife) 1998a. Application For A Permit For Scientific Research And To Enhance The Propagation Or Survival Of Endangered Imnaha River Chinook Salmon Under The Endangered Species Act of 1973. ODFW, Portland, Oregon. | N |
| ODFW 1998b. Request For Modification Of Permit 1011 For Scientific Research And To Enhance The Propagation Or Survival Of Endangered Grande Ronde River Basin Spring Chinook Salmon Under The Endangered Species Act. ODFW, Portland, Oregon. | N |

# Section 10 of 10. Key personnel

Administration

Key Personnel:

Scott Patterson

### Northeast Oregon Hatchery Coordinator

107 20th Street

La Grande, Oregon 97850

(541) 963-2138

Scott.D.Patterson@state.or.us

Resume	Work History

2000- present	Northeast Hatchery Coordinator, Oregon Dept. of Fish and Wildlife. Plan and Coordinate operations of the Northeast Region hatcheries and regional fish liberation and distribution operations.  It is primarily responsible for coordinating the development of new fish production programs ad associated facilities with National Marine Fisheries Service, U.S. Fish and Wildlife Service, Bonneville Power Administration, the Confederated Tribes of the Umatilla Indian Reservation, and the Nez Perce Tribe.  Develop annual operating Plans to guide Northeast Region hatchery operation in consultation with these federal agencies and tribes.

1994 – 2000	Assistant Fish Hatchery Manager (Supt. 1), Clearwater Hatchery Idaho Dept. of Fish and Game. Trained, supervised, and developed work schedules of 25 employees to produce 3 million spring chinook, 1 million steelhead, and 250,000 rainbow trout.  Collected adult salmon and spawned fish.  Monitored egg development, fish growth, nutritional requirements, and fish health.  Supervise fish transport, record collections, data analysis.  Wrote reports.  Conducted nutritional and behavior experiments on steelhead trout.  Ensure inventory, equipment, capital improvements, and safety requirements.

1990-1994	Fish Hatchery Manager (Supt. 1), Sandpoint Hatchery, Idaho Dept. of Fish and Game

Project leader of small hatchery.  Developed and monitored budget.  Maintained records and wrote hatchery reports.  Ensure inventory, equipment, and capital improvements, and safety requirements.  Worked with threatened and sensitive bull trout and white sturgeon.  Developed and implemented fish culture techniques for spawning, embryo development, and fish rearing of bull trout.  Designed, constructed, and operated closed water system to incubate eggs and rear white sturgeon.  Designed and constructed  8 net pens to rear 80,000 westslope cutthroat trout in Lake Pend Oreille.  Liaison between IDFG and sportsman groups.

1989 – 1990 	Assistant Fish Hatchery Manager (Supt. 1), Cabinet Gorge Hatchery, Idaho Dept. of Fish and Game.  Supervised spawning operation of kokanee salmon (14 million eggs).  Trained 12-man work crew.  Summarized population dynamics of adult kokanee.  Developed and implemented rearing techniques of kokanee.  Monitored fish health and water quality.  Restored spawning gravel for kokanee and bull trout.

1987 – 1989 	Fish Culturist, Magic Valley Steelhead Hatchery, Idaho Dept. of Fish and Game

Developed and implemented growth program for 2 million steelhead.  Monitored fish behavior and water quality.  Ensured fish nutrition.  Maintained small motors and hatchery grounds.  Repaired fish pumps, water lines, feed silos, and fish feeders.

Winter 1987	Fishery Biologist, Foreign Fishery Observer, Oregon State University

Determined catch composition, catch rates, and species composition.

Summers 	Bio-Aide, Mackay Hatchery, Idaho Dept. of Fish and Game

1984, 85, 86	Assisted in daily fish culture duties.  Stocked salmonids statewide.  Maintained and repaired concrete raceways and hatchery grounds.

EDUCATION

1998		Master of Science, Fishery Resources, University of Idaho, Moscow, ID

1985		Bachelor of Science Fishery Resources, University of Idaho, Moscow, ID

### Lookingglass Hatchery

Lookingglass Hatchery staff consists of Hatchery Coordinator (2 months), Hatchery Manager 2, F&W Technician 2 (Assistant Manager), two F&W Technician 1, and seasonal positions including F&W Technician 2 (6 months), F&W Technician 1 (28 months), and Laborer (3 months).  Nineteen months of F&W Technician 1 is funded by the BPA proposal.

Key Personnel:

Robert Lund

### Lookingglass Hatchery Manager 2

76653 Lookingglass Road

Elgin, Oregon 97827

(541) 437-9723

blund@oregonvos.net

Resume	WORK HISTORY

1996-present	Lookingglass Hatchery Manager 2

Responsible for the successful operations of Lookingglass Hatchery.  Maintain cooperation with district, pathology, research, other department personnel, and tribal co-managers. Accurately develop and monitor the budget and expenditures.  Directly supervise 6.5 employees.  Provide training and development opportunities for all crew members.  Develop work plans and write performance evaluations.  Participate in planning and program reviews.

1985-1996	Lookingglass Hatchery Assistant Manager (F&W Tech 1 & 2).

Assist Manager with hatchery operations.

  - Administrator 2.

Design, organize and implement a centralized distribution system.  Prepare budgets.  Interview, appraise, promote, evaluate and terminate personnel.  Supervise complex multi-faceted distribution interface with finance, data system, personnel, schools, facility and construction departments.

EDUCATION

1984		AAS Fisheries, Peninsula College, Port Angeles, WA

1968		BS Economics/Urban studies, Portland State, Portland, OR

1972		MS Urban studies, Portland State, Portland, OR

Chris Lauman

### Lookingglass Hatchery Asst. Manager (F&W Tech 2)

76645 Lookingglass Road

Elgin, Oregon 97827

(541) 437-9723

clauman@oregonvos.net

Resume		WORK HISTORY

1998-present	Lookingglass Hatchery Assistant Manager (F&W Tech 2).  Assist Manager with hatchery operations.

# Bonneville Hatchery  (F&W Tech 1).

1990-1991	Lookingglass Hatchery, Laborer.

EDUCATION

High School, Imbler

Fish Pathology, NE Region, La Grande OR

Fish Pathology staff consists of Director of Fish Health (1 months), Fish Pathologist, Microbiologist, Seasonal Experimental Biologist.

Key Personnel:

Sam Onjukka

Fish Pathologist

Badgley Hall

La Grande, OR 97850

(541) 963-3823

Resume    	Work Experience

1999 – Present	Project Leader – Fish Pathologist, Oregon Department of Fish & Wildlife, La Grande, OR. Supervise and directs fish health activities at the fish pathology laboratory in La Grande.  Conducts routine health examinations and fish loss investigations to determine fish health problems and recommend appropriate action in the interest of prevention of future loss.  Monitors and evaluates the prevalence of fish pathogens in hatchery and natural populations in NE Oregon.  Assists agency and tribal fish biologists with management decisions that impact fish health of ESA listed stocks.

  - Microbiologist 1, Oregon Dept. Fish & Wildlife, La Grande, OR

1985-1987           Research Assistant, Department of Botany and Plant Pathology, Oregon state University,

Corvallis, OR.

5/82 - 9/85           Biological Technician, United States Environmental Protection Agency (Western Fish

Toxicology Station), Corvallis, OR

EDUCATION

# 1985	B.S., Microbiology, Oregon State University, Corvallis, OR

Glenda M. Claire

Microbiologist

Badgley Hall

La Grande, OR 97850

(541) 963-3823

# Resume    	Work Experience

1999 – Present 	Microbiologist, Oregon Dept. Fish & Wildlife, E.O.U., Badgley Hall, La Grande, OR.

1995 – 1999	Production Assistant, Nez Perce Tribe, Enterprise, OR

1995 – 1995	Bio-Aide, Idaho Dept. of Fish & Game, Jerome, ID

1994–1994	Bio-Aide, Idaho Dept. of Fish & Game, McCall, ID

1994–1995	Lab Technician, University of Idaho, Moscow, ID

1988–1989	Faculty Research Associate, Oregon State University, Corvallis, OR

# 1987–1989	Research Associate and Microbiologist, Basic American Foods, Blackfoot, ID

EDUCATION

1987		B.S., Microbiology, Oregon State University

Fisheries, University of Idaho

###### Fish Research

### Richard W. Carmichael

Fish Research Program leader

211 Inlow Hall, Eastern Oregon University

1411 L Avenue

La Grande, Oregon 97850

###### Fish Liberations, NE Region, La Grande OR

Fish Liberation staff consists of Liberations Coordinator (F&W Tech. 3), F&W Tech. 2, and Seasonal F&W Tech. 2 (12 months), and three months seasonal Equipment Operator 2 funded by BPA.

Key Personnel:

### Bob Becker

### Northeast Oregon Liberation Coordinator (F&W Tech. 3)

107 20th Street

La Grande, Oregon 97850

(541) 963-2138

Resume    	Work Experience

1984–Present	NE Region Liberation Coordinator (F&W Tech 3), La Grande OR.

1978-1984	F&W Tech 1, Wizard Falls, Camp Sherman, OR.

EDUCATION

- 1977		Fisheries Technology, Mt. Hood Community College, Gresham, OR.