BPA Project Number 27019

Adult Salmon Abundance Monitoring

##### Response to ISRP Preliminary Review

Nez Perce Tribe

Department of Fisheries Resources Management

P.O. Box 365

Lapwai, ID 83540

October 10, 2001

ISRP General Comments:

“This is a strong and innovative proposal that would establish quantitative annual monitoring of the spring chinook escapement to the Minam River.  The Minam River spring chinook population is the only Grande Ronde Subbasin stock listed as an index population in the recent NMFS Biological Opinion.  The proposal provides good background and technical justifications but there are several questions that the ISRP recommends a response”

Response to General Comments:

We thank the ISRP for their review and comment on this project proposal and commend their efforts. We agree with the ISRP that Project 27019 “is a strong and innovative proposal that would establish quantitative annual monitoring of the spring chinook escapement to the Minam River.” Furthermore, we believe the recent NMFS Biological Opinion makes clear the need for adult abundance monitoring in the Minam River.

Thus, this proposed project will provide a scientific basis for salmon conservation in the Minam River and will contribute to the assessment of recovery thresholds in an index stream (NMFS 2000).  The project will use technologies for abundance information that are recognized within the scientific community (Foose et al. 1995, Botkin et al. 2000) and are recommended by the NMFS Biological opinion (NMFS 2000).  Finally, quantifying adult salmon spawner abundance will provide direct, measurable benefits to the Northwest Power Planning Council’s Fish and Wildlife Program and to the region’s knowledge of its salmon resources.

Response to Specific Comments:

ISRP Comment No. 1– “Although the Minam River has been identified as an index site, 	the proposal provides no background on the trends in chinook in the Minam or the data available on this population.  Are you confident that the numbers warrant this major investment? Further, at the briefings, it was revealed that splash dam logging had occurred on the Minam, which generates the question whether the stock and habitat in the Minam is truly representative of other spring chinook populations?

Response to Comment No. 1 – As stated in the proposal, the spring chinook population in the Minam River has experienced a drastic decline in recent decades as have all other Snake River stocks. Figure 1 provides the population trend analysis from 1964 to 1998.

Figure 1. Minam River chinook salmon population trend

A long term data set of redd counts specific to the Minam River spring chinook population exists from 1949 to the present. These data are generated annually from the spawning ground surveys conducted by the Nez Perce Tribe and Oregon Department of Fish and Wildlife. Trend analysis of these historic data somberly depicts the decline alluded to in the proposal. Yet all Snake River stocks have experienced similar declines. Therefore, in light of the Biological Opinion (NMFS 2000) recommendation for an accurate count of escapement in the Minam River, the Minam’s designation as an index stock, and its similar decline to that of other Snake River populations, we are confident that an investment in adult monitoring is warranted.

The operation of a splash dam between Threemile Creek and Garwood Creek on the Minam River between 1918 and 1924 did alter the natural hydrologic features of the lower half of the river. Some obstructions were removed to facilitate the log drives.  However, unconstrained ecosystem processes have contributed to the recovery of the riparian areas and dynamic equilibrium of the river over the past 67 years (USFS 1994). Although the Minam River watershed is primarily within a federally designated wilderness area, it is similar to many wilderness watersheds in that parts of the drainage experienced timber harvest in historical times. Indeed, a truly non-impacted watershed in the Pacific Northwest would be difficult to find. Again, because the habitat and stock of the Minam River is representative of other populations, it is reasonable to monitor its adult population to establish abundance. The importance of monitoring abundance in the Minam River is highlighted by the fact that it is the only Grande Ronde Subbasin stock listed as an index population in the Biological Opinion (NMFS 2000). Therefore, we agree with the scientists of the Validation Monitoring Panel (Botkin et al. 2000) “… the cost of not monitoring is simply too high”.

ISRP Comment No. 2 (a) - What is the advantage of the 4 independent systems. Is the benefit of the third or fourth system worth the incremental cost and complexity?  On what basis was this design recommended?

Response to Comment No. 2 (a) - We are not proposing 4 independent systems. The one proposed system is a multiplexing operation between four transducers. It is a very sophisticated and complex system that Pacific Northwest National Laboratory (PNNL) has deployed on numerous occasions.  The software handles the complexity and makes 4 transducers seamless in the dataset.  In other words, we can process the data independently or together.  Past applications of hydroacoustics toward providing upstream migrant counts have relied on one sample site.  We have proposed, essentially, four transducers all at a site in reasonably close proximity to one another, thus four independent estimates of passage.  One splitbeam transducer will provide a valid estimate of daily passage so the average of four independent estimates should provide an even better estimate of daily abundance.

Secondly, since confidence intervals (CI) are a function of the reciprocal of the square root of n, four transducers (independent sites) would decrease the CI by a factor of 0.50; 3 transducers would decrease the CI by 0.42; and finally, 2 transducers would decrease the CI by 0.29.  Thus, the basis of the sampling design is to derive a better estimate of passage through the mean of four independent counts with as tight a CI as practical.  The incremental cost of the hardware would be 38%; 25%; and, 13%, respectively.  The cost of processing and analysis would not change.

ISRP Comment No. 2 (b)  - What validation procedure would be implemented for both the number of chinook estimated and the species composition of the fish counted?

Response to Comment No. 2 (b) - Since this is a new proposal, part of project development will be the identification of an appropriate validation method. Based on preliminary assessment, we anticipate using videography for species composition.  However, during the high water runoff period hydroacoustics will be the only sampling method.  This is one of the reasons for the quad multiplexing system.  This type of system would provide four independent abundance estimates with much tighter confidence limits and allow for up and downstream movement detections.  When the video system is installed it will give composition information. Therefore, video can validate hydroacoustics results.  All large hydroacoustics fish targets would be classified as chinook salmon, as chinook salmon are the only salmon in the Minam River.  Only large bull trout could be mistaken for jack chinook salmon by hyroacoustics.  We believe the bull trout spawning migration begins after water levels have dropped and a video system can be operational.  At that time, video would provide the species composition for hydroacoustics estimates.

ISRP Comment No. 2 (c)  - It is not evident in the proposal that the NPT has the technical/hydroacoustic expertise in their staff.  These instruments require constant attention and refinement. Does the NPT anticipate recruiting these staff or are they included in this proposal?

Response to Comment No. 2 (c) - As stated in the proposal, the Nez Perce Tribe will enlist the design and engineering expertise of the Pacific Northwest National Laboratory (PNNL). For more than 30 years, scientists at the laboratory have studied the life cycle of Pacific salmon and the factors that affect their survival. They have developed new or refined existing technologies as solutions to salmon monitoring problems. PNNL has experience implementing hydroacoustic monitoring systems, Vaki fish and resistivity counters. They were instrumental in designing video and image-processing technology to monitor adult salmon passage for the Bonneville Power Administration. As contractor, the PNNL will bring the same extensive expertise to the Minam River Adult Abundance Monitoring project.

PNNL hydroacoustic expertise is a valuable asset to this project.  PNNL is the largest single purveyor of hydroacoustic expertise on the Columbia and Snake River drainages at the current time. PNNL has a staff of hydroacoustic experts that have combined experience of well over 100 years.  PNNL currently has the lead in riverine acoustics in the Pacific Northwest above all other groups or agencies.  PNNL will provide the training and expertise to members of NPT as needed.  Initially, the systems will require “on the ground” attention and monitoring. But once the systems are proven to provide the desired results most all control can be transferred to wireless communications from remote sites.  A list of PNNL team members and potential subcontractors for hydroacoustic projects accompanies this response (please see Attachment 1). Finally, in Section 8 of Part 1(Administration and Budgeting), we list $125,000 for salaries and fringe benefits in which to recruit and support appropriate NPT hydroacoustic staff.

ISRP Comment No. 3 – “The table on page 5, Section 9 provides a nice summary of methods but generates the question about what determined the recommendation to use hydroacoustics.  For example, the resistivity systems would be less difficult to use but maybe limited by the anticipated flow regimes.  Further justification for the recommended system is desirable.”

Response to Comment No. 3 – Each technology listed in the referred table has its own set of physical site and instream criteria for installation and operation.  Considerations for site location are site geology, road access during operation and construction, access to electricity, property ownership, etc.  In addition, numerous scientific literature exists identifying the type of instream characteristics required for installation of these preferred technologies.  Ransom et al. (1999) specify characteristics necessary for successful monitoring via hydroacoustic technology. A selected sampling site should have relatively laminar flow, an acoustically “soft” substrate (sand to small cobble), and a gently sloping bottom with a triangular cross section.

As stated in the proposal, after consultation with PNNL and a preliminary site visit, hydroacoustics showed the most promise for adult monitoring in the Minam River. Staff from PNNL reviewed the potential monitoring site and recommended hydroacoustics as the most desirable system. The typical late spring hydrograph of the Minam River would probably preclude a resistivity system. Also the Minam River is a listed as a “Wild and Scenic” River. Thus, a crump weir necessary for a resistivity system would not be appropriate given the designation of the river. We believe hydroacoustic technology would be the most benign method for the fish and for the nature of the river.  We also believe that prudent research dictates that passive, non-invasive methodologies be used to determine the abundance of populations facing extirpation.

Splitbeam hydroacoustics have been the tool of choice for non-invasive fisheries evaluations in the Columbia and Snake river drainages for over a decade (Daum and Osborne 1998; Ransom et al. 1999). Examples of successful monitoring with hydroacoustic technology are abundant in the literature. A partial list is included in this response (please see Attachment 2).

ISRP Comment No. 4 – “To apply the information on spawning escapements, the NPT will also need biological data on the returning adults.  What program will provide that or should that information be included in this proposal to ensure it is collected?”

Response to Comment No. 4 – The Minam River serves as a control stream for nearby supplemented populations. As such, surveys are conducted every year in the Minam River to obtain information from the returning adults. Objective 3 Task 3.8 on page 19 of this proposal states that NPT will continue to conduct spawning ground surveys in the Minam River with our co-manager the Oregon Department of Fish and Wildlife. As part of these surveys biological data are collected from recovered carcasses.

Additional Review Comments

ISRP Comment – “A final comment is that several organizations along the coast have implemented similar hydroacoustic systems, although experience in river systems is more limited than in lakes, etc.  The NPT may consider forming (or contracting) a technical advisory group to assist in software expertise, site preparation, etc.  The investment in this new program could be very worthwhile but the quality of the resulting data will be highly dependent on the site selected and the environmental conditions expected”.

Response to Comment - A technical hydroacoustic group already exists and PNNL is in communication with them.  Gene Ploskey (PNNL) attended a workshop on riverine acoustics last year and continues to be in touch with people from Alaska and British Columbia.  One ongoing project in British Columbia is on the Fraser River.  That project has informally (Mulligan, Department of Fisheries and Oceans, personnel communication) indicated they are confident in the accuracy of their fish counts (SD 10%, bias < 1%).  Projects in Alaska (Burwen, Alaska Department of Fish and Game, personal communication:  Daum, U. S. Fish and Wildlife, personal communication) using split-beam hydroacoustics are also confident in their accuracy.  Alaska Department of Fish and Game (ADFG) projects using Bendix and dual beam systems are in the process of converting to split-beam hydroacoustics due to their confidence in the increased accuracy.  Bob Johnson is also involved in the Shallow Water Fisheries Acoustics section of the International Council for the Exploration of the Sea (ICES).

ISRP Comment – “Confusion is evident in the outline of objectives and tasks as represented in the proposal’s budget sections. In Section 5, Budget for Construction/Implementation, Objective 2 and its Tasks a, b, and c are planning/design matters and belong in Sect. 4. An Objective 3, “Construct the apparatus” should be created in Section 5, and the former Task 2d should remain with it and be renumbered. Also, the out-year items in Section 7, Budget for M&E, should probably be moved to Section 6, as these are really operations. We realize that the whole project is in effect monitoring project, but in such a case, monitoring should be regarded as the operation, and only activities that evaluate the effectiveness of the monitoring operation should be classed as M&E.”

Response to Comment – We agree that Part I “Administration and Budgeting” can be confusing. We will make the recommended changes in Part I of the proposal. However, the total costs are accurate and necessary for project execution.

Attachment 1.

## PNNL Team Members for Hydroacoustic Projects

## PNNL Staff

| Name | Grade | Duty |
| --- | --- | --- |
| Steve Anglea | Research scientist | Project Lead/acoustics |
| Bob Johnson | Chief scientist | Team Leader/acoustics |
| Mary Ann Simmons | Research engineer | Data analyst |
| Craig McKinstry | Research scientist | Statistician |
| Joanne Duncan | Science/engrng assoc | Data processing |
| Susan Thorsten | Science/engrng assoc | Data management |
| Kris Hand | Science/engrng assoc | Data processing |
| Kenneth Ham | Senior research scientist | Data analyst/statistician |
| Carver Simmons | Senior research scientist | Physicist/scientist |
| Jake Tucker | Senior development engr I | Robotics/engineering |
| Chris Cook | Senior research scientist | Hydraulic engineering |
| John Serkowski | Research scientist | Animation |
| Pat Medvick | Senior research scientist | Data management/programmer |
| Tom Carlson | Chief scientist | Scientist/Innovator/acoustics |
| Gene Ploskey | Senior research scientist III | Project Leader/acoustics |
| Scott Titzler | Science/engrng assoc | Field technician |
| Bob Mueller | Senior science/engrng assoc | Field technician |
| Mickie Chamness | Science/engrng assoc | Data processing |
| Georganne O’Connor | Technical communication specialist | Technical Editor |
| Traci Degerman | Science/engrng assoc | Data processing/analysis |
| Rhett Zufelt | Science/engrng assoc | Data Processing/analysis |
| John Thomas | Chief scientist | Senior statistician |
| Mark Weiland | Senior research scientist I | Project Leader/acoustics |
| Derrek Faber | Research scientist I | Project Leader/sonic tracking |
| Dave Clark | Senior engineer | Engineering |
| Tim Schiebe | Senior scientist | Programmer/analyst |
| Marshall Richmond | Senior scientist | Senior hydrologist |

# Potential Subcontractors

| # Mike Macaulay # (Hydroacoustic Assessments) | # Senior research scientist | # Programmer/analyst |
| --- | --- | --- |
| Peter Johnson (MEVATEC) | Senior research scientist | Project Leader/acoustics |
| Carl Schilt (MEVATEC) | Research scientist | Physiologist/acoustics |
| Gary Johnson (BioAnalysts Inc.) | Chief scientist | Analyst/acoustics |
| James Dawson (BioSonics Inc.) | Senior scientist | Project Leader/acoustics |
| # George Keilman # (Sonic Concepts) | # Senior engineer | # Ultrasonic design engineer |
| # Jules Jaffe # (Scripps, UCSD) | # Chief scientist | # Oceanographer/acoustics |
| Jeff Condiotty (Simrad) | Senior research scientist | Vendor |
| Robert Asplin (Simrad/Mesotech) | Senior research scientist | Senior engineer/programmer |
| # John Skalski # (Skalski Statistical Services) | # Senior biometrician | # Senior biometrician |
| # Alan Wirtz # (PAS) | # Senior engineer | # Senior electronics engineer |
| John Hedgepeth (Tenera) | Senior scientist | Physicist/analyst |
| Ed Belcher (U of W) | Scientist/engineer | Acoustical engineer |

## Attachment 2:

## Hydroacoustics Applications

Bosch. D. and D. Burwen.  1999.  Estimates of Chinook salmon abundance in the Kenai River using split-beam sonar, 1997.  Alaska Dept. of Fish and Game, Fishery Data Series No. 99-3.

Burwen, D.L. and D.E. Bosch.  1996.  Estimates of Chinook salmon abundance in the Kenai River using split-beam sonar, 1995.   Alaska Dept. of Fish and Game, Fishery Data Series No. 96-9.

Burwen, D.L., D.E. Bosch and S.J. Fleischman.  Evaluation of hydroacoustic assessment techniques for Chinook salmon the Kenai River using split-beam sonar.  Alaska Dept. of Fish and Game, Fishery Data Series No. 95-45.

Daum, D.W. and B.M. Osborne.  1995.  Enumeration of Chandalar River fall chum salmon using split-beam sonar, 1994.  US Fish and Wildlife Service, Alaska Fish. Prog. Rpt. No. 95-4.

Daum, D.W. and B.M. Osborne.  1998.  Enumeration of Chandalar River chum salmon using split-beam sonar, 1997.  US Fish and Wildlife Service, Alaska Fish. Tech. Rpt. No. 47.

Daum, D.W. and B.M. Osborne.  1998.  Enumeration of Chandalar River fall chum salmon using split-beam sonar, 1998.  US Fish and Wildlife Service, Alaska Fish. Tech. Rpt. No. 50.

Ehrenberg, J.E. and S.V. Johnston. 1996.  Evaluation of the use of hydroacoustic pulse width data to separate fish by size group.  Report to Alaska Dept. of Fish and Game.

Environment Agency.  1997.  River Teifi hydroacoustic fish counter project progress report April-September 1997.  Environmental Appraisal Unit, Cardiff, Wales.

Enzenhofer, H.J. and G. Cronkite.  2000.  Fixed location hydroacoustic estimation of fish migration in the riverine environment:  an operational manual.  Canadian Tech. Rpt. Of Fish and Aquatic Sci. 2312).

Finnish Game and Fisheries Research Institute.  1999.  Hydroacoustic assessment of salmon in the River Tornionjoki.  European Union Study Project 96-069.

Gough, P. and J. Gregory. 1997.  The development of applications and validation methods for hydroacoustic salmonid counters.  Environment Agency, Environmental Appraisal Unit, Cardiff, Wales.

Gregory, J. and P. Clabburn.  1996.  Use of a hydroacoustic counter for accessing salmon stocks.  Annual progress report for period April 1995 to March 1996.  National Rivers Authority—Welsh Region.  Progress Rpt. 486/8/W.EAU Rpt. SE/EAU/96/3.

Gregory, J., P. Clabburn and L. Robinson.  1998.  The Use of a hydroacoustic counter for assessing salmonid stocks.  Environment Agency, Environmental Appraisal Unit, Cardiff, Wales.  R&D Tech. Rpt. W92.

Gregory, J., P. Clabburn, R. Davies, P. Gough and M. Good.  2000.  Operational guidelines for the commissioning, operation and validation of hydroacoustic fish counters.  Part One.  Overview of acoustic fish counting techniques.   Environment Agency, Environmental Appraisal Unit, Cardiff, Wales.  R&D Guidelines W2/037.

Hydroacoustic Technology, Inc.  1994.  Attributes of the ideal site for hydroacoustic counting of adult salmon in rivers.

Iverson, T.K.  1995.  Feasibility of using split-beam hydroacoustics to monitor adult Chinook salmon escapement in Deep Creek, Alaska.  HTI report to Alaska Dept. of Fish and Game.

Iverson, T.K.  1996.  Hydroacoustic evaluation of adult Chinook salmon in Deep Creek during 1996:  second year feasibility study.  HTI report to Alaska Dept. of Fish and Game.

Iverson, T.K.  1998.  Results of hydroacoustic monitoring in the Malad River Diversion Flumes in August, 1998.  Report by Hydroacoustic Technology, Inc. to Idaho Power Co., Boise, Idaho.

Iverson, T.K. 1997.  Feasibility of using hydroacoustics to estimate fish passage in the Malad River diversion flumes.  Report by Hydroacoustic Technology, Inc. to Idaho Power Co., Boise, Idaho.

Iverson, T.K., S.V. Johnston and T.W. Steig.  1996.  Feasibility of using split-beam hydroacoustics to count adult Atlantic salmon and sea trout in the River Avon.  HTI report to National Rivers Authority, England.

Johnston, S.V.  1993.  Feasibility of using hydroacoustics to enumerate adult steelhead trout in the Illinois River.  HTI report to Oregon Dept. of Fish and Wildlife.

Johnston, S.V. and B.H. Ransom.  1994.  Feasibility of using hydroacoustics to count adult Atlantic salmon in the River Spey.  HTI report to River Spey Fishery Board.

Johnston, S.V. and D. Daum.  1995.  Escapement estimation of Chandalar River chum salmon with split-beam techniques.  17th Northeast Pacific Pink and Chum Salmon Workshop, Bellingham, Wash.

Johnston, S.V. and J. Hopelain.  1990.  The application of dual-beam target tracking and Doppler-shifted echo processing to assess upstream salmonid migration in the Klamath River, California.  Rapp. P.-v Reun. Cons, int. Explor. Mer, 189:210-222.

Johnston, S.V. and T.W. Steig.  1995.  Evolution of fixed-location hydroacoustic techniques for monitoring upstream migrating adult salmonids (Oncorphynchus app.) in riverine environments.  ICES International Symposium on Fisheries and Plankton Acoustics, Aberdeen, Scotland.

Levy, D.A., P.A. Nealson and P., Cheng.  1991.  Fixed-aspect hydroacoustic estimation of Fraser River sockeye salmon abundance and distribution at Mission, B.C., in 1986.  Pacific Salmon Commission, Vancouver, B.C.

Locke, V., J. Gregory and P. Clabburn.  1998.  River Teifi hydroacoustic fish counter annual report, 1997.  Environment Agency, Environmental Appraisal Unit, Cardiff, Wales.  EASE/REP/98_8.

Nealson, P.A. and J. Gregory.  1999.  Hydroacoustic differentiation of adult Atlantic salmon and aquatic macrophytes in the River Wye, Wales.  2nd Int’l. Conf. On Shallow Water Fisheries Sonar, 1-9 Sept. 1999, Seattle, WA.

Nealson, P.A. and S.V. Johnston.  1995.  Feasibility of using hydroacoustics to count adult Atlantic salmon in the River Tornio.  HTI report to Finnish Game and Fish Research Institute.

Osborne, B.M. and D.W. Daum.  1997.  Enumeration of Chandalar River fall chum salmon using split-beam sonar, 1996.  US Fish and Wildlife Service, Alaska Fish. Tech. Rpt. No. 42.

Osborne, B.M. and D.W. Daum.  1997.  Estimation of Chandalar River fall chum salmon using split-beam sonar, 1996.  US Fish and Wildlife Service, Region 7, Fairbanks, Alaska.

Ransom, B.H., S.V. Johnston and T.W. Steig.  1998.  Review on monitoring adult salmonid (Oncorhynchus and Salmo spp.) escapement using fixed-location splitbeam hydroacoustics.  Fisheries Research (35) 33-42).

Ransom, B.H., S.V. Johnston, T.C. Torkelson and T.W. Steig, 1996.  Improved split-beam hydroacoustic techniques.  Int’l Workshop on Shallow Water Fisheries Sonar, 16-18 June 1996, Egham, England.

Ranson, B.H., S.V. Johnston and T.W. Steig.  1999.  Summary of the use of hydroacoustics for quantifying the escapement of adult salmonids (Oncorhynchus and Salmo spp.) in rivers.  2nd Int’l Conf. On Shallow Water Fisheries Sonar, 1-9 Sept. 1999, Seattle, Wash.

Romakkaniemi, A., T. Marjomaki and J. Jurvelius.  1998.  Hydroacoustic estimation of salmon (Salmo salar) spawning run in the Tornion River – project results 1995-1996.  Finnish Game and Fisheries Research Institute.

Skalski, J.R., A. Hoffmann, B.H. Ransom and T.W. Steig.  1993.  Fixed-location hydroacoustic monitoring designs for estimating fish passage using stratified random and systematic sampling.  Can. J. Fish. Aquat. Sci. 50:  1208-1221.

Steig, T.W. and T.K. Iverson.  1995.  Feasibility of using split-beam hydroacoustics to count adult Atlantic salmon and sea trout in the River Tavy.  HTI report to National Rivers Authority, England.

Steig, T.W. and T.K. Iverson.  1996.  Feasibility of using split-beam hydroacoustics to count adult Atlantic salmon and sea trout in the River Torridge.  HTI report to National Rivers Authority, England.

Xie, Y., G. Cronkite and T.J. Mulligan.  1997.  A split beam echosounder perspective on migratory salmon in the Fraser River:  a progress report on the splitbeam experiment at Mission, B.C., in 1995.  Pacific Salmon Commission, Vancouver, B.C.