# Bonneville Power Administration

# FY 2002 Innovative Project Proposal Form

# PART 2 of 2. Narrative

Proposal No:	34031

Title:	Biological and Economic Feasibility of Reintroducing Fishwheels to the Columbia River System

# Section 3. Project description

Provide project detail for headings a through g.

a. Abstract

A collaborative project involving tribal fishermen, fisheries scientists, an engineer, and a natural resource economist is proposed to study the feasibility of reintroducing fishwheels as a viable means of harvesting salmon and other migratory fish species in the Columbia River Basin.  This proposal is based on the premise that salmon harvest techniques and strategies that facilitate selective and terminal fisheries, and at the same time provide unambiguous cultural, economic, and ecological benefits, are desirable and should be implemented.  Preliminary research by the project team has indicated that fishwheels would provide such benefits. The advantages of fishwheels over other harvest techniques include location, efficiency, and greater control over the composition, timing, and magnitude of salmon runs.  These attributes translate into increased incomes for fishermen  (Jaeger 1997) and would make it easier to protect and restore listed stocks of salmon and steelhead.

In the context of Columbia River fisheries, fishwheels represent an “innovative” harvesting technique in the sense that they are no longer employed on the river; yet hold great promise as selective and terminal fishing gear.  From the late 1800’s to the mid-1930’s, fishwheels were a common sight on lower reaches of the Columbia River (Donaldson and Cramer 1971).  According to Craig and Hacker (1940), each fishwheel caught between 40,000 and 100,000 pounds of Columbia River salmon (annual average, 1889-1992).   One fishwheel alone harvested was reported to have caught 6,400 adult salmon in a single day.  A casualty of political wrangling in the 1920’s and ‘30’s, fishwheels were eliminated first on the Oregon side and then on the Washington side of the Columbia River, and were replaced by boat-based fisheries.

Fishwheels have enjoyed a revival of late, especially among aboriginal fishermen; they are currently employed on the Fraser, Nass, and Yukon River systems.  This project will draw directly on the experience and expertise of individuals familiar with fishwheel technology and use in British Columbia rivers.

A key question is whether fishwheels can be successfully constructed and operated under the current regulatory and economic constraints that govern Columbia River fisheries.  In addition to addressing this question, the proposed research will determine the number and type of fish that can be harvested, the potential for releasing fish unharmed, and conditions under which fishwheels can be reliably fished.  Only one fishwheel will be constructed, so it will not be possible to statistically test for differences based on a multi-treatment experimental design.  It should nevertheless be possible to identify environmental factors that correlate with the number and type of fish caught in the fishwheel.  By identifying variables that appear to affect fishing success, this study would provide critical information that could be used in a more rigorous experimental design in the future.

The study is purposefully designed to cost-effectively address these and other critical uncertainties as a precursor to implementing fishwheel technology at a larger scale or elsewhere in the Columbia River system.  The project would proceed in three phases over an eighteen-month period.  In Phase I, contemporary and historical fishwheel technology and use would be reviewed through literature review and professional contacts.  The project technician and engineer would use this information to design an improved fishwheel, which would then be fabricated according to specifications.  In Phase II, the fishwheel would be deployed and tested in the field under representative environmental conditions; data would be collected on the number and type of fish caught in the fishwheel and the conditions under which they were caught.  If feasible, a limited number of adult salmon would be tagged, released, and resampled in upriver fisheries, dams, and spawning ground surveys.  Phase III would comprise a detailed assessment of the biological, economic, and fisheries management consequences of employing fishwheels to sample and commercially harvest Columbia River fish.

An added benefit of the study will be the involvement of the Cowlitz Indian Tribe, which in December 2001 was formally recognized by the federal government as a sovereign tribe, and the Friends of the Cowlitz, a local, 200+ member sport fishing organization.  The Cowlitz Indian Tribe does not as yet have the capacity to commercially fish in its traditional fishing area, including the lower Columbia River, the Cowlitz River, Lewis River, and several smaller tributaries in southwest Washington State.  This project, which has been strongly endorsed by the Cowlitz tribal chairman John Barnett, is intended to empower the Tribe to help manage and participate in fisheries sustainably by consulting it on where and when to fish, and by employing tribal members to operate the fishwheel and assist in data collection.  The Friends of the Cowlitz (Dave Becker, personal communication) has also volunteered its assistance in setting up and helping to monitor the fishwheel.  It is hoped that by establishing a close working relationship between the Tribe, FOC and other local stakeholders, future collaboration would be fostered and conflicts avoided between these sectors.

Due to the time required to design, build, and test the fishwheel, this study is scheduled to last 18 months.   Deliverables include a final report and a peer-reviewed publication on the economic and biological benefits of reintroducing fishwheels into the Columbia River system.  The results would be used to prepare a detailed scope of work, if warranted, for a full-scale implementation project in the future.

b. Technical and/or scientific background

There is strong support among fisheries professionals for terminal and stock-specific fisheries that utilize selective harvest methods and reduce the current emphasis on mixed-stock fisheries (Sustainable Fisheries Foundation 1996, NMFS 2000).  A recent bioeconomic study by one of the project team (Jaeger) has demonstrated that the reintroduction of the fishwheel into large salmon-bearing rivers of the Pacific Northwest provides a unique opportunity not only to improve salmon management, but also to lower economic costs, raise efficiency, and catalyze an industry-wide transition from an overcapitalized, unsustainable boat fishery to one that is sustainable (Jaeger 1997).

In appearance and operation, fishwheels resemble the steam-driven “paddle wheels” that powered the sternwheelers that once plied our nation’s rivers.  Project member Barry Manuck, who has built and operated fishwheels on the Fraser River, describes their operation thusly:

“The fishwheel is towed into position by a boat or with a shore-based winch and then secured in the fishing position. The ramp and lead net system is used to direct fish towards the fish wheel.  A fishwheel only scoops an area 15 feet wide by 10 feet deep, so ramp and lead nets make it possible to fish a much larger area; we’ve used ramp and lead nets to fish an area 150 feet wide by 60 feet deep.  Once the fish come up the lead nets they are scooped up by the fishwheel baskets.  When the fish are picked up by the baskets they slide down a chute into the live tanks.”

- Project member Barry Manuck (personal communication)

Fish caught in this way can be harvested or released unharmed.

Jaeger (1997) demonstrated several important economic and management advantages to using fishwheels over current methods of commercially harvesting salmon.  With the additional constraints imposed by the Endangered Species Act, the advantages of selective, live-capture methods of harvest are all the more apparent.  If used extensively, fishwheels would reduce harvest costs, thereby raising incomes and profits of commercial harvesters by very substantial amounts.  Fisheries managers would be able to exert greater control over the composition of the catches, the timing of harvest, and the number of fish that eventually spawn (Link and English 1996, Link 1999, Link and Nass 1999).  Hatchery stocks could be selectively targeted, wild fish more easily protected, and harvest more equitably allocated among commercial, tribal, and sport harvesters.

The potential magnitude of these benefits is evident from the following example:  in Washington State, if one-half of the fish currently harvested in gill net and purse seine fisheries were instead caught in fishwheels, it is estimated that harvesters would realize, on average, a five-fold increase in income, there would be no reduction in fishing-related employment, and depressed salmon stocks would double or triple in abundance in as little as 10 years (Jaeger 1997).

Fishwheels have utility beyond commercial fishing and avoiding take of listed fish species.  They can be modified to fish facing either up- or downstream, and equipped with different mesh sizes to selectively sample different species and life stages of fish.  One of the questions this research will address is whether the fishwheel is effective at capturing non-salmonid species (e.g., shad, smelt, and lamprey) and downstream migrating salmonids (e.g., smolts and kelts).  When equipped with gas-powered motors, fishwheels can fish in locations with little or no current. Moreover, fishwheels can be combined with ramp and lead net systems and weirs to capture up to 100 percent of migratory fish.

Information obtained from fishwheel catches can be used to calculate daily inseason estimates and annual, postseason escapement estimates and biological data on all species of salmon.  These data can be used adjust the location, timing, and quantity of harvest to reduce impacts on listed and other non-target species and to increase the catch of target species. The highly controlled nature of this harvest method (relative to most commercial fisheries in terms of time, area, gear, and quantity limits) makes it very easy to continually monitor and adapt in response to new information – an ideal adaptive management tool (Link and English 2000).

Clearly, fishwheel technology represents a “win-win” opportunity where management and economic goals can be promoted simultaneously.  Nevertheless, there are several obstacles that would need to be overcome if fishwheels are to be successfully reintroduced.  To gain acceptance, the analysis by Jaeger (1997) will need to be extended and the findings of this study extrapolated to other geographical areas, to other species of salmon, and other management regimes.  It is unclear, for example, how the application and benefits of fishwheel-based harvest methods might vary among systems as a function of river size, the number and type of fish available for harvest, harvesting restrictions imposed to protect listed or weak stocks, number and composition of commercial and sport fisherman, etc.  A feasibility study needs to be done to determine the extent to which fishwheels can be used elsewhere in the Columbia and in other drainages of the Pacific Northwest.

c. Rationale and significance to Regional Programs

The 2000 Federal Columbia River Power System (FCRPS) NMFS Biological Opinion calls for the development of selective/terminal fisheries gear and management strategies to reduce harvest-related impacts on ESA-listed stocks and to increase their escapement to spawning grounds.  Development and implementation of fishwheels and other selective harvesting techniques could potentially (1) reduce take of listed ESU's; and (2) enable harvest of abundant stocks where there is surplus production.

The ability to separate populations in fisheries and to selectively release individuals with minimal injury or stress is critically important when managers wish to minimize harvest impacts on specific populations (National Resource Council 1996; Northwest Power Planning Council).  Fishwheels and other live capture techniques, coupled with a marking program, provide a potential means of differentiating and selectively harvesting populations. Recent trials suggest that live capture gears and methods can reduce short-term, post-release mortality of incidentally caught adult salmon by an order of magnitude (from 60 percent to as low as 5 percent; DFO 2001, p. 5).

Fishery managers are planning to reintroduce anadromous salmonids habitat above currently impassable dams on several Columbia River tributaries, including the Cowlitz and Lewis Rivers. Most of these systems have hatcheries in their downstream reaches.  If listed stocks are going to be reintroduced and augmented in systems containing hatcheries and dams, selective harvest methods must be employed. Fishwheels would enable commercial harvest and broodstock collection of hatchery fish, while allowing natural-origin fish to be passed upriver.

Conducting subbasin- or river-specific analyses to determine the scope and magnitude of benefits gained through the use of fishwheels will be important for several reasons.  First, we need a better understanding of their effectiveness under a range of existing conditions.  Second, skeptics are unlikely to be convinced by an analysis (such as Jaeger’s) that is not linked to a specific river system or fishery.  And third, it is critical to be able to identify river systems and areas possessing suitable hydraulic characteristics where a demonstration project could be expected to be successful.  Hasty reintroduction of fishwheels in the wrong location or without consideration of their social and economic consequences could have disastrous effects on the support of further efforts.

This initiative addresses the Fish and Wildlife Program’s call for “innovative” and “experimental” approaches to fisheries management.  Our project would illustrate the type of creative problem solving, experimentation, learning, and cooperation possible at a small scale, with the potential for transferring information outward and upward to other stakeholders throughout the Columbia River system.  If successful, fishwheels would provide strong incentives for collaboration and trust between stakeholders that have traditionally opposed one another.  However, unless fishwheels are carefully tested, evaluated, and ultimately supported by regional fisheries managers and agencies, their potential benefits will remain unrealized.

d. Relationships to other projects

To the best of our knowledge, this project will not interfere with other research projects or management actions, either ongoing or proposed, in the Columbia River system.  Although salmon will be returned unharmed to the river, the operation of the fishwheel will result in the temporary collection and handling of adult salmon, including individuals from listed ESUs originating in the Columbia River basin.  The impacts of collection and handling, while expected to be negligible, will require that scientific collection and hydraulic project approval permits be obtained from Washington State Department of Fisheries and the National Marine Fisheries Service.  We will work with agencies and interested parties to ensure that this project is in compliance with all environmental regulations and does not adversely affect the activities or livelihood of other parties.

e. Proposal objectives, tasks and methods

Objectives

The goal of this project is to determine the feasibility of reintroducing fishwheels to the Columbia River system by implementing a small-scale field study designed to evaluate fishwheel technology and associated biological and economic benefits.  We envision a three-stage process that will take 18 months to complete.  If this pilot project concludes that fishwheels might be effectively employed in other areas, funding for further deployment testing of the concept will be sought through the Provincial Review funding process.

Tasks and Methods

Phase I Objective:  Fishwheel research, design, and construction.

The objective of Phase I, which will last approximately six months, will be to evaluate existing fishwheel technology, and based on this evaluation, to design and construct a full-size fishwheel suitable for deployment in the lower Columbia River or one of its major tributaries.

Task 1.1.  Literature review and interviews

Phase I will commence with a literature review and professional consultations with agency, tribal and other knowledgeable individuals to identify the most appropriate design and materials to use in constructing a fishwheel.  A field trip will be taken to the lower Fraser River to enable project staff to view firsthand several fishwheels in operation.  These projects have collectively demonstrated that fishwheels can be successfully integrated into a fisheries management system to the benefit of both the fish and local stakeholders.

Task 1.2.  River and site selection

The river and site(s) where the fishwheel is to be deployed will be selected on the basis of local flow and channel characteristics, fish runs, and availability of suitable access/anchor points.  The Cowlitz and Lewis Rivers have been tentatively selected due to their accessibility and run composition.  The participation and perspective of the Cowlitz Indian Tribe and local stakeholders (e.g., Friends of the Cowlitz) will be sought and their cooperation in the pilot project encouraged. Based on project selection criteria, a one or more sites will be chosen to serve as a demonstration project.

Task 1.3.  Fishwheel Design

Project team member Barry Manuck, who has extensive experience designing and operating fishwheels in British Columbia, will work with a structural engineer/fabricator to review and design a fishwheel suitable for this project.  The design will be adapted as needed to conditions in the Columbia River or tributary site selected.  Design drawings will be submitted for review by other individuals (e.g., Michael Link of LGL, Ltd) who have experience in fishwheel technology.  Once built, the unit will be transportable and capable of further modification.

The initial design will be based on existing fishwheels currently in use on the Fraser River.  The basic design includes foam-filled aluminum pontoons that ensure that the wheel will not sink.  The frame is constructed of neutral color-painted aluminum.  There are four baskets of knotless webbing that scoop fish and deposit them into a live tank.  The baskets A stable work deck (optionally covered) capable of supporting the crew and observer surrounds the live tank. If needed, the fishwheel will be equipped with a variable speed power assist run by a 60 horse power gas engine, rubber mounted to reduce vibration, at a 285 to 1 reduction gear, equipped with a hydraulic selector valve that enables control of the speed of the wheel.

Task 1.4.  Fishwheel Construction

The fishwheel and trailer will be fabricated under Mr. Manuck’s direct supervision, assembled and tested onsite, then disassembled and transported to the project location.  An experienced fabricator (Screaming Eagle Boat Works of British Columbia) will be employed to construct the fishwheel.

Phase II Objective:  Fishwheel deployment, operation, and evaluation.

The second phase of the project will involve the installation, operation, and testing of a fishwheel in one or more river systems in southwest Washington (most likely the lower Columbia, Cowlitz River, and/or Lewis River).  The fishwheel will be operated at multiple sites over a 6-month period to evaluate their effectiveness under a range of environmental conditions.  Fish, environmental, and economic data will be collected when the fishwheel is in use.  Operation of the fishwheel and the collection of data will be overseen by experienced technicians and fisheries biologists. These data will be used to conduct the biological analyses and recalibrate the economic model developed in Phase III of the study.

Task 2.1. Develop objectives, methods, and sampling protocols.

Identify research objectives, sampling design, and data collection and analytical protocols based on operational and regulatory constraints and local environmental conditions (time, location, flow, etc.) to be evaluated.  Select test sites.  Develop a work plan and secure the necessary permits for operating the fishwheel and obtaining the requisite data.

Task 2.2.  Deploy fishwheel and collect data.

The fishwheel will be deployed at multiple sites under a range of environmental conditions (flow, channel width and depth, habitat type, etc.) in order to evaluate its efficacy.  The boat used to tow and secure the fishwheel in place will be kept on hand to transport people and materials, and to ensure the safety of the crew.

Fish captured by the fishwheel will be kept alive and released unharmed within one hour of capture.  If the density of fish in the live tanks becomes unacceptably high, a brake will be used to immediately stop the wheel.  The fish that are captured in the live tanks will be sampled (e.g., for species, sex, health, scales, length, weight, DNA) and released back into the river.  Environmental data, to include flow rate, temperature, light levels, and water clarity, will be collected concurrently.  The exact biological and physical data to be collected will be determined in consultation with state and federal agencies, and will likely vary between listed and non-listed, and salmonid and non-salmonid species.  Any fish removed from the live tanks will be dipped out with knotless webbing dip nets.

As currently conceived, sampling will target hatchery fall chinook and coho salmon runs in the Cowlitz River and, possibly, hatchery spring chinook runs in the Lewis River.  The fishwheel will be in operation from May to November, with a minimum of 14 days devoted to each site/fish species.  Depending on the availability of hatchery fish, it may be possible to tag and release fish that return to the hatchery downstream of the fishwheel in order to estimate its efficiency under different operating conditions.

Task 2.3.  Collect economic data

The number of hours fished and the number of fish caught will be used to estimate catch per unit effort data will gathered measured from the fishwheel program.  A market analysis will be used to estimate the value of the catch and compare this with catch per unit effort data in the Columbia River gill net fishery.

Phase III Objective:  Data analysis and reporting.

Task 3.1.  Biological Analysis

Describe and analyze the fish and environmental data and efficacy of the sampling gear.  Describe relative abundance, size, general health of each species caught. Correlate catch and catch efficiency with environmental data.  Calculate catch per unit effort for use in the economic analysis. Recommendations will be made to improve the fishwheel technology.

Information on the live-released by-catch in one year can be used to continually adapt the harvest location, timing, quantity, and technology to lower by-catch of non-target species and to improve catch of target species. The highly controlled nature of this harvest (more controlled than most commercial fisheries in time, area, gear, and quantity limits) makes it very easy to monitor and to alter in response to information, an ideal adaptive management tool. In addition, because the license was "experimental," it was connected to detailed reporting and was very sensitive to what was learned.

Task 3.2.  Economic Analysis.

Evaluate the costs and benefits of reintroducing fishwheels as selective, terminal harvesting and sampling gear.  The dynamic simulation model used by Jaeger (1997) would be recalibrated and extended to determine whether fishwheels, given carefully stated assumptions and constraints, might reduce costs and increase net economic benefits to fishers and local communities.

Task 3.3.  Reporting.

Verbally communicate findings of the study to policy makers, fishers, community members, and other interested parties.  Provide opportunity for feedback and further collaboration with stakeholders.

After completing our analysis and receiving public comment, we will publish the results of our study in both a final report and a peer-reviewed publication. The final report will be circulated for public and agency comment, and will summarize all relevant data and analyses, provide a detailed assessment of fisheries benefits, and make recommendations to guide further implementation of fishwheel technology.  The results will be used to develop an implementation scope of work for further research and implementation of fishwheel technology in the Columbia River basin.

f. Facilities and equipment

The primary facilities and equipment needed for this study are identified below (note: 1 = leased; 2 = purchased):

- Pickup truck (1)

- Motorhome for field crew (1)

- Boat and motor (1)

- Boat motor (1)

- Boat trailer (1)

- Fishwheel (2)

- Fishwheel trailer (2)

- Ramp and lead nets, stanchions (2)

- Laptop computer (1)

A photograph of the Fraser River fishwheel fabricated by Mr. Manuck (team member) is presented in Photo #1.

Photo #1.  Frontal view of Fraser River fishwheel designed, built, and operated by Barry Manuck (project team member).

#### Work Schedule

Phase I of the project would begin as soon as possible.  Field trips to view fishwheels in British Columbia and visits to potential lower Columbia River sites would occur in early fall (assuming October start date).  Permit approvals would be sought and presentations and discussions held with interest groups in the summer and fall. Quantitative assessments and recommendations would be published in draft and final interim reports.

Phase II would extend from May through November. We anticipate a minumum of 14 successful days of fishing per run (spring chinook, coho, fall chinook).

Phase III would overlap with Phase II, and would be completed by March 2004.

g. References

Donaldson, I. J., and F. K. Cramer. 1971. Fishwheels of the Columbia. Binfords and Mort. Portland, Oregon.

Craig, J. A. and R. L. Hacker. 1940. The history and development of the fisheries of the Columbia River. Bulletin of the Bureau of Fisheries, 49.

Jaeger, W. K.  1997. Better salmon management in the Pacific Northwest by combining technical and institutional innovations. Natural Resources Journal, Summer 1997 forthcoming.

Link, M. R. and K. K. English.  1996. The 1993 Fishwheel Project on the Nass River and an evaluation of fishwheels as an in-season management and stock assessment tool for the Nass River. Canadian Technical Report of Fisheries and Aquatic Sciences, 2130.

Link. M. R. 1999a. The 1996 fishwheel project on the Nass River, B. C. Canadian Manuscript Report of Fisheries and Aquatic Sciences 2476.

Link, M. R., and B. L. Nass. 1999b. Estimated abundance of chinook salmon returning to the Nass River, B.C., 1997. Canadian Manuscript Report of Fisheries and Aquatic Sciences 2475.

Link, M. R. and R. M. Peterman. 1998.  Estimating the value of in-season estimates of abundance of sockeye salmon (Oncorhynchus nerka).  Canadian Journal of Fisheries and Aquatic Sciences 55 (6): 1408-1418.

Link, M. R., and K. K. English. 1999. Long-term, sustainable monitoring of Pacific salmon populations using fishwheels to integrate harvesting, management, and research. Pages 667-674 in Sustainable Fisheries Management: Pacific Salmon. CRC Press.

National Marine Fisheries Service.  2000.   Biological Opinion: Operation of the Federal Columbia River Power System, Including the Juvenile Fish Transportation Program and the Bureau of Reclamation's 31 Projects, Including the Entire Columbia Basin Project.    Available at http://www.nwr.noaa.gov/1hydrop /hydroweb/docs/2000/2000Biop.htm.

Sustainable Fisheries Foundation.  1996.  Toward Sustainable Fisheries:  A Cooperative Strategy for Balancing the Conservation and Use of West Coast Salmon and Steelhead Populations.  Preliminary Draft for Review and Comment.  82 pp.

# Section 4. Key personnel

We have assembled a study team that brings together the expertise and skill required to successfully execute this project. The primary team members have an excellent understanding of fishwheel technology, harvest management, and salmon recovery efforts underway in the Pacific Northwest.  All have excellent written and oral communication skills.  Steward and Associates principal and lead scientist Cleve Steward will serve as overall project leader and contract administrator.  Tom Backman will serve as technical lead and William Jaeger will conduct economic analyses.  Barry Manuck is an experienced fishwheel fabricator and operator who will oversee construction and deployment of the fishwheel.  Robin Torner is a Cowlitz Indian Tribe council member who will arrange for fish monitors and assist in data collection and analysis.

Cleve Steward (MSc.) is a fisheries scientist and consultant with over 25 years experience and education in salmon and trout ecology and management, both as a government employee and as a consultant.  He is principle and lead scientist at Steward and Associates, an environmental consulting firm comprising fisheries and aquatic scientists, environmental policy analysts, and sustainability/low impact design specialists. As a consultant, Mr. Steward has provided technical assistance and directed numerous projects for federal, state, county and municipal agencies, tribes, universities, private firms and environmental groups throughout the Pacific Northwest.  He is frequently solicited to provide expert opinion and help resolve conflicts involving fisheries and aquatic resources, including surface water management, watershed impacts, salmon hatchery impacts, salmon smolt passage survival and behavior, and monitoring and evaluation techniques.  Mr. Steward is a member of the NMFS-appointed Technical Recovery Team for the Willamette and Lower Columbia Rivers, and is Executive Director of the Sustainable Fisheries Foundation, a non-profit organization dedicated to the protection, enhancement, and wise use of fisheries resources in the Pacific Northwest.

Tom Backman (Ph.D.) is a freshwater and marine ecologist with a strong background in salmon ecology and management. Dr. Backman has 30 years of experience in aquatic and fisheries research, administration, and instruction.  He has published on a wide range of topics including wetland restoration, gas bubble disease, hatchery supplementation, and endangered species recovery.  Along with Mr. Steward, Dr. Backman serves on the Technical Recovery Team for the Willamette and Lower Columbia Rivers.  Dr. Backman is also technical advisor to the Yakama Nation on the Lewis River hydro re-licensing project. He has been the president of the Oregon Chapter of the American Fisheries Society, and Chair of the Clackamas River Basin Council. In these roles, Dr Backman provides leadership, technical advice, and guidance on fishery policy, watershed restoration, and recovery goals.

William Jaeger (Ph.D.) is a natural resource economist on the faculty of the Department of Economics, Williams College, Williamstown, Massachusetts.  Dr. Jaeger spent the summers of 1994 and 1995 as a visiting professor at the School of Marine Affairs, University of Washington, Seattle.  While in Washington, Dr. Jaeger researched economic solutions to the current salmon problems in the Pacific Northwest. His work included a dynamic simulation modeling exercise to determine the benefits of a shift from non-selective gillnet and seine nets to fishwheels in a theoretical river system.  This work has been recently published in Natural Resources Journal (Jaeger 1997).  Dr. Jaeger brings to the study team a strong background in resource economics with a keen interest in using applied research to help solve real-world problems in the fishery.

Barry Manuck.is a Fisheries Supervisor with thirty-five years in the commercial fishing industry and seven years developing and fishing selective gear types in the Fraser River.  He has supervised and trained a large number of biologists and commercial and native fishermen in the fabrication and use of selective fisheries equipment. Mr. Manuck holds a patent on the power assisted fishwheel, fish trap, and a specially designed skiff and beach seine for selective fishing . He has designed, fabricated, and tested commercial fishing equipment for 29 years, including gillnets, lead traps, seines, tooth tangle nets, and aboriginal fisheries weirs and traps.  Mr Manuck was featured on the cover of a Canadian business magazine in 1997, in numerous television and printed documentaries, and in several newspaper articles promoting selective fishing.   The Department of Fisheries and Oceans Canada has promoted Mr. Manuck’s work by sending him to workshops and symposia throughout Canada and the United States.

Robin Torner is a tribal fisherman and council member of the Cowlitz Indian Tribe.  He is familiar with both the Cowlitz and Lewis Rivers, participates as tribal representative in the Lewis River dam relicensing proceedings, and is knowledgeable about fisheries issues affecting the tribe and lower Columbia River area.

Attachments, submitted by sponsors in May, 2002. Accepted as a comment on this proposal by Erik Merrill:

Revised Budget (in response to $200k cap)

Revised Narrative (in response to $200k cap)

Project member Barry Manuck has designed and operated several fishwheels on the Fraser River and was responsible for several key improvements in the technology, including a power-assist mechanism that enables the fishwheel to fish in slow currents, and for which he currently holds a patent.  Mr. Manuck will work with colleagues at the Screaming Eagle Boat Works of British Columbia to design and build the fishwheel to be used on this project.

It should be noted that 100% capture is not the objective of this project