Project ID:	198909801

Title:	Evaluate Supplementation Studies in Idaho Rivers

# Section 9 of 10. Project description

a. Abstract

The goal of the Idaho Supplementation Studies Project is to evaluate the usefulness of supplementation as a recovery/restoration strategy for depressed stocks of spring and summer chinook salmon in Idaho.  The project is a multi-agency effort, covering 31 streams throughout the Salmon and Clearwater river basins.  It is working to define the potential role of chinook salmon supplementation in managing Idaho’s natural spring and summer chinook populations, and identify genetic and ecological impacts to existing natural populations.   The ISS experimental design is split into three main approaches: (1) Large scale population production and productivity studies designed to provide Snake River basin wide inferences.  (2) Using study streams to evaluate specific supplementation programs.  (3) Small scale studies designed to evaluate specific hypotheses.  Approaches one and two measure population responses to supplementation and are long-term studies.  Approach three determines specific impacts of supplementation such as competition, dispersal, and behavior; and are short-term studies conducted in “controlled” environments.  We expect this research to demonstrate the best methods for supplementing existing natural populations of chinook salmon and re-establishing natural populations in streams where chinook salmon have become extirpated.  We expect supplementation effects and recommendations to be different for each stream.  The study design called for a minimum of 15 years (three generations) of research (Bowles and Leitzinger 1991).  Sampling was initiated in 1991, and implementation began in 1992. Supplementation effects are monitored and evaluated by comparing juvenile production and survival, fecundity, age structure, and genetic structure and variability in treatment and control streams of similar ecological parameters. The U.S. Fish and Wildlife Service contributes to the study through investigations on Clear Creek associated with the evaluation of operations at Kooskia National Fish Hatchery, and conducts redd surveys and monitors juvenile production on Pete King Creek.

b. Technical and/or scientific background

###### Idaho Supplementation Studies Development

The Idaho Department of Fish and Game (IDFG) spearheaded development of the Idaho Supplementation Studies (ISS) to address questions identified in the Supplementation Technical Work Group (STWG) Five Year Workplan (STWG 1988), as well as help define the potential role of supplementation in managing Idaho's anadromous fisheries and as a recovery tool for the basin.  Answers to these questions will help determine the best brood stock, rearing and release strategies for augmentation or restoring natural populations in various streams, and the effects of these activities on target and non-target natural populations.

The first steps in developing the Idaho Supplementation Study included formation of the Idaho Supplementation Technical Advisory Committee (ISTAC), development of a comprehensive experimental design and database, and initial collection of baseline genetic, physical and biological data. These steps were completed prior to implementing the Experimental Design.

The development of the Experimental Design was a cooperative project involving all the members of the ISTAC.  The committee was made up of representatives from the Forest Service (USFS) Intermountain and Northern regions, United States Fish and Wildlife Service (USFWS), Nez Perce Tribe (NPT), Shoshone-Bannock Tribes (SBT), Northwest Power Planning Council (NPPC), Bonneville Power Administration (BPA), Idaho Cooperative Fish and Wildlife Research Unit (ICFWRU), and Idaho Department of Fish and Game (IDFG).  Their roles were to technically review and provide input on the research design and coordinate with their respective management, research, and user groups.  This insures that long- and short-term management plans of respective agencies and tribes will not compromise the supplementation research design and that management and research concerns of the respective agencies and tribes were represented in the supplementation research design.  Through a subcontract with IDFG, the ICFWRU assisted directly in the development of the experimental design, with particular emphasis on the genetic and ecological effects of supplementation on natural populations.

###### History of Hatcheries and Supplementation

Hatcheries and supplementation activities have existed in the Columbia Basin for over 100 years.  The first hatchery in the Columbia Basin was built on the Clackamas River, Oregon in 1878.  The number of hatcheries and level of supplementation in the basin has been increasing ever since.  The first recorded supplementation of chinook salmon Oncorhynchus tshawytscha in Idaho was in 1920 on the Lemhi River.  Adult salmon were trapped in the Lemhi River and spawned at a cultural station in Salmon, Idaho.  The eggs were reared to fry and then released back into the Lemhi.  The station was abandoned in 1933 due to dwindling runs (Gebhards 1959).  The second record of outplanting was an attempt to reestablish chinook into the Clearwater River drainage above Lewiston Dam.  From 1947 to 1953, an average of 100,000 eggs/year were taken from wild spring chinook in the headwaters of the Middle Fork of the Salmon River.  Some adults returned to the Clearwater River as a result, but the exact numbers and their spawning success are unknown.

The second major attempt to reestablish chinook into the Clearwater began in 1961 with the advent of the Columbia River Fisheries Development Program.  This program began with the removal of barriers to upstream migration and the collection of 850,000 spring chinook salmon eyed eggs from the upper Middle Fork of the Salmon River and 610,000 eggs from upriver adult spring chinook trapped at the Bonneville Dam fish ladders.  These eggs were put into hatching channels in the upper Selway River (Nez Perce Tribe et al. 1990).  Once again, adults returned as a result, but extent and spawning success were not evaluated.

Presently, there are eleven state and federal anadromous hatcheries operating in Idaho: Clearwater, Oxbow, Rapid River, McCall, Sawtooth, Pahsimeroi, Dworshak, Kooskia, Hagerman National, Niagara Springs, and Magic Valley.  There are also three satellite rearing ponds: Powell, Red River, and Crooked River operated in conjunction with the Clearwater Hatchery.  These hatcheries have the combined capacity to produce 8.5 million spring chinook smolts, 2 million summer chinook smolts, 6.7 million A-run steelhead O. mykiss smolts, and 4 million B-run steelhead smolts annually.

The Lower Snake River Compensation Plan was authorized in 1976 to mitigate losses resulting from the construction of the four lower Snake River dams (Herrig 1990).  Sawtooth, McCall, Hagerman National, Magic Valley, Dworshak expansion, and the Clearwater Anadromous Fish Hatchery as well as the Red River, Crooked River, Powell, South Fork and East Fork of the Salmon River satellite facilities are part of this mitigation effort.  In general, the primary purpose of all these hatcheries is to return adult salmon and steelhead above Lower Granite Dam to provide fishing opportunity lost as a result of hydropower development.

Supplementation of natural stocks is not a mandated mitigation objective, but has become an important part of the hatchery programs.  Idaho has outplanted (i.e. off-site releases) over 5.5 million chinook fry, approximately 8 million smolts, and 8,000 adults into the Salmon River drainage since 1977 (IDFG et. al. 1990).  During the same period, over 17 million fry, 3 million smolts, and 2,000 adults were outplanted into the Clearwater River drainage (Nez Perce Tribe et. al. 1990).  In spite of widespread outplanting activities there has been little scientific evaluation of supplementation on rebuilding or influencing natural salmon populations both in Idaho and basin wide.  Furthermore, despite these hatchery mitigation efforts, anadromous fish stocks in Idaho continued to decline.

###### Role of Supplementation

It is well documented that most of the decline and continued depression of upriver chinook stocks is due predominately to poor survival (flows and passage problems) associated with the lower Snake and Columbia River dams and reservoirs (IDFG 1985; CBFWA 1990; IDFG 1991).  Although mitigation efforts should be focused on direct alleviation of passage and flow constraints, concurrent recovery efforts such as supplementation have been recognized as necessary to meet the Northwest Power Planning Council's interim doubling goals (NPPC 1987, 1994).

The utility of supplementation as a viable recovery tool continues to be the subject of much debate.  Although sound evaluation has been lacking, there is little doubt that past supplementation efforts have rarely met with success (Smith et al. 1985; Miller et al. 1990; Steward and Bjornn 1990).  We believe the verdict on supplementation is still out because previous outplanting programs were typically directed by conventional hatchery guidelines and criteria, and not current natural production and genetic conservation theory.  The potential benefits as well as risks associated with supplementation warrant more thorough investigation prior to negating or embracing supplementation as a recovery tool.  The following discussion provides a brief synopsis of current knowledge and theory on supplementation effects.

While there has been conflicting evidence, the majority of the research points out that outplanting programs have not been successful, especially when the intent was to boost natural production (Reisenbichler and McIntyre 1986; Miller et al. 1990).  Reestablishing runs (i.e. restoration) have shown some success.  Salmon with shorter freshwater life cycles and shorter migrations have had higher success than those with longer freshwater residency and longer migrations (Miller et al. 1990).  Miller et al. also states that the introduction of "locally adapted" smolts will yield adults but they warn smolt quality must be good (e.g. disease not a significant mortality factor).  Wild and natural fish do not perform as well in a hatchery as hatchery fish (Reisenbichler and McIntyre 1977).  Fish from distant stocks do not survive as well as fish from the local stocks.  Survival decreases as transfer distance increases (Kijima and Fujo 1984; Reisenbichler 1988).

With traditional hatchery practices, hatchery fish tend to become a different stock.  They adapt to the hatchery and can become different genetically (altered heterozygosity, gene frequency shifts) from the natural/wild stock from which it was derived (Reisenbichler and McIntyre 1977; Steward and Bjornn 1990).  These changes can be observed in fitness, growth, survival, and disease resistance. Hatchery fish have shown increased straying rates compared to wild and natural fish (Steward and Bjornn 1990).  This could pose a significant threat to non-target wild stocks.

Offspring resulting from hatchery X wild/natural crosses can have lower fitness for the local habitats.  Fitness was found to decrease as differences between hatchery and wild/natural fish increased (Bams 1976; Reisenbichler and McIntyre 1986; Chilcote et al. 1986).  Quantification of the relationship between some measure of “distance” (e.g. geographic, genetic) between stocks and resulting fitness of crosses is lacking.  Productivity of wild/natural stocks can also be reduced after introgression by hatchery fish (Snow 1974; Vincent 1985, 1987; Kennedy and Strange 1986; Petrosky and Bjornn 1988).  Offspring of hatchery adults can have relatively low survival in natural habitats relative to wild/natural offspring (Chilcote et al. 1986; Nickelson et al. 1986).  Genetic changes in hatchery fish even over a few generations can affect survival negatively in the natural environment (Reisenbichler and McIntyre 1977; Steward and Bjornn 1990).

It is generally felt that supplementation can increase natural production (i.e. total numbers produced) but not natural productivity (e.g. number of adults produced per natural spawner).  Reductions in natural productivity can be minimized through proper supplementation strategies so that enhanced production more than compensates for reduced productivity.  These same hatchery practices can minimize genetic drift of the hatchery stock away from the local stock from which it was derived by collecting eggs from throughout the run, using wild fish in the egg-take periodically and spawning males and females in a 1:1 ratio (Kapuscinski et al. 1991).

Interbasin stock transfers can result in “serious” risk to the fitness of native stocks.  Several biologists have recommended that if a supplementation program is initiated, the hatchery brood stock should be taken from the stock to be supplemented in order to maintain genetic identity and avoid disrupting locally attuned co-adapted gene complexes (Bams 1976, Reisenbichler 1981, 1984; Chilcote et al. 1986; Currens et al. 1991; Kapuscinski et al. 1991; McIntyre in press).  Estimates of the number of adults needed to start the brood stock range from 50 (Verspoor 1988) to 500 (Franklin 1980).  They also recommend that in order for supplementation to have the best chances of success, one needs to understand the ecology of the area (e.g. carrying capacity, survival rates and densities, habitat quantity and quality etc.), factors limiting present production, the unique qualities of the stock, and optimum methods of supplementation.

Certain life stages may have less of an impact on native stocks.  Introduction of locally adapted adults appears to minimize negative interaction potential between their offspring and offspring of wild fish.  It is assumed that spawning would occur in the same timeframe, emergence timing would be similar, and the fry would be subject to the same selective pressures as the wild/natural fish.  There would be no size advantage.  Locally adapted eggs on the other hand are questionable; one must make sure that the thermal history of the eggs in the hatchery is similar to the wild eggs in the stream to avoid a size advantage in the hatchery fry.

Fry appear to have the highest potential for harmful interactions with wild fish during the first generation (typically the hatchery fish have a size advantage over the wild/natural fish).  Second generation impacts are probably greater for smolts because the carrying capacity restraint is lifted.  Because the natural rearing carrying capacity can be exceeded with smolts, there stands a greater chance of swamping the natural population with returning hatchery adults.  This in turn can result in diluting the locally adapted gene complexes of the native fish.  If introgression of the hatchery and natural stocks is desired, brood, rearing and release strategies should mimic the natural conditions as best possible.  Genetic changes in the natural population resulting from supplementation can persist several generations after outplanting is discontinued.

It is widely held that for upriver stocks, supplementation cannot be considered an alternative to reducing downriver mortalities.  Success is dependent on concurrent improvement in flows and passage.  Flow and passage related mortality through the eight lower Snake and Columbia River dams and reservoirs is thought to be the most important limiting factor for upper Snake River stocks.  However, supplementation can be used as an interim measure to prevent demographic extinctions.  Other than flows and passage, the primary determinants of the success of outplanting are the source of parents, rearing density and environment, size, and time of year fish are released.

Due to the large geographic scope of this study, study streams were partitioned among four resource management entities for implementation.  These include Idaho Department of Fish and Game, Nez Perce Tribe, Shoshone-Bannock Tribe, and the U.S. Fish and Wildlife Service- Idaho Fishery Resource Office.  Allocations were based on interest, integration with ongoing programs, cost efficiency, logistics, and, to a lesser extent, relative equity.  Approximately one-half of the study will be implemented by Idaho Department of Fish and Game through the ISS contract with BPA.  The Nez Perce Tribe and Shoshone-Bannock Tribe have similar commitments to ISS, each comprising approximately 20% of the study.  Both of these components rely heavily on integration of existing or proposed tribal programs.  The U.S. Fish and Wildlife Service contributes 10% of the study implementation, most coming from investigations on Clear Creek associated with evaluation of operations at Kooskia National Fish Hatchery. The Idaho Department of Fish and Game is the lead agency regarding project development, coordination, and implementation.

c. Rationale and significance to Regional Programs

Note: For the sake of brevity, all links to reasonable and prudent action items in the 2000 Federal Columbia River Power System (FCRPS) Biological Opinion are denoted below simply as “FCRPS Action ###”.  Relationships to both of the NPPCs 1994 and 2000 Fish and Wildlife programs (FWP) are presented since this project has consistently focused on addressing critical uncertainties and information needs expressed in the FWPs.

The 2000 Fish and Wildlife Program has adopted as two of its’ regional objectives for anadromous fish, the task of restoring “the wildest possible set of healthy naturally reproducing populations of salmon…by 2012” and increasing the “total adult salmon and steelhead runs above Bonneville Dam by 2025” to achieve full mitigation for losses of anadromous fish (FWP 2000, Section C.2.a.1, pg.18). Artificial production strategies are currently employed in the basin. However, the risks and benefits of supplementation on wild and naturally spawning populations are unknown. The FWP has stated in its’ implementation of artificial production strategies that “Artificial production must be implemented with an experimental, adaptive management design that includes an aggressive program to evaluate the risks and benefits and address scientific uncertainties” (FWP 2000, Section 4. pg 27). The NPPC has called “for immediate efforts to gather data on wild and naturally spawning stocks, review impacts of the existing hatchery system and coordinate supplementation activities” to achieve its goal of doubling anadromous fish runs in the Columbia Basin as addressed in the Columbia Basin Fish and Wildlife program (NPPC 1994).   The overall goals of ISS are to address local and regional objectives and concerns with regard to the use of supplementation as a tool in rebuilding/reestablishing spring and summer chinook to harvestable levels in Idaho. Relationships between FWP (1994, 2000), NMFS 2000 FCRPS Biological Opinion-RPAs, Clearwater and Salmon River subbasin summaries, and the ISS research objectives are demonstrated below.

The 2000 FWP Action 184 states the need to provide funding for a “hatchery research, monitoring, and evaluation program consisting of studies to determine whether hatchery reforms reduce the risk of extinction for Columbia River basin salmonids and whether conservation hatcheries contribute to recovery”. This need was also addressed in the 1994 FWP (Section 7.3B.2) stating the importance of developing “ a clear policy to guide the use of supplementation” and “implement the high priority supplementation projects including…monitoring and evaluation”.  ISS Research Objectives 1, 2, and 3 (Implementation Phase) are a clear attempt to provide the needed monitoring and evaluation of supplementation and in the long-term provide answers to supplementation’s role in rebuilding and/or reestablishing spring chinook runs in Idaho.

With the current trend of declining abundance of salmon, it has become necessary to use artificial propagation and the proper use of hatchery fish to supplement wild and natural spawning populations of salmon as a rebuilding measure (FWP 1994, Section 7.0A). It is also stated in the NMFS Biological Opinion on Artificial Propagation of Anadromous Salmonids in the Snake River Basin (Section 10.2) that “The action agencies shall monitor and evaluate their respective artificial propagation programs in the Columbia River Basin.” The need for continued “monitoring and evaluation programs for fish supplementation” and a “cooperative/shared approach” is stated as a specific immediate or critical need in the 2001 Clearwater Subbasin Summary (pg.247).  ISS is a cooperative effort to monitor and evaluate supplementation strategies in Idaho. Objectives 1 and 3 directly address the issue of identifying which supplementation strategies (brood stock and release stage) if any, will be most affective in increasing natural production without adverse effects on natural productivity.

Recommendations made in Action 182 (2000 FCRPS Biological Opinion) are to fund studies "to determine the reproductive success of hatchery success relative to wild fish” and concerns over the genetic implications are expressed.  The FWP 1994, Section 7.1B.1 recommends a “review (of) current efforts to conserve genetic diversity within and among salmon stocks” and make recommendations on “how to achieve sustainable increases in salmon... populations”.  The 2000 Clearwater Subbasin Summary calls for a province-wide genetic assessment of salmon as a baseline for monitoring hatchery introgression into wild populations (pg. 249). ISS Research Objective 2, to monitor and evaluate changes in productivity and genetic composition of target and adjacent populations following supplementation, addresses this recommendation.  Adult monitoring components of the ISS address interactions between hatchery and wild chinook, a need identified in the 2000 summary (pg.249).

Action 174 identifies the need for “additional sampling efforts and specific experiments to determine relative distribution and timing of hatchery and natural spawners”. A need was also identified in the 1994 FWP (Section 7.1C.3) to “collect information on wild and naturally spawning populations with the long-term objective of collecting information on the sustainability of wild and naturally spawning salmon populations”.  In ISS Research Objective 2 we establish a baseline profile for evaluation and monitoring, we will include a genetic profile analysis for treatment and control streams.

The Fish and Wildlife Program (FWP 1994, Section 7.2A) states:  “...regional standards and procedures for operations should be developed that are consistent with the goal of rebuilding weak wild and naturally spawning stocks”. ISS Research Objectives 1 through 4 were developed to document which methods are best for supplementing existing, naturally reproducing populations of chinook salmon and reestablishing naturally producing populations in streams where they have been extirpated.

A major contributor in the design of the ISS project has been the Regional Assessment of Supplementation Project (RASP) “which was designed to provide a comprehensive framework for supplementation- the practice of using carefully selected stocks of hatchery fish to “reseed” streams”(FWP 1994 Section 7.3A). The ISS experiment was designed parallel to development of the RASP process, and RASP guidelines were incorporated in the design.

Wy-Kan-Ush-Mi Wa-Kush-Wit: Volume I: 5B–14-22; Volume II: 2-118-127.  “Implement supplementation projects that have met the screening criteria of RASP (1992) and Cuenco et al (1993)”, which includes the ISS project.  “Establish additional programs for each of the subbasin tributary systems to monitor adult escapement and resulting smolt production, and to evaluate (by measuring the number of adults returning) the ability of managers to meet goals set by the Columbia River Management Plan.”

d. Relationships to other projects

Due to the large geographic scope of this study, study streams were partitioned among four resource management entities for implementation. These include the Idaho Department of Fish and Game, U.S. Fish and Wildlife Service- Idaho Fishery Resource Office, Nez Perce Tribe, and the Shoshone-Bannock Tribe. Allocations were based on interest, integration with ongoing programs, cost efficiency, logistics, and, to a lesser extent, relative equity. Approximately one-half of the study will be implemented by Idaho Department of Fish and Game through the ISS contract with BPA.  The Nez Perce Tribe and Shoshone-Bannock Tribe have similar commitments to ISS, each comprising approximately 20% of the study. The U.S. Fish and Wildlife Service contributes approximately 10% of the study implementation. The Idaho Department of Fish and Game is the lead agency in project development, coordination and implementation.

All cooperators meet together to plan project activities and discuss adaptive changes necessary to maintain project relevancy and effectiveness.  Each ISS cooperator completes requirements for the National Environmental Policy Act (NEPA) with land management agencies where project activities occur on public land.  ESA section 10 permits are acquired through the National Marine Fisheries Service.

In addition to the relationship with the cooperative studies mentioned above, ISS also coordinates field activities and data collection efforts within the Clearwater River subbasin including the Steelhead Supplementation Studies in Idaho Rivers (9005503), Idaho Habitat/ Natural Production Monitoring (9107300), the Nez Perce Tribal Hatchery O&M (8335000).  ISS project also coordinates with and transfers data to projects in the Salmon River subbasin including the Monitoring Smolt Migration of Wild Snake River Spring/Summer Chinook Salmon (9102800), Salmon River Habitat Enhancement (9405000), Johnson Creek Artificial Propagation Enhancement (9604300), Monitoring Listed Stock Adult Chinook Salmon Escapement (9703000), Salmon River Production Program (9705700).

ISS cooperators collect a tremendous volume of data.  This data is requested by other entities in the Salmon and Clearwater drainages including IDFG regions and headquarters, USFS, Bureau of Land Management (BLM), NMFS, USFWS, private landowners, hatchery managers, etc.  Many entities rely on the information we collect in making management decisions.

The PIT Tag Information System (PTAGIS), administered by the Pacific States Marine Fisheries Commission, enables and assists us in the use, interrogation, and data base management of Passive Integrated Transponder (PIT) tags.

ISS works closely with the Lower Snake River Compensation Plan to coordinate on hatchery supplementation treatments.

e. Project history (for ongoing projects)

Project numbers:

The Idaho Salmon Supplementation (ISS) Studies in Idaho Rivers project started in 1989 as project 89098, (Idaho Department of Fish and Game, current project (8909800).  In 1992, the U.S. Fish and Wildlife Service, Nez Perce Tribe, and Shoshone-Bannock Tribes were funded to assist in the ISS project as cooperative agencies with project numbers of 8909801, 8909802, and 8909803 respectively.  The Idaho Cooperative Fish and Wildlife Research Unit (ICFWRU, University of Idaho) was subcontracted by the Idaho Department of Fish and Game to conduct small-scale investigations under the ISS study.

Adaptive Management Implications:

ISS data addressing current population levels and life history descriptions for many of the chinook salmon (including ESA listed) producing streams in the Salmon and Clearwater drainages is being utilized in the PATH process, hydro-system evaluations, and captive brood programs.

While not directly implemented for ISS, data collected on ISS PIT tagged chinook (wild/natural and hatchery origin) at Snake and Columbia River passage facilities will aid in mainstream smolt monitoring of timing and passage requirements and may contribute to the management/modification of main stem dam operations.  Implementation of captive brood programs including: stream prioritization, collection techniques, and monitoring and evaluating techniques will use ISS data.

The ISS study results and recommendations will help guide state, tribal, and federal hatchery programs.  For example, brood years 1994 and 1995 chinook salmon were all stocked as smolts, since analysis of 1992-1994 data demonstrated higher minimum rates of detections at main stem fish passage facilities for smolt releases over parr and pre smolt released fish.  Population characteristics including historical resiliency to low return years, life history, and genetic descriptions from baseline sampling will also play a vital role in determining which supplementation strategy, if any, produces the best adult-to-adult production without adverse genetic impacts to natural populations.

Project reports and technical papers:  Additional reports for each cooperating agency are listed in section h of this proposal.

ISS Project Reports

Bowles, E. and E. Leitzinger, 1991. Salmon Supplementation Studies in Idaho Rivers. Experimental Design to the U.S. Department of Energy, Bonneville Power Administration. Project No. 89-098. Contract No. DE-B179-89BP01466. (www.efw.bpa.gov/cgi-bin/ws.exe/webcql.dir/FW/PUBLICATIONS/QueryPublications.pl)

Idaho Department of Fish and Game. 2001. Salmon Supplementation Studies in Idaho Rivers- Five year summary report. Prepared for Bonneville Power Administration, U.S. Department of Energy, Portland, Oregon.

Peery, C.A., and T.C. Bjornn. 1996. Small-scale investigations into chinook salmon supplementation strategies and techniques: 1992-1994. Technical Reports 96-3 ICFWRU, University of Idaho. IDFG and BPA, Portland, Oregon.

USFWS Reports

Rockhold, E.A., R.B. Roseberg, and J.M. Olson. 1997. Idaho Supplementation Studies Pete King and Clear creeks progress report 1991-1993. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon.

Olson, J.M., and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek 1997 progress report. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon.

Olson, J.M., and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek progress report for field activities 1998-2000. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon.

Summary of Results Achieved:

The ISS Experimental Design was completed and published in 1991.  (To view the experimental design click the words ‘Link Now’ at the end of this sentence, enter 01466-1 in the DOE/BP field, and click on ‘Select’ at the bottom of the dialogue box. Link Now.) Baseline data collection and development of supplementation brood stocks (Phase I) began in 1991. Over a period of about five years, supplementation brood stocks were developed for seven hatchery trap/release locations as identified in the experimental design:

Sawtooth Fish Hatchery – Upper Salmon River

Pahsimeroi Fish Hatchery – Pahsimeroi River

McCall Fish Hatchery – South Fork Salmon River

Clearwater Fish Hatchery Satellites

Crooked River

Red River

Powell (Colt-killed Creek)

Other treatment streams in Clearwater River basin

Kooskia National Fish Hatchery – Clear Creek.

As adult fish began to return from the Phase I supplementation brood stock juvenile releases, the project progressed into Phase II. Phase II uses the returning adults to supplement natural origin recruits in treatment streams, and maintains supplementation brood stocks for juvenile production and release.  Juvenile fish releases through brood year 1996 include 1,281,755 fish in the Clearwater River basin and 1,954,048 fish in the Salmon River basin.  Adult salmon returns to the entire Snake River basin were extremely poor in 1995 and 1996 that impacted brood stock maintenance and target numbers of juveniles to release in 1997 and 1998. The ISS project plays a lead role in developing brood stock management plans in such years, focusing more on conservation hatchery management objectives, and NMFS-ESA permitting requirements for hatchery operations. Current project hatchery production and natural production survival data is considered in determining the allocation of adults to natural spawning and supplementation brood stocks.

This project is now transitioning from Phase II to Phase III, monitoring the effects of supplementation. On Clear Creek, we expect 2002 to be the final year in which adults will be collected for supplementation brood stock, thus completing Phase II of the study.  We expect to begin Phase III in 2004 at which time juvenile releases from supplementation brood stocks into Clear Creek will stop; returning adults from prior juvenile releases will be released to supplement spawning of natural origin recruits; and monitoring of production and productivity response variables in control and treatment streams will continue.

Monitoring production and productivity response variables in control and treatment streams is an on-going task.  Small-scale studies subcontracted to the ICFWRU were completed (cited below with other reports) and results and recommendations were incorporated into subsequent fish releases. Types and extent of some of the current monitoring programs are described in the following paragraphs. Where possible these results have been referenced back to the stated objective and tasks presented in section f. Data for several key performance indices of Clear Creek and Pete King Creek are provided as an example of the information available in the 5-year summary report (Walters et al. 2001) and the annual progress reports prepared by the U.S. Fish and Wildlife Service.

Objective 1.	Monitor and evaluate the effects of supplementation on presmolt and smolt numbers and spawning escapements of naturally produced salmon.

Task 1.a   	The Clear Creek and Pete King Creek components of the ISS study rely heavily upon both Kooskia and Dworshak National Fish Hatcheries, and the Clearwater Anadromous Fish Hatchery for collection of adults, spawning, rearing, marking and release of fish used for this study.

Task 1.b	All hatchery reared supplementation smolts released into Clear Creek have received either a right ventral or a left ventral fin clip to distinguish them from general hatchery production fish.  Parr released into Pete King Creek have received either a left or right ventral clip, or were coded-wire tagged.

Task 1.c	We have continued to PIT tag a minimum of 500-750 supplementation smolts and general hatchery production smolts prior to their release into Clear Creek. With the exception of 1998 when all parr were coded-wire tagged, a minimum of 1,000 parr have been PIT tagged prior to their release into Pete King Creek.

Task 1.d	In the experimental design (Bowles and Leitzinger 1991) Clear Creek was designated as a smolt treatment stream.  The prescribed treatment for Clear Creek is a release of 50,000 smolts with the brood stock coming from Kooskia National Fish Hatchery. We have released a total of 267,000 smolts into Clear Creek since the treatments began in 1995.  The prescribed releases into Clear Creek have been met for all years of the study with the exception of brood years 1995 and 1999. In 1995 only 40 adults returned to the Kooskia National Fish Hatchery. In 1999 only 157 adults returned. Due to the low adult returns, the egg-take requirements of the hatchery could not be met. In 1995 all eggs were used for general hatchery production and no adults were passed above the weir for natural production. In 1999 twenty adults were passed above the weir for natural production but no adults were taken specifically for supplementation brood stock. We are proposing to extend our brood stock selection into 2002 to make up for the loss of production in 1999 allowing us to complete five years of treatments using known origin brood stock as prescribed by the experimental design (Bowles and Leitzinger 1991).  Pete King Creek was designated as a parr treatment stream, with a prescribed release of up to 15,000 parr from brood stock coming from Powell, a satellite facility operated by the Idaho Department of Fish and Game.  Pete King Creek has received a total of approximately 53,000 parr since treatments began in 1993.

Task 1.e	 Intensive snorkeling was used to estimate summer parr population estimates from 1991-1996.  Data from these counts have resulted in imprecise estimated.  Additional efforts, such as snorkeling a larger percentage of each stream would be required to increase this precision.  Given the numerous other tasks of the study the ISS cooperators did not believe that the increased efforts were feasible.   The U.S. Fish and Wildlife Service continues to monitor observed parr densities using snorkel techniques, although at a less intense rate. The information is used by U.S. Forest Service as part of their watershed and fisheries monitoring program, and by the Idaho Department of Fish and Game in their Idaho Natural Production and Monitoring Program (9107300). Figure 1 summarizes the observed parr densities in Clear Creek and Pete King Creek from 1991-2000.

Figure 1. Observed parr density for spring chinook salmon in Clear and Pete King creeks for survey years 1990-2000. ISS began decreasing snorkel efforts in 1998.

Task 1.f	PIT-tag data is used to estimate smolt production and survival to Lower Granite Dam. Our task was to PIT tag a minimum of 500 naturally produced juveniles on each Clear and Pete King creek to estimate survival to Lower Granite Dam. Despite an increase in effort, we have met with little success on either stream. We have met the minimum goal of 500-700 juveniles once on Clear Creek (1999), and narrowly missed it in 1995.  We do expect to easily meet the minimum PIT tagging goal during the 2001 field season based on the number of redds counted in 2000.   We also predict we will be able to meet or exceed the minimum goal in 2002 based on the numbers of adults currently returning to Clear Creek.

The interrogation rates of juveniles PIT tagged from Clear Creek in brood years 1996, 1997, and 1998 are shown in Figure 2.  We have seen through these interrogations that supplementation smolts, which are given a ventral fin clip to distinguish them from general hatchery production, were detected at a slightly lower rate than hatchery smolts that were given only an adipose fin clip.  In 1996 and 1997 the naturally produced smolts were detected at a higher rate than either supplementation or hatchery smolts.

Figure 2. Interrogation rates for juveniles PIT-tagged on Clear Creek for brood years 1996-1998(based on queries done 03/01).

Task 1.g.	We use a rotary screw trap to collect, PIT tag, and enumerate emigrating juveniles on Clear Creek.  We continue to use the existing adult weir on Clear Creek to identify and enumerate returning adults.

It is too early to evaluate the adult return rates from the second generation.  The first offspring from second generation, composed of known origin (localized) brood stock, were released as smolts in 1999 and have not yet returned.  We expect the majority of these fish to return as II-Ocean adults this year (2001); some will return as III-Ocean adults in 2002.  Adult returns to the weir on Clear Creek at Kooskia National Fish Hatchery are presented in Table 1.  Data from 2001 is not complete because adults are still returning as this document is being prepared.  Due to the extremely large numbers of adults returning to the Clear Creek weir, we have been unable to keep the trap open throughout the entire run.  Our total adult returns for 2001 will be estimated rates rather than actual counts as in years past.

Table 1. Summary of adult spring chinook returns to the Clear Creek weir for 1991-2001. Summary includes the number of adults released over the weir for natural production, origin based on fin clips, and the average number of eggs per female.

| Return Year | No. SCS Released Over weir | Males and Females Combined |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | I Ocean | II – III Ocean | FIN CLIPS |  |  |  | Eggs Per Female |
|  |  |  |  | Hatchery | Supplementation |  | Natural |  |
|  |  |  |  | AD | RV | LV | None |  |
| 2001a | 82 | 26 | 2101 | 1896 | 4 | 171 | 56 | ------ |
| 2000 | 92 | 966 | 615 | 1275 | 201 | 36 | 61b | 3,555 |
| 1999 | 20 | 72 | 85 | 135 | 10 | 3 | 9b | 4,378 |
| 1998 | 27 | 1 | 407 | 372 | 8 | 6 | 22 | 3,726 |
| 1997 | 127 | 7 | 1650 | 1530 | 14 | 2 | 111 | 3,545 |
| 1996 | 32 | 88 | 114 | 189 | 1 | 0 | 12 | 3,565 |
| 1995 | 0 | 21 | 19 | * | * | * | * | 3,961 |
| 1994 | 25 | 1 | 231 | * | * | * | * | 4,106 |
| 1993 | 91 | 11 | 1169 | * | * | * | * | 4,270 |
| 1992 | 20 | 14 | 298 | * | * | * | * | 3,963 |
| 1991 | 11 | 10 | 457 | * | * | * | * | 4,117 |

a-data incomplete as adults are currently returning. Counts are as of 07/17/01.

b-Cwt with no external clips (2 fish)

*Clear Creek did not have ISS fin-clipped supplementation fish returning until 1996.

Task 1.h	Each year, a combination of aerial and ground redd counts are conducted in all treatment and control streams in the Clearwater and Salmon River subbasins.  All carcasses recovered are measured for length and examined for marks.  The visceral cavity of fish is opened to verify sex and determine the percentage of completed spawning.  The age class of each fish is determined by length frequency or from scale or fin ray analysis.

From the start of the study there had been a large discrepancy between the number of adults released over the weir at Kooskia NFH, and the number of redds observed in Clear Creek. In 1997 the USFWS- Idaho Fishery Resource Office added a radio telemetry component to the study to address this issue. The use of radio telemetry has helped us locate spawning areas, enabled us to monitor spawning distribution and timing, and document possible spawning interactions between supplementation and natural fish on Clear Creek. We expect the 2001 redd counts to be similar, if not exceed, the 2000 redd counts on both streams based upon the high number of adult returns to the basin. The number of redds per kilometer for Clear Creek and Pete King Creek are shown in Figure 3.

Figure 3. Spring chinook redds per kilometer for Clear Creek and Pete King Creek from 1991 to 2000.

Objective 2.	Monitor and evaluate changes in natural productivity and genetic composition of target and adjacent populations following supplementation.

Task 2.a	Most of the juvenile chinook are collected and enumerated using a rotary screw trap on Clear Creek.  The trap is operated from March until freeze up in November. Juveniles are also trapped using minnow traps, backpack electrofishing gear, and hook-and-line techniques on both Clear Creek and Pete King Creek. The number of juveniles we have collected and PIT-tagged are shown in Table 2.

Table 2. Number of natural spring Chinook salmon that have been collected and PIT tagged from Clear and Pete King creeks for the ISS project for project years 1992-2000.

| Stream | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Clear Creek | - | 368 | 299 | 492 | 8 | 302 | 351 | 982 | 349 | 3,151 |
| Pete King Creek | - | - | - | - | - | 300 | 2 | - | - | 302 |
| Total | - | 368 | 299 | 492 | 8 | 602 | 353 | 982 | 349 | 3,453 |

Task 2.b	Tissue samples from adult returns to the Kooskia weir on Clear Creek have been taken since the onset of the study. These samples are sent to the Idaho Department of Fish and Game to be used for DNA analysis. No adult returns have been captured and no carcasses have been recovered on Pete King Creek.

Task 2.c	Straying is monitored with the use of the adult weir on Clear Creek, the adult collection facility at Dworshak National Fish Hatchery, and others in the basin.  Carcass surveys and radio telemetry are other methods of getting at stray information, although we have documented very little, if any, on Clear and Pete King creek using these methods.

Task 2.d	At this point in the project we have done very little to predict population viability and determine if populations will maintain themselves through time.  Without return data from the second generation it is unlikely that we would be able to accurately predict if the population will sustain itself through time.

Objective 3. 	Determine which supplementation strategies (brood stock and release stage) provide the quickest and highest response in natural production without adverse effects on productivity.

Task 3.a	Monitoring production and productivity response variables in Clear Creek and Pete King Creek is an on-going task and one which will continue throughout out the life of this study. Specific monitoring tasks have been presented previously under objectives 1 and 2.  Based on the PIT tag interrogations at the detection facilities presented in Figure 2 the lowest percent of detections has been on the presmolt and parr life stages.  This data, granted a very small sample, indicates that the best survival rates come from the juveniles we tagged as smolts. This leads us to believe, at this point in the study, that smolt releases will be more successful than parr and presmolt releases.

Task 3.b	Local brood stocks on Clear Creek have been collected since 1997 for all but one year, 1999. In 1999 the adult returns were too low to allow us to collected brood stock for a supplementation release in 2001.  We are proposing to spawn local brood stock on Clear Creek with the known natural component in 2002.  This extension will allow us to make up for the loss of production in 1999 enabling us to complete five years of treatments as prescribed by the experimental design (Bowles and Leitzinger 1991).

Task 3.c	Comparisons between the first and second generations of natural production and productivity have not yet have not been completed because the second generation has not yet had a chance to return.  The first adults are expected to return in 2001, at the writing of this proposal.

### Data Base Development. The ever-increasing size of the data set collected by the ISS project has prompted the development of a new integrated database.  During the last two years, considerable effort has been devoted to the development of this database. The main purpose of this effort is to centralize all data collected by all cooperating agencies into a common database.  This will allow uniform and repeatable queries and analysis of the data set.   All cooperators are, or soon will be, sending data remotely into a central server at IDFG headquarters.  Currently, the juvenile trapping data entry form and tables have been developed. The redd count and adult carcass information tables are being developed and will be used for the 2001 spawning surveys.

All data collected prior to 2001 is currently in an electronic format and will be uploaded into the new centralized database over the next year.  When complete this will be one of the largest sets of life history and migration data for both anadromous and resident fish in the state of Idaho. This data will be shared with STREAMNET.

Years underway / Past costs:  The USFWS has been funded for ten years under the project 8909801. Our annual budgets have ranged from $73,461 to $147,344 for a total of $1,081,179.

f. Proposal objectives, tasks and methods

Objectives:

OVERALL MANAGEMENT GOAL FOR SUPPLEMENTATION:

The general expectation for supplementation among management entities and user groups in Idaho is to use artificial propagation to help build self-sustaining and harvestable populations of chinook salmon in the Salmon and Clearwater River drainages without adversely impacting existing wild and natural populations.

The specific RESEARCH GOALS of this project are:

1.	Assess the use of hatchery chinook salmon to increase natural populations of spring and summer chinook in the Salmon and Clearwater River drainages.

2.	Evaluate the genetic and ecological impacts of hatchery chinook salmon on naturally reproducing chinook populations.

The specific RESEARCH OBJECTIVES of this project are:

1.	Monitor and evaluate the effects of supplementation on pre-smolt and smolt numbers and spawning escapements of naturally produced salmon.

2.	Monitor and evaluate changes in natural productivity and genetic composition of target and adjacent populations following supplementation.

3.	Determine which supplementation strategies (brood stock and release stage) provide the quickest and highest response in natural production without adverse effects on productivity.

4.	Develop supplementation recommendations.

RESEARCH QUESTIONS

In Idaho we have the opportunity to address several questions associated with the two broad uncertainties:  "Can supplementation work?" and "What supplementation strategies work best?" These questions relate directly to questions 2), 3), 6) and 7) specified as important critical uncertainties by the Supplementation Technical Work Group (STWG 1988).  We hope to address each of these questions through this study.

1.	Does supplementation-augmentation of existing chinook populations in Idaho enhance natural production?

2.	Does supplementation-restoration utilizing existing hatchery stocks establish natural populations of chinook salmon in Idaho?

3.	Does supplementation-augmentation of existing chinook populations in Idaho reduce natural productivity of target or adjacent populations below acceptable levels (e.g. replacement)?

4.	How often is supplementation required to maintain populations at satisfactory levels?

5.	Can existing hatcheries and brood stocks be used effectively to supplement target populations within local or adjacent sub basins?

6.	Is there an advantage to developing new, localized brood stocks with a known natural component for supplementation of existing natural populations?

7.	Which life stage released (i.e. parr, pre-smolt, smolt) provides the quickest and highest response in rebuilding natural populations?

8.	Which life stage released results in the least deleterious effects on existing natural productivity and genetic composition?

Specific hypotheses for research Objectives 1-3 are as follows:

Objective 1. 	Monitor and evaluate the effects of supplementation on presmolt and smolt numbers and spawning escapements of naturally produced salmon.

H01a:	Supplementation-augmentation of existing Chinook populations in Idaho does not affect natural production. Corollary: Rejecting H01a indicated that supplementation can enhance of deter natural production.

H01b:	Supplementation- restoration utilizing existing hatchery stocks does not establish natural populations of chinook salmon in Idaho.  Corollary: Rejecting H01b indicates that existing hatchery stocks can be used to restore natural populations of chinook salmon in Idaho.

Objective 2.	Monitor and evaluate changes in natural productivity and genetic composition of target and adjacent populations following supplementation.

H02a:	Supplementation-augmentation of existing Chinook populations in Idaho does not reduce productivity of target or adjacent populations below acceptable levels (e.g. replacement). Corollary:  Rejecting H02a indicates that supplementation can conversely affect survival and performance of existing populations.

H02b:	Supplementation does not lead to self-sustaining populations at some enhanced level (e.g. 50% increase in abundance maintained over time.)  Corollary: Rejecting H02b indicates that certain supplementation strategies are successful in establishing self-sustaining populations or enhancing the level at which populations maintain themselves.

Objective 3. 	Determine which supplementation strategies (brood stock and release stage) provide the quickest and highest response in natural production without adverse effects on productivity.

H03a:	Use of existing hatchery brood stocks in Idaho is an effective strategy to supplement existing populations of chinook salmon within local or adjacent subbasins. Corollary:  Rejection of H03a indicates that development of new supplementation brood stocks for supplementation within the local or adjacent subbasin is needed.

H03b:	Development of new, local brood stocks with a known natural component for supplementation does not provide an advantage over using existing hatchery brood stocks for supplementation within the local or adjacent subbasin.  Corollary: Rejection of H03b indicates that development of new supplementation brood stocks from the target populations can be more successful for supplementation than using existing brood stocks.

H03c:	The effect of supplementation on natural production and productivity does not differ among life stages (parr, presmolt, smolt) of hatchery fish released.  Corollary: Rejecting H03c indicates which supplementation release strategies (life stages) are most effective (or least deleterious) in rebuilding natural populations.

Tasks:

A thorough programmatic explanation of the experimental design and methods for analysis is provided in Salmon Supplementation Studies in Idaho Rivers (ISS)—Experimental Design (Leitzinger and Bowles 1991).  Nineteen treatment and twelve control streams in both the Clearwater and Salmon basins have been divided among four resource management entities for implementation.  Each cooperator is responsible for the activities on their respective streams.  The U.S. Fish and Wildlife Service is responsible for ISS project activities in Clear Creek and Pete King Creek, both in the Clearwater drainage.

The methods are not described by objective or task here since all tasks must be completed in synchrony to test the research hypotheses, and each objective may test more than one hypothesis.  All tasks listed below must be performed annually to successfully evaluate the production and productivity response variables and to meet the project objectives.  The production and productivity response variables measured by performing these tasks are described later in this section.  The basic annual tasks to be performed by the U.S. Fish and Wildlife Service on Clear Creek and Pete King Creek are as follows.

Objective 1.	Monitor and evaluate the effects of supplementation on presmolt and smolt numbers and spawning escapements of naturally produced salmon.

Task 1.a	Continue to use “standardized” spawning, rearing, marking, and release protocols for supplementation programs.

Task 1.b	Differentially mark all hatchery supplementation and general production fish released in or nearby the study streams.

Task 1.c	PIT-tag 750 general hatchery production, and 750 supplementation fish prior to release for estimating

survival.

Task 1.d	Release various life stages of chinook salmon; smolts on Clear Creek and parr on Pete King Creek.

Task 1.e 	Estimate late summer parr densities.

Task 1.f	PIT tag a minimum of 500 to 700 naturally produced juveniles from Clear Creek and Pete King Creek to estimate survival.

Task 1.g	Use existing weir on Clear Creek to collect, PIT tag, and enumerate emigrating fish and to identify and enumerate returning adults.

Task 1.h	Count returning adults using existing weir on Clear Creek, and use redd walks and carcass surveys on Clear and Pete King creeks

Objective 2.	Monitor and evaluate changes in natural productivity and genetic composition of target and adjacent populations following supplementation.

Task 2.a	Collect and enumerate juvenile chinook.

Task 2.b 	Collect tissue samples for DNA analysis.

Task 2.c	Monitor straying of hatchery and supplementation adults with weirs, carcass surveys, and radio telemetry.

Task 2.d	Predict population viability based on spawner to recruitment relationship to determine if the population will maintain itself through time in the absence of additional supplementation.

Objective 3. 	Determine which supplementation strategies (brood stock and release stage) provide the quickest and highest response in natural production without adverse effects on productivity.

Task 3.a	Monitor natural production (count number of presmolt, smolt, and adults) and productivity (survival, life stage characteristics, straying, genetic composition) of supplemented populations.

Task 3.b	Spawn local brood stocks with known natural component from the target population during the second generation of supplementation (differentiation of natural and hatchery returns possible through fin clips).

Task 3.c	Compare natural production and productivity between first generation and second generation.

Methods- general: Description of experimental design and statistical analysis.

Although interrelated, the design is split into three main approaches.  The first and main level of evaluation is large-scale population production and productivity studies designed to provide relatively generic inferences statewide.  The second level utilizes these same study streams as individual "case histories" to evaluate specific supplementation programs (e.g. supplementation from Sawtooth Hatchery into the upper Salmon River).  This is essentially a default scenario in case the statistical power for spatial inferences is too weak.  The third level represents small-scale studies designed to evaluate specific hypotheses.  The first two levels will focus on measuring population responses to supplementation and identifying critical life history intervals where supplementation effects are evident.  The third level will help determine the mechanisms and specific impacts of supplementation on these critical life history intervals.

Long Term Studies

The overall measure of success for supplementation is the relative increase in natural production as compared to the relative loss or maintenance of existing natural productivity.  Multi-generation (10-15 years) studies designed to monitor and evaluate these large-scale population responses are necessary to adequately measure the success of supplementation programs.  Limited research opportunities (e.g. potential treatment and control streams) and unacceptable risks preclude application of this approach throughout most of the Columbia River basin.  This “big picture” approach to supplementation evaluation is ideally suited to Idaho because of the relative availability of treatment and control streams in grossly underseeded habitats.  A major emphasis of this research will be to monitor and evaluate these population responses to supplementation.  In addition, focusing research on existing supplementation programs reduces the potential risks associated with supplementation research.

Our long-term studies are split into two main categories: supplementation-augmentation of existing natural populations and supplementation-restoration of extirpated populations.  Supplementation (augmentation) research activities will be limited predominantly to streams with existing populations located in the Salmon River drainage.  A primary research emphasis will be to determine effects of supplementation on these natural populations.  Our approach will evaluate supplementation with smolts from existing subbasin hatchery/natural stocks for one generation, followed by supplementation with smolts from locally developed brood stocks with a high composition of natural fish.  Restoration efforts will be evaluated predominantly in the Clearwater River drainage where existing natural populations are scarce.  Research will determine relative success of rebuilding natural populations through outplanting parr (fingerling), acclimated presmolts, and smolts.

Small Scale Studies

"Small scale" studies were designed to address specific hypotheses concerning the mechanisms of supplementation effects (e.g. competition, dispersal and behavior).  These studies are relatively short-term and will be conducted in laboratory streams or "controlled" field environments.  They were developed to provide valuable information without requiring large resource commitments.

Although we have identified several areas of critical uncertainty, these studies will remain flexible to respond to feedback from the long-term studies.  Potential research includes: 1) evaluation of juvenile performance and survival of progeny from various ratios of hatchery: natural spawners, 2) identification of random vs. selective mortality events associated with natural incubation and rearing environments, 3) effects of releasing larger hatchery fry and parr on top of smaller natural fish, 4) dispersal and interactions associated with multiple vs. single release sites, 5) effects of hatchery releases on resident fish, and vice versa, 6) overwinter habitat selection and carrying capacity for hatchery-reared and natural presmolts, 7) emigration survival for volitional vs. forced releases of presmolts and smolts, and 8) effects of steelhead smolt releases and residualism on natural chinook survival and performance.  The following discussion on the experimental design pertains to the long-term supplementation/restoration objectives (first and second approaches).

Statistical Design

This research will utilize a repeated measures profile analysis (split-plot through time) statistical design to evaluate supplementation effects (Johnson and Wichern 1982).  This multivariate design uses parametric statistics and thus requires that normality, homogeneity of variance and independence assumptions be met.  Strengths of this design include utilization of the "synchrony" of treatment and control streams to factor out variability associated with broad ranging environmental and system effects in order to enhance precision and power of detecting treatment effects.  A weakness of this design is that it does not handle a phased implementation of treatments over time very well.  Utilization of a "staircase" design (Walters et al. 1988) would allow for a phased approach, but the inability to adapt to missing data points (years) once the treatment has been implemented makes this option undesirable.

Our basic design tests the response of populations to treatments (supplemented) over time as compared to controls (unsupplemented) and baseline data.

Treatments. Treatment (e.g. supplementation in general, supplementation with a particular life stage, supplementation with a particular brood source) effects will be tested directly by hypotheses.  In general, treatments will be applied for one to two generations (5-10 years) following approximately one generation of pretreatment data.  Population responses to supplementation will be monitored a minimum of one generation (5 years) following supplementation.

The experimental units are the study streams themselves.  We will use eight treatment streams in the Salmon River and 11 treatment streams in the Clearwater River to test objectives one, two, and three.  Treatment streams were selected on the basis of agency management plans, habitat suitability, stock status and history, and supplementation risk.  Although limited research opportunities precluded complete randomization of study streams and treatments, "biological" independence has been maximized.

Blocks. To help partition variability, some of our hypotheses utilize a block design under the assumption that variability of treatment effects within blocks will be less than variability among blocks.  Depending on the hypothesis, the blocks may include: status of existing population, brood source, life stage outplanted and stream productivity.

Controls. The primary purpose of our control streams is to help “control” population responses unrelated to treatments (e.g. trends and variability of passage, ocean survival, harvest, etc.).  We will use eight control streams (experimental units) in the Salmon River and four in the Clearwater River to test hypotheses for objectives one, two, and three.  Wherever possible, control streams were selected to be representative of treatment streams (e.g. similar habitat, location, etc.) and independent of treatment effects (e.g. straying, changes in production, changes in productivity).

Replication. Spatial and temporal replication is necessary to maximize the applicability of our research to long-term regional and Statewide needs.  Temporal replication (one to two generations) in our design is adequate to provide descriptive inferences concerning site-specific (case history) findings.

Spatial replication is much more tenuous in our design because of limited research opportunities constrained by agency management plans, scarcity of streams with viable natural populations, and limited supplementation facilities.  In spite of these constraints, we have maintained 4-11 spatial replicates to test each hypothesis, which should provide adequate power for spatial inferences within our sampling realm (see following section on power analysis).

Because of the aforementioned constraints, true randomization of our treatment and control streams was not possible.  We do not feel this imposes serious statistical interdependence because the design incorporates spatial interspersion, and allocations were determined by factors assumed predominantly independent of potential treatment effects.  This in itself does not preclude the possibility of pseudoreplication (i.e. replicates not independent) occurring in our design (Hurlbert 1984).  Assumptions of independence must be carefully qualified prior to using inferential statistics if pseudoreplication exists.

Power Analysis. Existing databases on two of our evaluation points (parr density and redd counts) were used to predict the power and sensitivity of our experimental design.  These Monte-Carlo type computer simulations incorporated 10-15 years of data on 16 streams to provide estimates of temporal (annual) and spatial (statewide) variability following imposed supplementation effects of 25%, 50%, and 100% on natural production.  Lognormal transformations were used to account for the expected negative binomial distributions and unequal variances.  A univariate split-plot in time repeated measures design was used to approximate the multivariate design for "a priori" power analysis.

The majority of within-stream, among-year variation is contributed by large-scale environmental and system effects (e.g. flows, passage, etc.) so the use of control streams keeps this large source of variation from masking true treatment effects.  We also have relatively large among-stream, within-year variation.  Some of this variation will be removed by analyzing data as a function of carrying capacity, relative stream productivity, and parental adult escapement.  Much of this variability will be largely uncontrolled and represents the spatial diversity we wish to make inferences across.  Within-stream, within-year variation is mainly controlled by the intensity of our sampling design.  Based on the previous results of intensive stream surveys, we anticipate our design will control this source of variation to approximately a 15% coefficient of variation (SEM/M).

Although “a priori” power analysis is rarely used in fisheries research (Peterman 1990), we believe this design provides good power for inferences compared to other field biological studies (Lichatowich and Cramer 1979).  Analysis of trend redd count data indicates that for inferences within our sampling realm, our design should provide at least a 75% chance of detecting a 25% change (alpha=0.05, beta=0.25) in fish numbers following supplementation of 11 treatment streams.  This analysis utilized density, escapement and log transformations, and represents substantial improvement in power over analysis of the raw data (less than 33% chance of detecting a 25% change in fish numbers).

Reducing sample size (number of treatment streams) can potentially impair the sensitivity of the design.  Reducing to five treatment streams provides only a 60% chance of detecting a 25% change in production, whereas we would still have over 95% chance of detecting a 50% change.  Use of only three treatment streams reduces power to approximately a 50% chance of detecting a 25% change in production but still over 85% chance of detecting a 50% change in production.

It is difficult to make an “a priori” assessment of power associated with the parr density evaluation point.  Existing databases represent predominantly trend data that does not necessarily incorporate standardized or thorough sampling designs.  Our analysis of these trend databases indicated at least 60% chance of detecting a 50% change in natural production following supplementation of eight streams.  This should be viewed as a minimum estimation of power.  We anticipate actual power will be much higher because our design will quantify and effectively remove several major sources of variation not accounted for in the trend databases.  For example, parr sample location with respect to redds and preferred rearing habitat is a major source of variation for trend data, which often uses few (<6) sample sites per stream.  Parental spawning escapement is another major source of variability among streams.

Our design will stratify sampling to help partition variability associated with habitat type, habitat quality and stream productivity.  The design can also incorporate cohort analysis to account for variability associated with parental spawning escapement levels.  In addition, parr sampling sites have been increased from typically less than six to over 36 in our study streams.

Methods-specific:  Description of proposed treatments, methods, and evaluation.

Population responses to supplementation will be monitored for a minimum of one generation (5 years) following supplementation.  The experimental units are the study streams themselves. Final evaluation is ideally dependent on the response of adult escapements to treatments; several interim evaluation points will be useful in indicating initial population responses and test specific hypotheses.   The production response variables that we are monitoring include:

Mid-summer parr- 1992-1997 counts of summer parr using snorkeling have resulted in imprecise estimates.  Additional effors (e.g. snorkeling a larger percentage of each stream) would be needed to increase this precision, which is not feasible given the numerous other study tasks.  Thus, snorkel counts have been temporarily dropped from the study design, but will be added in FY 2002 if more precise techniques are developed.  A minimum of 500-700 summer parr will be PIT-tagged on each study stream.  The tagged parr will be used to estimate survival to Lower Granite Dam.

Fall and spring emigrants (presmolt and smolt)- Juvenile emigration numbers and timing are estimated with out migrant (rotary screw) traps.  Traps are operated to sample the fall and spring emigration period until icing or water velocity is prohibitive.  Capture efficiency is estimated by recapture of marked emigrants transported above traps.  Capture efficiencies are monitored as a function of stream flow and water temperature.  The USFWS-IFRO will operate a screw trap on Clear Creek.

Smolt production- Survival of smolts reaching Lower Granite Dam will be estimated based on fish PIT tagged as parr, presmolts, and smolts.  Survival of PIT-tagged hatchery smolts to Lower Granite Dam will be compared to naturally produced smolts.  Minimum survival estimates of smolts reaching Lower Granite is estimated for all treatment and control streams.  Approximately 700 juveniles are PIT tagged prior to or during emigration from the study streams and hatcheries.  A similar number of hatchery fish are PIT tagged prior to release into treatment streams.

Adult escapement- Escapement to Clear Creek is determined using an adult weir located near the mouth at the Kooskia NFH.  Aerial and ground redd counts are used to estimate adult escapement.  Potential egg deposition is estimated from fecundity of females taken into the hatchery nearest each study stream.

In addition to the above production response variables, we are evaluating the following productivity response variables:

Survival - Natural production estimates for the production response evaluation points will be used to estimate survival relationships for up to eight life stage intervals. Redd (egg)-to-parr, parr-to-smolt (at Lower Granite Pool), smolt-to-redd, and redd-to-redd survival rates will be estimated for all treatment and control populations.  The survival relationships will be estimated as a function of fish numbers or density.

In-hatchery survival relationships will be monitored for egg-to-fry, fry-to-fall pre-smolt, and fall presmolt-to-release intervals.  These survival rates will be measured as a function of density but are assumed to be predominately limited by density independent factors up to the hatchery capacities.

Fecundity - Fecundity schedules, by age and length, will be as measured from hatchery and natural fish collected for each supplementation brood stock and pooled across years within generations.  Supplementation effects will be measured as trends in these fecundity schedules.  Fecundity will not be monitored directly for populations in control streams.

Age structure - Age-of-return for adult male and female chinook will be determined from scales and coded-wire tags recovered from carcasses surveyed in natural spawning areas and from adults returning to weirs.

Spawning distribution - Temporal and spatial distribution of spawning will be monitored in all treatment and control streams.  Run timing will be quantified directly for streams with weirs and qualitatively for study streams without weirs.  Spatial distribution of spawning will be monitored by peak redd counts (ground or aerial) conducted throughout the entire study stream.

Spawning ratio - The spawning ratio will be monitored for all treatment streams.  The ratio will be determined by counting marked (supplementation) verses unmarked (natural) adult returns at weirs followed by ground carcass surveys to estimate egg retention and pre-spawning mortality.  This information will be analyzed directly or as a covariate to indicate spawning success and progeny survival associated with various proportions of hatchery and natural spawners.

Emigration timing - Emigration timing will be monitored for study streams with weirs and juvenile traps.  This information will be used to indicate shifts in the proportion of fall and spring emigrants, and the temporal distribution of emigration within each season.

Genetic composition - Genetic structure and variability will be monitored for natural and hatchery populations associated with our research.  Allelic frequencies will be monitored through starch gel electrophoresis.  All inferences from genetic data will incorporate other ecological (i.e. life history, health, behavior, abundance) and environmental (i.e. carrying capacity, temperature, flows, habitat) data. This information will provide a valuable tool to assess supplementation risk and track potential genetic impacts of supplementation on long-term population fitness.

Limiting Factors: We assume that main stem passage and flow will allow for net replacement or increase in adult-to-adult production.  Our efforts will be negated without improvements in main stem passage and acceptable water flows.

Potential risks to target and non-target species:

The risks associated with ISS were evaluated under the 1991 draft RASP criteria. ISS treatment streams already have on-going hatchery programs.  Consequently, ISS hatchery protocol should pose minimal ecological risk, if any, to the chinook salmon populations in these streams.  Risks are primarily associated with not conducting ISS, and failing to identify and implement the best recovery measures resulting in the continued decline or extinction of the population and adversely impacting wild\natural populations through the use of inappropriate supplementation due to lack of information.  The use of out-migrant traps and adult weirs impose a limited risk to individual animals in term of direct mortality and migration alteration.

g. Facilities and equipment

Brood stock collection and juvenile production of chinook salmon for supplementation of treatment streams uses existing hatcheries in Idaho.  Treatments do not require additional production, but are coordinated and consistent forms of ongoing hatchery production.  Costs associated with production of supplementation fish are covered under individual hatchery budgets.

The USFWS-IFRO operates out of the Dworshak Fisheries Complex in Ahsahka, Idaho. We rely on existing hatchery personnel and facilities at both Kooskia and Dworshak National Fish Hatcheries for transportation, spawning and rearing of supplementation fish.  We use approximately 30 radio transmitters per year, a combination of new and used, two fixed-site radio telemetry stations, and one manual radio telemetry receiver.  Crews from the USFWS-Vancouver FRO are hired to ventral fin clip supplementation fish.  Juvenile trapping is accomplished with the use of one rotary screw trap, minnow traps, backpack electrofishing gear, and hook-and-line fishing techniques.  We have one PIT-tag station that is shared by the Dworshak Fisheries Complex.  We use standardized PIT-tag protocol when tagging juveniles.  We have two desktop computers and one laptop computer.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Bams, R.A. 1976. Results of a pink salmon transplant using males native to the recipient stream. Fisheries and Marine Service Technical Report No. 642. |  |
| Chilcote, M.W. , S.A. Leider, and J.J. Loch. 1986. Differential Reproductive success of hatchery and wild summer-run steelhead under natural conditions. Transactions of the American Fisheries Society 115:726-735. |  |
| Columbia Basin Fish and Wildlife Authority.1990. Integrated system plan for salmon and steelhead production in the Columbia River Basin. Public Review Draft. Prepared for Northwest Power Planning Council, Portland, Oregon. |  |
| Currens, K.P., C.A. Busack, G.K. Meffe, D.P. Philipp, E.P. Pister, F.M. Utter, and S.P. Yundt. 1991 (MS). A hierarchical approach to conservation genetics and production of anadromous salmonids in the Columbia River Basin. Product of the 1990 Sustainability Workshop. Northwest Power Planning Council, Portland, Oregon. |  |
| Franklin, I.R. 1980. Evolutionary change in small populations. Pages 135-149 in M.E. Soule’ and B.A. Wilcox (eds.) Conservation Biology; and evolutionary-ecological perspective. Sinauer Associates, Sunderland, Massachusetts. |  |
| Gebhards, S.V. 1959. The effects of irrigation on the natural production of Chinook salmon (Oncorhynchus tshawtscha) in the Lemhi River, Idaho. Master’s Thesis, Uitah State University, Logan, Utah. |  |
| Herrig, D.M. 1990. A review of the Lower Snake River Compensation Plan hatchery program. U.S. Fish and Wildlife Service, Lower Snake River Compensation Plan Office, Boise, Idaho. |  |
| Hurlbert, S.H. 1984. Pseudoreplication and the design of ecological field experiments. Ecological Monographs 54(2): 187-211. |  |
| Idaho Department of Fish and Game 1985. Anadromous fisheries management plan, 1986-1990. Boise, Idaho. |  |
| Idaho Department of Fish and Game 1991. Anadromous fisheries management plan, 1991-1995. Boise, Idaho. |  |
| Johnson, R.A., and D.W. Wichern. 1982. Applied Multivariate Statistical Analysis. Prentice-Hall, Inc., Englewood Cliffs, New Jersey. |  |
| Kapucinski, A.R., C.R. Steward, M.L. Goodman, C.C. Krueger, J.H. Williamson, E.C. Bowles, and R. Charmichael. 1991 (MS). Genetic conservation guidelines for salmon and steelhead supplementation. Production of the 1990 Sustainability Workshop, Northwest Power Planning Council, Portland, Oregon. |  |
| Kennedy, G.J.A., and C.D. Strange. 1986. The effects of intra- and interspecific competition on the survival and growth of stocked juvenile Altantic salmon, Salmo salar L., and resident trout, Salmo trutta L., in an upland stream. Journal of Fish Biology 28:479-490. |  |
| Kijima, A., and Y. Fujio. 1984. Relationship between average heterozygosity and river population size in chum salmon. Bull. Jpn. Soc. Sci. Fish. 50:603-608. |  |
| Lichatowich, J. and S. Cramer. 1979. Parameter selection and sample sizes in studies of anadromous salmonids. Oregon Department of Fish and Wildlife Information Report series, Fisheries Number 80-1, Portland Oregon. |  |
| Miller, W.H., T.C. Coley, H.L. Burge, and T.T. Kisanuki. 1990. Analysis of salmon and steelhead supplementation: emphasis on unpublished reports and present programs. Part 1 in W.H. Miller (ed.). Analysis of salmon and steelhead supplementation, Parts 1-3. Technical Report 88-100, Bonneville Power Administration, U.S. Department of Energy, Portland, Oregon. |  |
| Nez Perce Tribe of Idaho and Idaho Department of Fish and Game. 1990. Clearwater River sub-basin salmon and steelhead production plan. Prepared for Northwest Power Planning Council, Portland, Oregon. |  |
| Nickelson, T.E., M.F. Solazzi, and S.L. Johnson. 1986. Use of hatchery coho salmon (Oncorhynchus kisutch) presmolts to rebuild wild populations in Oregon coastal streams. Canadian Journal of Fisheries and Aquatic Sciences 43(12): 2443-2449. |  |
| Northwest Power Planning Council (NPPC). 1987. Columbia River Basin Fish and Wildlife Program. Portland, Oregon. |  |
| Northwest Power Planning Council (NPPC). 1994. Columbia River Basin Fish and Wildlife Program. Portland, Oregon. |  |
| Peterman, R.M. 1990. Statistical power analysis can improve fisheries research and management. Canadian Journal of Fisheries and Aquatic Sciences. 47:2-15. |  |
| Petrosky, C.E. and T.C. Bjornn. 1988. Response of wild rainbows (Salmo gairdneri) and cutthroat trout (S. clarki) to stocked rainbow trout in fertile and infertile streams. Caadian Journal of Fisheries and Aquatic Sciences 45(12): 2087-2105. |  |
| Regional Assessment of Supplementation Project (RASP). 1991. Draft status report for review and comment. Prepared for Bonneville Power Administration PJSP, Portland, Oregon. |  |
| Reisenbichler, R.R. 1981. Columbia River salmonid broodstock management – annual progress report (unpublished). National Fishery Research Center, U.S. Fish and Wildlife Service, Seattle, Washington. |  |
| Reisenbichler, R.R. 1984. Outplanting: potential for harmful genetic change in naturally spawning salmonids. Pages 33-39 in J.M. Walton, and D.B. Houston (eds.). Proceedings of the Soviet-American symposium on aquaculture. National Fisheries Research Center, Seattle, Washington. |  |
| Reisenbichler, R.R. 1988. Relation between distance transferred from natal stream and recovery rate for hatchery coho salmon. North American Journal of Fisheries Management 8:172-174. |  |
| Reisenbichler, R.R. and J.D. McIntyre. 1977. Genetic differences in growth and survival of juvenile hatchery and wild steelhead trout, Salmo gairdnrei. Journal of the Fisheries Research Board of Canada 34:123-128. |  |
| Reisenbichler, R.R. and J.D. McIntyre. 1986. Requirements for integrating natural and artificial production of anadromous salmonids in the Pacific Northwest. Pages 365-374 in R.H. Stroud (ed.) Fish Culture in Fisheries Management. American Fisheries Society, Bethesda, Maryland. |  |
| Smith, E.M., and B.A. Miller, J.D. Rodgers, and M.A. Buckman. 1985. Outplanting anadromous salmonids- a literature survey. Bonneville Power Administration, U.S. Department of Energy, Project 85-68, Portland, Oregon. |  |
| Snow, H.E. 1974. Effects of stocking northern pike in Murphy’s Flowage. Wisconsin Department of Natural Resources Technical Bulletin 79, Madison. |  |
| Steward, C.R., and T.C. Bjornn. 1990. Supplementation of salmon and steelhead stocks with hatchery fish: a synthesis of published literature. Part 2 in W.H. Miller (ed.). Analysis of salmon and steelhead supplementation, Parts 1-3. Technical Report 88-100, Bonneville Power Administration, U.S. Department of Energy, Portland, Oregon. |  |
| Supplementation Technical Work Group (STWG). 1988. Supplementation research- proposed five-year work plan. Northwest Power Planning Council, Portland, Oregon. |  |
| Verspoor, E. 1988. Reduced genetic variability in first-generation hatchery populations of Atlantic salmon (Salmo salar). Canadian Journal of Fisheries and Aquatic Sciences 45:1686-1690. |  |
| Vincent E.R. 1985. Effects of stocking catchable trout on wild trout populations. Pages 88-91 in W. King (ed.). Proceedings of the wild trout management symposium. Trout Unlimited. |  |
| Vincent E.R. 1987. Effects of stocking catchable-sized hatchery rainbow trout on two wild trout species in the Madison River and O’Dell Creek, Montana. North American Journal of Fisheries Management 7:91-105. |  |
| Walters, C.J., J.S. Collie, and T. Webb. 1988 Experimental designs for estimating transient responses to management disturbances. Canadian Journal of Fisheries and Aquatic Sciences 45:530-538. |  |
| ISS Project Reports |  |
| Bowles, E. and E. Leitzinger, 1991. Salmon Supplementation Studies in Idaho Rivers. Experimental Design to the U.S. Department of Energy, Bonneville Power Administration. Project No. 89-098. Contract No. DE-B179-89BP01466. (www.efw.bpa.gov/cgi-bin/ws.exe/webcql.dir/FW/PUBLICATIONS/QueryPublications.pl) |  |
| Idaho Department of Fish and Game. 2001. Salmon Supplementation Studies in Idaho Rivers- Five year summary report. Prepared for Bonneville Power Administration, U.S. Department of Energy, Portland, Oregon. |  |
| Peery, C.A., and T.C. Bjornn. 1996. Small-scale investigations into chinook salmon supplementation strategies and techniques: 1992-1994. Technical Reports 96-3 ICFWRU, University of Idaho. IDFG and BPA, Portland, Oregon. |  |
| IDFG Reports |  |
| Leitzinger, E.J., K. Plaster, P. Hassemer, and P. Sankovich. 1996. Idaho supplementation studies annual progress report 1993. Idaho Department of Fish and Game annual report to U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Leitzinger, E.J., K. Plaster, and E. Bowles. 1993. Idaho supplementation studies annual report 1991-1992. Fisheries Research Section, Idaho Department of Fish and Game annual report to U.S. Department of Energy-Bonneville Power Administration, Portland, Oregon. |  |
| Nemeth, D., K. Plaster, K. Apperson, J. Brostrom, T. Curet, and E. Brown. 1996. Idaho supplementation studies annual report 1994. Idaho Department of Fish and Game annual report to U.S. Department of Energy-Bonneville Power Administration, Portland, Oregon. |  |
| Nez Perce Reports |  |
| Arnsberg, B.D. 1993. Salmon Supplementation Studies in Idaho Rivers. Annual work summary for 1992. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Hansen, J.M. and J. Lochart. 2001. Draft. Salmon Supplementation Studies in Idaho Rivers. Annual Report 1997 (Brood Years 1995 and 1996). Nez Perce Tribe report to U.S. Department of Energy- Bonneville Power Administration, Portland, Oregon. |  |
| Hesse, J.A., and B.D. Arnsberg. 1994. Salmon Supplementation Studies in Idaho Rivers. Annual Report- 1993. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Hesse, J.A., P.J. Cleary, and B.D. Arnsberg. 1995. Salmon Supplementation Studies in Idaho Rivers. Annual Report-1994. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Lochart, J., T. Tabor, and J.A. Hesse. 2001 Draft. Salmon Supplementation Studies in Idaho Rivers. Annual Report 1998 (Brood Years 1997). Nez Perce Tribe report to U.S. Department of Energy - Bonneville Power Administration, Portland, Oregon. |  |
| Shoshone-Bannock Reports |  |
| Keith, R.M., M. Rowe, C.A. Reighn, J.Honena, and T. Trahant. 1996. Salmon Supplementation Studies in Idaho Rivers-Annual Report 1995. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| USFWS Reports |  |
| Rockhold, E.A., R.B. Roseberg, and J.M. Olson. 1997. Idaho Supplementation Studies Pete King and Clear creeks progress report 1991-1993. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Olson, J.M., and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek 1997 progress report. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |
| Olson, J.M., and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek progress report for field activities 1998-2000. U.S. Department of Energy-Bonneville Power Administration. Portland, Oregon. |  |

# Section 10 of 10. Key personnel

# (See attached resumes)

# Project Manager:	Michael P. Faler, Assistant Project Leader (IFRO),

GS-12. 240hrs.

Project Duties:	Provide technical supervision and guidance for ISS project. Assist in field activities as needed.     Supervise and assist in preparation of progress reports, and proposals. Attend project coordination meetings.

Qualifications:	Twenty years experience in fishery biology (research and management), with seventeen of those in the Columbia River Basin. His primary emphasis has been in Chinook salmon, steelhead, and bull trout.

_______________________________________________________________________

Field Investigator:	Jill M. Olson, Fisheries Biologist, GS-9.   1,120hrs.

Project Duties:	Coordinate and lead field activities and data collection.  Oversee PIT-tag operations, data base management, brood stock selection, and spawning. Participate in ISS cooperator meetings, prepare budget estimates, work statements, and progress reports. Represent the ISS- Clear and Pete King creeks study in hatchery evaluation team, and interagency coordination meetings.

Qualifications:	Ten years of experience in collecting field data on anadromous fish including redd walks, fish collection, trap operations, snorkel surveys, habitat surveys, PIT tagging.

________________________________________________________________________

Field Investigator:	Justin K. Bretz, Fishery Biologist, GS-7. 1,000 hrs.

Project Duties:	Assist in field activities, data collection, and data entry. Conduct day-to-day PIT tagging, radio tracking, and trap operations.

Qualifications:	Five years of experience in collecting field data on anadromous fish. Experience includes radio telemetry, creel census, PIT tagging, operation of traps, electrofishing.

Micheal P. Faler

EDUCATION

Master of Science—South Dakota State University	1988

Major:	Fisheries Sciences	Brookings, South Dakota

Bachelor of Science—Western Kentucky University	1981

Major:	Biology		Minor:	     Chemistry	Bowling Green, Kentucky

EMPLOYMENT

Supervisory Fishery Biologist	1996-Present

U.S. Fish and Wildlife Service	Ahsahka, Idaho

First line supervisor of two biologists and one biological technician.  Assist with redd surveys, juvenile enumeration, and spawning and rearing activities associated with spring chinook salmon studies in the Clearwater River, Idaho.  Participate in the technical advisory team for bull trout recovery the Clearwater Basin as established for implementation of Idaho’s (Governor Batt’s) bull trout conservation plan.  Primary investigator in the preparation of the status, distribution, and threat analysis of bull trout in the Snake River Basin, as part of the 1997 ESA listing team and development of the final rule.

Fishery Biologist	1994-1996

U.S. Forest Service	Vancouver, Washington

Provided program oversight and development to habitat inventory, evaluation, and restoration projects.  Provided technical assistance to biologists in the development of smolt production estimates.  Initiated and coordinated steelhead recovery efforts in the Wind River, Washington, and was primary investigator of a bull trout radio-tracking study in the Lewis River, Washington.

Fishery Biologist	1988-1994

U.S. Forest Service	Carson, Washington

South Zone program manager for fisheries and hydrology resources on the Gifford Pinchot National Forest.  I directly supervised the activities of 2 biologists, 1 hydrologist, and 1 technician.  Worked cooperatively with other agencies and private parties in developing habitat evaluation and restoration projects for fisheries and aquatic resources.  Participated in and supervised participation in several interdisciplinary teams established to prepare NEPA documents for evaluating the environmental effects of proposed actions on Federal Lands.

Fishery Biologist	1986-1988

U.S. Fish and Wildlife Service	Vancouver, Washington

Supervised two biologists and a laborer in an off-site pen rearing program of upriver bright fall chinook salmon in Columbia River backwaters.

Fishery Biologist	1983-1986

U.S. Fish and Wildlife Service-Research	Cook, Washington

Primary investigator in radio-tracking study of walleye and northern squawfish in the John Day Pool.  The project was part of a predation study on juvenile salmonids, and was used to help determine seasonal “closure” of population segments for the enumeration of predators in the reservoir and tailrace.

EXPERTISE—I have worked over fifteen years as both a research and management fishery biologist in the Columbia River Basin.  The primary emphasis has been in chinook salmon, steelhead, and bull trout migratory behavior (adult and juvenile), habitat use, and limiting factors.  I have broad knowledge and expertise in data management and writing skills, in addition to certifications in open water SCUBA diving and electrofishing through the Fisheries Academy.

SELECTED REPORTS

Faler, M.P.  1995.  An Evaluation Using a Mark-Recapture Population Estimator as a Monitoring Tool for an Adfluvial Bull Trout Population.  Aqua-Talk (R-6 Fish Habitat Relationship Technical Bulletin), Number 9, August, 1995.

Faler, M.P. and T.B. Bair.  1991.  Migration and Distribution of Adfluvial Bull Trout in Swift Reservoir, North Fork Lewis River and Tributaries.  1991 Challenge Cost Share Report, USDA-Forest Service, Carson, WA.

Faler, M.P., L.M. Miller and K.I. Welke.  1988.  Effects of Variation in Flow on Distributions of Northern Sqauwfish in the Columbia River below McNary Dam.  North American Journal of Fisheries Management, 8:30-35, 1988.

Jill M. Olson

EDUCATION

Bachelor of Science— College of Idaho	1985

Major:	Zoology		Caldwell, Idaho

EMPLOYMENT

Fishery Biologist 	1995-Present

U.S. Fish and Wildlife Service	Ahsahka, Idaho

Took over as lead biologist for Supplementation Studies in Idaho Rivers (ISS) in October 1997.  Responsible for collection of brood stock, transportation, spawning and rearing of  ISS adults and progeny for ISS project.  Implement radio-telemetry study on adult spring chinook salmon for monitoring movement and spawning activities.  Provide logistical support such as scheduling, hiring of personnel and training of field staff.   Lead field crews in the completion of snorkel and habitat surveys, operation of rotary screw traps, electro fishing, PIT tagging, redd/adult spawner surveys on Pete King and Clear creeks.  Create, validate, submit and interrogate PIT tagging files using personal computers and PTAGIS software.  Attend and participate in ISS coordination meetings.  Preparation of the Clear and Pete King creeks progress report.  Prepare work plans, annual budget projections, quarterly and annual progress reports.  I am also involved in the coded-wire tag (CWT) data recovery and management activities including collection of biological data on hatchery rack returns, spawning records of both spring chinook salmon and summer steelhead trout, maintaining historical CWT information.  I am member of both the Kooskia and Dworshak Hatchery Evaluation Team (HET).

Biological Science Technician (Fisheries)	1993-1995

U.S. Fish and wildlife service	ahsahka, idaho

Assist in parr monitoring activities such as snorkel and habitat surveys for ISS projects on Clear and Pete King creeks.  Assist lead biologist in collection and PIT tagging of juvenile spring chinook salmon using out migrant traps and electro fishing equipment.  Conduct redd and spawner surveys.  Assist in the preparation of annual activity reports.  Assist in the capture of adults and the rearing of summer steelhead trout for the ISS- Performance/Stock Productivity Impacts of Hatchery Supplementation study , project leader Reg Reisenbichler NBS.

Biological Science Technician (Fisheries)	1992

U.S. Forest Service    -  intermountain research station	boise, idaho

Lead fish habitat inventory crews in data collection for the development of “Desired Future Condition” values for anadromous streams in Idaho and Utah.

EXPERTISE

I have worked over 14 years in leading field crews in data collection for use in management of  both fisheries and wildlife resources.  For the past six years my work has focused specifically on anadromous fisheries of the Columbia River Basin, both the Salmon River and Clearwater River subbasins.  I have skill in hatchery operations such as spawning and rearing techniques, as well as a broad knowledge of fisheries research and management.  I have specific training in cryopreservation of salmonid sperm.   I hold certificates in radio-telemetry and electro fishing techniques from the U.S. Fish and Wildlife Service National Conservation Training Center.

SELECTED REPORTS

Rockhold, E. Anne, R.B. Roseberg, and J.M. Olson. 1997.   Idaho Supplementation Studies- Pete King and Clear Creeks Progress Report: January 1, 1991 to December 31, 1993.  Bonneville Power Administration. Portland, Oregon.  DE-A179-92BP49446.

Olson, J.M. and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek 1997 progress report. U.S. Department of Energy - Bonneville Power Administration. Portland, Oregon.

Olson, J.M. and J. K. Bretz. 2001. Idaho Supplementation Studies: Clear Creek and Pete King Creek  progress report for field activities 1998-2000. U.S. Department of Energy - Bonneville Power Administration. Portland, Oregon.

Justin K. Bretz

# EDUCATION

Bachelor of Science-University of Idaho    1998	Major: Fisheries Resource Management       Moscow, Idaho

# EMPLOYMENT

# Fisheries Biologist  								      	1999-Present

U.S. Fish and Wildlife Service, Ahsahka, Idaho

Responsible for collection of fisheries related field data for the Idaho Supplementation Study.  Duties include operation and maintenance of rotary screwtrap; PIT tagging of captured fish; radio telemetry of adult spring chinook salmon; conducting snorkel surveys; electrofishing; spawning ground surveys; angling; developing databases, graphs, and charts; assisting in adult broodstock selection and spawning of adult spring chinook salmon. I assist Dworshak National Fish Hatchery in spawning of adult spring chinook salmon, coho salmon, fall chinook salmon, and summer steelhead.  I assist other project leaders in conduction of boat electrofishing; backpack electrofishing; radio telemetry; coded-wire-tag recovery and retention; PIT tagging; beach seining; and jet-boat operation and maintenance.

Fisheries Technician                            						1998-1999

Idaho Department of Fish and Game, Lewiston, Idaho

I was responsible for conducting angler creel surveys.  This included identification, enumeration and length of catch, and time spent angling.  With this information I conducted length-frequency analysis of harvested fish and determined catch-per-unit effort.  I conducted research on migratory habits of summer steelhead in the Selway River, Idaho.  This project included developing radio telemetry system to determine usage of fish passage facility, and aerial telemetry to determine migration and distribution of adult steelhead within the watershed.  I developed a database for this information.  I assisted the lead biologist in utilizing fyke-nets and boat electrofishing to capture black crappie and largemouth bass for exchange program with Washington Department of Fish and Wildlife, and restocking of these species in area lowland lakes.

Fisheries Technician    							       1997-1998 (seasonal)

University of Idaho, Moscow, Idaho

I assisted in research on juvenile fall chinook salmon in the Hell’s Canyon portion of the Snake River, Idaho.  My duties included beach seining, jet-boat operation and maintenance, fish culture, PIT tagging, fish transport, operation of the Diversion-by-Code equipment at Little Goose Dam for recapture of PIT tagged juvenile fall chinook salmon, and maintenance of field sampling equipment.

Wildfire Crew-Leader  	 							1994-1996

Clearwater-Potlatch Timber Protective Association, Orofino, Idaho

I was responsible for leading wildfire crews on training, and suppression of wildfires.  Training involved operation of suppression equipment such as hand tools, pumps and hoses, chainsaws, helicopter insertion (helitack), aerial fire suppression (helicopter bucket-drops, fixed-wing retardant), and heavy equipment (fire engines, and bulldozers), and assessment of situations regarding fire-safety, and fire behavior.

# CERTIFICATIONS

I have completed the following certification courses:

-Snorkel Surveys-Idaho Department of Fish and Game, 1999

-Spawning Ground Surveys –Idaho Department of Fish and Game, 2000

-Motorboat Operators Certification-U.S Department of the Interior, 2000

-PADI Open-water Dive Certification, 1994

-Electrofishing Theory Certification, U.S. Fish and Wildlife Service, 2000