Project ID:	(199204000)

Title:	(Redfish Lake Sockeye Salmon Captive Broodstock Rearing and Research)

# Section 9 of 10. Project description

a. Abstract

The National Marine Fisheries Service (NMFS), in partnership with Idaho Department of Fish and Game (IDFG) has been maintaining US Endangered Species Act (ESA) listed Snake River sockeye salmon (Oncorhynchus nerka) from Redfish Lake, Idaho, in a captive broodstock program since 1992.  Captive broodstocks are a form of artificial propagation where fish are cultured in captivity for most or all of their life cycle.  These programs provide a safety net to prevent populations from going extinct.  Captive broodstock programs generate much higher egg-to-spawner survival (usually > 50%) than occurs in nature (usually < 1.0 %).  This higher survival of captive broodstock salmon enables them to produce many more adults, eyed eggs, fry, and smolts per generation than wild fish.  This larger number of progeny per generation is being used by the program to "jumpstart" the restoration of ESA-listed endangered Redfish Lake sockeye salmon.

In the Salmon Subbasin Summary (SSS), federal, state, and tribal agencies repeatedly call for artificial production programs, like the Redfish Lake sockeye salmon captive broodstock program, to meet goals and objectives (for confirmation see SSS, Section 5.2).  The use of artificial production programs (e.g., captive broodstocks) for salmon stocks deemed at risk of extinction is also identified as Fisheries Needs number 14 and 15 in the SSS summary.  The continuation of current programs, such as the Redfish Lake sockeye salmon captive broodstock program, is also a required reasonable and prudent action (item 177) in the NMFS 2000 FCRPS Biological Opinion.  In addition, the implementation and refinement of captive broodstocks for the recovery of Snake River sockeye salmon have been identified as priorities in the 1994 NWPPC Columbia Basin Fish and Wildlife Program (7.4A.1-3), are part of the overarching and regional objectives of the 2000 NWPPC Columbia Basin Fish and Wildlife Program, and are priorities described in the NMFS proposed Recovery Plan for Snake River salmon.

The original sources of NMFS captive broodstocks are juvenile and adult fish captured, held, and spawned by the Idaho Department of Fish and Game (IDFG).  The fish are reared to adulthood in fresh well water, or from smolt to adult in a pumped, filtered, and UV-sterilized seawater system.  NMFS has spawned Redfish Lake sockeye salmon captive broodstock yearly since 1994.  Fry to adult survival has ranged from 14-84% and currently averages over 50%.  Eyed-egg viability has averaged about 60%.  The NMFS captive broodstock program has produced over 840,000 viable eggs for use in recovery efforts.

Since 1994, captive broodstock progeny have been returned to Idaho as prespawning adults, eyed eggs, fry, and smolts for release in recovery efforts.  These releases helped produce the return of 7 and 257 anadromous sockeye salmon to the Salmon River Basin lakes in 1999 and 2000, respectively.  The 2000 return alone was 16 times greater than the number of naturally produced adults (n = 16) returning to the lakes in the decade of the 1990’s.  Over the next funding cycle, NMFS proposes to continue these same captive broodstock efforts that have helped prevent Redfish Lake sockeye salmon from becoming extinct.

b. Technical and/or scientific background

The Redfish Lake captive broodstock program is a safety net program producing fish for restoration of anadromous sockeye salmon runs to the Snake River Basin.  In December 1991, NMFS listed Snake River sockeye salmon (Oncorhynchus nerka) as endangered under ESA (Waples et al. 1991).  Snake River sockeye salmon are a prime example of a species on the threshold of extinction.  The last known remnants of this stock return to Redfish Lake, Idaho.  In 1991 and 1992 combined, only four adult anadromous sockeye salmon returned to Redfish Lake.  On the basis of these critically low population numbers, NMFS, in cooperation with IDFG, the Bonneville Power Administration (BPA), the Shoshone-Bannock Tribe, and others, implemented a captive broodstock project as an emergency measure to save Redfish Lake sockeye salmon from extinction (Flagg 1993; Johnson 1993; Spaulding 1993; Flagg and McAuley 1994; Flagg et al. 1994; Kline 1994; Teuscher et al. 1994; Flagg et al. 1995; Johnson and Pravecek 1995, 1996; Kline and Younk 1995; Teuscher et al. 1995; Flagg et al. 1996; Teuscher and Taki 1996; Kline and Lamansky 1997; Pravecek and Johnson 1997; Taki and Mikkelsen 1997; Flagg et al. 1998; Flagg et al. 2001).  The Redfish Lake project is intended as an emergency gene rescue program that can be used to produce large numbers of juvenile fish for restoring anadromous sockeye salmon runs to the Snake River.

The ESA mandates that listed population segments be restored to self sustaining populations in their natural ecosystems.  It recognizes that conservation of listed species may be facilitated by artificial means, such as captive broodstock programs, while factors impeding population recovery are rectified (Hard et al. 1992).  Frequently, restoration of severely depleted populations will be hindered for lack of suitable numbers of juveniles for effective supplementation (i.e., release of hatchery-propagated fish to increase natural production), even if factors impeding recovery could be corrected (Flagg et al. 1995a).  For restoration of these populations to occur in a timely fashion, the full reproductive potential of Pacific salmon must be harnessed in the short-term to produce large numbers of juveniles.  Often the only reasonable avenue to build populations quickly enough to avoid extinction is through captive broodstock technology (Flagg and Mahnken 1995).

Captive propagation of animals to maximize their survival and reproductive potential has won acceptance in endangered species restoration (Gipps 1991, Johnson and Jensen 1991, DeBlieu 1993, Olney et al. 1994, Flagg and Mahnken 1995).  These efforts range from establishment of free-roaming breeding colonies on localized preserves to full-term captive rearing (Gipps 1991, Johnson and Jensen 1991, DeBlieu 1993, Olney et al. 1994, Flagg et al. 1995b).  Full-term rearing of captive broodstocks maximizes potential production of juveniles for enhancement.  The relatively short generation time of Pacific salmon and their potential to produce large numbers of offspring make them suitable for captive broodstock rearing.  Survival advantages offered through protective culture can be significant.  Theoretically, survival of fish reared in protective captive broodstock culture can exceed wild survival by 100-to-1,000 fold (Flagg et al. 1995b).  The substantial survival advantage for captive-reared fish provides potential to produce large numbers of juveniles to amplify the natural population during the second generation.

Even though captive broodstock theory is promising, artificial propagation and captive broodstock technologies are not without risks.  There is limited data regarding the effects of broodstock manipulations (e.g., sourcing, mating, rearing, feeding, and release strategies) on the health, physiology, or genetic stability of the population, or, most importantly, on reproductive performance (Flagg and Mahnken 1995).  The potential hazards of using captive culture (inbreeding, genetic drift, domestication, selection, behavioral conditioning, and exposure to disease) and the negative interactions of hatchery and wild fish have been well documented (Hynes et al. 1981, Krueger et al. 1981, Kincaid 1983, Allendorf and Ryman 1987, Kapuscinski and Jacobsen 1987, Waples 1991).  However, waiting for restoration of natural production is often a more dangerous risk because the entire population is threatened.  The continued decline in population size risks additional loss of genetic variability and possible extinction of the population (Kincaid 1993).

Two captive broodstock approaches are being applied to salmon recovery in the Pacific Northwest.  One strategy involves capturing wild prespawning adults, fertilized eggs, or juveniles from their native habitats and rearing the populations to maturity in hatcheries.  The first or second generation offspring are then stocked into ancestral lakes or streams at one or more juvenile life stages (e.g., fry, parr, smolt).  Another strategy involves rearing the broodstock in captivity to adulthood, then releasing the adults back into their natal habitats to spawn naturally.  Both strategies require extended culture to adulthood.

Captive broodstock survival to adulthood can vary from low to high.  Past broodstock survivals have ranged from 0% to 90% (Flagg et al. 1995b).  The major disease problem noted in most salmonid captive broodstock programs has been bacterial kidney disease, caused by Renibacterium salmoninarum.  Disease problems can be reduced considerably when fish are cultured in water with low concentrations of pathogens (e.g., fresh well water or filtered and sterilized seawater) rather than in seawater net-pens (Flagg et al. 1995b).  Using optimum culture techniques (e.g., pathogen free water and low density culture), fishery managers can currently anticipate survivals of 50-80% in captive broodstocks (Schiewe et al. 1997).

The dramatic difference between the natural environments experienced by wild Pacific salmon and the artificial environments experienced by captively reared fish appears to create a number of differences in their relative reproductive potential.  In general, captively reared Pacific salmon appear less reproductively fit than their wild cohorts (Berejikian et al. 1997, 2000).  The size and age of maturity of captively reared adults are generally less than wild cohorts (Flagg et al. 1995b, Schiewe et al. 1997).  Part of this size discrepancy can be attributed to early maturity of captively reared fish.  Even in cases where age at maturity of captively reared fish mimics wild fish, fish size is generally 20-50% less than wild stock (Flagg et al. 1995b, Schiewe et al. 1997).  Average viability of eggs from captively reared spawners (30-70%) is also commonly lower than the 75-95% viability of similar strains of hatchery-spawned wild fish (Flagg et al. 1995b, Schiewe et al. 1997).

The reasons for the generally poorer reproductive performance of artificially propagated captively reared fish compared to ocean ranched and wild cohorts are not well understood.  Most captive broodstock programs use spawners collected from the wild population.  Therefore, it seems intuitive that much of the poor performance, at least in first-generation offspring, can be attributed to the effects of the artificial culture environments.  However, the effects of genetic change in the captively reared populations as a basis for reduced spawner size, egg viability, and reproductive behavior remains a possibility.  Ongoing research efforts to refine captive broodstock technology have and should continue to provide methodologies to improve broodstock performance in the future.

Salmonid captive broodstock technology, although still in its initial development stages, appears sufficiently advanced to allow carefully planned programs to proceed.  Viability of captively reared spawners may be less than wild fish.  Nevertheless, captive broodstock programs have the potential to provide the amplification necessary to both reduce extinction risk and begin recovery measures for depleted stocks.  In the case of Redfish Lake sockeye salmon, the NMFS captive broodstock efforts for this endangered species (BPA Project 9204000) have already resulted in over 840,000 progeny returned to Idaho for use in recovery efforts.  It is clear that captive broodstocks cannot be a substitute for restoring fish in the habitat.  However, it appears unrealistic to rely solely on habitat improvements and harvest restrictions to effect recovery, especially when populations have reached critically low numbers.  For severely depleted populations, captive broodstocks are often the only method to rebuild numbers quickly enough to reduce inbreeding or avoid extinction.

c. Rationale and significance to Regional Programs

The use of captive broodstock fish to restore anadromous runs of Snake River sockeye salmon is an action required to reach many of the objectives of the Salmon Subbasin Summary (SSS) and the 2000 NWPPC Columbia Basin Fish and Wildlife Program.  In addition, safety net captive broodstocks are among the Reasonable and Prudent Alternative (RPA) actions called for in the 2000 NMFS Biological Opinion, and are an ESA mandated item in the NMFS Recovery Plan for Snake River Salmon (Schmitten et al. 1995, 4.1a and 4.1b).

Artificial production programs, such as the captive broodstocks for salmon stocks deemed at risk of extinction, are identified as a Fisheries Need under items 14 and 15 of Section 5.4.2 of the SSS.  The need for propagation programs such as captive broodstock safety nets are also referred to in many other areas of the SSS.  Following is a list derived from the SSS (Section 5.2) demonstrating common goals and objectives shared by federal, state, and tribal agencies that relate to the Redfish Lake sockeye salmon captive broodstock program.

- BPA

- Objective 1 - Avoid jeopardy and assist in meeting recovery standards for Columbia Basin Salmon…that are affected by the FCRPS.

- Hatchery Strategy 2 - Use a safety net program on an interim basis to avoid extincition while other recovery actions take place for sturgeon and anadromous fish.

- Hatchery Strategy 3 - Use hatcheries in a variety of ways and places to aid recovery.

- NMFS

- The goal of NMFS in the Salmon subbasin is to achieve the recovery of Snake River spring/summer and fall chinook, sockeye, and steelhead resources.

- Tribes

- Goal 1 - Restore anadromous fish in rivers and streams at levels to support the historical, cultural, and economic practices of the tribes.

- Management Objective 15 - Develop conservation hatcheries for supplementation of ESA listed fish populations.

- Artificial Production Objective 2 - Prevent further decline of salmon, steelhead and other species stocks through the use of artificial propagation.

- Artificial Production Objective 3 - Begin to reestablish runs of salmon, steelhead, and other species that are no longer present in the Salmon subbasin.

- State of Idaho, General

- Goal 1 - Preserve, protect, perpetuate, and manage Idaho’s 5000+ fish and wildlife species as steward of public resources.

- Objective 1 - Minimize the number of Idaho species identified as threatened or endangered under the provisions of the Endangered Species Act of 1973, as amended.

- State of Idaho, Fisheries Bureau

- Goal 2 - To preserve Idaho’s rare fishes to allow for future management options.

- Strategy 3 - Assist in recovery of rare species through captive rearing projects, supplementation, and protection.

- State, Statewide Fisheries Management

- Idaho’s overall goal is to restore and maintain wild native populations and habitats of resident and anadromous fish to preserve genetic integrity, ensure species and population viability, and provide sport fishing and aesthetic benefits.

- Objective 4 - Maintain genetic integrity of wild native stocks of fish and naturally managed fish when using hatchery supplementation.

- State of Idaho, Anadromous Fisheries Management

- Idaho’s overall anadromous fisheries goal is to recover wild Snake River salmon and steelhead populations and restore productive salmon and steelhead fisheries.

- Objective 1 - Maintain genetic and life history diversity and integrity of both naturally- and hatchery-produced fish.

- Strategy 4 - Establish facilities for captive culture of salmon and steelhead populations likely to become extirpated in the near-term future.

- Strategy 6 - Establish captive populations for stocks or populations likely to become extinct in the near-term future.

- Objective 2 - Rebuild naturally reproducing populations of anadromous fish to utilize existing and potential habitat at an optimal level.

- Strategy 1 - Use appropriate and proven supplementation techniques to restore and rebuild populations outside of wild production refugia.

- Strategy 4 - Implement proven hatchery intervention where necessary and ecologically prudent to provide a safety net for selected populations at risk.

The Redfish Lake Sockeye Salmon Captive Broodstock Rearing and Research Project (199294000) not only meets the SSS goals, objectives, and needs, but is specifically identified as an ongoing BPA-funded conservation action (Section 4.6.1).

The Project’s primary objective of recovering sockeye salmon runs in the Snake River directly meets the NWPPC 2000 Fish and Wildlife program’s overarching objective of “recovery of fish and wildlife affected by the development and operation of the hydrosystem that are listed under the Endangered Species Act”.  The captive broodstock project’s restoration efforts are a critical activity for attaining the NWPPC 2000 Fish and Wildlife Program regional objectives of: 1) “Halt declining trends in salmon and steelhead populations above Bonneville Dam by 2005…”, 2) “Restore the widest possible set of healthy naturally reproducing populations of salmon and steelhead in each relevant province by 2012, and 3)  “Increase total adult salmon and steelhead runs above Bonneville Dam by 2025 to an average of 5 million annually in a manner that supports tribal and nontribal harvest.  Within 100 years achieve population characteristics that, while fluctuating due to natural variability, represent on average full mitigation for losses of anadromous fish.”

The NWPPC 2000 Fish and Wildlife Program’s primary artificial production strategy of using artificial production “under the proper conditions, to 1) complement habitat improvements by supplementing native fish populations up to the sustainable carrying capacity of the habitat with fish that are as similar as possible, in genetics and behavior, to wild native fish, …” also calls for restoration activities like those conducted in the Redfish Lake Captive Broodstock Rearing and Research Project.  In addition to conforming with the current Program, the project is part of the priority guidelines for implementation and refinement of captive broodstocks for the recovery of Snake River sockeye salmon identified in the earlier 1994 NWPPC Columbia Basin Fish and Wildlife Program (CBFWP 1994, 7.5A.1-3).

The Redfish Lake project was initially designed to fulfill the needs of the NMFS proposed Recovery Plan for Snake River salmon (Schmitten et al. 1995, 4.1a and 4.1c).  Currently, maintenance of an ESA-listed captive broodstock that can be used to restore anadromous sockeye salmon to the Snake River is a NMFS identified safety net program meeting the needs of RPA action item 177 identified in Section 9.6.4.3 of the 2000 NMFS FCRPS Biological Opinion.

In summary, the recovery of Snake River sockeye salmon has been a major goal of federal, state, and tribal agencies since their listing as endangered under the ESA.  For restoration to occur in a timely fashion, the full reproductive potential of the remaining population must be harnessed to produce large numbers of juveniles in the shortest period of time.  Captive broodstock technology not only provides the only safety net for this population segment, but is also the only reasonable avenue to restore the population within our lifetime.  The Redfish Lake Captive Broodstock Rearing and Research program should continue to produce hundreds of adults and hundreds of thousands of eggs each year for supplementation releases into historic habitats.  Thus, barring environmental or other catastrophes, this project should help stabilize runs of anadromous of sockeye salmon to the Snake River Basin.

d. Relationships to other projects

The NMFS Redfish Lake sockeye salmon captive broodstocks (BPA Project 199204000) are complementary to those reared by IDFG (BPA Project 199107200) and are intended to reduce the risk of catastrophic loss of this valuable gene pool.  The program interconnections are multifaceted.  In addition to population amplification through the NMFS and IDFG captive broodstock programs, necessary habitat improvements are being undertaken by the Shoshone-Bannock Tribe (BPA Project 199107100), and genetic monitoring is being conducted by the University of Idaho (BPA Project 199009300).  Research to refine captive broodstock technology (BPA Project 199305600) should help improve broodstock performance and maximize their contribution to recovery goals.  In upcoming years, the interconnection of these programs should help provide hundreds of adults and hundreds of thousands of eggs for use in recovery efforts in Idaho.

NMFS is coordinating captive broodstock rearing activities for Redfish Lake sockeye salmon through the BPA chaired Stanley Basin Sockeye Technical Oversight Committee (SBSTOC).  Membership on the committee includes representatives from NMFS, IDFG, BPA, the Shoshone-Bannock Tribe, other state and federal agencies, and private groups interested in sockeye salmon restoration in Idaho.

e. Project history (for ongoing projects)

a).  Project numbers - BPA Project 9204000 (unchanged)

b).  Adaptive management implications: For severely depleted populations, captive broodstocks will often be the only method to rebuild numbers quickly enough to avoid extinction.

c.  Project reports and technical papers:

Flagg, T. A.  1993.  Redfish Lake sockeye salmon captive broodstock project, p. 3-5.  NMFS NWFSC Quarterly Report, October-December 1993.

Flagg, T. A.  1993.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1992.  Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 16 p.

Flagg, T. A., K. A. Johnson, and J. C. Gislason.  1994.  Redfish Lake sockeye salmon broodstock programs.  In Proceedings of the 1993 Alaska Department of Fish and Game Sockeye Culture Workshop, Cooper Landing, Alaska, 10 p.

Flagg, T. A. and W. C. McAuley.  1994.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1993.  Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 99 p.

Flagg, T. A. and W. C. McAuley.  1995.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from December 1991 through December 1994 under ESA Section 10, Propagation Permit 795, 22 p.

Flagg, T. A., C. V. W. Mahnken, and K. A. Johnson.  1995.  Captive broodstocks for recovery of depleted populations of Pacific salmon.  Amer. Fish. Soc. Symp. 15:81-90

Flagg, T. A., K. A. Johnson, C. V. W. Mahnken, J. Bauer, and J. C. Gislason.  1995.  Captive broodstock technology and its application to Redfish Lake sockeye salmon, p. 9.  Proceedings of the Role of Captive Breeding/Artificial Propagation in the Restoration of Endangered Species workshop, Newport, OR.  (Abstract).

Flagg, T. A. and W. C. McAuley.  1996.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from December 1994 through December 1995 under ESA Section 10, Propagation Permit 795, 17 p.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, and C. V. W. Mahnken.  1996.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1994.  Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 98 p.

Flagg, T. A. and W. C. McAuley.  1997.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from December 1995 through December 1996 under ESA Section 10, Propagation Permit 795, 35 p.

Flagg, T. A. and W. C. McAuley.  1998.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from January through December 1997 under ESA Section 10, Propagation Permit 1005, 22 p.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, C. V. W. Mahnken, and J. C. Gislason.  1998.  Redfish Lake Sockeye Salmon Captive Broodstock Program, NMFS, p.  In R. Z. Smith (editor), Proceedings of the 48th Annual Northwest Fish Culture Conference, Dec. 2-4, 1997, Gleneden Beach, Oregon.

Flagg, T. A., W. C. McAuley, and W. T. Fairgrieve.  1999.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from January through December 1998 under ESA Section 10, Propagation Permit 1148, 27 p.

Flagg, T. A. and C. V. W. Mahnken.  2000.  Endangered species recovery:  captive broodstocks to aid recovery of endangered salmon stocks, p. 290-292.  Encyclopedia of Aquaculture, J. Wiley and Sons, New York.

Flagg, T. A., W.C. McAuley, D. A. Frost, M. R. Wastel, W. T. Fairgrieve, and C. V. W. Mahnken.  2001.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1995-2000.  Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 66 p.

Frost, D. A., W. C. McAuley, D. J. Maynard, and T. A. Flagg.  2001.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from January through December 2000 under ESA Section 10, Propagation Permit 1148, 21 p.

McAuley, W. C., D. A. Frost, and T. A. Flagg.  2000.  NMFS Northwest Fisheries Science Center report to NMFS Office of Protected Resources for captive broodstock rearing of Redfish Lake sockeye salmon from January through December 1999 under ESA Section 10, Propagation Permit 1148, 31 p.

Schiewe, M. H., T. A. Flagg, and B. A. Berejikian.  1997.  The use of captive broodstocks for gene conservation of salmon in the western United States.  Bull. Natl. Res. Inst. Aquacult., Suppl. 3:29-34.

- Years underway:  Nine since 1992.

- Summary of major results achieved: The Redfish Lake captive broodstock project has been underway since 1992.  The NMFS captive broodstocks are complementary to those reared by IDFG and are intended to reduce the risk of catastrophic loss of this valuable gene pool.  The sources of NMFS captive broodstocks are wild juvenile and adult fish captured, held, and spawned by IDFG between 1992 and 1998.  During this period, only 16 sockeye salmon adults (0 to 8 individuals per year) returned to Redfish Lake.  IDFG divided the gametes from these fish with NMFS on an approximate 50:50 basis.  NMFS has maintained F1 lineages for the 1991-, 1993-, 1994-, and 1996-broods produced from returning female anadromous fish (only males returned in 1992 and 1998, no fish returned in 1995 and 1997).  In addition, a few fish from each of these broods have been kept full-term through F2, and now F3, generations to establish safety nets that can be used in poor survival years.  The captive broodstock fish are reared either full term to adult in fresh well water or from smolt to adult in a pumped, filtered, and UV-sterilized seawater system.  Fry to adult survival has ranged from 14 to 84% and currently averages over 50%.  Eyed-egg viability has averaged about 60%.  Pre-spawning adults, eyed eggs, and juveniles are returned to Idaho to aid recovery efforts.

NMFS has produced a total of about 840,000 eyed eggs that have been returned to Idaho for use in recovery programs (Table 1).  In addition, NMFS has returned 181 prespawning adults to Idaho for direct release into Stanley Basin lakes.  The overall production from the NMFS program equates to a direct amplification of about 165 times the about 5,000 total seed stock received from Idaho.  Importantly, these amplification numbers are thousands of times the numbers that would have been produced had the 16 wild fish returning in the decade of the 1990s been left to reproduce naturally. The current relatively high juvenile survival of broods in protective culture should result in continued production of up to 100-200,000 eggs yearly.

Table 1.  History of NMFS eyed egg production from Redfish lake sockeye salmon captive broodstocks.

| Year | Number of eyed eggs |
| --- | --- |
| 1994 | 48,000 |
| 1995 | 0 |
| 1996 | 412,000 |
| 1997 | 168,100 |
| 1998 | 47,500 |
| 1999 | 65,400 |
| 2000 | 96,700 |

The release (by IDFG) of captive broodstock progeny from Projects 199204000 and 199107200 back into Snake River Basin lakes began in 1994 with the fall release of 14,119 yearling presmolts.  In 1995, almost than 95,000 juveniles were released back into Stanley Basin lakes.  The first planting of eyed eggs (105,000) occurred in 1996 along with the release of about 14,000 juvenile-to-smolt stage fish.  The number of eyed eggs (105,767) and juveniles (256,411) released into the lakes peaked in 1997.  In 1998, over 140,000 juveniles and 81,000 smolts were released to restore anadromous salmon runs to the Snake River Basin.  In 1999, about 20,000 eyed eggs, and 50,000 juvenile-to-smolt stage fish were released.  In 2000, more than 50,000 eyed eggs and 72,000 juveniles were released.  In addition to these egg and juvenile plants, the captive broodstock programs have generated releases of up to 120 prespawning adults per year into the lakes.

Initially, the Redfish Lake captive broodstock projects concentrated on building the captive population as a safety net to maintain the gene pool.  However, the program is now producing significant numbers of captive broodstock progeny that are being released to restore anadromous sockeye salmon runs to the Snake River Basin.  These releases returned 7 anadromous adults in 1999 and 257 in 2000 to Snake River Basin lakes.  The vast majority of these returning adults were produced by the release of smolts from the NMFS program that were reared at Oregon Department of Fish and Wildlife (ODFW) Bonneville Hatchery.  These returns clearly demonstrate that the captive broodstock project is succeeding both as a safety net and as a tool to restore anadromous salmon runs.  It is virtually certain that without the boost provided by these captive broodstocks, Redfish Lake sockeye salmon would have become extinct.

f.  Past costs:  FY 1992 - $552,900; FY 1993 - $425,700; FY 1994 - $460,000; FY 1995 - $459,300;  FY 1996 - $496,000; FY 1997 - $499,000; FY 1998 - $500,000; FY 1999 - $499,500, FY 2000 - $517,500, FY 2001 – $549,800.

f. Proposal objectives, tasks and methods

Objective 1: Rear safety net captive broodstock for ESA-listed sockeye salmon from Redfish Lake, Idaho.

Time Element:  Ongoing (Will continue through at least September 2005)

Testable Hypothesis:  None – non-research component.

Products:  1) Safety net rearing of Redfish Lake sockeye salmon to help prevent extinction of this ESA-listed population; (2) Annual progress reports to BPA.

Task a:  Maintain anadromous Redfish Lake sockeye salmon in a safety net captive broodstock program.

Method:  NMFS obtained lots of about 300-1,000 fertilized eggs from anadromous adults returning to Redfish Lake from IDFG for the safety net captive broodstock program from 1991 to 1996.  In addition, during the early 1990s similar lots of eggs from outmigrating smolts captured, reared, and spawned by IDFG were incorporated into the program.  Currently, lots of about 300-500 eggs from select second and third generation captive broodstock lineages and from ocean returns of captive broodstock releases are incorporated into the program annually.  NMFS currently rears an annual total of about 2,000 fish from all lineages and year classes.

All NMFS captive broodstock fish are currently being reared either in circular tanks supplied with fresh well water at the NMFS leased Burley Creek Hatchery (BCH) near Burley, Washington or in circular tanks supplied with filtered and ultraviolet light (UV) treated seawater at the NMFS Manchester Research Station near Manchester, Washington.  NMFS provides daily staffing at both facilities for protective culture of these fish, with constant electronic security and facilities monitoring.  Staffing during some weekends and holidays may be covered by drop-in site inspections.

The fish are reared using standard fish culture practices and approved therapeutics (for an overview of standard methods see Piper et al. 1982, Leitritz and Lewis 1976, Rinne et al. 1986, Pennell and Barton 1996, and FRED 1983).  Rearing density is maintained below 8 kg/m3 (0.5 lbs/ft3) for most of the rearing cycle; however, fish density may range up to 15 kg/m3 (1.0 lbs/ft3) at maturity.  Fish are reared on a commercial (e.g., Biodiet) grower ration until they approach maturation age when they are switched to a commercial brood diet.   Swimup fry are started with hand feeding in 1.8-m diameter circular tanks.  When the fish are large enough to be PIT tagged they are transferred to 3.6-m diameter circular tanks where their diet is rationed by automated feeders.  Every effort is made to maintain the fish on low levels of natural lighting following the natural photoperiod.  In order to minimize the impact of handling stress, these ESA listed fish are not routinely sampled.  This results in only end point data, such as maturation age, size, fecundity, survival, and the primary cause of death being routinely collected.  Occasionally each tank is subsampled to assess fish size for determining proper feed size and ration.

The captive broodstock fish are typically reared to maturity at both freshwater and marine facilities.  In summer and fall, fish culturists at the Manchester seawater rearing facility conduct maturation checks on fish in all groups suspected of having ripening adults.  All maturing fish in the marine tanks at Manchester are moved to freshwater facilities for final maturation.  Most maturing fish are held until they are ripe at which time females are killed, their eggs stripped and fertilized using fresh or cryopreserved sperm (see Objective 2 for details).

Fish health is checked daily by observing feeding response, external condition, and behavior as initial indicators of developing problems.  A fish pathologist routinely monitors captive broodstock mortalities to determine cause of death.  When a treatable pathogen is either detected or suspected, a veterinarian prescribes appropriate prophylactic and therapeutic drugs to control the problem.  Select mortalities are appropriately preserved for pathology, genetic, and other analyses.  Specimens that are not vital to analysis are disposed of in a manner consistent with the Project’s ESA permit.  All spawners are analyzed for common bacterial and viral pathogens, e.g., bacterial kidney disease, infectious hematopoietic necrosis virus, etc.

The NMFS obtains all required permits for interstate transport of eggs, fish, and progeny.  The NMFS coordinates its captive broodstock rearing protocols and activities through the SBSTOC.

Task b:  Secure a long term facility for the freshwater culture phase of Redfish Lake sockeye salmon captive broodstock.

The NMFS captive broodstocks complement those reared by IDFG (BPA Project 9107200) and are intended to reduce the risk of catastrophic loss of this valuable gene pool.  Rearing these captive broodstocks at two facilities separated by a wide geographic distance is a key bet-hedging strategy to protect this ESA listed population from catastrophic loss resulting from natural disasters, disease epidemics, or massive mechanical failure at either site.  Historically, NMFS conducted the freshwater rearing component at the University of Washington’s Big Beef Creek Research Station.  However, mounting costs, falling water production, and the University’s preference for research over offsite salmon restoration projects resulted in NMFS moving the Redfish Lake sockeye salmon captive broodstock program to the Burley Creek Hatchery owned by Fish Pro Farms, a private vendor.  While NMFS has a yearly lease for this facility that is theoretically extendable to 2010, either party can break the lease with less than 2 months notice.  Loss of this site would result in the NMFS program having no freshwater facilities to rear fish, no freshwater facility for final maturation holding, and no freshwater facility to incubate eggs for transfer to Idaho or Oregon hatcheries.  Not only does NMFS have no other freshwater rearing facility that it could move fish to, but the fish in NMFS portion of the program would also exceed IDFG’s captive broodstock rearing capacity.  Thus, loss of the leased site would constitute considerable jeopardy for the NMFS captive broodstocks.  Therefore, it seems prudent to request BPA to purchase the Fish Pro Farms hatchery site.

The Burley Creek Hatchery is located within 20 minutes travel time of the Manchester Research Station.  The site has 500 gpm of pathogen free well water available for fish rearing that meets current drinking water quality standards.  The site has a building that contains eleven 12’ circular tanks, fourteen 6’ circular tanks, an array of isobucket incubation troughs, a 12’ x 20’ office, a 20’ by 20’ wetlab-spawning area, and 20’ by 20’ shop area.  The facility has two separate wells and pumps to ensure water flow in the event one well or pump fails.  In addition, the facility is equipped with an UV treatment system for effluent water to meet fish health transfer permit standards.  The facility also is equipped with a backup power generator that produces sufficient power to operate the pumps and the UV system during utility supplied power interruptions.  In addition, to reducing jeopardy on the ESA listed Redfish Lake Sockeye Salmon, purchase of the site would ultimately be more economical for the project.

The purchase of this (or if deemed more cost effective, another similar Western Washington) freshwater rearing facility will significantly reduce the jeopardy to the ESA listed fish by ensuring NMFS can continue to mature and spawn adults and incubate eggs to the eyed stage for restoration of salmon to the Snake River Basin.  It is anticipated that in coming years this facility will play a crucial role in producing the eyed eggs and fish necessary for restoring viable runs of sockeye salmon to Redfish Lake in the next decade.

Objective 2: Restore anadromous runs of sockeye salmon to Snake River Basin lakes.

Time Element: Ongoing (Will continue through at least September 2005)

Testable Hypothesis: None – non-reseach component

Products: (1) Hundreds of adults and hundreds of thousands of eggs for recovery efforts for ESA-listed Redfish Lake sockeye salmon; (2) Annual progress reports to BPA.

Task a:  Provide pre-spawning adults, eyed eggs, and juveniles to aid recovery of this ESA-listed stock in Idaho

This production component focuses on using the captive broodstock reared under Objective 1, Task a to generate fish for release into the Stanley Basin lake watersheds (e.g., Redfish, Alturas, Pettit Lakes) at different life history stages (prespawning adults, eyed eggs, fry, and smolts) to help restore ESA-listed endangered Snake River sockeye salmon.  Each year, as the fish in the NMFS captive broodstocks begin to reach maturity, some will be selected for transfer to Idaho for release as prespawning adults.  The remainder of the maturing fish will be maintained until they ripen and are spawned.  All spawning will follow mating protocols prepared by NMFS genetics staff.  Fertilized eggs from each mating will be disinfected in iodophore and reared in isobuckets until ready for transfer as eyed eggs or ponding as swimup fry.  Current production targets are for production of 200-250 prespawning adults for release in Idaho each year and captive spawning of enough adults to produce 100-150,000 eyed eggs annually.

All spawners will be appropriately sampled to obtain transfer permits required to move their progeny across fish health management zones.  The progeny of these spawners will be incubated to the eyed egg stage at Burley Creek Hatchery.  Many of the fish will be transferred to Idaho as eyed eggs for use by IDFG in egg and juvenile releases to historic habitats.  In addition to these transfers, up to 100,000 eyed eggs from the combined IDFG and NMFS captive broodstock projects will be shipped to ODFW’s Bonneville Hatchery where they will be reared to smolt for release.  NMFS will coordinate the rearing and release of these smolts (see Objective 3 for details).  NMFS will obtain appropriate health certifications and permits for interstate transport of adults, eggs, and smolts.  NMFS will coordinate all its transfers with the other agencies and tribes involved in Snake River sockeye salmon recovery through the SBSTOC.  The release of these captive broodstock groups into Snake River Basin lakes is expected to help restore a viable run of anadromous sockeye salmon to the area.

Objective 3: Determine the effectiveness of smolt releases for restoring anadromous runs of Snake River sockeye salmon.

Time Element: Ongoing (Will continue through at least September 2005)

Testable Hypotheses:

Experimental Question:  Release of which life history stage produces the greatest survival from the age of release to the time of anadromous adult return?

- H0:  All release life history stages produce similar survival to the anadromous adult return stage.

- H1:  Egg releases produce the greatest survival to the anadromous adult return stage.

- H2:  Presmolt releases produce the greatest survival to the anadromous adult stage.

- H3:  Smolt releases produce the greatest survival to the anadromous adult stage.

Products:  1) Determination of the effectiveness of smolt releases to restore ESA-listed Redfish Lake sockeye salmon to their native habitat; 2) Annual progress reports to BPA.

Task a:  Evaluate the release to adult survival of sockeye salmon smolts released from the captive broodstock program back into the Snake River system.

IDFG is evaluating the effectiveness of egg-to-adult stage releases back into Stanley Basin habitats under Project 199107200.  Concurrently, NMFS is coordinating outplanting of smolts reared at the ODFW Bonneville Hatchery from eggs supplied by IDFG and NMFS to Stanley Basin watersheds (see Objective 2).  Current available data suggests smolt releases may have the best potential for rapidly restoring viable runs of anadromous sockeye salmon to the Salmon River Basin.  To fully evaluate this strategy, prior to release all fish will be coded wire tagged and fin clipped as appropriate and a subsample PIT tagged.  Relative survival rates of released fish will be quantified and compared with data from IDFG studies on prespawning adult, eyed egg, and presmolt releases.

The information provided by this task will be used in an adaptive manner to determine the best release strategy for rebuilding Idaho’s ESA-listed endangered Snake River anadromous sockeye salmon runs.  Contingency table analysis will be used to statistically compare the relative survival of fish from the different release types.  It is anticipated that the finding of these studies will assist captive broodstock programs in determining the best way to release fish for rapidly recovering ESA-listed salmon stocks.

Objective 4:  Implement best protocols for rearing anadromous sockeye salmon in captive broodstock programs.

Time Element: Ongoing (Will continue through at least September 2005)

Testable Hypotheses:

Question:  Do endangered Redfish Lake sockeye salmon grown to maturity in an experimental treatment (e.g., enhanced brood diet) have better growth, survival, and reproductive success than fish grown in the standard control treatment (e.g., standard brood diet)?  Note - this is a directional question that uses one-tail distributions for statistical analysis.

- H0:  no difference.

- Ha:  the fish in experimental treatments perform better than control treatment.

Products: 1) Determination of best captive broodstock culture practices for producing the greatest quantity and highest quality fish for restoration of ESA-listed Snake River sockeye salmon; 2) Annual progress reports to BPA.

Task a:  Compare alternate rearing protocols.

Captive rearing programs for ESA-listed species try to utilize the best-known rearing practices.  However, as captive broodstock technology is still relatively poorly developed, there is little guidance available beyond that known for traditional ocean ranched fish.  These conventional practices often prove to be inadequate for salmon kept in captivity beyond the smolt phase.  Captive broodstock salmon tend to mature at an earlier age, suffer lower fecundity, and produce less viable fry than their wild reared or ocean ranched counterparts.  Project 199305600 (Assessment of Captive Broodstock Technology) has taken on the task of investigating optimal methodologies for improving the growth, survival, and reproductive success of captive broodstocks with surrogate fish.  We propose to transition these concepts into the captive broodstock program and further validate these concepts with the rearing of ESA-listed stocks.

To minimize the risk to the ESA-listed fish, research would only be conducted using experimental protocols that are considered by Project 199305600 to provide a potential important benefit.  Current broodstock rearing practices would serve as controls.  Potential areas of investigation would include seawater vs. freshwater rearing, diet, rearing density, loading density, exercise, lighting, tank type, tank size, tank color, and alternate tank cleaning practices.

The first step in all these experiments would be to divide a population of fish into two equivalent rearing groups.  This would fit with the current captive broodstock practice where populations are usually divided into two groups to avoid the loss of an entire gene pool due to a catastrophic event occurring in a single tank.  Each group of fish would then be reared identically except for the experimental protocol under investigation.  The experiments will use a paired approach where several populations (e.g., brood years) of listed fish would be established into these paired groups to provide replication.  In order to eliminate sampling stress on these listed fish, only endpoint data on maturation age, size, fecundity, and survival would be used as response variables.  Paired t-tests will be used to compare the data with alpha set at 0.05.  These will be single tail directional tests due to the directional nature of the hypothesis.  It is anticipated this almost zero-risk experimentation will yield valuable information for improving captive broodstock culture techniques for listed sockeye salmon.

g. Facilities and equipment

BPA Project 19204000 is being conducted at the NMFS Manchester Research Station located on Clam Bay, a small bay adjoining the central basin of Puget Sound.  The station is located on nine hectares of land surplused from the U.S. Navy to NMFS in the late 1960s.  The main building at the Manchester Station contains three laboratories, seven offices, and computer and conference rooms.  Adjoining the main building is a disease diagnostic laboratory containing a pathology lab, a bioassay lab, and two offices.  A land-based seawater captive broodstock rearing complex houses three offices, wet and dry labs, and 400 m2 of floor space for fish rearing tanks in one building, and 1,280 m2 in another.

A major advantage of the site is the excellent seawater quality.  Clam Bay is a major tidal mixing zone between Sinclair and Dyes Inlets to the west and waters of central Puget Sound to the east.  Annual seawater temperature at the site normally ranges from 7-13°C and salinity ranges between about 26-29 ppt.  The high quality seawater environment, combined with a 250-m pier made available to the station by the EPA Region X Laboratory, make the Manchester Station an excellent site for experimentation/culture of a variety of finfish and shellfish.

A 700-m-long pipeline from the end of the pier supplies about 6,000 L/min (1,500 gpm) of pumped seawater to the Station’s land-base facilities.  Water is pumped via 50-hp centrifugal pumps.  The system is outfitted with back-up 50-hp pumps in case of primary pump failure.  An alarm system monitors the pumps and electrical supply and is tied into an automatic dialer system linked to pagers and home and office telephones.  Redundant emergency generators are automatically serially activated in the event of a power failure.

The 400-m2 seawater laboratory contains six 4.1-m, four 3.7-m and six 1.8-m diameter circular fiberglass tanks.  The1,280-m2 facility houses 20 6.1-m diameter circular fiberglass tanks.  Portions of both are used for the project.  The seawater supplied to these tanks is processed to ensure quality.  Filtering consists of primary sand filters containing number 20-grade sand; this filters out all organic and inorganic material more than 20 microns in diameter.  Water exiting the sand filters immediately enters a secondary cartridge filter system capable of filtering out all material more than 5 microns in diameter.  The water then passes through UV-sterilizers to inactivate remaining organic material.  Flow and pressure sensors monitor flow through the seawater filtration/sterilization system.

Before entering fish rearing tanks, the processed seawater is passed through packed column degassers to strip out any excess nitrogen and to boost dissolved oxygen levels.  Any interruption in water flow activates an emergency oxygen supply to all rearing containers.  The Station complies with Washington State quarantine certification standards and all water exiting captive broodstock rearing areas is depurated.

A freshwater satellite facility for the Manchester Research Station is located at Fish Pro Farm’s Burley Creek Hatchery near Burley, WA (approximately 20 minutes from Manchester).  This fresh water hatchery has been redesigned as a protective rearing facility for salmonid captive broodstocks.  The facility includes a 613-m2 building.  The building contains eleven 3.6-m, and fourteen 1.5-m diameter tanks.  A separate hatchery room accommodates down-well incubators for isolated egg incubation.

The hatchery is supplied with about 2,000 L/min of high-quality 10°C pumped well water.  Before distribution to the tanks the water is passed through packed column degassing towers that strip out any excess nitrogen and boost dissolved oxygen levels to 90% saturation.  Water flow, fire, and intruder alarms are monitored through a security system linked to pagers and home and office telephones.  Effluent from the hatchery is depurated through a settling basin and UV-sterilization system.  An emergency generator is automatically activated in the event of a power failure.

The unique seawater and freshwater rearing facilities and staff expertise make the NMFS Manchester Station an ideal facility for conducting captive broodstock rearing and research projects.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Allendorf, F. W. and N. Ryman. 1987. Genetic management of hatchery stock: past, present, and future. In N. Ryman and F. Utter (editors), Population genetics and fisheries management, p. 141-159. Univ. Washington Press, Seattle. Appleby, A. and K. Keown (editors). 1995. History of White River spring chinook broodstocking and captive brood rearing efforts. In T. A. Flagg and C. V. W. Mahnken (editors), An assessment of the status of captive broodstock technology for Pacific Salmon, p. 6-1 to 6-32. Report to Bonneville Power Administration, Contract DE-AI70 93BP55064. Berejikian, B. A., E. P. Tezak, S. L. Schroder, C. M. Knudsen, and J. J. Hard. 1997. Reproductive behavioral interactions between wild and captively reared coho salmon (Oncorhynchus kisutch). ICES J. Mar. Sci., 54: 1040-1050. Berejikian, B. A., E. P. Tezak, and A. L. LaRae. 2000. Female mate choice and spawning behavior of chinook salmon (Oncorhynchus tshawytscha) under experimental conditions. J. Fish. Biol. 57: 647-661. Captive Breeding Specialist Group (CBSG). 1991. Regional captive propagation programs worldwide. CBSG News 2(4):12. Columbia River Basin Fish and Wildlife Program (CBFWP). 1994. Available from Northwest Power Planning Council, 851 SW Sixth Avenue, Suite 100, Portland, OR 97204-1348. DeBlieu, J. 1993. Meant to be wild: the struggle to save endangered species through captive breeding. Fulcrum Publishing, Golden, Colorado, 302 p. Alaska Department of Fish and Game, Division of Fisheries Rehabilitation, Enhancement and Development (FRED). 1983. Fish culture manual. Alaska Dep. Fish Game, Juneau, AK, 90 p. Flagg, T. A. 1993a. Redfish Lake sockeye salmon captive broodstock project, p. 3-5. NMFS NWFSC Quarterly Report, October-December 1993. Flagg, T. A. 1993b. Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1992. Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 16 p. Flagg, T. A., K. A. Johnson, and J. C. Gislason. 1994. Redfish Lake sockeye salmon broodstock programs. In Proceedings of the 1993 Alaska Department of Fish and Game Sockeye Culture Workshop. Cooper Landing, Alaska, 10 p. Flagg, T. A., K. A. Johnson, C. V. W. Mahnken, J. Bauer, and J. C. Gislason. 1995a. Captive broodstock technology and its application to Redfish Lake sockeye salmon, p. 9. In, Proceedings of the role of captive breeding/artificial propagation in the restoration of endangered species workshop, Newport, OR. (Abstract). Flagg, T. A. and C. V. W. Mahnken (editors). 1995. An assessment of captive broodstock technology for Pacific salmon. Report to Bonneville Power Administration, Contract DE-AI79 93BP55064, 299 p. Flagg, T. A. and W. C. McAuley. 1994. Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1993. Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 99 p. Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, and C. V. W. Mahnken. 1996. Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1994. Report to Bonneville Power Administration, Contract DE-AI79-92BP41841, 98 p. Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, C. V. W. Mahnken, and J. C. Gislason. 1998. Redfish Lake Sockeye Salmon Captive Broodstock Program, NMFS, p. In R. Z. Smith (editor), Proceedings of the 48th Annual Northwest Fish Culture Conference, Dec. 2-4, 1997, Gleneden Beach, Oregon. Flagg, T. A., F. W. Waknitz, and C. V. W. Mahnken. 1995b. The captive broodstock concept: application to Pacific salmon, p. 1-1 - 1-60. In T. A. Flagg and C. V. W. Mahnken (editors), An assessment of captive broodstock technology for Pacific salmon. Report to Bonneville Power Administration, Contract DE-AI79 93BP55064. Gipps, J. H. W. (editor). 1991. Beyond captive breeding: reintroducing endangered species through captive breeding. Zool. Soc. London Symp. 62, 284 p. Hard, J. J., R. P. Jones, Jr., M. R. Delarm, and R. S. Waples. 1992. Pacific salmon and artificial propagation under the Endangered Species Act. U.S. Dep. Commer., NOAA Tech. Memo. NMFS-NWFSC-2, 56 p. Hynes, J. D., E. H. Brown, J. H. Helle, N. Ryman, and D. A. Webster. 1981. Guidelines for the culture of fish stocks for resource management. Can. J. Fish. Aquat. Sci. 38:1867-1876. Johnson, J. E. and B. L. Jensen. 1991. Hatcheries for endangered freshwater fish. In W. L. Minckley and J. E. Deacon (editors), Battle against extinction, p. 199-217. Univ. Arizona Press, Tucson. Johnson, K. A. 1993. Research and recovery of Snake River sockeye salmon, 1991-1992. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 38 p. Johnson, K. A. and J. J. Pravecek. 1995. Research and recovery of Snake River sockeye salmon, 1993. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 37 p. Johnson, K. A. and J. J. Pravecek. 1996. Research and recovery of Snake River sockeye salmon, 1994-1995. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 43 p. Kapuscinski, A. R. and L. D. Jacobsen. 1987. Genetic guidelines for fisheries management. Minn. Sea Grant Res. Rep. 17, St. Paul, MN. Kincaid, H. L. 1983. Inbreeding in fish populations used in aquaculture. Aquaculture 3:215-227. Kincaid, H. L. 1993. Breeding plan to preserve the genetic variability of the Kootenai River white sturgeon. Report to Bonneville Power Administration, Contract DE-AI79 93BP02886, 18 p. Kline, P. A. 1994. Research and recovery of Snake River sockeye salmon, 1993. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 52 p. Kline, P. A. and J. A. Lamansky. 1997. Research and recovery of Snake River sockeye salmon, 1995-1996. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 78 p. Kline, P. and J. Younk. 1995. Research and recovery of Snake River sockeye salmon, 1994. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 46 p. Krueger, C. A., A. Garret, T. Dehring, and F. Allendorf. 1981. Genetic aspects of fisheries rehabilitation programs. Can. J. Fish. Aquat. Sci. 38:1877-1881. Leitritz, E. and R. C. Lewis. 1976. Trout and salmon culture (hatchery methods). Calif. Dep. Fish Game Fish Bull. 164, 197 p. Olney, P. J. S., G. M. Mace, and A. T. C. Feistner. 1994. Creative conservation: interactive management of wild and captive animals. Chapman and Hall, London, England, 571 p. Pennell, W. and B. A. Barton (editors). 1996. Principles of salmonid culture. Elsevier, Amsterdam, 1039 p. Piper, R. G., I. B. McElwain, L. E. Orme, J. P. McCraren, L. G. Fowler, and J. R. Leonard. 1982. Fish hatchery management. U.S. Dept. of the Interior, Fish and Wildlife Service, Washington, D.C., 517 p. Pravecek, J. J. and K. A. Johnson. 1997. Research and recovery of Snake River sockeye salmon, 1995-1996. Report to Bonneville Power Administration, Contract DE-BI79-91BP21065, 30 p. Rinne, J. N., J. E. Johnson, B. L. Jensen, A. W. Ruger, and R. Sorenson. 1986. The role of hatcheries in the management and recovery of threatened and endangered fishes. In R. H. Stroud (editor), Fish culture in fisheries management. Proceedings of a symposium on the role of fish culture in fisheries management, March 31-April 3, 1985, Lake Ozark, Missouri, p. 271-285. American Fisheries Society, Bethesda. Schiewe, M. H., T. A. Flagg, and B. A. Berejikian. 1997. The use of captive broodstocks for gene conservation of salmon in the western United States. Bull. Natl. Res. Inst. Aquacult., Suppl. 3:29-34. Schmitten, R., W. Stelle, Jr., and R. P. Jones. 1995. Proposed Recovery Plan for Snake River Salmon, 347 p., plus appendices. Spaulding, S. 1993. Snake River sockeye salmon (Oncorhynchus nerka) habitat/limnological research, 1992. Report to Bonneville Power Administration, Contract DE-BI79-91BP22548, 78 p. Taki, D. and A. Mikkelsen. 1997. Snake River sockeye salmon habitat and limnological research, 1996. Report to Bonneville Power Administration, Contract DE-BI79-91BP22548, 97 p. Teuscher, D., D. Taki, W. A. Wurtsbaugh, C. Luke, P. Budy, H. P. Gross, and G. Steinhart. 1994. Snake River sockeye salmon habitat and limnological research, 1993. Report to Bonneville Power Administration, Contract DE-BI79-91BP22548, 136 p. Teuscher, D., D. Taki, W. A. Wurtsbaugh, C. Luke, P. Budy, and G. Steinhart. 1995. Snake River sockeye salmon habitat and limnological research, 1994. Report to Bonneville Power Administration, Contract DE-BI79-91BP22548, 137 p. Teuscher, D. and D. Taki. 1996. Snake River sockeye salmon habitat and limnological research, 1995. Report to Bonneville Power Administration, Contract DE-BI79-91BP22548, 85 p. Waples, R. S., O. W. Johnson, and R. P. Jones, Jr. 1991. Status review for Snake River sockeye salmon. U.S. Dep. Commer., NOAA Tech. Memo. NMFS-F/NWC-195, 23 p. Waples, R. S. 1991. Genetic interactions between wild and hatchery salmonids: lessons from the Pacific Northwest. Can. J. Fish. Aquat. Sci. 48 (Supplement 1):124-133. |  |

# Section 10 of 10. Key personnel

1.  Mr. Thomas A. Flagg, Supervisory Fisheries Research Biologist.  Salmon Enhancement Program Manager @ 8% FTE.  Duties include program management; project coordination with IDFG, Stanley Basin Sockeye Technical Oversight Committee, and others; Data analysis and report writing; etc.  [See attached resume for qualifications.]

2.  Dr. Desmond J. Maynard, Fisheries Research Biologist.  Hatchery Technology Team Leader @ 19% FTE.  Duties include internal project oversight; project coordination with Stanley Basin Sockeye Technical Oversight Committee; Data analysis and report writing etc. [See attached resume for qualifications.]

3.  Mr. Wm. Carlin McAuley, Endangered Species Biologist.  Hatchery Manager @ 50% FTE.  Duties include all phases of fish husbandry and hatchery oversight/coordination. [See attached resume for qualifications.]

4.  Mr. Michael R. Wastel, Fisheries Biological Technician.  Hatchery support staff @ 50% FTE.  Duties include fish husbandry.  [See attached resume for qualifications.]

5.  Ms. Deborah A. Frost, Fisheries Biologist.  Hatchery biologist @ 100% FTE.  Duties include fish husbandry at the BCH hatchery.  [See attached resume for qualifications.]

6.  Dr. Lee W. Harrell, Fisheries Research Biologist.  Fish Veterinarian @ 12% FTE.  Duties include oversight of fish health issues.  [See attached resume for qualifications.]

#### CURRICULUM VITAE--Thomas Alvin Flagg

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- B.S., Fisheries Biology, University of Washington, Seattle, WA, 1976.

- M.S., Fisheries Biology, University of Washington, Seattle, WA, 1981.

- Ph. D. program, University of Idaho, Moscow, ID, present.

Professional Experience:

###### Position				Organization		City		State	Dates

###### Fisheries Research Biologist 	NMFS 			Manchester	WA	1/78-present

Current Responsibilities:   Program Manager,  Salmon Enhancement Projects.  Responsibilities include: development of captive broodstock programs to conserve depleted gene pools of salmonids; development of supplementation techniques for restoration of depleted stocks of salmonids to their native habitats; and development of fish husbandry technology to produce wild-type juvenile salmon for release from hatcheries.

Expertise:   Mr. Flagg has participated in a number of captive broodstock programs for Pacific and Atlantic salmon.  His current research focuses on reform of fish husbandry strategies for conservation hatcheries.  Past research included: determination of status of depleted stocks of fish including those proposed for listing as threatened or endangered under the Endangered Species Act; development of the passive integrated transponder (PIT) tagging system for salmonids; development of freshwater and seawater net-pen aquaculture husbandry and captive broodstock techniques for Atlantic and Pacific salmon (including research in the areas of aquaculture systems design and development, stock rearing strategies, nutrition, disease investigations, maturation and spawning, hormonal sex reversal, smoltification, and stock performance); investigation of fish-collection and transportation related mortalities in juvenile salmonids in the Columbia River system; evaluation of the impact of the 1980 Mt. St. Helens eruption on juvenile salmonids in the Columbia River system; and investigation of the relationship between swimming behavior, smoltification status, and seawater survival for coho salmon.

Selected Publications:

Flagg, T. A., B. A. Berejikian, J. E. Colt, W. W. Dickhoff, L. W. Harrell, D. J. Maynard, C. E. Nash, M. S. Strom, R. N. Iwamoto, and C. V.W. Mahnken.  2000.  Ecological and behavioral impacts of artificial production strategies on the abundance of wild salmon populations.  U.S. Dep. Commer., NOAA Tech. Memo. NMFS-NWFSC-41, 91 p.

Flagg, T. A. and C.V.W. Mahnken.  2000.  Endangered species recovery:  captive broodstocks to aid recovery of endangered salmon stocks.  Encyclopedia of Aquaculture, J. Wiley and Sons, p. 290-292.

Schiewe, M. H., T. A. Flagg, and B. A. Berejikian.  1997.  The use of captive broodstocks for gene conservation of salmon in the western United States.  Bull. Natl. Res. Inst. Aquacult., Suppl. 3:29-34.

Flagg, T. A., C. V. W. Mahnken, and K. A. Johnson.  1995.  Captive broodstocks for recovery of Snake River sockeye salmon.  Am. Fish. Soc. Symp. 15:81-90.

Flagg, T. A. and C. V. W. Mahnken (editors).  1995.  An assessment of captive broodstock technology for Pacific salmon.  Report to Bonneville Power Administration, Contract DE-AI79 93BP55064, 299 p.

CURRICULUM VITAE--Dr. Desmond J. Maynard

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- A.A., Business management, Cape Cod Community College, Hyannis, MA, 1971.

- B.S.,  Marine Biology, University of Massachusetts, North Dartmouth, MA, 1974.

- M.S., Fisheries Science, University of Washington, Seattle, WA, 1980.

- Ph.D., Fisheries Science, University of Washington, Seattle, WA, 1987.

Professional Experience:

###### Position/Title			Organization		City		State	Dates

Fish. Research Biologist		NMFS			Manchester	WA	6/88-present

Fish & Wildlife Instructor		Grays Harbor College	Aberdeen	WA	9/87-6/88

Consulting Biologist		Island County		Clinton		WA	1/80-12/81

Fisheries Biologist		NMFS			Seattle 		WA	9/77-9/79

Teaching Assistant		University of Washington	Seattle		WA	9/75-6/78

###### Research Associate		Survey Chemistry	Dartmouth	MA	6/74-1/75

Current Responsibilities:  Hatchery Technology team leader and principal investigator on the BPA  sockeye salmon captive broodstock, BPA chinook salmon captive broodstock , BPA NATURES project, and  HSRG NATURES project.  Dr. Maynard’s responsibilities include overseeing captive broodstock culture; developing captive broodstock and NATURES rearing protocols; designing experiments to evaluate the effect of these protocols on salmon behavior, morphology, growth, and survival; oversight of experimental activities; data analysis; publishing finding in annual reports and journal articles; and participation in interagency technical meeting.

Expertise:  Dr. Maynard’s primary expertise is in fish behavior and culture.  He has taught graduate level courses on fish sociobiology and behavioral ecology, conducted research on the social behavior of salmon, and investigated the effects of petroleum on salmon homing and migration.  Dr. Maynard has been a member of the Animal Behavior Society since 1977, where he has served on the applied animal behavior and film committees.  He has taught college level courses on Aquaculture and his research since 1992 has focused on developing culture techniques to increase the postrelease survival of hatchery salmon.  Dr. Maynard also has expertise in fish taxonomy and evolution and has been a member of the NMFS Biological Review Teams for several petitioned listings.  In addition, he has expertise in fish tagging and has led several investigations comparing the effects of tags on fish survival.

Selected Publications:

Maynard, D. J., T. A. Flagg, and C. V. W. Mahnken, and S. L. Schroder.  1996.  Natural rearing technologies for increasing postrelease survival of hatchery-reared salmon.  Bull Natl. Res. Inst. Aquacult., Suppl. 2:71-77.

Maynard, D. J., G. C. McDowell, E. P. Tezak, and T. A. Flagg.  1996.  The effect of diets supplemented with live-food on the foraging behavior of cultured fall chinook salmon. Prog. Fish-Cult. 58:187-191.

Maynard, D. J., D. A. Frost, F. William Waknitz, and Earl F. Prenctice.  1996. Vulnerability of marked age-0 steelhead to a visual predator. Trans. Am. Fish. Soc. 125:130133.

Maynard, D. J., T. A. Flagg, and C. V. W. Mahnken.  1995.  A review of semi-natural culture strategies for enhancing the postrelease survival of anadromous salmonids.  American Fisheries Society Symposium 15:307-314.

Maynard D. J., and D. D. Weber. 1981. Avoidance reactions of juvenile coho salmon (Oncorhynchus kisutch) to monocyclic aromatics. Can. J. Fish. and Aquat. Sci

CURRICULUM VITAE--W. Carlin McAuley

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- B.A. Zoology, University of Washington, Seattle, WA, 1973.

Professional Experience:

###### Position/Title			Organization		City		State	Dates

Endangered Species Biologist	NMFS			Manchester	WA	10/91-present

Hatchery Biologist		Domsea Farms Inc.	Gorst		WA	10/73-3/91

Current Responsibilities:  Hatchery Manager for NMFS Manchester Research Station captive broodstock programs for recovery of ESA-listed endangered Redfish Lake sockeye salmon and threatened Snake River spring/summer chinook.  Responsible for every aspect of life cycle including feed rations, disease detection and control, detailed record database, and spawning.

Expertise:   Mr. McAuley has participated in a number of captive broodstock programs for Pacific salmon.  He has conducted research into captive broodstock programs using non-endangered Lake Wenatchee sockeye salmon captive broodstock (BY 1990 and 1991) reared in three different environments.  Responsible for daily care including feed, disease detection and control, detailed record database, spawning, and egg incubation.  Provided support for other researchers investigating physiological developments in these same fish.  Specialized skills include various fish tagging techniques (coded wire tag, PIT tag, elastomer tag, freeze branding), and Fluorescent Antibody Technique for detection of fish disease pathogens.  Provided aquaculture consulting to Domsea Farms Inc.  Primarily responsible for continuation of 13 year genetics breeding program for captive broodstocks of Pacific salmon at Domsea Farms.  Duties consisted of management of captive breeding program of fish reared in freshwater, including collection and input of data into genetics database, tracking and maintaining separate identity of 40 families, and decision making for various program steps

Selected Publications:

Flagg, T. A., W. C. McAuley, D. A. Frost, M. R. Wastel, W. T. Fairgrieve and C. V. W. Mahnken.  2001.  Redfish lake sockeye salmon captive broodstock rearing and research, 1995-2000.  Report to Bonneville Power Administration, Contract DE-AI79 92BP41841, 66 p.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, C. V. W. Mahnken, and J. C. Gislason.  1998.  Redfish Lake Sockeye Salmon Captive Broodstock Program, NMFS.  Proceedings of the 48th Annual Northwest Fish Culture Conference, Gleneden Beach, Oregon, p. 127-135.

Flagg, T. A., and W. C. McAuley.  1993.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1991-1993.  Report to Bonneville Power Administration, Contract DE-A179-92BP41841.

McAuley, W. C.  1981a.  DOMSEA coho broodstock program.  In T. Nosho (editor), Salmonid broodstock maturation, p.23-24.  Proceedings of the salmonid broodstock maturation workshop. University of Washington Sea Grant Pub. WSG-WO-80-1.

McAuley, W. C.  1981b.  DOMSEA coho broodstock program-update.  In T. Nosho (editor), Salmonid broodstock maturation, p.65-66.  Proceedings of the salmonid broodstock maturation workshop.  University of Washington Sea Grant Pub., WSG-WO-80-1.

CURRICULUM VITAE--Michael R. Wastel

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- A.S. Fisheries - Peninsula College, Port Angeles, WA, 1977.

Professional Experience:

###### Position/Title			Organization		City		State	Dates

Fisheries Biological Technician, 	NMFS 			Manchester	WA	92-present

Fisheries Technician		WDFG			Olympia		WA	91-92

###### Hatchery Manager		Domsea Farms Inc	Gorst		WA	80-91

Current Responsibilities:  Provide technician support for NMFS Manchester Research Station captive broodstock programs for recovery of ESA-listed endangered Redfish Lake sockeye salmon and threatened Snake River spring/summer chinook.  Lead contact for construction of captive broodstock research facilities for freshwater and seawater rearing at Manchester.  Responsible for aspect of life cycle culture including feed rations, disease detection and control, detailed record database, and spawning.

Expertise:   Mr. Wastel has participated in a number of captive broodstock projects for Pacific salmon. 1991-1992--Fisheries Technician, Steelhead Stock Assessment Program, Washington Department Fish and Wildlife, Olympia, Washington.  Responsible for the collection of data on steelhead life histories for 22 Washington State rivers, all tributaries of the Columbia River.  1980-1991--Hatchery Manager, Fisheries Research Division, Domsea Farms Inc. Gorst Creek Hatchery, Gorst, Washington.  Supervised and participated in all phases of hatchery operations.  Responsible for all fish rearing activities.  Worked on both production and broodstock programs.  Supervised six employees.  Assigned work schedules.  Formulated fiscal budget.  Produced monthly reports.  Maintained hatchery systems including; wells, pumps, generators and alarm system.  Expanded and upgraded hatchery incubation.  Installed additional tanks.  Assisted in the formation of coho salmon broodstock program which produced fish with superior growth and survival rates.  As the offspring of fish from the broodstock program outperformed all other hatchery fish, the program expanded and became a major part of my responsibilities.

Selected Publications:

Flagg, T. A., W. C. McAuley, D. A. Frost, M. R. Wastel, W. T. Fairgrieve and C. V. W. Mahnken.  2001.  Redfish lake sockeye salmon captive broodstock rearing and research, 1995-2000.  Report to Bonneville Power Administration, Contract DE-AI79 92BP41841, 66 p.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, C. V. W. Mahnken, and J. C. Gislason.  1998.  Redfish Lake Sockeye Salmon Captive Broodstock Program, NMFS.  Proceedings of the 48th Annual Northwest Fish Culture Conference, Gleneden Beach, Oregon, p. 127-135.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, and C. V.  W. Mahnken.  1996.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1994.  Report to Bonneville Power Administration, Contract DE-AI79 92BP41841, 98 p.

Hymer, J., R. Pettit, M. Wastel, P. Hahn, and K. Hatch.  1992.  Stock Summary reports for Columbia River Anadromous Salmonids, Volume 3.  BPA, Division of Fish and Wildlife, Project No. 88-108.

CURRICULUM VITAE--Deborah A. Frost

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- A.A., Lower Columbia College, Longview, WA, 1984.

- B.S., Zoology, University of Washington, Seattle, WA, 1986.

Professional Experience:

###### Position/Title			Organization	City		State	Dates

###### Fisheries Research Biologist	 NMFS 		Manchester	WA	5/94-present

Fisheries Biologist		NMFS		Manchester	WA	5/90-5/94

###### EKG Technician			Swedish Hosp.	Seattle		WA	10/87-5/90

Current Responsibilities:  Site Manager for freshwater rearing facility.  Directly involved with the daily culture of captive Redfish Lake sockeye salmon through all life phases.  Includes maintaining strict isolation procedures for these fish, administering medicated feed on schedule, analyzing mortalities and conducting fluorescent antibody technique (FAT) procedures for bacterial kidney disease.  Organized the PIT tagging of captive broodstock.  Organizes spawning and incubation activities.  Maintains daily records of feed, mortality, and water temperature for all fish.

Expertise: Fisheries Biologist, Manchester Research Station and Burley Creek Hatchery.  Assisted in the development and evaluation of various passive integrated transponder (PIT) tag systems for fish.   Involved with conducting captive broodstock culture and growth research on non-endangered Lake Wenatchee sockeye salmon (organized the PIT tagging of this group of fish as well as the monthly collection of growth data).  Observed salmon behavior with respect to various PIT-tag interrogation passageway models in lab and stream.  Conducted various comparative tagging predation and survival studies in rearing pools and in a natural stream.  Involved in the initial natural feed and habitat rearing methods for the NMFS NATURES program.  Involved in a study to test a model for survival estimates for juvenile chinook salmon passage through Snake River dams and reservoirs.  This consisted of assembling a PIT tagging station and relocating it to different sites on the Snake River, PIT tagging chinook salmon, teaching others to PIT tag salmon and operate digitizer board, and maintaining and uploading tagging data to the database.

Selected Publications:

Flagg, T. A., W. C. McAuley, D. A. Frost, M. R. Wastel, W. T. Fairgrieve and C. V. W. Mahnken.  2001.  Redfish lake sockeye salmon captive broodstock rearing and research, 1995-2000.  Report to Bonneville Power Administration, Contract DE-AI79 92BP41841, 66 p.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, C. V. W. Mahnken, and J. C. Gislason.  1998.  Redfish Lake Sockeye Salmon Captive Broodstock Program, NMFS.  Proceedings of the 48th Annual Northwest Fish Culture Conference, Glenden Beach, Oregon, p. 127-135.

Flagg, T. A., W. C. McAuley, M. R. Wastel, D. A. Frost, and C. V. W. Mahnken.  1996.  Redfish Lake sockeye salmon captive broodstock rearing and research, 1994.  Report to Bonneville Power Administration, Contract DE-AI79 92BP41841, 98 p.

Maynard, D. J., D. A. Frost, F. W. Waknitz, and E. F. Prentice.  1996.  Vulnerability of marked age-O Steelhead to a visual predator.  Transactions of the American Fisheries Society 125:330-333.

Prentice, E. F., D. J. Maynard, S. L. Downing, D. A. Frost, M. S. Kellett, D. A. Bruland, P. Sparks-McConkey, F. W. Waknitz, R. N. Iwamoto, K. McIntyre, and N. Paasch.  1994.  A Study to Determine the Biological Feasibility of a New Fish Tagging System (1990-93).  Report to Bonneville Power Administration, Contract DE-AI79-84BP11982, 209 p. + appendices.

CURRICULUM VITAE--Lee W. Harrell

Current Employer:  Northwest Fisheries Science Center, National Marine Fisheries Service

Education:

- B.S., Animal Husbandry, University of Florida, Gainesville, FL, 1960.

- D.V.M., Veterinary Medicine, Auburn University, Auburn, AL, 1964.

- M.S., Fisheries Biology, University of Washington, Seattle, WA, 1973.

Professional Certifications:

- Certified Fish Pathologist (AFS) #35;

- Washington State Veterinary practice license # 653

- Florida State Veterinary license # 857.

Professional Experience:

###### Position/Title			Organization	City		State	Dates

Fisheries Research Biologist, 	NMFS 		Manchester	WA	73-present.

Current Responsibilities:  Manager of Fish Health projects, Manchester Research Station.  Duties include fish disease diagnosis and treatment; conducting research on freshwater and marine diseases of salmonids; and involvement in broodstock restoration  methods.  Pathologist representative, Pacific Northwest Fish Health Protection Committee. Consulting Veterinarian, Washington State Department of Fisheries and Wildlife.

Expertise:  Dr. Harrell has expertise in all areas of fish veterinary fish medicine.  He has conducted research with all phases of salmonid fish health and disease diagnosis and treatment; development of freshwater and seawater net-pen aquaculture husbandry; development of captive broodstock techniques for Atlantic and Pacific salmon.

Selected Publications:

Harrell, Lee W.  1995.  Fish health aspects of broodstock restoration, pp. 5-1 - 5-14.  In T. A. Flagg and C. V. W. Mahnken (eds.), An assessment of captive broodstock technology for Pacific salmon.  Report to Bonneville Power Administration, Contract DE-AI79 93BP55064.

R. A. Elston, M. L. Kent, and L. W. Harrell.  1987.  An intranuclear microsporidium associated with acute anemia in the chinook salmon, Oncorhynchus tshawytscha.  J. Protozool. 34(3):274 277.

Harrell, L. W., T. A. Flagg, and F. W. Waknitz.  1987.  Snake River Fall Chinook Salmon Broodstock Program, 1981-1986.  Final report to Bonneville Power Administration.  24 p.

R. A. Elston, L. W. Harrell, and M. T. Wilkinson.  1986.  Isolation and in vitro characteristics of chinook salmon Oncorhynchus tshawytscha rosette agent. Aquaculture 56:1-21.

Harrell, L. W., C. V. W. Mahnken, T. A. Flagg, E. F. Prentice, F. W. Waknitz, J. L. Mighell, and A. J. Novotny.  1984.  Status of the NMFS/USFWS Atlantic salmon brood-stock program (Summer 1984).  Annual report of research (to NMFS/NER). 16 p.