# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID:	28014

Title:	Bull trout population assessment and life history characteristics in association with habitat quality and land use:  template for recovery planning.

# Section 9 of 10. Project description

a. Abstract

The goal of this project is to understand and document population abundance and rates of population change for threatened bull trout (Salvelinus confluentus) in the Salmon River (Little Salmon) Subbasin, and to relate population and life history characteristics to habitat quality and land use.  The data and conservation assessment tools provided by this project will be used in bull trout recovery planning and will provide a template for research, monitoring, and evaluation programs for bull trout populations throughout this as well as other provinces.  We propose to do a comprehensive population assessment for all life stages of bull trout in combination with detailed habitat assessments for the streams identified.  This assessment will provide information on densities, population abundance and structure, movement, and habitat quality.  Basic population abundance and density information is crucial for determining population status, for monitoring population size and trends, and to evaluate opportunities for, and the effectiveness of, management activities aimed at bull trout recovery.  Based on established and cost effective mark and recapture techniques, the Pradel-type mark/recapture analysis we have proposed provides a simple response variable, lambda, which can be used to evaluate how each sub-population is responding to current habitat conditions or would likely respond to future habitat improvements.  We will develop a simple population life-cycle model based on bull trout abundance data and life history characteristics combined with information on habitat quality and land use patterns.  Within each of the proposed watersheds, we have identified core areas (streams), which demonstrate a range of habitat quality as well as different management types (e.g., private vs. USFS).  Further, the USFS Effectiveness Monitoring program annually provides detailed stream habitat assessments for different land use management types for watersheds throughout the Columbia Basin, which may ultimately be used for evaluating the effect of habitat quality on bull trout survival in additional areas.

b. Technical and/or scientific background

Bull trout populations in the Columbia River Basin were listed as threatened by the U.S. Fish and Wildlife Service under the Endangered Species Act (Office of the Federal register 63:31647 in June of 1998.  This listing reflects the depressed status and decreased range of bull trout populations overall.  Developing recovery plans requires basic population abundance information in order to evaluate population status and to monitor population size and trends.  In addition, the relationship between population abundance and habitat is necessary in order to identify opportunities for, and the effectiveness of, management activities aimed at bull trout recovery (Meffe et al. 1997).  The need for bull trout population assessment information has been identified by the USFWS and NWPPC Fish and Wildlife Program and Sub-basin Summaries in order to aid in recovery planning and adaptive management in the region.

For this study, we have selected the Rapid River and Boulder Creek, and associated tributaries, for bull trout population assessments and habitat evaluations.  Idaho Governor Phil Batt initiated development of a conservation plan to restore bull trout populations in Idaho in 1995.  Further, the Clearwater Technical Advisory Team identified the Little Salmon River subbasin, Rapid River and Boulder Creek, as priority/high importance bull trout watersheds based on known bull trout spawning areas and other important habitat needed during a bull trout’s life cycle (CBBTTAT 1998).   These stream areas or tributaries are defined as local population units and core areas (USFWS 1998) for bull trout, and both resident and fluvial life forms are present.  The Little Salmon River drainage is characterized as having multiple spawning subpopulations, an estimated population size from 250-500, a declining status and trend with no risk of stochastic extirpation (USFWS 1998).  Little Salmon River, Boulder Creek, Hazard Creek, and Hard Creek were classified by the State of Idaho as ‘Stream Segments of Concern.  Forestry, grazing, and agriculture are identified as potential threats (USFWS 1998).  The USFS has identified the Little Salmon drainage as a priority index area for bull trout recovery planning (H. Schaller, USFWS, pers. comm.).

The Little Salmon River is located in southwestern Idaho and is 43 miles long, entering the main Salmon at RM 82.  Total acreage within the subbasin is 372,500 acres, and elevations range from 1,720 feet at the mouth of the Little Salmon River to over 9,000 feet (CBBTTAT 1998).  The Little Salmon River flows through a broad, low gradient upper meadows, then enters a steep gradient canyon.  The Little Salmon River experienced a storm and flood event in 1997, and significant flood scouring damage resulted along the lower portion (below 5,000 feet).  Land ownership in the Little Salmon River is dominated by USFS (67.8%) and Private ownership (23%) with 3.9% and 5.3 % owned by the state and BLM respectively (Subbasin Plan, IDFG 1990). Primary land uses are livestock grazing, recreation, residences, and timber harvest (CBBTTAT 1998).  In addition, private ownership controls essential water rights.  Water use has been noted to have caused temperature and flow problems in several tributaries of the Salmon subbasin.  Some mining also exists, and turbidity problems may be present in isolated areas due to natural factors or mining (Subbasin Plan, IDFG 1990).  The Nez Perce have been residents of this area for more than 10,000 years (CBBTTAT 1998).

Rapid River, the major tributary of the Little Salmon River drainage is part of the national Wild and Scenic Rivers System (Subbasin Plan, IDFG 1990).  It is 21 miles long and located in largely pristine habitat; however, natural occurrences like mass failure of hillsides, stream channel scouring, and localized flash flooding continuously shape land features.  The lower two miles are the only portion accessible by road.  The upper end of Rapid River is roadless but has not received wilderness recommendations in the forest plan, and most of the West Fork of Rapid River is blocked by a natural falls.  Boulder Creek is currently undergoing road construction and heavy logging in previously un-accessed sites.

The Little Salmon drainage is part of the native range of bull trout; however, historic abundance and trend data are scarce because bull trout were considered a nuisance fish (CBBTTAT 1998). Data is lacking for population size, movement, and/or life histories of bull trout utilizing the Little Salmon River.  However, some studies have been completed on populations and movement of fluvial bull trout in the Little Salmon River, Rapid River (Schill et. al. 1994).  The CBBTTAT notes that “ This drainage is considered a key refugia watershed for bull trout and probably is the only watershed in west-central Idaho that supports a stable fluvial bull trout population.  It could be considered a “stronghold” as a bull trout source for colonization of other watersheds.”  The Rapid River spawning population has ranged from 91-461 fish over the last 20 years (Schill et al. 1994) based on records from the Rapid River chinook hatchery.  For this proposal, the Rapid River serves as our index of good habitat, as the only major development or land-disturbing activities occur in the lower portion of the watershed.

Boulder Creek is another important core spawning and early rearing area for bull trout within the little Salmon River drainage.  All reaches of Boulder Creek were extensively snorkeled during a 1991 Forest Service Intermountain Station fish inventory.  According to that survey, 69% of all bull trout (64 fish) were found in the middle stream reach near Yellow Jacket Creek (approximately stream mile 10), and larger sized fish (greater than 300 mm) were conspicuously absent.  Boulder Creek also provides spawning and rearing habitat for spring/summer chinook salmon and steelhead trout, but no systematic, long-term trend survey has been conducted in Boulder Creek (USDA-FS 1998).  In contrast to the Rapid River, most of the Boulder Creek drainage has been altered, and an intensive road network is found throughout the upper and lower watershed (road densities range 3-4 miles of road per square mile of area).  This road network has reduced habitat connectivity at some location by eliminating fish passage (USDA, FS 1998).  Further, according to CBBTTAT (1998), the upper 5-6 miles of Boulder Creek has been isolated from the rest of the stream due to a culvert installation, which created a velocity barrier and poor passage conditions.  Past and recent landslides have contributed significant amounts of sediment to Boulder Creek.  For this proposal, Boulder Creek serves as our index of poor habitat for reasons described above.

Population Assessment.

Information on fish population abundance and life-stage specific survival and limiting factors are required for determining population status and identifying management actions aimed at recovery (Meffe et al. 1997).  Currently, quantitative population assessment data collected with rigorous sampling techniques is extremely limited for most threatened populations of bull trout in the Columbia River basin (Rieman and McIntyre 1993; Buchanan et al. 1997; USFWS 1998).  Further, bull trout populations can be difficult to evaluate because of their largely nocturnal behavior (Shepard et al. 1984; Goetz 1991; Bonneau et al. 1995), different life history strategies which often coexist together (e.g., migrating and resident forms; Fraley and Shepard 1989; Goetz 1991; Rieman and McIntyre 1993), and their potentially diverse habitat requirements (Pratt 1984; Goetz 1994).  In addition, Dunham et al. (2001) recently evaluated bull trout redd counting methods for different sources of error and variability.  They demonstrated that in addition to substantial observer error in counting redds, bull trout spawning activity was highly variable both temporally and spatially.  In addition to these difficulties in assessing bull trout population abundance, Rieman and McIntyre (1993) originally suggested that metapopulation theory may be important to consider for bull trout conservation.  However, for most populations, data that describe detailed population structure and movement among metapopulations are generally lacking (USFWS 1998).

Mark and recapture techniques provide a robust method for estimating population size, evaluating movement among streams and subpopulations, and for evaluating population response to habitat quality and improvement or restoration (Cooch and White 2001).  At a minimum, simple mark/recapture data can provide a non-lethal estimate of population size with confidence intervals (Krebs 1999).  In addition, when mark/recapture information is specific to individuals or tagging location, analyses can also include individual covariates that relate an individual’s survival to a specific habitat relationship (Franklin, in press; White et al. in press) or information about movement among streams, sub-populations, and metapopulation structure (White et al., in press), respectively.  Further, with the appropriate study design, these techniques can potentially help overcome the inherent difficulties of assessing bull trout population abundance and can provide a simple response variable (lambda) for evaluating population response to factors such as habitat quality, productivity, or management actions aimed at recovery (Pradel 1996; Franklin, in press).

Franklin describes the use of Pradel mark/recapture models for evaluating  recruitment rates and rates of population change (lambda).  These models are based on a re-parameterization of the classic Jolly-Seber model (Jolly 1965;  Seber 1965) that permits the estimation of an annual finite rate of population change (lambda) and/or rates of recruitment (Pradel 1996).  Although not identical to the lambda derived from a basic life-cycle model or matrix model, conceptually (and mathematically), both reflect the annual rate of change for the population and provide an analytical bridge between the individual and population level processes (Franklin, in press).  Assumptions underlying the Pradel approach require that the study area size and boundary configuration remains unchanged through time and all animals must have the same probability of being captured throughout the study.  When lambda is known (or estimated), life-stage specific survival rates can also be calculated allowing the examination of the link between isolated habitat quality or changes in that habitat (e.g., spawning and rearing grounds) and linked life stage survival rates (e.g., egg-to-parr survival).  The ability to link specific management activities with life-stage specific survival is necessary for adaptive management and for evaluating recovery strategies (NMFS 2000).

Each of these sophisticated mark/recapture analyses, the metapopulation analyses described above, and the Pradel models, are available through the shareware program MARK (White et al., in press).  MARK provides not only parameter estimates but also a conditional measures of precision, quasi-likelihood procedures to correct for over-dispersion of the data, and bootstrapping for goodness of fit (Cooch and White 2001).  The explicit incorporation of uncertainty in population and other parameter estimates facilitates the use of this type of model in risk averse conservation planning and decision analysis (Burgman 1994).

Mark and recapture techniques are non-lethal and relatively cost effective.  In addition, resighting (instead of recapture) can be used as a technique to limit handling when ESA concerns prevail (Krebs 1999).  Our proposed approach combines multiple capture techniques with resighting during comprehensive snorkel surveys.  Our combined approach will therefore provide not only population estimates and parameters that describe survival and population structure, but also a comparison to techniques that have been used in the past and are being used in other ongoing projects.  For example, juvenile abundance surveys are often based on night snorkeling (Shepard et al. 1984; Goetz 1991; Bonneau et al. 1995), however, there is some concern that these underwater surveys may underestimate juvenile bull trout abundance (Fraley and Shepard 1989; Thurow and Schill 1996).  We will be able to compare population estimates from 1) marks and combined recaptures from trapping, shocking, and resighting during snorkel surveys, and 2) modified Hankin and Reeves type snorkel-based abundance estimates, where densities are estimated for habitat units then expanded upward for the entire stream (Hankin and Reeves 1988).  The results from this comparison will help direct and standardize future bull trout population assessment techniques for the region as a whole.

Relating habitat quality to fish survival and population structure requires the ability to measure some index of life-stage specific survival that reflects the effects of habitat on that specific life stage.  One index that reflects habitat quality is straight survival from the parr stage to the sub-adult stage (pre-migrating), data that is easily obtained from mark/recapture data (Burnham et al. 1987).   For salmon, estimates of survival based on mark and recapture from the parr stage to the downstream-migrating smolt stage have been used as an index of habitat quality and land use patterns (Paulsen and Fisher 2001).  However, while useful for making broad comparisons, this index of survival is limited in assessing habitat effects (rearing and spawning habitat), as the survival estimate includes experiences the fish had outside of the habitat area of interest.  For example, in the Paulsen example, fish survival includes over-winter survival (often in downstream areas as the fish move out) and survival to Lower Granite dam on the Columbia River mainstem.  A more direct indicator of freshwater spawning and rearing habitat quality and land use effects on survival is egg-to-parr survival (Petrosky et al. 2001).  Unlike other estimates of survival, this life-stage specific survival measure is desirable in that it accounts for variability in spawner abundance and reflects only the effects of habitat on survival in that habitat.  Estimates of egg-to-parr survival, however, require considerable data including either redd or spawner counts, sex ratios, fecundity, and a robust parr estimate.  Further, Dunham et al. (2001) demonstrated significant observation error can accompany bull trout redd counts, one of the simplest and most cost-effective ways of measuring spawner numbers.

###### Habitat assessment

Bull trout have more specific habitat requirements than most other salmonids (Rieman and McIntyre 1993).  Habitat components that influence bull trout distribution and abundance include water temperature, cover, channel form and stability, valley form, spawning and rearing substrate, and migratory corridors (Fraley and Shepard 1989; Goetz 1989; Hoelscher and Bjornn 1989; Sedell and Everest 1991; Howell and Buchanan 1992; Pratt 1992; Rieman and McIntyre 1993, 1995; Rich 1996; Watson and Hillman 1997).  Preferred spawning habitat consists of low gradient stream reaches with loose, clean gravel (Fraley and Shepard 1989) and water temperatures of 5 to 9 degrees Celsius (41 to 48 degrees Fahrenheit) in late summer to early fall (Goetz 1989).  In the Swan River, Montana, abundance of bull trout redds was positively correlated with extent of bounded alluvial valley reaches, which are likely areas of groundwater-surface water exchange (Baxter et al. 1999).  Survival of bull trout embryos planted in stream areas of groundwater upwelling used by bull trout for spawning was significantly higher than for embryos planted in areas of surface-water recharge not used by bull trout for spawning (Baxter and McPhail 1999).  Pratt (1992) indicated that increases in fine sediment reduce egg survival and emergence.  Watson and Hillman (1997) concluded that watersheds must have specific physical characteristics to provide habitat requirements for bull trout to successfully spawn and rear, and that the characteristics are not necessarily present throughout these watersheds.  Because bull trout exhibit a patchy distribution, even in pristine habitats (Rieman and McIntyre 1993), fish should not be expected to simultaneously occupy all available habitats (Rieman et al. 1997b).

Since 1998, the Fish and Aquatic Ecology Unit of the Forest Service and Utah State University have been assessing aquatic habitat to ensure effectiveness of standards identified in earlier consultation efforts related to land management activities conducted by federal agencies (NMFS 1998).  These survey efforts have focused on insuring the Forest Services land management standards are effective at protecting habitats of listed species.  These surveys are unlike others conducted by the Forest Service in that they do not focus on evaluating the effects of specific projects. The current design is collected following a stratified random basis.  Intensive quality control/quality assurance in part of the survey protocol.  This effort is the only standardized method of collecting data on stream habitat and macroinvertebrate data throughout the Columbia River Basin.  Currently the data is being use to evaluate the effects and effectiveness of management activities on stream habitat attributes (Kershner, in press).  The data collected by the Effectiveness Monitoring program provide the necessary information to evaluate and compare the habitat components that affect bull trout growth and survival and provide a means of contrasting different land management strategies.

In addition, migratory corridors link seasonal habitats for all bull trout life histories.  For example, in Montana, migratory bull trout make extensive migrations in the Flathead River system (Fraley and Shepard 1989), and in tributaries of the Bitterroot River resident bull trout move downstream to over-winter in tributary pools.  The ability to migrate is important to the persistence of bull trout (Rieman and McIntyre 1993; Rieman et al. 1997b).  Migrations facilitate gene flow among local populations when individuals from different local populations interbreed, stray, or return to non-natal streams.  Bull trout migrants may also reestablish local populations that are extirpated by catastrophic events.  Understanding movement among streams and sub-populations is key to understanding the role of migratory corridors in structuring populations and identifying core areas for bull trout.

c. Rationale and significance to Regional Programs

USFWS Recovery Planning

The goals of this project are directed towards fulfilling USFWS needs for bull trout recovery planning.  The USFWS goal is to describe courses of actions necessary for the ultimate delisting of a species and ensure the long-term persistence of self-sustaining, complex interacting groups of bull trout distributed across the species’ native range (Lohr et al. 1999).  To meet this overall goal, USFWS has identified several objectives which require the type of information provided by this project: 1) maintain current distribution of bull trout within core areas in all recovery units and restore distribution where needed to encompass the essential elements for bull trout to persist, 2) maintain stable or increasing trends in abundance of bull trout in all recovery units, and 3) restore and maintain suitable habitat conditions for all bull trout life history stages and strategies.  Further, the USFWS recovery planning document (Lohr et al. 1999) embraces the idea of core areas.  Conserving respective core areas and their habitats within recovery units is intended to preserve genotypic and phenotypic diversity and allow bull trout access to diverse habitats.  The continued survival and recovery of individual core area populations is thought to be critical to the persistence of recovery units and their role in overall recovery of the Columbia distinct population segment.  Our proposed project will provide critical information about bull trout population abundance, trends, relationships to habitat, and potential for improving survival through habitat protection or restoration that will allow USFWS to describe the necessary courses of action and evaluate proposed management actions.

Subbasin Plan

The goals of this project will help managers evaluate threats to listed salmon and trout from potential habitat degradation as identified in the Salmon River Subbasin Plan (Plan) and the Lower Snake River Subbasin, Snake River Subbasin, Lower Salmon River Subbasin, and Little Salmon River Subbasin Bull Trout Problem Assessment, Prepared for the State of Idaho (CBBTTAT 1998).  Further, the  State of Idaho classified the following tributaries as ‘Stream Segments of Concern’: Little Salmon River, Boulder Creek, Hazard Creek, and Hard Creek.  Mandatory site specific Best Management Practices (SSBMPs), developed by local working committees for some these watersheds, minimize impacts that may result from timber management.  Although the ‘Stream Segments of Concern’ program local working committees no longer exist (passage of Senate Bill 1284 -BAG and WAG process), the developed SSBMPs are still in effect today.

In relation to the proposed project, these assessments suggest that efforts for conservation and restoration within the Little Salmon drainage should include: 1) continued maintenance and protection of high quality bull trout habitat at the watershed level for Rapid River; 2) continued or increased fish population inventory and monitoring efforts for Rapid River, Boulder Creek, Hazard/Hard Creek, and Little Salmon River; 3) active restoration of degraded bull trout spawning and early rearing habitat, with a subbasin emphasis on the Boulder Creek watershed, and 10) barrier removal.  They also suggest that active restoration efforts at the subbasin level should include improvements to water quality (i.e. temperature and sediment) and flood event impacts to mainstem Little Salmon River.

More specifically, they highlight that it is important to continue monitoring, or start active monitoring, in known bull trout streams and that these efforts should include bull trout population trends and redd surveys.  They also highlight bull trout distribution and movement studies as important.  Priority streams for intensive bull trout surveys and monitoring include the Little Salmon River: Rapid River, and Boulder Creek, the streams identified for study in this proposal.  In regard to identifying core habitat areas, they suggest that “areas of degraded spawning and early rearing habitat that have high inherent potential should be identified and actively restored.  Areas adjacent to existing high quality habitat and populations should be prioritized, along with degraded areas that are occupied by bull trout”(CBBTTAT 1998).

In addition, these goals should also provide a benefit to listed salmon and steelhead populations in this basin.  The Subbasin Plan identifies the following relevant data gaps or research needs:

1.	Seasonal habitat use, juvenile rearing potential, and smolt yield for mainstem Salmon and major tributary mainstems.   Continuation of physical habitat evaluation to determine benefits of habitat improvements.

7.	Effects of sedimentation on seasonal habitat capacities and survival rates.

8.	Migration timing and survival for smolts in mainstem and tributaries.  Determination of where and why major losses of smolts occur prior to Lower Granite Dam.

The goals of this proposed project are directly applicable to the efforts identified in the Subbasin Plan.  The potential for increasing fish survival from habitat changes needs to be identified, and core areas need to be protected.  Further, evaluation needs to occur when habitat changes are implemented, in order to evaluate the effectiveness of management actions and aide in future bull trout planning for this subbasin as well as other areas.

Habitat Component

Stream habitat surveys are currently being used by state and federal conservation agencies (Bain et al. 1999) to address legal mandates.  Consultation protocols for aquatic species protected under the Endangered Species Act include documentation of the stream habitat characteristics (NMFS 1996). There are also attempts to utilize aquatic habitat metrics as thresholds in meeting the mandates of the Clean Water Act, and physical attributes of stream are being used as management standards in federal land management plans.  These habitat data need to be explicitly related back to fish survival and recovery.

d. Relationships to other projects

This project is a cooperative effort between the USGS Utah Cooperative Fish and Wildlife Research Unit, the USFWS, and the USFS and was designed to compliment other ongoing bull trout work within the Columbia Basin and fulfill USFWS bull trout recovery planning needs (H. Schaller, USFWS, pers. comm.).  The Subbasin Plan notes that one objective for habitat protection is to “Maintain close liaison with the U.S. Forest Service, Bureau of Land Management and other state and federal agencies involved in land and water use programs, and encourage, advocate and support implementation and enforcement of programs that will reduce stream degradation.

In addition, this project has a parallel project proposed for the Imnaha Subbasin in the Blue Mountain Province, with similar goals and approaches.  The data collected from the two paired subbasins is complimentary, providing contrast between different regions (e.g., geology) and land use patterns; however, each proposed project could be successfully completed independent of the other.  The USFS Habitat Effectiveness Monitoring program, from which the habitat component of this project is based, has been on-going since 1998. Over $800,000 has been spent collecting data throughout the Columbia River Basin in the last three years.

This project is complimentary to BPA Project ID # 199405400,  Characterize the Migratory Patterns, Structure, Abundance, and Status of Bull Trout Populations from Subbasins in the Columbia Plateau (formerly Project ID numbers 199405400 – ODFW, 199405400 – CTWSRO, 25088 – ODFW, 199801600 – ODFW).  This proposed project is also complimentary to the approach employed by the Oregon Plan for Salmon and Watersheds Monitoring Program (Nicholas 1997a, 1997b, 1999) as adapted to bull trout in Oregon’s portion of the Columbia Plateau.  Density and population estimates from comprehensive snorkel counts will supplement regional (and BPA funded) parr and smolt monitoring programs (e.g., IDFG General Parr Monitoring Program).  Further, data and empirical modeling will be useful for validating the NWPPC Ecosystem Diagnostics and Treatment (EDT) model for the Imnaha and Salmon River sub-basins, a regional goal (The technical evaluation of the Ecosystem Diagnosis & Treatment Model – a FWP project).

e. Project history (for ongoing projects)

NEW PROJECT

f. Proposal objectives, tasks and methods

Project Outline:

All data and methods will be collected, analyzed, and summarized by core area or local population unit.  We have proposed evaluating 3-4 of the primary bull trout population units in the Little Salmon drainage (Figure 1): Rapid River, Boulder Creek, and associated tributaries (possible Hazard and Hard Creeks).  Each task will be completed for each of the 3-4 streams or population units.  Streams and subbasins were chosen based on data availability, bull trout presence and population strength, contrast in habitat quality and land use, and project feasibility.

Objective 1.  Comprehensive bull trout density and population assessment and monitoring.

Our primary objective involves collecting current density and population abundance data by life history stage using mark/recapture techniques (all life stages), trapping at critical migration points (downstream migrating sub-adults and upstream migrating adults), snorkeling assessments, and redd and/or spawner counts (adults).  These data are necessary for understanding bull trout population structure, trends, rates of population change and movement among subpopulations and metapopulations.  The population assessment will occur every year (2002, 2003, and 2004) for three years.  Data will be summarized and available online annually by March of the following year.  After the first three years of comprehensive data are collected, it may be possible to design a reduced study design for monitoring purposes.  In addition, egg-to-parr survival estimates provide an index of survival that directly relates to the effects of freshwater spawning and rearing habitat quality.  This survival index requires information on spawner number, sex ratio, fecundity, and parr abundance.

Task 1.1  Marking.  We propose to mark juveniles and adults with PIT tags and floy tags (unique for each local population unit) and recapture marked and unmarked individuals using a combinations of electroshocking, screw traps, and weirs with consideration of ESA restrictions that may affect sampling protocol in specific areas.  PIT tags will provide unique information (e.g., time and location of tagging, recapture history) on each fish allowing more extensive mark/recapture analyses described below (e.g., migration, movement, population growth rates).  Floy tags will allow resighting during snorkeling (Task 3.1 below), as a method of recapture, to supplement other means of recapture and provide for a more robust estimate of juvenile and sub-adult population abundance.  In addition, location-specific floy tags will provide information about movement among core spawning and rearing areas.  Bull trout parr will be seined and/or electroshocked in the spring, anesthetized, tagged with both a floy tag and electronic tag, and released.  All captured fish will be weighed and measured before release, to obtain information about annual growth rates and the effects of fish size on survival.  Our goal is to tag as many juveniles and sub-adults as possible (maximum = 500 per local population unit or stream core area, 4 streams, 2000 total).

Task 1.2  Recapture.  Recapture will begin at least 1 month after tagging has been completed and will continue until conditions limit fieldwork.  Recapture will continue for the duration of the study (minimum of three years).  We will recapture tagged and untagged individuals using a combination of techniques including electroshocking (if permitting allows), seining, angling, and screw traps and/or innovative pass-through technology described in Objective 3 below.  Recaptured fish will be passed over a PIT-tag detector and all information about each individual fish will be retained electronically.  In addition, resighting of floy tags during snorkel surveys will be used to supplement recapture data.  Tagged bull trout will be recaptured and released for the duration of the study (3 years) to provide annual estimates of survival, a robust population estimate and to parameterize the Pradel mark/recapture model.  Recapture location will also provide information about movement and sub-population vs. metapopulation structure (see also Objective 3 below).  All captured fish will be weighed and measured before release, to obtain information about annual growth rates and the effects of fish size on survival.

Task 1.3  Snorkel surveys for juvenile densities.  In addition to mark/recapture methods described above, we also propose to do annual nighttime bull trout snorkel surveys for each core stream area or local population unit (4 areas total).  We will use a modified Hankin and Reeves (1988) approach.  Pool and riffle area will be visually estimated for every habitat unit.  Every tenth pool and riffle will be snorkeled and measured for precise habitat area.  Snorkelers will move upstream so as not to frighten fish.  During snorkeling surveys, juvenile trout and salmon will be enumerated.  Resighting of floy tags will also be recorded to supplement recapture data for mark/recapture analyses.  Simultaneous counts of other listed species (e.g., chinook and steelhead) will also be useful for estimating abundance, density, and egg-to-smolt survival).  Habitat unit based counts will be expanded to estimate stream sub-population abundance with confidence intervals.  Habitat units evaluated for the habitat assessment described above will be automatically selected for fish snorkel abundance surveys.  Recapture location will also provide information about movement and sub-population vs. metapopulation structure (see also Objective 3 below).

Task 1.4  Adult and egg information, egg-to-parr survival.

In order to estimates egg-to-parr survival, we will need information on spawner number, sex ratio, fecundity, and parr abundance.  Where possible, spawners will be enumerated to avoid potential error in redd counts (Dunham et al. 2001).  Where it is not possible to enumerate spawners directly, we will complete comprehensive (stream wide) redd counts, taking special precautions to avoid redd count observer error as discussed in Dunham et al. (2001) and to encompass the entire spawning area and time period.  A small sub-sample of adults will be taken for fecundity and sex ratio estimates.  Scales will be removed from this small sub-sample for age and growth analyses.  Parr abundance estimates will come from Tasks 1.1-1.3. above.

Objective 2.  Comprehensive stream and riparian habitat assessment and monitoring.

For the habitat component of our study, we propose to select multiple USFS Effectiveness Monitoring stream and riparian habitat sites within each major spawning and rearing area for annual habitat assessments.  These existing habitat assessment data will be used along with the simple life-cycle model described above, for understanding and predicting the relationship between bull trout population abundance and growth rates and habitat quality and land use.  Here we define habitat quality to include all aspects of bull trout habitat that may affect fish survival and population growth rates.  The habitat assessment will occur every year (2002,2003, and 2004) for three years.  Data will be summarized and available online annually by March of the following year.  After the first three years of comprehensive data are collected, it may be possible to design a reduced study design for monitoring purposes (e.g., the sites that are randomly chosen for the USFS Effectiveness and Monitoring program, independent from this study, may be sufficient).

Task 2.1  Habitat assessment.

Five sites within each stream will be sampled annually, for a total of 20 sites within the Little Salmon drainage.  Table 2 lists the attributes that will be collected.

In addition, 3 temperature monitors will be placed in each stream (12 total), distributed from headwater areas down to the confluence.  Monitors will record daily temperature minimums, maximums and averages.

__________________________________________________________________

Table 2.  Attribute selection summary, showing relationship to stressors, a composite usability ranking, and an indication of how the data will be gathered.

Indicator                                                 Direct/Indirect1       Usability       Data Collection2

Land Use and Current Management

equivalent road acres	D	high	all*

road density - hydrologically connected	D	high	all*

# of culverts and stream crossings	D	high	office, field* culvert failure rate	D	high	office, field

mining history/extent	D	 ?	office, field

forest condition: fire frequency, harvest	D	med/high	office, field

roads: landslide frequency, size, location	D	med	office, field*

Riparian/Floodplain  Habitat

Bank material – soil type, comp., infilt.	I	high	field*

fragmentation of riparian veg. - high contrast	I	high	rm, field

seral stage / structural complexity of riparian	I	high	rm, field

floodplain interactions/connectivity	I	med/high	field

effective ground cover	D	high	field*

In-channel/Community Integrity

invertebrate community structure	I	med/high	field*

water quality - direct measures	I	med	field*

water temperature - direct measures	I	high	field*

frequency, distribution, arrangement of LWD	I	high	field*

cross section mapping	I	high	field*

width to depth ratio, frequency of large pools,	I	high	field, rm*

longitudinal profiles, residual pool depth,

bank angles, % undercut bank, substrate comp.,

bank stability

_____________________________________________________________________________

1 Direct (D) or indirect (I) measure of a stressor

2 Remote sensing (rm) = aerial photos, maps, infra-red, and satellite imagery; office = information on file in USFS offices or that can be gathered through library research; field = requires field data collection; all=all three of these techniques are used.  Data is quantitative, measured, and not estimated.

Objective 3.  Feasibility of innovative pass-through PIT-tag monitoring system.

We propose to evaluate the effectiveness of a new PIT-tag system currently under evaluation.  This system uses a set of stationary antennae hoops placed at key locations within streams and sub-basins that automatically detect and read the PIT tag each time a fish swims through.  We propose evaluating this system in 2002 in the smaller streams (e.g., Lick and Big Sheep creeks) in lieu of screw traps.  This system will provide detailed information about fish movement and habitat use and is much more efficient and cost effective than a screw trap.    Fish are tagged with larger PIT tags (23 mm long), which allow a much longer read range (up to 1 m from the antenna loop plane) than 12 mm tags.  In addition, large pass-through antennae can be constructed (up to 4 m in width by 1.5 m in height).  Pass-through PIT-tag technology has been developed to monitor movements of fish through large fishway orifices, and multiple antenna arrays have allowed comprehensive monitoring of the entire width of a small stream (Zydlewski et al. 2001).  This system has been successfully implemented and validated for continuously monitoring seasonal movements of Atlantic salmon parr and smolts at 93% efficiency (Zydlewski et al. 2001).

In addition to these passive techniques, we will also have the ability to actively monitor for tags using a wand and backback system.  This approach will be applied to monitor freshwater movements and habitat use. A portable detection system using a Destron-Fearing 2001F reader will be deployed.  The reader will be connected to an antenna wand 2 m in length with an open coil inductor loop 0.5 m in diameter attached to the end.  The reader and battery will be enclosed in a plastic housing carried in a small aluminum frame backpack

Applications of this technology include, but are not limited to: examining seasonal movements of juveniles, estimating winter survival, migration timing between two or more stationary systems, overall migratory run timing to and between passage structures, monitoring fine-scale spatial movements to assess microhabitat preference variables, and monitoring smolt to adult survival. Dr. Gayle Zydlewski at the Abernathy Fish Technology Center of the U.S. Fish and Wildlife Service is evaluating this system.  This evaluation will be completed in December of 2002.  If successful and deemed feasible in larger streams, pass through PIT-tag technology will replace screw traps where possible for subsequent years of the study.

Task 3.1   Tagging, detection, and fish movement.

Sampled fish (see also Task 1.2 above, “Recapture”) will be PIT-tagged using the larger PIT tags, and detection systems will incorporate full-duplex PIT-tag technology.  We will construct pass-through systems at locations where small streams under high flow conditions are constricted to flow through a defined region, such as under bridges or in culverts. Stationary detection systems will be deployed at 2 sites per stream, in 2 streams.  One detection system will be located near the upper end of the stream and one just above the confluence with the next stream or drainage to capture movement among sub-populations and major spawning and rearing areas. Each site will require 2 – 3 antenna arrays that will each be powered by an FS1001A Destron-Fearing reader.  PIT-tag based remote monitoring methods will be applied to monitor freshwater movements and habitat use. A portable detection system using a Destron-Fearing 2001F reader will be deployed.  The reader will be connected to an antenna wand 2 m in length with an open coil inductor loop 0.5 m in diameter attached to the end.  These systems will be similar to the system being tested at the U.S. Fish and Wildlife Service, Abernathy Fish Technology Center (BPA innovative project, Project #2001-012-00).

Objective 4.  Data analysis.

Data collected in Objectives 1-3 above will be summarized and analyzed as tasks are completed throughout the study.

Task 4.1  Analysis of mark/recapture data; population estimates and movement.

Annual mark/recapture data will analyzed and available each year by March of the following year.  Using MARK software as well as other analytical techniques, mark/recapture data will provide a population estimate with confidence intervals for each stream or population unit.  These mark/recapture data will also provide annual survival estimates with conditional measures of precision, quasi-likelihood procedures to correct for over-dispersion of the data, and bootstrapping for goodness of fit.  Length and weight data collected from captured parr and sub-adults will be provided and may be useful for evaluating growth.  In addition, the mark data will be used to parameterize the Pradel mark/recapture model for estimating lambda, annual rates of population change.  Lambda will be used as a response variable to describe population status and the effectiveness of management actions.  Mark and recapture data will also provide estimates of movement among streams or local population units, and thus information about population structure and metapopulations.  In addition, the population estimate derived from the mark/recapture data can be compared to the population estimate derived from habitat-based snorkel surveys.  This comparison will allow the evaluation of the different approaches and aid in developing future standardized bull trout monitoring programs.

Task 4.2  Analysis of snorkel data:  parr density and habitat use.

Snorkel data will be analyzed each year by March of the following year and provide comprehensive density and abundance estimates.  Habitat unit based counts will be expanded to estimate stream sub-population abundance by stream with confidence intervals.  Habitat units that were evaluated for the habitat assessment described above will be automatically selected for fish snorkel abundance surveys.  We will explore the relationship between habitat use (relative densities) and habitat attributes (e.g., Horan et al.  2000). Recapture location will be analyzed to provide information about movement and sub-population vs. metapopulation structure.

Task 4.3  Analysis of adult and egg data:  egg-to-parr survival.

Adult spawner or redd data from Task 1.4 above will be summarized and available online each year by March of the following year.  Data will be summarized and combined with parr estimates above to estimate egg-to-parr survival, a measure of the effects of freshwater spawning and rearing habitat quality on bull trout survival.

Task 4.4  Analysis of habitat attributes in relation to fish survival and density.

Habitat assessment data will be summarized and available each year by March of the following year.  Habitat attributes will be compared across different habitat quality streams (good to bad) within sub-basins (e.g., Rapid River vs. Boulder Creek) and different sub-basins (Imnaha and Little Salmon) will be compared and evaluated. Annual rates of survival (from mark/recapture and egg-to-parr estimated) for each of the 3-4 streams in addition to estimates of juvenile density will be related to habitat attributes.  We will evaluate potential relationships between habitat attributes and land use patterns and bull trout population structure and life history characteristics.  These analyses will be used to protect core areas and prioritize and evaluate restoration activities.

Objective 5.  Summarizing available information into a simple population model.

Our fifth objective is to build a simple population model based on baseline population data, to be used as an analysis tool and ultimately for a bull trout recovery planning.  The model will use a life-cycle simulation model approach or a Leslie matrix approach that estimates lambda, the rate of population change.  The model will be developed based on all available population and life history data and will include some measure of uncertainty and stochasticity.  Where data allow, predictions of egg-to-parr survival will be made, as this life stage relates most directly to spawning and rearing habitat of bull trout.  Separate local population units (core areas) will be modeled independently.  Ultimately, baseline estimates of lambda and egg-to-parr survival will be calibrated and validated with mark/recapture data described in Objectives 1-3 above.  This model will allow us to evaluate current conditions and monitor trends, to explore options for recovery, and to evaluate management actions.   The baseline model will be built by September of 2002.

Task 5.1  Assemble and summarize all existing bull trout population and life history data for the selected tributaries of the Little Salmon drainage.

We will assemble and summarize all available bull trout population and life history data for the tributaries of the Little Salmon drainage using published literature, gray literature, information from the state, and federal and tribal governments.  We will search for any abundance, counts, or presence/absence data that will allow us to build a preliminary model as described above.  Table 1 provides a preliminary example of the types of information that may be available.  Information that will be particularly useful includes spawner or redd counts, snorkel surveys, trapping, and any growth data from scales.  We expect data to be limited, but chose this subbasin partly because there is some data available (see Table 1).  The model will be calibrated and validated with the population data from our comprehensive mark/recapture and life history study (Objectives 1-3).

Task 5.2   Building the population life-cycle model.

We will build a simple population life-cycle model that incorporates past and existing population data.  The model will be built in a general fashion for both sub-basins (as a recovery planning tool), but parameterization will be based on all empirical data available for each core area and local population unit.  Life stages will remain separate where data are available for parameterization.  The model will estimate annual rates of population change and egg-to-parr survival where possible.  The model will incorporate uncertainty and stochasticity.

Objective 6.  Describe current habitat conditions and land use patterns as they relate to bull trout survival and growth.

Our final objective is to describe baseline habitat conditions and land use patterns as they relate to bull trout survival and growth.  In order to achieve this objective, we will first complete a detailed analysis and summary of all available stream and riparian habitat data for the bull trout streams of the Little Salmon drainage.  Secondly, we will evaluate relationships between these habitat variables and bull trout population and life history characteristics (e.g., growth, survival, annual rates of population change) where data allow.  This approach will allow us to better understand the relationship between bull trout survival and habitat, to identify important core areas that need protection or restoration and to investigate opportunities for habitat improvement across streams within sub-basins as well as across sub-basins.  The baseline habitat assessment will be completed by December of 2002.

Task 6.1  Summarize and quantify all available habitat data.

We will summarize and quantify all available habitat data for the tributaries of the Little Salmon drainage using published literature, gray literature, information from the state, and federal and tribal governments. We will focus on those variables that are thought to be important to bull trout and use the existing USFS Effectiveness Monitoring data where available.  Examples of potential habitat variables of interest are described under Objective 2.  In addition, we will be looking for measures of embeddedness and stream productivity (e.g., nutrients, primary production, secondary production).

The USFS Effectiveness Monitoring program has already sampled several sites within this basin and will continue to sample selected sites in the future as part of their program (Kershner, in review).  In addition, 5 sites within each stream population unit will be sampled annually as part of Objective 2 above.

Task 6.2  Exploring the relationship between habitat and bull trout population status indicators.

We will relate these descriptors of baseline stream and riparian habitat to bull trout density, survival, abundance, and/or presence/absence surveys.  Model estimates of lambda and egg-to-parr survival will be related to existing conditions as estimated through the habitat assessment data review.  The baseline habitat assessment model will be compared to the habitat data collected as part of our proposed expansion of the USFS habitat assessment described as Objective 2 above.

Task 6.3  Model calibration and validation.

The population life-cycle model will be calibrated and validated with the population data obtained in Objectives 1-3 above.  The relationship between habitat attributes and key life stage specific survival rates (e.g., egg-to-parr survival) will be incorporated into the model.  The model will be made available for annual assessments of population change and for recovery planning.  Model estimates of lambda and egg-to-parr survival across different habitat quality streams (good to bad) within sub-basins (e.g., Rapid River vs. Boulder Creek and different subbasins (Imnaha and Little Salmon) will be compared and evaluated.  These comparisons of life-stage survival rates can be used to identify potential fro improving habitat and I in recovery planning to prioritize management actions in these sub-basins as well as in other sub-basins where listed bull trout reside.   This empirical model will be available for evaluating predictions of survival and productivity from large-scale hypothetical or expert models like EDT.

g. Facilities and equipment

The Fish Ecology Lab of the Utah Cooperative Fish and Wildlife Research Unit at Utah State University is fully capable of handling all aspects of field research and subsequent data analysis.   Accessible workspace includes two university offices, two storage facilities for equipment, one fully-equipped university laboratory with fume hood, otolith processing equipment, image analysis equipment, several microscopes, two freezers, four computer printers (including one color printer), five desktop personal computers and three laptop computers (including necessary scientific, graphical, data analysis, and statistical software).  Vehicles include 6-8 full-sized pick up trucks.  Field sampling gear includes: McNiel coring apparatus and sieves, pH meter, conductivity meter, flow meter, backpack and canoe-mounted electrofishing units, handheld GPS units, temperature and oxygen meters, temperature data loggers, water sampling equipment (including access to analysis equipment), camping gear, snorkeling and diving gear, waders, and all peripheral equipment.   In addition, year-round access is available to a state-of-the-art wet lab facility for the holding of all aquatic organisms.  This facility includes 10 high-volume tanks and 26 fifty-gallon aquaria.  All tanks have flow-through and water temperature control capabilities including 24-hour alarm monitoring.

The only high cost equipment to be purchased with project funds includes 1 screw trap (an additional screw trap will be donated by USFWS) and innovative pass-through PIT- tag equipment (Objective 3).

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Bain, M. B., T. C. Hughes, and K. K. Arend. 1999. Trends in methods for assessing freshwater habitats. Fisheries 24:16-21. | n |
| Baxter, J.S., and J.D. McPhail. 1999. The influence of redd site selection, groundwater upwelling, and over-winter incubation temperature on survival of bull trout (Salvelinus confluentus) from egg to alevin. Canadian Journal of Zoology 77:1233-1239. | n |
| Baxter, C. V., Frissell, C. A., and F. R. Hauer. 1999. Geomorphology, logging roads, and the distribution of bull trout spawning in a forested river basin: implications for management and conservation. Transactions of the American Fisheries Society 128:854-867. | n |
| Bonneau, J. L., R. F. Thurow, and D. L. Scarnecchia. 1995. Capture, marking, and enumeration of juvenile bull trout and cutthroat trout in small, low-conductivity streams. North American Journal of Fisheries Management 15:563-568. | n |
| Buchanan, D. V., M. Hanson, and B. Hooton. 1997. Bull trout status report for Oregon. Oregon Department of Fish and Wildlife. Portland, Oregon. | n |
| Burgman, M.A., S. Ferson, and H. R. Akcakaya. 1994. Risk assessment in conservation biology. Chapman and Hall, London. | n |
| Cooch, E., and G. White. 2001. Program MARK. A gentle introduction. Colorado State University, Fort Collins, Colorado. <www.cnr.colostate.edu/~gwhite/mark/mark.htm/> | n |
| Clearwater Basin Bull Trout Technical Advisory Team. Lower Snake River Subbasin, Snake River Subbasin, Lower Salmon River Subbasin, and Little Salmon River Subbasin Bull Trout Problem Assessment, Prepared for the State of Idaho (1998). | n |
| Dunham, J., B. Rieman, and K. Davis. In press. Sources and magnitude of sampling error in redd counts for bull trout Salvelinus confluentus. North American Journal of Fisheries Management. | n |
| Fraley, J. J., and B. B. Shepard. 1989. Life history, ecology, and population status of migratory bull trout (Salvelinus confluentus) in the Flathead Lake river system, Montana. Northwest Science 63:133-143. | n |
| Franklin, A. B. In press. Exploring ecological relationships in survival and estimating rates of population change using program MARK. Colorado State University. Fort Collins, Colorado. <www.colostate.edu/depts/coopunit/> | n |
| Goetz, F. 1989. Biology of the bull trout, Salvelinus confluentus, a literature review. U.S. Department of Agriculture, U.S. Forest Service, Williamette National Forest, Eugene, Oregon. | N |
| Goetz, F. 1991. Bull trout life history and habitat study. U.S. Department of Agriculture, Forest Service, Deschutes National Forest, Bend, Oregon. | N |
| Hankin, D. G., and G. H. Reeves. 1988. Estimating total fish abundance and total habitat area in small streams based on visual estimation methods. Canadian Journal of Fisheries and Aquatic Sciences 45:834-844. | N |
| Horan, D. L., J. L. Kershner, C. P. Hawkins, and T. A. Crowl. 2000. Effects of habitat area and complexity on Colorado River cutthroat trout density in Uinta Mountain streams. Transactions of the American Fisheries Society 129:1250-1263. | N |
| Hoelscher, B., and T. C. Bjornn. 1989. Habitat, density and potential production of trout and char in Pend Oreille Lake tributaries. Project F-71-R-10, Subproject III, Job No. 8. Idaho Department of Fish and Game, Boise, Idaho. | N |
| Howell, P. J., and D. V. Buchanan, editors. 1992. Proceedings of the Gearhart Mountain bull trout workshop. Oregon Chapter of the American Fisheries Society, Corvallis, Oregon. | N |
| IDFG (Idaho Department of Fish and Game). 1990. SALMON RIVER SUBBASIN, Salmon and Steelhead Production Plan. Co-writers: Nez Perce Tribe of Idaho and Shoshone-Bannock Tribes of Fort Hall. Columbia Basin System Planning. Funds Provided by the Northwest Power Planning Council, and the Agencies and Indian Tribes of the Columbia Basin Fish and Wildlife Authority. | N |
| Jolly, G. M. 1965. Explicit estimates from capture-recapture data with both death and immigration stochastic model. Biometrika 52:225-247. | n |
| Kershner, J. L. In review. Effectiveness monitoring of aquatic and riparian resources in the area of PACFISH/INFISH and the biological opinions for bull trout, salmon, and steelhead. U. S. Forest Service, Logan, Utah. | n |
| Krebs, C. J. 1999. Ecological methodology. Benjamin Cummings, Menlo Park, California. | n |
| Lohr, S., T. Cummings, W. Fredenberg, and S. Duke. 1999. Listing and recovery planning for bull trout. U.S. Fish and Wildlife Service publication. Boise, Idaho. <www.r1.fws.gov/crfpo> | n |
| Meffe, G. K., C. R. Carroll, and contributors. 1997. Principles of conservation biology. Sinauer Associates, Inc. Sunderland, Massachusetts. | n |
| NMFS (National Marine Fisheries Service). 1996. Making Endangered Species Act determinations of effects for individual or grouped actions at the watershed scale. National Marine Fisheries Service, Environmental and Technical Service Division. 32 pgs. <www.nwr.noaa.gov/1habcon/ habweb/pubs/matrix.pdf> | n |
| NMFS. 1998. Biological Opinion for the Land and Resource Management Plans for the National Forests and Bureau of Land Management Resource Areas in the Upper Columbia River Basin and Snake River Basin Evolutionary Significant Units. <www.nwr.noaa.gov/1publcat/1998/lrmp-1998.pdf> | n |
| NMFS. 2000. Biological Opinion: Effects to listed species from operations of the federal Columbia River power system. National Marine Fisheries Service, Northwest Region, Portland, Oregon. <www.nwr.noaa.gov/1hydrop/hydroweb/docs/Final/ 2000Biop.html> | n |
| Pradel, R. 1996. Utilization of capture-mark-recapture for the study of recruitment and population growth rate. Biometrics 52:703-709. | n |
| Paulsen, C. M., and T. R. Fisher. 2001. Statistical relationship between parr-to-smolt survival of Snake River spring-summer chinook salmon and indices of land use. Transactions of the American Fisheries Society 130:347-358 | n |
| Petrosky, C. E., H. A. Schaller, and P. Budy. 2001. Productivity and survival rate trends in the freshwater spawning and rearing stage of Snake River chinook salmon (Oncorhynchus tshawytscha). Canadian Journal of Fisheries and Aquatic Sciences 58:1196-1207. | n |
| Pratt, K. L. 1984. Habitat selection and species interactions of juvenile westslope cutthroat trout (Salmo clarki lewisi) and bull trout (Salvelinus confluentus) in the upper Flathead River basin. Master's Thesis, University of Idaho, Moscow, Idaho. | n |
| Pratt, K. L. 1992. A review of bull trout life history. Pages 5-9 in P. J. Howell and D. V. Buchanan, editors. Proceedings of the Gearhart Mountain Bull Trout Workshop. Oregon Chapter of the American Fisheries Society, Corvallis, Oregon. | n |
| Rich, C. F. 1996. Influence of abiotic and biotic factors on occurrence of resident bull trout in fragmented habitats, western Montana. M.S. Thesis, Montana State University, Bozeman, Montana. | n |
| Rieman, B. E., and J. D. McIntyre. 1993. Demographic and habitat requirements for conservation of bull trout. U.S. Forest Service General Technical Report INT-302. | n |
| Rieman, B. E. and J. D. McIntyre. 1995. Occurrence of bull trout in naturally fragmented habitat patches of varied size. Transactions of the American Fisheries Society 124:385-296. | n |
| Rieman, B. E., D. C. Lee, and R. F. Thurow. 1997. Distribution, status, and likely future trends of bull trout within the Columbia River and Klamath River basins. North American Journal of Fisheries Management 17: 1121-1125. | n |
| Seber, G. A. F. 1965. A note on the multiple recapture census. Boimetrika 52:249-259. | n |
| Sedell, J. R., and F. H. Everest. 1991. Historic changes in pool habitat for Columbia River Basin salmon under study for TES listing. Draft U.S. Department of Agriculture Report, Pacific Northwest Research Station, Corvallis, Oregon. | n |
| Schill, D. J, R. Thurow, and P.K. Kline. 1994. River and stream investigations. Seasonal movement and spawning mortality of fluvial bull trout in Rapid River, Idaho. Project F-73-R-15. IDFG. Bosie, ID | n |
| Shepard, B., S. Leathe, T. Weaver, and M. Enk. 1984. Monitoring levels of find sediment within tributaries to Flathead Lake and impacts of fine sediment on bull trout recruitment. Proceedings of Wild Trout III Symposium, Mammoth Hot Springs, Yellowstone National Park, Wyoming. | n |
| Smith, B., and W. Knox. 1992. Report of findings. Bull trout density sampling. Unpublished report. Oregon Department of Fish and Wildlife. Wallowa Fish District, Enterprise. | n |
| Thurow, R.F., and D. J. Schill. 1996. Comparison of day snorkeling, night snorkeling, and electrofishing to estimate bull trout abundance and size structure in a second-order Idaho stream. North American Journal of Fisheries Management 16:314-323. | n |
| USDA-FS. 1998. Boulder Creek watershed analysis - working draft. USDA, FS, Payette National Forest, New Meadows Ranger District, New Meadows, ID. | n |
| USFWS (U.S. Fish and Wildlife Service) 1998. Klamath River and Columbia River bull trout population segments: status summary. Prepared by the Service's bull trout listing team. Boise, Idaho. | n |
| USFWS. 2000. Biological Opinion: Effects to listed species from operations of the federal Columbia River power system. United States Fish and Wildlife Service, Regions 1 and 6, Portland, Oregon. | n |
| Watson, G., and T. W. Hillman. 1997. Factors affecting the distribution and abundance of bull trout: an investigation at hierarchical scales. North American Journal of Fisheries Management 17:237-252. | n |
| White, G. C., K. P. Burnham, and D. R. Anderson. In press. Advanced features of program MARK. Colorado State University. Ft. Collins, Colorado. <www.colostate.edu/depts/coopunit/> | n |
| Zydlewski, G. B., A. Haro, K. G. Whalen and S.D. McCormick. 2001. Performance of stationary and portable passive transponder detection systems for monitoring of fish movements. Journal of Fish Biology 58:1471-1475. | n |

# Section 10 of 10. Key personnel

Phaedra Budy – Principal Investigator

_______________________________________________________________________

Utah State University, Department of Fisheries and Wildlife

Utah Cooperative Fish and Wildlife Research Unit

Logan, UT 84322-5290

Phone: 435-797-7564, FAX: 435-797-4025, email:

________________________________________________________________________

### EDUCATION

Ph.D.- Aquatic Ecology, Utah State University. Dissertation: ‘ Adding nutrients to enhance the growth and production of  endangered sockeye salmon:  Trophic transfer in an oligotrophic lake.’  Chris Luecke- major advisor.

Bachelor of Science- University of California, Davis.  June 1991

Independent Major in ‘Limnology’  P.Moyle and C.R. Goldman major advisors.

### RECENT PREVIOUS EMPLOYMENT

2000-present.  Utah State University/ USGS Utah Cooperative Fish and Wildlife Research Unit, Department of Fish and Wildlife, Logan, UT 84322-5290.  Faculty and Assistant Coop leader.

1997-2000.   U.S. Fish and Wildlife Service.  Quantitative Fishery Biologist, GS12-02, Columbia River Fisheries Program Office, Conservation Assessment Team Leader.

1996-97.  Utah State University/ Colorado State University/ Puerto Rico LTER – Post doc. on, Atyad shrimp population dynamics and conservation genetics.

1996-97.   Assistant Program Chair for Ecological Society of America-1997.

FIVE RELEVANT PUBLICATIONS

Petrosky, C.E., H.A. Schaller, and P. Budy.  2001.  Evaluation of survival trends in the freshwater spawning and rearing life stage for Snake River spring/summer chinook.   Canadian Journal of Fisheries and Aquatic Sciences 58:1196-1207.

Budy, P., G.P. Thiede, N. Bouwes, C.E. Petrosky, and H. Schaller.  (In press).  Linking earlier hydrosystem experience to mortality in the estuary and ocean: evidence for delayed mortality of Snake River salmon.  North American Journal of Fisheries Management.

Budy, P., C. Luecke, and W. A. Wurtsbaugh.  1998.  Adding nutrients to enhance growth and  production of endangered sockeye salmon:  Trophic transfer in an oligotrophic lake.  Transactions of the American Fisheries Society 127:19-34.

Budy, P., C. Luecke, W.A. Wurtsbaugh, and H. Gross.  1994.  Effects of nutrient enhancement on juvenile sockeye salmon growth.  Lake and Reservoir Management, 9(1):140-145.

Budy, P. C. Luecke, W.A. Wurtsbaugh, and H. Gross. 1995.  Limnology of Sawtooth Valley Lakes with respect to potential growth of juvenile Snake River sockeye salmon.  Northwest Science 69(2):133-150.

________________________________________________________________________

Howard A. Schaller – Principal Investigator

U.S. Fish and Wildlife Service

Columbia River Fisheries Program Office

9317 NE Highway 99, Suite I

Vancouver, Washington 98665

Howard_Schaller@fws.gov

Education:

B.S., Biology, York College, City University of New York (1975)

Masters of Science, Marine Science, C.W. Post Center, Long Island University (1980)

Brookville, New York . Thesis: A simulation predicting the effect of sewage treatment on phytoplankton in the lower Hudson Estuary.

Ph. D., Oceanography (Fisheries), Old Dominion University (1984)

Norfolk, Virginia. Dissertation:  Determinants for the timing of escapement from the sockeye salmon fishery of the Copper River, Alaska: A simulation model.

Professional Experience:

1999-Present. Project Leader for US Fish and Wildlife Service’s Columbia River Fisheries Program Office. Supervise the activities of this Fisheries Resource Office, which is responsible for the Service’s stock assessment of Columbia River fish and aquatic species.  Oversee a Conservation Assessment team, Natural Production team, Harvest and Hatchery Assessment team, and a Columbia River Hydrosystem Coordination team. For details see:   I provide technical guidance to our staff in the areas of: fish stock assessment; population recovery and viability assessment; bull trout recovery planning and design of a monitoring and evaluation plans; Columbia Basin water management; evaluation of habitat restoration projects; and ecosystem evaluations. I represent the US Fish and Wildlife Service on a number of Columbia River technical forums.

1990-1999. Biometrics Program Leader in the Interjurisdictional Fisheries Management Program for the Oregon Department of Fish and Wildlife (ODFW). Supervise and participate in the development of analytical models and statistical procedures to assess, monitor, and describe factors limiting naturally produced fish populations of Oregon. These analytical techniques incorporate and integrate ecology, conservation biology, and population dynamics principles using probabilistic approaches.  Tasked with ensuring that state of the art techniques are used in fish population assessment methods.

1984- 1990.  Senior Fisheries Scientist for the Columbia River Inter-Tribal Fish Commission (CRITFC), Portland, Oregon. Co-Chair of the Pacific Salmon Commission’s (PSC) Chinook Technical Committee.  Responsible for developing analyses to evaluate the impacts of long and short-term fishing proposals on the coastwide chinook salmon rebuilding program. Chief technical advisor to the U.S. delegation on chinook salmon issues. Responsible for supervising staff to assess terminal and mixed stock fisheries on salmon and other finfish populations of the Columbia River for CRITFC.

Selected Publications

Schaller, Howard A and P. R. Mundy.  1982.  Quantitative aspects of the migratory timing of adult chinook salmon (Oncorhynchus tshawytscha) in the Lower Yukon, Alaska.  Virginia Journal of Science, 33(3):151.

Debrot, A, H. Schaller, and M. Matylewich.  1989.  Estimates of sustainable exploitation rates for Columbia River landlocked White Sturgeon: Evaluating the importance of a maximum size limit. Columbia River Inter-Tribal Fish Commission Technical Report 89-4.

Schaller, H. A, C. E. Petrosky, and O. P. Langness.  1999.  Contrasting patterns of productivity and survival rates for stream-type chinook salmon (Oncorhynchus tshawytscha) populations of the Snake and Columbia rivers. Can. J. Fish. Aquat. Sci. 56: 1-15.

Schaller, H.A., C.E. Petrosky and O.P. Langness.  2000.  Reply to Zabel and Williams’ comments on “Contrasting patterns of productivity and survival rates for stream-type chinook salmon (Oncorhynchus tschawystcha) of the Snake and Columbia Rivers” by Schaller et al. (1999). Canadian Journal of Fisheries and Aquatic Sciences 57:1742-1746.

Petrosky, C.E., H.A. Schaller, and P. Budy.  2001.  Productivity and survival rate trends in the freshwater spawning and rearing stage of Snake River chinook salmon (Oncorhynchus tshawytscha). Journal of Fisheries and Aquatic Sciences 58:1196-1207.

_____________________________________________________________________________

Jeffrey L. Kershner – Principal Investigator

National Fish Ecologist, U.S.D.A. Forest Service

Associate Research Professor, Utah State University

Fish and Wildlife Department

Utah State University

Logan, UT. 84322-5210

w (435) 797-2500  email:kershner@cc.usu.edu

Education:

B.A. Humboldt State University 1976 - Fisheries

M.S. Humboldt State University 1981 - Natural Resources

Thesis title: Characteristics and attitudes of some Klamath River anglers

Ph.D. University of California, Davis 1991 - Ecology

Dissertation title: The role of physical factors in the distribution and

abundance of rainbow and brown trout in the Little Truckee River.

Publications:

Hilderbrand, R.H. and J.L. Kershner. 2000.  Conserving inland cutthroat trout in small

streams: how much is enough? North American Journal of Fisheries Management

20:513-520.

Hilderbrand, R.H. and J.L. Kershner. 2000.  Movement patterns of stream-resident

cutthroat trout in Beaver Creek, Idaho-Utah. Transactions of the American

Fisheries Society 129:1160-1170.

Kershner, J.L., C.M. Bischoff, and D.L. Horan.   1997.  A comparison of population,

habitat, and genetic characteristics of Colorado River cutthroat trout in wilderness

and non-wilderness streams in the Uinta mountains.  North American Journal of

Fisheries Management 17:1134-1143.

Kershner, J. L. 1997.  Watershed restoration monitoring and adaptive management. Pages

116-135 in J.E. Williams, M.P. Dombeck, and C.A. Wood, eds. Watershed

Restoration: Principles and Practices.  American Fisheries Society, Bethesda,

Maryland.

Goodwin, C.N., C.P. Hawkins, and J.L. Kershner. 1997. Riparian restoration in the

western United States: A review of the state of the science.  Restoration Ecology 4:4-14.

____________________________________________________________________________

GARY P. THIEDE – Research Associate

583 East 700 South, Logan, Utah 84321.  gary.thiede@cnr.usu.edu

Home phone: (435) 753-0521. Work: (435) 797-2203. FAX: (435) 797-4025.

EDUCATION

1997	Utah State University.  Logan, Utah.  Master of Science degree in fisheries and wildlife.  Thesis: Impact of lake trout predation on prey populations in Lake Tahoe: a bioenergetics assessment.

1990		University of Wisconsin.  Madison, Wisconsin.  Bachelor of Science degree in zoology.

EXPERIENCE

Feb. 2001-	Research Associate.  Utah State University.  Logan, Utah.

present	Projects manager overseeing several research studies.  Duties include: logistical support; budgeting and purchasing; hiring, supervising, training, and evaluating employees; coordinating research activities with state agencies; preparing reports, manuscripts, and presentations; constructing and maintaining research equipment.

June 2000-	Project Leader. Oregon Department of Fish and Wildlife. Madras, Oregon.

Feb. 2001	Lead researcher on kokanee salmon ecology study on Lake Billy Chinook, Oregon.  Duties include: coordinating all project operations; identifying research goals and objectives; budgeting and purchasing; hiring, supervising, training, and evaluating up to three employees; developing experimental design; data collection and analysis including statistical analysis; preparing reports and presentations; public outreach; and working with state, private, and tribal agencies.

Feb.- June	NR Specialist 3.  Oregon Department of Fish and Wildlife.  Portland, Oregon.

2000	Provided technical support for quantitative and theoretical analyses of past and future management impacts on salmon listed under the Endangered Species Act in the Columbia River Basin.  Critically reviewed and evaluated Environmental Impact Statements, draft management plans, and proposed research studies.  Conducted literature reviews and prepared reports.  Collaborated with state, federal, and tribal agencies.

Sept. 1997-	Aquaculture Extension Agent.  United States Peace Corps.  Zambia, Africa.

Nov 1999	Instructed rural subsistence farmers in all aspects of fish culture, small animal husbandry, and farming system integration. Developed training materials for extension agent training.  Prepared reports and presentations.

June 1995-	Research Associate.  Utah State University.  Logan, Utah.

Sept. 1997	Project manager overseeing several ecological research studies aimed at recovery of native and endangered fishes.  Studies examined effects of predation, predator removals, and habitat restoration.  Supervised personnel and managed logistics.  Coordinated research activities, including experimental design, with state and federal agencies. Prepared study plans, reports, and presentations.   Constructed research equipment and facilities.

CHOSEN PUBLICATIONS AND REPORTS

Budy, P., G.P. Thiede, N. Bouwes, C. Petrosky, and H. Schaller.  In press.  Linking earlier hydrosystem experience to mortality in the estuary and ocean: evidence for delayed mortality of Snake River salmon. North American Journal of Fisheries Management.

STUFA (State, Tribal, and U.S. Fisheries Agencies). 2000. A technical review of the National Marine Fisheries Service Leslie matrix model of Snake River spring and summer chinook populations. April 28, 2000. 118 pp.  Technical report.

Thiede, G.P., D.A. Beauchamp, M.W. Kershner, B.C. Allen, and C.A. Gemperle.  In review.  Impact of lake trout predation on prey populations in Lake Tahoe.  Transactions of the American Fisheries Society.

Crowl, T.A., G.P. Thiede, C.J. Schaugaard, and L. Lentsch.  1997.  Effects of nonnative fish on native fish habitat selection, abundance, and growth in the middle Green River, Utah: an in situ experimental assessment.  Technical report.

Stahl, T.S., G.P. Thiede, R.A. Stein, M.F. Austin, and E.M. Lewis.  1996.  Factors affecting survival of age-0 saugeye, Stizostedion vitreum X S. canadense stocked into Ohio Reservoirs.  North American Journal of Fisheries Management 16: 378-387.