# Bonneville Power Administration

# FY 2002 Provincial Project Review

# PART 2. Narrative

Project ID:	29043

Title:	SSHIAP – Columbia Cascades Province

Section 9 of 10. Project description

a. Abstract

The Salmon and Steelhead Habitat Inventory and Assessment Project (SSHIAP) is a partnership-based information system that characterizes freshwater and estuary habitat conditions and distribution of salmonid stocks in Washington.  The SSHIAP system provides a consistent residence, tracking, and data delivery mechanism for these key habitat data elements. To date, SSHIAP efforts have been focused in western Washington; this project reflects the expansion of SSHIAP to the Columbia Cascades Province of eastern Washington.  Work under this project will: 1) update the base USGS hydrolayer to reflect current water channel locations, 2) utilize a recently developed GIS program to automate stream segmentation based on physical characteristics, gradient, and habitat type, 3) assemble existing current and historic salmonid habitat in the Columbia Cascades Province, and 4) deliver web-based and hardcopy products to users.  Project Partners on this effort include: Upper Columbia River Watershed Planning Team, Yakama Nation, Foster Creek Conservation District, USFWS, Washington Conservation Commission-Limiting Factors Analysis, Washington Department of Ecology, and the Washington Department of Fish and Wildlife (lead).

b. Technical and/or scientific background

The SSHIAP effort is designed to address the following key data issues:

Disconnected Habitat Data Sets.  Salmonid habitat assessments have been undertaken by a number of organizations in the Columbia Cascade Province.  For example, substantial inventory efforts have been made by the Chelan, Okanogan, and Foster Creek Conservation Districts and the National Resource Conservation Service (water quality monitoring, Okanogan Watershed Water Quality Management Plan, culvert surveys, Limiting Factors Analysis, soil surveys, Entiat stream survey), Chelan Conservation District/Natural Resources Conservation Service/USDA Forest Service (Entiat Cooperative River Basin Study April 1979, Entiat Valley Watershed Study Coordinated Resource Management Plan August 1999, Ag Fish Water Tour May 24, 2000), USDA Forest Service (Hydrologic Analysis for Forested Lands Entiat River Basin State of Washington June 1978, Watershed Assessment Entiat Analysis Area April 1996, Level 2 stream surveys, fish distribution, spawning ground surveys, culvert inventories, stream width measurements, water temperature data, vegetation mapping, Land Type Associations), US Fish and Wildlife Service (National Wetland Inventory, spawning ground surveys), Chelan County Watershed Program (Channel Migration Zone study and riparian vegetation mapping), Washington Conservation Commission (Limiting Factors Analysis), Chelan Public Utility District (fish distribution, historic records, water quality monitoring), Douglas Public Utility District (fish distribution, water quality monitoring), Washington Department of Fish and Wildlife (SSHEAR, StreamNet, SaSI, HPA database, spawning ground surveys, screw trap data, Priority Habitats and Species, Land Cover types), Department of Natural Resources (aerial photos, GIS transportation layer, Washington Natural Heritage Program), Department of Ecology (Initial Watershed Assessment Water Resources Inventory Area 46 Entiat River Watershed 1995, GWIS water rights/water use database, GIS data for dams and hazardous discharge facilities), Department of Transportation (GIS data for stormwater outfalls, wells, gravel pits and quarries, active and abandoned railroads, and other hydrologic modifications such as major cities, and rest areas), Utah State University (vegetation mapping of Okanogan and Colville National Forests), US Geological Survey (flow gauges, NAWQA), Environmental Protection Agency (Storet), USGS/WDFW (GAP Analysis), USFS/BLM (ICBEMP), Department of Fisheries and Oceans Canada (Okanagan Lake Action Plan Year 4 1999 Report, climate, hydrology, air and water temperature, dissolved oxygen, and sockeye spawning distribution) and Canadian Wildlife Service/Ministry of Forests/The Nature Trust of BC and coordinated by Habitat Inventory and Analysis (historic analysis of the south Okanogan and Similkameen).

While all deal with aquatic habitat in some fashion, these efforts have been designed to address differing priorities, are at different spatial scales, and have not been well connected.  In addition, key data attributes relevant to salmonid recovery planning and conservation strategies (e.g., historical conditions, riparian conditions) remain very inconsistent or yet uncollected.

Habitat as ESA Listing and De-Listing Criteria.  As salmonids have become listed under the ESA, a main factor contributing to their declines has been the loss or degradation of habitat.  Habitat is routinely a de-listing criteria for the majority of other ESA-listed species (plants, wildlife, invertebrates).  In March, 2001, NMFS’ Technical Recovery Teams (TRTs) have agreed to use habitat conditions as a criteria for de-listing (T. Backman pers. comm.), thus making the role of detailed and consistently arranged habitat data (and trends in habitat conditions) imperative.

Outdated Hydrolayer.  Contained within the Columbia Cascades Province are lands and waterways that have been substantially modified by agricultural conversion, irrigation, timber harvest, and urbanization.  Many new stream alignments and ditches have not been recorded on the USGS hydrolayer.  An updated hydrolayer is the backbone to which aquatic habitat data is attached, and serves as the primary platform for GIS data delivery and analysis.

Integration of Federal and Non-federal Inventories Needed.  Aquatic habitat inventories and watershed assessments on federal and non-federal lands have been conducted.  However, these data sets have not (or rarely) been integrated in a formal, consistent way across the broader subbasins and the larger landscapes of the region.  It is crucial that these data sets be integrated in a consistent manner to improve the assessment capability for recovery and conservation efforts.

c. Rationale and significance to Regional Programs

- Relationship and furthering the goals of the 2000 FWP:

2000 FWP p. 22 under D. Strategies: “In general, the purpose of the strategies at the basin level is to allow maximum local flexibility while assuring that subbasin plans follow the best available scientific knowledge, are consistent with one another, and, together, for a well-integrated, well-organized, and comprehensive fish and wildlife program”.

Work under this project is in focused support of the strategies, in that the SSHIAP data system uses scientifically-supported protocols (Johnson et al. 2001) and methodologies, the latest computer technology and programming skills, and robust delivery mechanisms.  Further, the stated purpose of this proposal is to assemble, assimilate, and expand upon existing salmonid habitat data sets to provide a consistent, organized, integrated, and comprehensive habitat information base across the Province (as well as across all of Washington).

2000 FWP p. 22 under 2. Linkage of general biological objectives with strategies:  “Because this is a habitat-based program, implementation strategies will vary depending on the current condition and the restoration potential of the habitat for the species and life stages of interest. …… the first consideration in any particular area is the current condition of the habitat for spawning and rearing and the potential for protection or restoration of that habitat for natural production.”

And, FWP p. 25 under 3. Habitat Strategies:  “Primary strategy: Identify the current condition and biological potential of the habitat, and then protect or restore it to the extent described in the biological objectives.”

Under this proposal, SSHIAP is specifically focused on assembling and delivering current and historical habitat conditions for key aquatic and riparian habitat variables at the 1:24,000 scale for approximately 10,000 miles of mainstem Snake River and tributaries in the Columbia Cascades Province (for a map of the anadromous ESUs in the Columbia Basin, see) http://www.salmonrecovery.gov/Final_Strategy_Map_2.pdf).

- Relationship to Subbasin Summaries

There are 6 subbasins within the Columbia Cascade Province (Entiat, Lake Chelan, Methow, Okanogan, Columbia Upper Middle, and Wenatchee).  At this time, all of these subbasins have draft subbasin summaries (see http://www.cbfwa.org/files/province/plateau/subsum.htm).  SSHIAP provided cleaned and routed hydrolayers with gradient information to the Chelan County Watershed Program for inclusion in the Subbasin summaries.  The summaries include as much information as possible until they are replaced with the more comprehensive subbasin plans.

The goals, objectives, and strategies from the available subbasin summaries that will be supported by work under this proposal are summarized below:

Entiat Goals, Objectives and Strategies supported by SSHIAP:

- Goal 1: Protect or enhance the structural attributes, ecological function, and resiliency of habitats needed to support healthy populations of fish and wildlife.

- Objective 1.	Where appropriate, identify & eliminate barriers to spawning & rearing habitat.

Strategy 3.	Inventory/assess the extent to which dams/dikes act as fish passage barriers.

Strategy 4.	A culvert barrier study needs to be conducted for the Entiat subbasin and the information incorporated into a database and mapped.

Objective 2.	Restore connectivity, diversity, and function to stream channels and the floodplain.

Strategy 1.	Define and map flood-prone extents so potential and past loss of floodplain capacity can be determined and actions can be taken to restore or protect these areas.

Strategy 2.	Identify the factors contributing to the loss of floodplain function for each given reach, and review and select a method for evaluating impaired floodplain functions that addresses causal mechanisms relative to watershed processes.

Strategy 3.	Map the Corps of Engineers dike and any other dikes in the Entiat watershed.

Strategy 4.	Inventory stream channel crossings & document the manner/extent to which they are acting as constrictions within the meander zone, and affecting sediment gravel transport, local scour, LWD movement, & channel meander w/n the floodplain.

Strategy 5. 	Assess the degree to which the Entiat River Road and other roads in the floodplain limit the ability to restore hydraulic processes in the lower 30 miles of the mainstem Entiat River and identify and implement projects to restore a functioning floodplain.

Strategy 7.	Identify and map stream sections within the Entiat that are dredged and recommend hydrogeomorphically based alternatives. This includes reestablishing a connection to the floodplain where appropriate and/or reducing bedload input in the drainage.

Objective 3.	Protect and Restore Riparian Habitat diversity and function.

Strategy 2.	Retain natural areas in developed landscapes, especially undeveloped publicly owned land that contains priority habitats or species. Provide and plan for a network of greenways/corridors to connect existing natural areas.

Strategy 10.	Avoid constructing roads, utility lines, or conducting activities involving stream crossings within riparian zones.

Strategy 11.	Secure riparian habitat, riparian bottomland and side channels between the terminal moraine & Fox Creek & those in the lower Mad River, Stormy Creek, & Roaring Creek, either through conservation agreements, easements, or direct purchases.

Objective 4.	Enhance water quality and quantity.

Strategy 2.	Identify facilities within the Entiat watershed with general and individual wastewater discharge permits and map them into GIS. Record the type and quantity of discharge and assess the extent to which the industrial discharges affect salmonids.

Strategy 3.	Map the location of past, present, and planned water quality monitoring stations into GIS along with associated records detailing type and duration of data collection and the entity responsible for the recording station.

Strategy 7.	Map, with attached data, the active state general permits for stormwater discharge in the Entiat watershed identified in the Needs Assessment for the Wenatchee Water Quality Management Area (DOE 1996).

Strategy 8.	Further investigate winter low water temperatures as a factor limiting the ability of the habitat to sustain populations of salmonids.

Strategy 17.	Outline/map areas of valley bottoms in continuity w/ the surface waters to assess the impact ground water withdrawals have on water availability in the Entiat River.

Lake Chelan Goals, Objectives and Strategies supported by SSHIAP:

### Federal Energy Regulatory Commission: (2) provide funds for developing and implementing plans to address issues related to riparian revegetation, wildlife and dust control in the Stehekin Flats area and to monitor for changes to the Stehekin River channel at its mouth;

U.S. Fish and Wildlife Service: Management goals and objectives of the USFWS include, in addition to responsibilities under ESA, preservation and enhancement of the nation’s fish and wildlife resources, and assurance that fish and wildlife will be given equal consideration with the Lake Chelan Project’s purpose.

National Marine Fisheries Service: Goals and objectives specific to the Lake Chelan Project are protection of habitat for spawning, incubation and rearing of fall chinook salmon in the lower Chelan River and Project tailrace.

U.S. Forest Service: Goals and objectives include implementation of management plans to ensure sustainable ecosystems and provide recreation, water, timber, minerals, fish and wildlife, wilderness and aesthetics for current and future generations.

Bureau of Indian Affairs: Goals and objectives relative to the Lake Chelan Project are to maintain a trust responsibility to trust lands involved. This trust is a blanket trust for fish, human and cultural resources.

Yakama and Colville Tribes: Goals and objectives relative to the Lake Chelan Project are to provide recreation that is compatible with healthy fish and wildlife populations, protect and enhance fish and wildlife habitat, and implement a management plan to maintain the compatible mix of native and non-native species to satisfy present and future sport fishing demands.

Washington Department of Fish and Wildlife: Management goals and objectives are to preserve, protect, and perpetuate diverse fish and wildlife resources and habitat.

Washington Department of Ecology: Goals specific to the Lake Chelan Project are to maintain water quality and to preserve water clarity.

National Park Service: The Lake Chelan NRA Final General Management Plan/Implementation Plan Alternatives/Environmental Impact Statement (NPS, 1995) provides management direction for the NPS lands within the Lake Chelan NRA. The plan addresses the following issues and corresponding goals:

- Lower Stehekin River channel and floodplain management—preserve and restore the free-flowing character and natural processes of the river and its tributaries;

- Wetlands—preserve and restore ecological processes and conditions in wetlands, floodplain, shoreline, and riparian areas;

- Threatened, endangered, or rare species—preserve and restore species and ecological relationships that would exist were it not for human impacts;

Lake Chelan Comprehensive Fishery Management Plan

Goal 1. Emphasize restoration/enhancement of native species, where feasible.

Goal 5. Develop an M&E framework that includes an Adaptive Management component.

Objective 1	Restore native fish species to Lake Chelan while supporting the existing recreational trout fishery.

Strategy 5.	Develop monitoring and evaluation (M&E) program to assess efficacy of management actions.

- Objective 2	Balance the populations of species inhabiting Lake Chelan (e.g., kokanee, landlocked chinook salmon, and lake trout).

Strategy 7.	Develop M&E program to assess efficacy of management actions, particularly for assessing contribution of kokanee stocking program.

- Objective 3	If feasible, reintroduce self-sustaining populations of bull trout in waters they historically inhabited in the tributaries that drain into the Stehekin River or directly into Lake Chelan.

Strategy 2.	If a fluvial bull trout population is found, then determine if habitat conditions exist which have limited their re-colonization of the system.

Strategy 3.	Eliminate the factor(s) limiting bull trout or determine if adequate population exists to provide broodstock.

Strategy 6. 	Develop an M&E program to assess efficacy of management actions.

Lake Chelan Comprehensive Fishery Management Plan: Chelan River

Goal 2: Meet water quality standard for designated beneficial uses.

Goal 3: Provide spawning and rearing habitat for summer chinook and steelhead in Reach 4.

Goal 4: Provide spawning and rearing habitat for summer chinook and steelhead in the Project tailrace.

Objective 1.	Establish a naturally functioning aquatic ecosystem in the bypassed reach of the Chelan River

Objective 2.	Establish minimum flows adequate to support riparian vegetation, benthic food organisms, cutthroat trout and native cool-water species in Reaches 1, 2 and 3

Objective 3.	Establish flows and habitat adequate to support spawning, incubation and early rearing of chinook salmon and steelhead trout in Reach 4 and the tailrace.

Methow Goals, Objectives and Strategies supported by SSHIAP:

Goal:  The habitat goal in the Methow Subbasin is to restore and maintain normative biological and physical processes such that healthy indigenous populations of aquatic and terrestrial species can sustain themselves over the long-term.

Objective 1.	Protect intact healthy habitat and restore habitat connectivity and overall habitat quality in degraded areas.

Strategy 2.	Restrict residential development within the floodplain. Enforce existing regulations under NEPA, SEPA and the Shoreline Management Act.

#### Washington Department of Fish and Wildlife

#### Lost River Subwatershed

Strategy 1.	Develop an alternative to maintaining the dike on Lost River (built on National Forest land). Reestablish the habitat forming processes themselves by including structural components that complement the restoration of the watercourse’s access to the stream meander zone and riparian growth and instream woody debris maintenance.

Strategy 2.	Allow no further development on the alluvial fan and immediately upstream to the bridge, that would constrict or constrain the channel, degrade riparian areas, negatively impact ground water and surface water interactions, or in any other way degrade stream channel functions.

#### Upper Methow Subwatershed: Goat Creek

Strategy 1.	The Methow River between Winthrop and the Lost River confluence is the most productive spring chinook salmon spawning habitat in the entire Methow Subbasin. Protecting functioning floodplain, riparian habitat and side channels within the channel migration zone of the Methow River in this subwatershed is critical to sustaining naturally producing spring chinook in the Methow watershed.

Strategy 4.	Address the affects of roading, logging, stream crossings, grazing, and the water diversions on the hydrology of Goat Creek. Habitat projects in this drainage should address restoring channel function by reducing road density/proximity, eliminating grazing impacts, reducing water crossing structure impacts, and reestablishing mature riparian vegetation along degraded stream reaches.

Strategy 5.	Restore fish passage at the USFS Rd. 52 crossing on Whiteface Creek.

Strategy 6.	Restore channel function within the floodplain in the lower 1.5 mile channelized section of Goat Creek.

Strategy 7.	Roads above Vanderpool Crossing should be obliterated and replanted, as identified in watershed analysis (USFS 2000c).

##### Upper Methow Subwatershed: Little Boulder & Hancock Springs

Strategy 1.	Replace the fish-blocking culvert on Hwy. 20 at Little Boulder Creek with a bridge or bottomless arch.

Strategy 2.	Address low flow concerns in lower Little Boulder Creek to improve fish passage.

Strategy 3.	Replace the fish-blocking culvert on Hancock Creek upstream to Wolf Creek Road with a bridge or bottomless arch.

Strategy 5.	Restore riparian buffers in Fawn Creek. Improve LWD levels in Fawn Creek.

##### Upper Methow Subwatershed: Wolf Creek

Strategy 4.	Develop a channel condition assessment and restoration needs assessment for Little Wolf Creek.  The assessment should evaluate the current channel condition and its effects on Wolf Creek.

#### Upper Methow Subwatershed: Early Winters Subwatershed

Strategy 2.	Improve riparian conditions in the lower reach.

#### Chewuch River Subwatershed: Chewuch Mainstem

Strategy 4.	Reduce road densities, particularly in highly erosive areas (such as mid-slope areas) and riparian areas.

##### Chewuch River Subwatershed: Chewuch Tributaries

Strategy 1.	Implement habitat projects to restore floodplain function and increase the LWD in the alluvial fans of Twentymile and Farewell creeks.

Strategy 3.	Habitat projects aimed at decreasing road densities in Cub, Boulder, Eightmile and Falls Creek drainages, through road abandonment and road stabilization, should be pursued to reduce sediment delivery and improve surface hydrology impacts, two factors contributing to habitat degradation in this portion of the Chewuch subwatershed.

Strategy 4.	Determine if Eightmile road is creating a barrier and if so, repair.

#### Middle Methow Subwatershed: General Strategies

Strategy 1.	Protect the channel migration zone of the Methow River from activities that will further constrict or constrain the channel, degrade riparian areas, negatively impact ground water and surface water interactions, or in any other way degrade stream channel functions.

Strategy 2.	Restore access to floodplain areas that have been disconnected by dikes.

Strategy 3.	Restore access by the mainstem channel to side channels disconnected by dikes.

Strategy 5.	Increase LWD levels in the mainstem. This should be done by: restoring the river’s access to its floodplain to allow habitat-forming processes to occur (i.e., LWD recruitment, stream energy dissipation, riparian plant community development, bedload transport and deposition); and improving riparian habitat conditions to allow for the development of a mature stand component.

##### Middle Methow Subwatershed: Beaver Creek

Strategy 5.	Purchase property to provide for channel migration.

#### Twisp River Subwatershed: Twisp Mainstem

Strategy 1.	Increase LWD levels, recruitment and retention in the lower sections of the Twisp River.

Strategy 2.	Reduce road densities and their effects on hydrology and instream sediment conditions.

Strategy 3.	Protect floodplains through acquisition and conservation easements.

Strategy 4.	Restore access to the floodplain and reconnect side channels in the lower 15 miles of the Twisp River.

Strategy 5.	Evaluate critical areas ordinances and floodplain ordinances for inclusion of floodplains not presently mapped (Okanogan County 1996). Floodplains are defined as “lowland areas that are periodically inundated by the lateral overflow of streams or rivers”.

##### Twisp River Subwatershed: Twisp Tributaries

Strategy 2.	Do not remove the culvert acting as a barrier on Reynolds Creek. Brook trout are found below the culvert and bull trout above it. Replacing the fish-blocking culvert with a passable structure would expose the bull trout population in upper Reynolds Creek to brook trout competition.

Strategy 3.	Address road densities and their effects on hydrology and instream sediment conditions in the subwatershed.

Objective 2.	Improve instream water quantity and quality within Subbasin.

Early Winters Subwatershed.

Strategy 1.	Address improving low flow conditions in the lower reach and determine biologically based instream flows below the two diversions.

#### Twisp River Subwatershed: Twisp Mainstem

Strategy 1.	Investigate alternatives to improve low flow conditions in the subwatershed.

Strategy 2.	Gather baseline temperature data.

#### Yakama Nation

Objective 1	Protect intact healthy habitat and restore habitat connectivity and overall habitat quality in degraded areas.

Strategy 1.	Habitat projects that support improved instream base flows (i.e., restoring drained wetlands), restore cut off side channels, rehabilitate riparian areas, and remove constrictions and constraints within the channel migration zone (i.e. dikes, roads and inadequately sized stream crossing structures) should receive priority.

Strategy 2.	The McKinney dike should be considered for removal. The side channel blocked-off by this dike is located in the reach of the upper Methow River that usually maintains surface flows even during dry years when the main channel both upstream and downstream dewaters. To restore access to the year-round juvenile rearing habitat blocked by the McKinney dike and to restore the functionality of this reach, the dike will need to be removed.

Strategy 3.	Existing LWD needs to be protected and overall LWD levels need to be increased to “acceptable levels” within the mainstem Methow River. Options for facilitating further recruitment and establishment of LWD need to be investigated.

Strategy 5.	Prevent further development within the channel migration zone that will constrict or constrain the channel, degrade riparian areas, negatively impact ground water and surface water interactions, or in any other way degrade stream channel functions.

### Wildlife Goals, Objectives and Strategies

The primary Methow Subbasin wildlife goals are to protect, enhance, restore, maintain and/or increase wildlife populations and associated habitats to viable or management objective levels, for ecological, social, recreational, subsistence, and aesthetic purposes within the Subbasin. Emphasis is placed on PHS listed species and habitats. Special effort is directed at securing critical habitat components that are in limited supply, under imminent threat of development, and underrepresented in the pubic land base.

#### Riparian/floodplain

Objective 1	Maintain the ecological function and associated biodiversity of deciduous riparian forest within the Subbasin

Strategy 1.	Halt or reverse loss of riparian/floodplain forest to development.

Strategy 2.	Protect existing riparian/floodplain habitat through acquisition and conservation easements.

Strategy 3.	Restore native riparian vegetation on suitable sites.

Okanogan Goals, Objectives and Strategies supported by SSHIAP:

#### Confederated Tribes of the Colville Reservation

Goal  Maintain and protect instream and riparian habitat and support ecological function in these habitats.

Objective 1:  Identify key ecological attributes specific to the Okanogan subbasin.

Objective 2:  Maintain adequate stream flow in the Okanogan Watershed to support salmonids at all life stages.

Objective 3:  Reduce summer water temperatures in the Okanogan Watershed to meet the needs of salmonids in all life stages.

Strategy 1:  Identify priority areas for riparian protection and restoration.

Strategy 2:  Restore existing riparian habitat to buffer stream temperatures.

### Upper Columbia Salmon Recovery Board

Goal:  Restore the complexity of the stream channel and floodplain in the Okanogan Subbasin.

Objective 1:  Allow unrestricted stream channel migration, complexity, and flood plain function.

Strategy 1:  Provide fish access to disconnected stream sections or oxbows,

Strategy 2:  Remove dikes (or similar structures) that prevent stream channel migration,

Strategy 3:  Change the points of origin for problematic water withdrawals to less sensitive site(s),

Strategy 4:  Screen water intakes to prevent impingement or stranding of juvenile fish,

Strategy 7:  Remove passage barriers.

### UCSRB objectives for the Okanogan subbasin specifically

Goal:  Protect and Restore Salmonid Habitat in the Okanogan Subbasin.

Objective 1:  	Protect the remaining sockeye and summer chinook spawning and rearing habitat that remains within this watershed.  In particular, the summer chinook spawning habitat located in the lower Similkameen (Category 2) and in the mainstem Okanogan River between Ellisford and Riverside (Category 2) and the remaining sockeye spawning habitat that remains downstream of McIntyre Dam (Category 2).

Objective 2:  	Reconnect smaller tributary streams with the mainstem Okanogan River.  Many of the smaller tributaries once provided thermal refuge for summer and fall migrating adults and for rearing of stream-type juvenile salmonids.

Objective 3:  	Establish a normative hydrograph, decrease the width: depth ratio, increase riparian coverage, and decrease sediment input will also improve the water quality, quantity and would provide for improved upstream migration and over-summer rearing conditions.  Water rights should be purchased or secured through trust for increasing late-summer instream flows of tributary streams.

Columbia Upper Middle Goals, Objectives and Strategies supported by SSHIAP:

#### National Marine Fisheries Service

Objective 1	Between 2001 and 2012, restore habitat, acquire riparian corridors, modify flow regimes, reduce non-point pollution, develop improvement plans for all reaches.

#### Objective 2	Beginning in 2001, identify sampling reaches, survey conditions, describe cause-and-effect relationships, identify research needs.

#### Washington Department of Ecology

Goal:  	Ensure State water quality standards to protect beneficial uses are met. (John Stormon, WDOE, personal communication).

Strategy 1:	Reduce water temperatures to meet water quality standards.  Research and pursue methods for providing cooler waters to anadromous fish at critical stages in their life cycles.

#### Chelan County PUD

Goal 1: 	Protect species of concern  (spring chinook salmon, fall/summer chinook salmon, sockeye salmon, steelhead, and coho salmon (after naturally spawning populations are reestablished)).

Objective  1:  	Insure that the operation of Rock Island and Rocky Reach dams have no net impact (NNI) on the salmonid species of concern.  The NNI concept takes into account the fact that 100 percent survival cannot be achieved at the projects alone, but must also include off-site measures to increase salmonid productivity.  The NNI standard consists of two components.

Strategy 2:  	Compensate for the 9 percent unavoidable project mortality through hatchery programs (7%) and tributary habitat improvements (2%).  The survival standard, hatchery compensation, and habitat improvement combine to provide a 100 percent no net impact on the species of concern.

#### Foster Creek Conservation District

Goal 1:  	Protect natural resources and enhance sustainable, profitable agriculture; and improve the quality of life in Douglas County (Long Range Plan 2001 Update).

Objective 1:  	Facilitation and negotiation of a county-wide habitat conservation plan to address ESA listings in the agricultural community.  The District’s mission in undertaking this project is to enhance the local quality of life in Douglas County by protecting and increasing wildlife species habitat while at the same time providing regulatory certainty and protection from incidental takings for local farmers, ranchers, and orchardists.

Objective 2:  	Serve as lead entity for salmon recovery activities in the Foster and Moses Coulee watersheds.

Strategy 1:  	Administer and facilitate a Citizen Advisory Group in soliciting and prioritizing salmon recovery projects (E.S.H.B. 2496).

Objective 3:  	Serve as lead entity for the Watershed Planning under E.S.H.B. 2514.

Strategy 1:  	Facilitate, administer, and provide technical support to the Douglas County Watershed Planning Association in conducting watershed assessments.

Strategy 2:  	Complete a comprehensive watershed management plan that addresses water quantity, instream flows, water quality, and fish habitat issues in Douglas County.

Wenatchee Goals, Objectives and Strategies supported by SSHIAP:

Goal: The overall goal is to protect, restore and enhance fish and wildlife and their habitats in the Wenatchee subbasin to provide ecological, cultural, economic, and recreational benefits.

Goal 1. Maintain and protect existing high quality habitat and the native populations inhabiting those areas, as described in “Habitat Areas and Quality” and “Fish and Wildlife Status.”

Objective 1	Maintain the distribution, diversity, and complexity of watershed and landscape scale features to ensure protection of the aquatic systems to which species, populations and communities are uniquely adapted.

Strategy 2	Restrict or mitigate management activities that would prevent maintenance or enhancement of existing good habitat. These could include road building, timber harvest, fire prevention, etc. Allow natural processes such as fire, riparian vegetation growth, and woody debris input to continue.

Strategy 3	Protect riparian areas where large woody debris (LWD) is at good levels currently.

Objective 2	Maintain biological diversity associated with native species and ecosystems.

Strategy 1	No further reduction of genetic variability and viability of remaining fish stocks from present levels through improvement of habitats for holding, rearing, and spawning, and through provision of adequate water (quantity and quality) for migration through the system

Strategy 2	Manage critical wildlife habitat to improve the status of threatened and endangered species to a point where they no longer need protection under the Endangered Species Act.

Objective 3	Maintain the spatial and temporal connectivity within and between watersheds. Included are the drainage network connections, floodplains, wetlands, upslope areas, headwater tributaries, and intact refugia.

Strategy 1 	Maintain and restore the timing, variability, and duration of floodplain inundation and water table elevation in meadows and wetlands

Strategy 2	Maintain live and dead connectivity along stream courses, ridge tops, and large forest blocks.

Objective 4 	Maintain favorable streamflows and riparian conditions.

Strategy 1	Maintain the species composition and structural diversity of plant communities in riparian areas and wetlands to provide adequate summer and winter thermal regulation, nutrient filtering, appropriate rates of surface erosion, bank erosion, and channel migration and to supply amounts and distribution of coarse woody debris sufficient to sustain physical complexity and stability.

Strategy 2	Maintain the physical integrity of the aquatic system include shorelines, banks and bottom configurations

Strategy 3	Maintain instream flows sufficient to create and sustain riparian, aquatic, and wetland habitats and to retain patterns of sediment, nutrient, and wood routing.

Strategy 4	Protect areas where stream shading is good. Dedicate streamside areas for riparian management.

Objective 5	Maintain the water quality necessary to support healthy riparian, aquatic, and wetland ecosystems.

Strategy 1	Annual maximum 24-hour water temperatures should not exceed 61 degrees Fahrenheit

Strategy 3	Woody debris within the stream system should average 100 per mile as defined within the Wenatchee Forest Plan.

Goal 2. Restore degraded areas, and return natural ecosystem functions to the subbasin as described in “Habitat Areas and Quality.”

Objective 1	Restore the distribution, diversity, and complexity of watershed and landscape scale features to ensure protection of the aquatic systems to which species, populations and communities are uniquely adapted.

Strategy 1	Provide large woody debris (LWD) for long-term soil productivity and potential and instream.

Strategy 3	Maximize infiltration of precipitation and melt in order to minimize surface runoff. Maintain the integrity of near-surface groundwater movement.

Strategy 6	Restore canopy to provide effective evapo-transpiration and interception to buffer storm events.

Strategy 11	Maintain closed canopies in moist forest communities so that near surface groundwater would not be concentrated and trigger landslides and the potential for surface runoff during connective storms and rapid melt events would be reduced. Avoid large open patch sizes in dense dry forest stands that have little understory vegetation where surface runoff would be accelerated.

Strategy 17	The use of prescribed fire could be used to return the distribution of structural stages within each forest group back to historic conditions. Design timber harvest plans to maintain a distribution of different seral stages within drainage basins, in particular MLSA/LSR's.

Objective 2	Restore biological diversity associated with native species and ecosystems.

Strategy 1	Allow for and promote a more diverse riparian forest type with respect to species and age classes. This will also provide for fish habitat over time and help to maintain diversity within the aquatic system.

Objective 3	Restore the spatial and temporal connectivity within and between watersheds. Included are the drainage network connections, floodplains, wetlands, upslope areas, headwater tributaries, and intact refugia.

Strategy 1	Improve fish screens within the river system.

Strategy 2	Improve and replace stream crossings (culverts) where fish passage barriers exist.

Strategy 3	Correct existing barriers and screen diversions and prevent new passage problems.

Strategy 4	Maintain connectivity of habitats throughout watershed by maintaining adequate low flows

Strategy 5	Restore access to habitat for salmon by removing existing barriers, preventing creation of new barriers, and screening all diversions.

Strategy 6	Restore live and dead connectivity along stream courses, ridge tops, and large forest blocks.

Objective 4:	Restore habitat to support well-distributed populations of native plant, and riparian-dependent species, including habitat necessary for sustaining salmonids at critical life history stages of spawning, rearing and migration.

Strategy 1	Protect, maintain and restore adult holding cover and ensure adequate water quantity for upstream migration.

Strategy 3	Moderate the frequency and occurrences of peak flows to near natural conditions.

Strategy 4	Improve fish screens within the river system.

Strategy 5	Improve holding, resting and juvenile rearing habitat.

Strategy 6	Reverse degradation of holding, spawning, and rearing habitat in through habitat improvements either instream or riparian management to improve bank stability and shading of the water surface.

Strategy 7	Promote the growth of large woody debris wherever possible adjacent to streams.

Strategy 10	Improve riparian areas through planting trees and allowing growth (e.g. brush removal) where LWD is in poor condition. Dedicate streamside areas for growth of healthy multi-layered stand to provide shade and large woody debris.

Strategy 11	Improve shading where it is currently poor by planting trees and tail brush. Dedicate streamside areas for riparian management.

Strategy 13	Restore the availability and effectiveness of the riparian habitats to within historic conditions. Rehabilitate areas at dispersed campsites that have access to riparian areas.

Strategy 17	Manage Riparian Reserves to improve or maintain quality where needed.

Strategy 18 	Enhance habitat to prevent the need for listing species on the Regional Forester’s sensitive species list.

Objective 5:	Increase amounts of water to protect and restore fish habitat.

Strategy 1	Establish instream flows for watersheds that support important fish stocks.

Strategy 2	Protect and/or restore instream flows by keeping existing flows and putting water back into streams where flows are diminished by existing uses — especially illegal or wasteful uses or by poor land use practices.

Strategy 3	Moderate the frequency and occurrences of peak flows to near that found naturally.

Strategy 4	In areas where low stream flow conditions have been identified, install pressurized water systems to provide water on an as needed/used basis. Works with other agencies/tribes/irrigation districts/cities to better manage water use.

Objective 6	Restore the water quality necessary to support healthy riparian, aquatic, and wetland ecosystems.

Strategy 6	Protect natural ecosystems such as wetlands, stream corridors and uplands from adverse effects of agricultural practices.

Strategy 8	Eliminate impacts to surface and ground waters by reducing contamination of stormwater.

Strategy 13	Increase connectivity of late-successional and riparian habitats in areas where extensive human development is not likely to occur.

Goal 3. Restore, maintain, and enhance fish and wildlife populations, as described in “Fish and Wildlife Status,” to sustainable levels and also, when applicable, to harvestable levels, while protecting biological integrity and the genetic diversity of the watershed.

Objective 1. 	Increase or establish salmonid stocks and runs to a level where they can maintain themselves through natural spawning and rearing.

Strategy 1 	Protect and restore spawning, rearing and migration habitat as described under Goals 1 and 2

Strategy 10	Maintain an adequate number of all life stages of trout (especially bull trout) that are well distributed throughout the watershed and are sustained through high quality habitat.

Strategy 12	Allow no further reduction of genetic variability and viability of remaining fish stocks from present levels through improvement of habitats for holding, rearing, and spawning, and through provision of adequate water (quantity and quality) for migration through the system.

Objective 3	Use the strategies and accomplish the objectives described in Goals 1 and 2 to maintain and restore the habitat upon which Wenatchee subbasin fish and wildlife depend.

Goal 4. Increase the information and knowledge needed to protect, restore and manage fish, wildlife and their habitats.

Objective 1.	Provide scientific basis for protecting aquatic ecosystems and enable planning for sustainable resource management

Strategy 2	Annually evaluate project performance and expand or adapt studies as data indicate is necessary or appropriate.

Strategy 3	Develop better understanding of fish passage needs, especially juvenile salmon migration habits and needs.

Strategy 4	Create a permit file for all on-site sewage systems in Chelan County. Using Global Positioning System, place all sites on a GIS database.

Strategy 11	Complete watershed-based inventories and prioritization of fish passage problems.

Objective 2	Accurately assess the responses in fish and wildlife populations and their habitats to specific strategies undertaken.

Strategy 1	Develop and promote the use of appropriate analysis and assessment tools, monitoring plans and guidance to support the strategy and related watershed and regional responses.

Strategy 2	Develop and promote complementary, integrated and flexible approaches for the collection, analysis and sharing of monitoring information within and across sites, watersheds and regions.

Strategy 4	Conduct fish surveys to establish presence/absence and relative abundance of salmonids during appropriate times of the year to catch migrating fish.

Strategy 6	Provide information needed to prepare the biennial “State of the Salmon” report.

Objective 3 	Assess water supply and use in the Wenatchee subbasin

Strategy 1	Prepare a list of studies, plans, and assessments already completed in the watershed

Objective 4  	Determine adequacy of existing instream flows within Wenatchee subbasin for fish and community needs.

Strategy 2	Prepare a list of studies, plans, and assessments already completed in the watershed

Strategy 5	Prepare a streamflow data summary and hydrograph synthesis

Strategy 7	Evaluate the relationship between instream flow and habitat

Goal 5. Improve management, regulation and enforcement, public involvement and government incentives and funding to maintain and restore natural ecosystem and the species they support.

Objective 1.	Make decision-making about and management of fish, wildlife populations and their habitats more effective.

Strategy 1	Tribal, federal, state, and other land and resource managers are encouraged to resolve inter-jurisdictional impediments to salmon recovery.

Strategy 2	Make stewardship of salmonid populations the first priority in managing fishery resources.

Strategy 4	Integrate fish passage and screening activities into implementation of watershed planning and other planning and restoration efforts.

Strategy 5	State and federal agencies will integrate the Endangered Species Act (ESA) and Clean Water Act (CWA) to offer agencies and landowners a predictable, practical and coordinated process to meet the needs of both laws.

Strategy 6	Use scientific principles and information consistent with recovery of healthy salmon populations as the basis to identify and establish geographic priorities for habitat protection and restoration.

Strategy 10	Provide leadership, coordination and technical assistance to agencies and other Statewide Strategy to Recover Salmon partners.

Strategy 11	Status and productivity of wild salmonid populations and their habitats will be regularly monitored to evaluate the performance of protection and recovery actions.

Objective 2 	Strengthen plans and regulations to restore and maintain habitat to support healthy, harvestable quantities of fish.

Strategy 4	Focus state and local land use and salmon recovery efforts first in areas with Endangered Species Act (ESA) listings and areas with potential for high quality habitat.

Objective 3	Use incentives and government funding to support the protection and restoration of fish, wildlife and their habitats.

Strategy 4	Allocate a greater portion of new state and federal funds to habitat protection than to restoration.

Strategy 5	Create a comprehensive long-term funding strategy that uses federal, state, local and private dedicated funds and project mitigation funds to expand correction programs and monitor effectiveness of those programs.

Strategy 6	Create a comprehensive long-term funding strategy that uses federal, state, local and private dedicated funds and project mitigation funds to expand correction programs and monitor effectiveness of those programs.

Strategy 7	Allocate most new state and federal funds for salmon habitat protection and restoration to higher priority geographic areas.

Strategy 8	Provide continuing technical and financial support to ensure that decisions within high priority areas are scientifically sound.

Objective 4.	Build support, involve and mobilize citizens to assist in restoration, conservation and enhancement of fish and wildlife habitat.

Strategy 1	Use volunteer-based organizations where appropriate to gain the best use of limited funds.

The SSHIAP system provides a relational database that includes 13 core and 6 secondary salmonid habitat elements attached within a GIS to a 1:24,000 routed hydrolayer. SSHIAP is designed to 1) provide a current and historical inventory of salmonid habitat condition; 2) assess salmonid habitat conditions at varying scales; and 3) act as a backbone upon which users may attach additional spatially explicit information. Work under this proposal will provide for 1) the creation of 1:24,000 cleaned and routed hydrolayers for 6 subbasins; 2) the creation and systematic integration of fish distribution information and habitat data to the SSHIAP system for 6 subbasins covering approximately 22,500 miles of aquatic habitat within the Columbia Cascade Province; and 3) the distribution of this data and information to salmon recovery partners.  This system will then be utilized to identify and guide management and project actions of the greatest potential significance to salmonid productivity within the region.  The information assembled, synthesized, and delivered from this SSHIAP effort will have a direct and substantial role in the successful development and implementation of subbasin planning and implementation efforts.

3) Relationship to NMFS 2000 Biological Opinion (http://www.nwr.noaa.gov/1hydrop/hydroweb/fedrec.htm)

p. 9-170:  Objectives for monitoring should be set at a subbasin or smaller scale.  Habitat research areas should be identified by assessments and should include management or project actions of greatest potential significance to salmonid productivity in that region.

p.12-2  PFMC has recommended to the Secretary of Commerce an EFH (Essential Fish Habitat) designation for the Pacific salmon fishery that includes all streams, lakes, ponds, wetland, and other water bodies currently or historically accessible to salmon in Washington, Oregon, Idaho, and California, except above the impassable barriers identified by the PFMC 1999.  Salmon EFH excludes areas upstream of longstanding, naturally impassable barriers.  In the estuarine and marine areas, the designated salmon EFH extends from the nearshore and tidal submerged environments within state territorial waters out to the full extent of the exclusive economic zone.

The SSHIAP system is designed to 1) provide a current and historical inventory of salmonid habitat condition; and 2) assess salmonid habitat conditions at varying scales. Work under this proposal will provide for an inventory of essential fish habitat (EFH) through both the creation and systematic integration of data sets relative to the Washington portion of the Columbia Cascade Province.  This system will then be utilized to identify and guide management and project actions of the greatest potential significance to salmonid productivity within the region.

4) Relationship to the ICBEMP:  Although the final Record of Decision has not yet been finalized, many USFS/BLM offices are already using the Subbasin Review Guide (http://www.icbemp.gov) to assist in their subbasin reviews and assessments.  “Key Questions” (Subbasin Review Guide p. 27) being asked through this process specifically relevant to work under this proposal include:  1) “What are the estimated distribution, population condition, and trend of important aquatic species?”, 2) “What are the distribution, condition, and trend of aquatic habitat?”, and 3) “What are the distribution, condition, and trend of riparian systems and overall watersheds?”.  Further, the Subbasin Review Guide recognizes the important role of integration with non-federal lands (p. 10):  “…. Subbasin recommendations and priorities should consider conditions and activities on or within adjacent non-federal lands that may affect recommended actions on BLM- or Forest Service-administered lands.”  Work under this proposal will directly contribute to addressing the questions of fish distribution, habitat conditions, and the integration of information on federal and non-federal lands.

5) Relationship to the Basinwide Salmon Recovery Strategy (“All H Paper”):  Volume 1 of the “All H” documents identify two key habitat-related Recovery Strategies (see p. 4 in http://www.salmonrecovery.gov/Final_Strategy_Vol_1.pdf).  These Recovery Strategies state:  “Take immediate actions to restore streamflow, remove passage barriers, protect high quality habitat and screen diversions” and “Complete subbasin assessments and plans to prioritize longer-term actions.”  The “Habitat Plan”(p. 5-6) follows these Strategies, and provides additional text around immediate habitat actions, and protecting and improving estuary, tributary, and mainstem habitats.  Volume 2 of the “All H” documents http://www.salmonrecovery.gov/Final_Strategy_Vol_2.pdf) contains a section (p. 1-38) entitled “Habitat Element of the Basinwide Salmon Recovery Strategy”.  This section reflects the details of a habitat conservation strategy.  Noted in Table 1 (p. 3-4) are the habitat requirements for the salmon’s life cycle and habitat concerns associated with these life cycle components.  Work under this proposal will assemble, synthesize, and deliver current and historic condition data on the majority of habitat attributes highlighted in the habitat portion of the “All H” documents for the Washington portion of the Columbia Cascade Province.

6) Relationship to the Washington Salmon Recovery Funding Board

The 1999 Washington Legislature created and authorized the Salmon Recovery Funding Board (SRFB)(http://www.wa.gov/iac/salmonmain.html) to guide spending of funds targeted for salmon recovery activities and projects.  The SRFB's mission is to support salmon recovery by funding habitat protection and restoration projects, and related programs and activities that produce sustainable and measurable benefit for the fish and their habitat.  SSHIAP is directly involved in supporting Lead Entities (LEs) and Regional Fisheries Enhancement Groups (RFEGs) (both are key recipients of SRFB funds) to enhance and prioritize their habitat restoration and protection efforts.  Both a LE and RFEG are active in the Columbia Cascades Province, and will be one of the primary audiences for (and Partners with) SSHIAP products under this proposal.

7) Relationship to the Washington State Transportation Permit Efficiency and Accountability Committee (TPEAC – SSB 6188).   The TPEAC legislation was passed in the 2001 legislative session and is framed around environmental permit streamlining and mitigation accountability for transportation projects in Washington State.  The senior TPEAC policy committee under the TPEAC legislation has formally recognized SSHIAP in the following statements:

  - SSHIAP is a logical repository for the Best Available Information (statewide) for salmonids,

  - and that it is a valuable tool for achieving the vision of the TPEAC legislation.

d. Relationships to other projects

Note:  This section is divided into three parts:

Part I.   Projects within the Columbia Cascade Province supported by SSHIAP.

Part II. Basin/State Projects supported by SSHIAP affecting the Columbia Cascade

Province.

Part III.  SSHIAP Partners and Letters of Support for this SSHIAP Proposal.

Part I.   Projects within the Columbia Cascade Province supported by SSHIAP.

BPA Project # 199604200  Okanogan Focus Watershed.  The coordination of a watershed planning project that will assist with the restoration and enhancement of anadromous fish resources.  Gather data pertinent to current and desired watershed conditions.

BPA Project # 200020042  Okanogan/Methow.  Integrating Okanogan and Methow Watershed Data for Salmonid Restoration.  Gather, compile, and integrate all relevant watershed, fisheries, and water-quality information into a pre-developed computerized information tool for dissemination to policy makers and stakeholders for use in watershed restoration planning and monitoring.

BPA Project # 199604200  Okanogan.  Okanogan Focus Watershed.  Initiate the coordination of a watershed planning project that will assist with the restoration and enhancement of anadromous fish resources.  Gather data pertinent to current and desired watershed conditions.

BPA Project # 91999155  Methow.  Establish the Methow Watershed Council.  Form a watershed council composed of multiple stakeholders that will address the challenge of preserving the biological integrity of the Methow Valley watershed through implementation and coordination of conservation and restoration efforts.

BPA Project # 19999046  Methow.  Identify Res Fish & Macroinvertebrate Taxa & Function in Anad Fish Habitat.  Identify resident and non-game fish species and macroinvertebrate genera presence, relative abundance and distribution in the Methow watershed, and assess the ecological role these organisms play in anadromous fish habitat.

This SSHIAP proposal has a strong supportive role and interrelationship to a set of projects now being proposed to BPA by other organizations under this Columbia Cascade Solicitation. These are:

- EDT Analysis for the Upper Columbia Basin. Colville Confederated Tribes. Provides for a comprehensive Ecosystem Diagnosis and Treatment modeling of the Entiat, Okanogan, Wenatchee, and Methow subbasins.

- Physical Processes Method.  Colville Confederated Tribes.  Developing a process to link ecosystem analysis (e.g. EDT habitat conditions) with the physical and causal processes controlling the environment (e.g., temperature, sediment) and identify the appropriate treatment methods.

- Comprehensive Inventory and Prioritization of Fish Passage and Screening Problems in the Wenatchee and Entiat Subbasins.  WA Dept. Fish and Wildlife – SSHEAR Program.  Focus is on fish passage and water diversion inventory and restoration prioritization.

II.  Basin/Statewide Projects supported by SSHIAP that affect the Columbia Cascade Province.

The Independent Science Panel (ISP) was created by the Washington state legislature in 1998 to provide scientific oversight of Washington’s salmon, steelhead, and trout recovery efforts.  The ISP has recently published the “Recommendations for Monitoring Salmonid Recovery in Washington State” (ISP Report 2000-2, PO Box 43135, Olympia WA 98504).  In the report the ISP recommends a comprehensive monitoring program having eight characteristics centering on goals, objectives, statistical designs, indicators, protocols, data management and QA/QC features, funding, and support for integrating findings into management decisions.  Work under this proposal is in direct support of key ISP recommendations (e.g., habitat-based objectives, indicators, protocols, data management and QA/QC aspects).

The Washington Governor’s Salmon Recovery Office published the “Statewide Watershed Assessment Guidance for Salmon” and the “Guide for Watershed Plans for Salmon Habitat” (both are Draft - February 2001).  The focus of the documents was to offer guidance on “the process of compiling and analyzing information on watershed conditions compared to those needed for salmon ….” and “what is needed in watershed plans to restore and conserve the habitat upon which healthy salmon populations rely”, respectively.  As salmonid habitat is the central theme of these documents, work under this project has a very direct link to supporting the technical aspects of the WA Governor’s Salmon Recovery Office efforts.

Limiting Factors Analysis (LFA).  LFA is being undertaken by the WA Conservation Commission (http://www.conserver.org/salmon/index.php3).  The focus of LFA is to collect and assemble known information about the limiting factors within Watershed Resource Inventory Areas (WRIAs). The key objectives of LFA are to put existing limiting factor information into one place rather than creating new data and to make this information available to all interested individuals and organizations.  SSHIAP is integrating and updating LFA information as part of its larger data acquisition methodology.  Although LFA is somewhat general with regards to salmonid habitat data attributes, SSHIAP is gleaning the best of LFA information, and is also using the fish distribution products from LFA reports.  Data integration is rapid, as LFA staff work alongside SSHIAP staff, often in shared offices.

StreamNet (http://www.streamnet.org/):  StreamNet is a data system that maintains current static data and trends for specific kinds of fisheries information for waters within the Columbia Basin.  Salmonid habitat data provided by StreamNet is limited to restoration projects (largely Oregon-based), while fish distribution is delineated upon a 1:100,000 hydrolayer.  The SSHIAP system provides a 1:24,000 routed hydrolayer upon which aquatic habitat is attached relative to geomorphology and habitat type.  Work under this proposal will 1) develop this system over approximately  22,500 river miles within the Columbia Cascade Province; 2) integrate core salmonid habitat data; 3) provide finer-scale fish distribution information; and 4) deliver this data and information to salmon recovery partners.

Data Consistency Across the Columbia Basin.  SSHIAP is the lead organization on a publication entitled:  “Monitoring Salmon Habitat in the Pacific Northwest” (Johnson et al. 2001).  This document provides a synthesis of 492 protocols for the collection of salmon habitat across the region.  A subset of protocols are recommended for use by volunteers and management/research personnel.  The focus of this document is to provide a strong scientific basis for the consistent use of data collection methodologies and data flow across the region.

Part III.  SSHIAP Partners and Letters of Support for this SSHIAP Proposal.

Project Partners:  SSHIAP acts as a conduit and depository for salmon habitat data in Washington.  The data system currently has 31 Project Partners:  Batelle Northwest Laboratory; Evergreen State College; Grays Harbor College; Green River Community College; Jefferson County; King County; Kitsap County; Skagit County; National Marine Fisheries Service; People for Puget Sound; Pierce County Conservation District; Salmon Recovery Funding Board; University of Washington; US Forest Service; US Geological Survey; South Sound Regional Fisheries Enhancement Group; Washington Conservation Commission/Limiting Factors Analysis; Washington Conservation Commission/Conservation Reserve Enhancement Program; Washington Department of Ecology; Washington Department of Natural Resources; Washington Department of Transportation; Western Washington University; Lower Columbia Fish Recovery Board; Yakama Nation; Confederated Tribes of the Colville Reservation; Asotin County Conservation District; Nez Perce Tribe.  The Western Washington Treaty Tribes and the Washington Department of Fish and Wildlife are the lead organizations on this project.

Letters of Support for this SSHIAP Proposal (n=4, as follows):

- Yakama Nation

- Foster Creek Conservation District

- Wenatchee and Entiat Watershed Planning Team (Dept. of Ecology letterhead)

- Pacific Biodiversity Institute

The Pacific Biodiversity Institute

Conserving our rich biological heritage with science,

creative thinking and compassion for people and nature

Executive Director

Peter Morrison

Officers

President

Dan Stroh

Director, City of Bellevue 
Planning Department

Vice President

Vicky Welch

Organic farmer

Secretary - Treasurer Aileen Jeffries

Research Investigator,
WA Department of Health

Board of Directors

David Brubaker, Ph.D.  Associate Professor of Biology, Seattle University

Linda Brubaker, Ph.D.  Professor of Forest Ecology, University of Washington

Kathleen Learned

King County

Superior Court Judge

Chad McCabe, Ph.D.

Geologist, GIS Expert

Trileigh Tucker, Ph.D.

Director of Ecological 
Studies Program, 
Seattle University

Advisory Council

John Adams, Ph.D.

Remote Sensing Expert

Steve Beckwitt

Sierra Biodiversity Institute

Charles Convis

Environmental Systems 
Research Institute

Mitch Friedman

Executive Director,

NW Ecosystem Alliance

David Stokes, Ph.D.

Conservation Biologist

Sonoma State University

David H. Johnson

Washington Department of Fish and Wildlife

Habitat Sciences Program

600 Capitol Way, North

Olympia, Washington  98501-1091

December 12, 2001

Dear Mr. Johnson,

The Pacific Biodiversity Institute supports the Salmon and Steelhead Habitat Inventory and Assessment Program (SSHIAP) in creating a standardized framework to coordinate Salmon Recovery efforts at the Regional level in eastern Washington.  The SSHIAP information system is designed for watershed-, basin- and regional-scale habitat analyses to focus salmonid protection and restoration efforts, and to detect trends in habitat over time.  For this reason, we feel that SSHIAP will be especially useful in the Subbasin Planning Process and for many other uses.

Regional resource managers are in need of a comprehensive and contiguous GIS structure for Strategy Development.  SSHIAP provides this. It may be used as a basis for analysis, spatial representation of resources and a tool for the decision making process.  SSHIAP helps to clearly visualize areas that need protection, identifies barriers to spawning and rearing habitat, identifies areas that will restore connectivity, diversity and function to stream channels and the floodplain, and maps Valley Bottom areas.

SSHIAP’s data structure provides a common spatial framework for storing and relating different types of habitat information, such as fish distribution, gradient, fish passage barriers, flow and hydrologic modifications.  SSHIAP obtains and incorporates existing information, creates and incorporates new data, and is designed for scheduled updates.  This provides the user with “one-stop data shopping” with data in one location and in a consistent reporting format.

This partnership-based information system provides a comprehensive “picture” of the watershed and allows users to create summary data and maps for their area of choice.  This can assist decision makers locally and from outside the area in prioritizing recovery efforts and dollars.   It is our hope that state efforts with SSHIAP continue and are enhanced in central and eastern Washington.

Sincerely,

Jason W. Karl

Senior GIS Analyst

Pacific Biodiversity Institute

e. Project history (for ongoing projects)

Begun in 1995, the Washington Department of Fish and Wildlife (WDFW) and the western Washington Treaty Indian Tribes have been the lead entities on SSHIAP (http://www.wa.gov/wdfw/hab/sshiap/index.htm).   While substantial efforts have been undertaken in western Washington, this proposal marks the beginning of SSHIAP efforts in eastern Washington; there has been no prior history with BPA to date.  A very key product from the SSHIAP effort is the cleaned and routed (and segmented) hydrolayer.  This 1:24,000 hydrolayer is a core and particularly valuable template upon which the arrays of datasets pertinent to salmonids, population distribution and status, land use, etc. are being attached.

f. Proposal objectives, tasks and methods

Objective:  Provide a consistent, comprehensive, and scientifically-robust freshwater and riparian data system for salmonid areas in the Columbia Cascades Province.

Tasks:

Task A) Clean, route, and segment hydrolayer (Columbia Cascade Province - 6 subbasins).

This task will be accomplished using the following procedures:

- Cleaning 1:24K hydrolayer:  Using a 1:24K hydrolayer, remove polygons representing lakes, reservoirs, and ponds to a separate layer called ‘waterbodies’ and delete from the stream layer.  Lakes and double-banked streams are changed to a centerline with connector arcs to the tributaries. Breaks in the linework are corrected and hanging streams are connected to main channels. Arcs are checked for direction and corrected as necessary.

- Routing Hydrolayer:  The 100K routes and stream names are collated to the cleaned 24K layer and additional 24K streams are assigned where appropriate with route IDs assigned.  Corrections to names are made at this time.  A temporary route system without measures is constructed from the 100K and additional named 24K streams.

- Gradients, basin gathering information and stream ordering is completed.  During this routine unassigned type 9 linework with < 5 acre gathering basin will be removed.

- Stream Segmentation:  Segment points are assigned based on gradient breaks and confinement using the 10 m DEM and various wetland coverages as a base. Points are also assigned at the confluence of tributaries that have more than one reach upstream from the mainstem.

- Additional points are digitized at locations where tributaries and mainstems enter a lake or wetland or other major polygonal feature.

- Final routes are then applied.

Task B) With SSHIAP staff and Project Partners, collate data on the core and secondary habitat attributes and enter into the SSHIAP system.  Determine & record gradient, confinement and elevation attributes using GIS for the stream segments identified in Task A.  Collect data on core data attributes not otherwise readily available.

Under this task, the steps are 1) assemble available salmonid habitat data sets; 2) incorporate salmon stock distribution and status.  Habitat data for SSHIAP core and secondary attributes follow protocols recommended in the following publication:  Johnson, D. H., N. Pittman, E. Wilder, J.A. Silver, R.W. Plotnikoff, K.K. Jones, P. Roger, T. A.O’Neil, and C. Barrett.  Inventory and Monitoring of Salmon Habitat in the Pacific Northwest.  Washington Department of Fish and Wildlife, Olympia. 212 p.

SSHIAP core habitat attributes are: Stream Segments (Confinement, Gradient, and Habitat Type), Channel Length, Fish Distribution, Fish Passage Barriers, Hydromodifications, Estuarine-Nearshore Marine Habitat, Riparian Conditions, Historical Habitat Conditions, Flow, Elevation, and Geology.  SSHIAP secondary habitat attributes are: Stream Width, Temperature, Wood Debris, Water Withdrawals, Land Use, and Water Quality.  Supporting the SSHIAP system is a Microsoft ACCESS database linked to GIS mapping capabilities.

*  Stream Segments.  Each watershed is delineated into stream segments on 1:24,000-scale maps based on gradient, confinement and habitat type using current TFW methodologies.  These stream segments are the basic building blocks of all other data storage and analysis capabilities.

*  Habitat Types.  Hydrological features providing salmonid habitat are used in determining and labeling stream segments.  Habitat types include: small tributary, large tributary, side channel, side channel slough, distributary slough, lake/pond, wetland/pond complex, and seasonally flooded wetlands.

*  Fish Distribution.  SSHIAP attributes each stream segment with stock use by compiling information from stream surveys, Salmonid Stock Inventory (SaSI), WA Conservation Commission “Limiting Factors Analysis” mapping efforts, StreamNet, the WDFW Stream Catalog, Watershed Analyses, and field biologists.  Known fish distribution includes habitat that is documented to presently sustain fish populations and areas that have historic records of fish use, even if the fish have been extirpated.  Presumed fish distribution includes stream segments that have no records of fish use but that are below natural barriers and otherwise conform to stock-specific habitat criteria.  Potential fish distribution includes stream segments that either have historic records of fish use or no records of fish use and lie below natural barriers and otherwise conform to stock-specific habitat criteria and are located above a man-made barrier to migration.

*  Fish Passage Barriers.  Natural and artificial barriers to fish passage are recorded by stream segment.  The SSHIAP approach recognizes the variable blocking potential of individual barriers according to hydrology and fish species, and utilizes the SSHEAR methodology for fish passage criteria.

*   Hydromodifications.  Direct changes to habitat, such as dikes, revetments, ditching, stream-adjacent roads, stream crossings, and gravel removal, are recorded by stream segment.

*  Historical Habitat:  Quantifying historical habitat is necessary to answer the question “How much historic habitat has been lost or altered from salmon production?”  A methodology for quantifying historical habitat is currently under development by the SSHIAP team; methodology will follow approaches outlined in Bortleson et al. 1980, Sedell and Luchessa 1982, Thomas 1983, Sedell and Froggatt 1984, Beechie et al. 1994, Kondolf and Larson 1995, Jay and Simenstad 1996, Collins 1997, and Pess et al. 1998.  Historical reconstruction of lost salmon and steelhead habitat provides an essential context for contemporary limiting factors analyses and restoration efforts.

Task C)  Deliver web-accessible, hardcopy maps, hydrolayer, and summary products to users.

Under this task, hardcopy maps will be delivered through the WDFW Priority Habitats and Species Program.  GIS data (including hydrolayers) and summary products will be made available for download at the SSHIAP website (http://www.wa.gov/wdfw/hab/sshiap/).

g. Facilities and equipment

Staff associated with this project will use standard office facilities and equipment.

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |  |
| --- | --- | --- |
| web site for SSHIAP: http://www.wa.gov/wdfw/hab/sshiap/index.htm Beechie, T., E. Beamer, and L. Wasserman. 1994. Estimating coho salmon rearing habitat and smolt production losses in a large river basin, and implications for habitat restoration. North American Journal of Fisheries Management 14: 797-811. Bortleson , G.C., M.J. Chrzastowski, and A.K. Helgerson. 1980. Historical changes of shoreline and wetland at eleven major deltas in the Puget Sound region, Washington. Atlas HA-617, Department of the Interior, U.S. Geological Survey. Collins, B. 1997. Effects of land use on the Stillaguamish River, Washington, ~1870 to ~1990: implications for salmonid habitat and water quality and their restoration. A report to the Tulalip Tribes Natural Resources Dept., Snohomish County Dept. of Public Works, Stillaguamish Tribe of Indians, and State of Washington Dept. of Ecology. 77 p. + app. Jay, D.A., and C.A. Simenstad. 1996. Downstream effects of water withdrawal in a small, high-gradient basin: erosion and deposition on the Skokomish River delta. Estuaries 17: 702-715. Johnson, D. H., N. Pittman, E. Wilder, J.A. Silver, R.W. Plotnikoff, K.K. Jones, P. Roger, T. A.O’Neil, and C. Barrett. Inventory and Monitoring of Salmon Habitat in the Pacific Northwest. Washington Department of Fish and Wildlife, Olympia. 212 p. Kondolf, G.M., and M. Larson. 1995. Historical channel analysis and its application to riparian and aquatic habitat restoration. Aquatic Conservation: Marine and Freshwater Ecosystems 5: 109-126. Nowak, M. K. 2001. Draft Grande Ronde Subbasin Summary. Prepared for the Northwest Power Planning Council. Pess, G.R., B.D. Collins, M. Pollock, T.J. Beechie, S. Grigsby, and A. Haas. 1998. Historic and current factors that limit coho salmon (Oncorhynchus kisutch) in the Stillaguamish river basin, Washington state: implications for salmonid habitat protection and restoration. Sedell, J. R., and J. L. Froggatt. 1984. Importance of streamside forests to large rivers: the isolation of the Willamette River, Oregon, USA, from its floodplain by snagging and streamside forest removal. Interntl Vereinigung fur theoretische und angewandte Limnologie Verhandlungen 22: 1828-1834. Sedell, J. R., and K. J. Luchessa. 1982. Using the historical record as an aid to salmonid habitat enhancement. P. 210-223 in Armantrout, N. B. ed. Acquisition and utilization of aquatic habitat inventory information symposium. American Fisheries Society, Western Division, Bethesda, MD. Stovall, S. H. (editor). 2001. Draft Asotin Creek Subbasin Summary. Prepared for the Northwest Power Planning Council. Thomas, D. 1983. Changes in Columbia River estuary habitat types over the past century. Columbia River Estuary Data Development Program, Columbia River Estuary Study Task Force, Astoria, OR. |  | n |

# Section 10 of 10. Key personnel

# David H. Johnson – Principal Investigator (1 FTE)

# Fish & Wildlife Research Scientist , WA Dept of Fish and Wildlife, 600 Capitol Way North, Olympia, WA  98501-1091, Phone: (360)-902-2603; Fax: (360)-902-2946; E-mail:  johnsdhj@dfw.wa.gov

Education

M.S. in Wildlife Science, Oregon State University, 1993; B.A. in Biology, Minor in Archaeology, Bemidji State University, 1986; Diploma, Natural Resource Technology, Brainerd Area Vocational Technical Institute, 1979; Diploma, Civil Engineering, Mankato Area Vocational Technical Institute, 1975

Biological Work Experience

- Current: Fish and Wildlife Research Scientist, WDFW 1995 to present

- Conservation Biologist, Oregon Dept. Fish and Wildlife, 1994-1995.

- Spotted Owl Coordinator, Oregon Dept. Fish and Wildlife, 1991-1994.

- Spotted Owl/Forest Management Research, Oregon State University, 1987-1991.

- Habitat Specialist, MN Dept. of Nat. Res., Wildlife Management, 1983-1987.

- Area Technician/Inventory Forester, MN Dept. of Nat. Res., Forest Mgt, 1979-1983.

- Assistant Manager/Buyer, Minnesota Hide and Fur, 1979-1980.

- Engineering Technician, Bureau of Land Management, 1978 and 1979.

- Biological Technician, US Fish and Wildlife Service, 1979.

Selected Publications

- Has 40 conservation-based publications on wildlife, forestry, fisheries, and archaeology; e.g.:

Johnson, D.H. and T.A. O'Neil (Manag. Dirs.). 2001. Wildlife-Habitat Relationships in Oregon and

Washington. Oregon State University Press, Corvallis. 736 pp. (Book/CD).

- Cederholm, C.J., D.H. Johnson, R.E. Bilby, L.G. Dominguez, A.M. Garrett, W.H. Graeber, E.L. Greda, M.D. Kunze, B.G. Marcot, J.F. Palmisano, R.W. Plotnikoff, W.G. Pearcy, S.A. Simenstad, and P.C. Trotter.  2000.  Pacific Salmon and Wildlife - Ecological Contexts, Relationships, and Implications for Management.  Special Ed. Tech. Rep. WA Fish and Wildlife, Olympia, WA. 138 p.

- Duncan, J.R., D.H. Johnson, and T.H. Nichols (eds). 1997. Biology and conservation of owls of the

Northern Hemisphere: 2nd International Symposium; 1997 February 5-9 1997; Winnipeg, MB. U.S.

Forest Service Gen. Tech. Rep. NC-190. St. Paul, MN. 635 p.

Professional Expertise:

Engaged in the natural resource field for 26 years, with a primary emphasis on senior scientific, legal, and professional management applications in the fields of wildlife, fisheries habitat, forestry, civil engineering, and marine ecology.   Played a lead role in the development of a wildlife habitat relationships project in Oregon and Washington; salmon habitat data system for freshwater and marine habitats of Washington; surveys and management aspects of Northern Spotted Owls and Marbled Murrelets in Oregon, including a key role in the development of the Recovery Plan for the Northern Spotted Owl and subsequent work under President Clinton's Northwest Forest Plan.  Recent work has included fish/wildlife habitat and Key Ecological Function assessments across the US portion of the Columbia River Basin.  The above work has included participation on many science and advisory teams.  Since 1990, actively engaged in international fish and wildlife conservation efforts (e.g., Australia, Russian Far East, Gambia, Ecuador).  Additionally, involved in archaeology and tribal issues, especially in the Pacific Northwest. Research activities have been focused on wildlife and fish ecology and habitat relationships, with particular involvement in the worldwide conservation of owls.

## Honors and Awards:

Special Achievement Award, Washington Chapter of The Wildlife Society for the book “Wildlife

Habitat Relationships in Oregon and Washington”; Letter of Commendation; 2001 WDFW “Certificate of Merit”. Oregon Dept. Fish and Wildlife for efforts on the Northern Spotted Owl; Letter of Appreciation. USFS. Jack Ward Thomas for involvement in preparation of Viability Assessments and Management Considerations for Species Associated with Late-Successional and Old-Growth Forests of the Pacific Northwest - Report of the Scientific Analysis Team; 1992. Special Commendation.  Secretary of the Interior, Manual Lujan, Jr.  Highest civil service award given to non-Interior Dept. individuals for involvement in drafting the Northern Spotted Owl Recovery Plan. US Army Award for Science Fair innovation.

### Lisa R. Anderson – Co-Project Manager (focus on GIS & SSHIAP Data; 1 FTE)

P.O. Box 503, Ellensburg, WA 98926

Phone: (509) 963-1752; E-mail: anderlra@dfw.wa.gov

Education:

M.S. in Natural Resource Management, Central Washington University, Ellensburg WA, 1994-1996.

B.A. in Fine Art, Graphic Design, Central Washington University, Ellensburg, WA, 1985-1990

Liberal Arts, 1978 - 1979 University of Minnesota, Minneapolis, MN, 1978-1979.

Biological Work Experience:

- Current: Fish and Wildlife Biologist 3, WA Dept. of Fish and Wildlife, 2/2001-present

- Data Systems Specialist/GIS-Analyst, Yakama Indian Nation, Toppenish, Washington, 1997-present.

- Interim Director, National Center for Resource Innovations (NCRI), Central Washington University, Ellensburg, WA. 1999.

- Project Coordinator/GIS Specialist, NCRI, Central WA University, Ellensburg, WA, 1994 -1996.

- Graduate Teaching Assistant, Central Washington University, Ellensburg, WA, 1993-1996.

- Co-Instructor of Desktop Cartography, Central Washington University, Ellensburg, WA, 1993, 1992 - 1994/1989 - 1990

- Graphic Design Project Manager, Productions - Central Washington University, Ellensburg, WA, 1992-1994; 1989-1990.

Selected Publications:

The Unauthorized Use of Federally Developed Water: A Product of the Reclamation Era. 1996.

Professional Expertise:

Organized, operated and maintained a GIS framework for the YN Water Program · Participated in management planning for YN cultural and natural resource departments including: Fisheries, Wildlife, Cultural Resources, Range, Environmental Protection, Forestry and Water Program · Data development and map production for the Water Program and other YN DNR offices · GPS data collection/development  · Coordinated with other GIS personnel to structure and facilitate a Tribal GIS network · Supervised and instructed Tribal technicians and interns.

Evaluated Cooperative Program status with: U.S. Dept of Agriculture, NRCS, Yakama Indian Nation, Kittitas Reclamation District, U.S. Bureau of Reclamation, Kittitas County, The Nature Conservancy, for projects including: Riparian/fisheries habitat delineation, surface water data development, soils data development, endangered plant species site delineation, road atlas development, irrigation facility technical support · Budget evaluation and structuring · Hardware procurement for GIS · Participation in nation workshop as Northwest Regional representative for NCRI · Confer with local, state and federal agencies for ongoing cooperative relationships.

Oversee GIS projects · Procedural planning and scheduling, · Training and supervision of student employees · Develop GIS layers for soil type, riparian habitat, fisheries habitat, endangered plant species, irrigation facility  · Transform scanned imagery/data conversion · Quality control procedure development · Proof and edit data · Archive and retrieve data · Map design and production.

Projects:

Data development for the Wapato Irrigation Project.  Digitizing all linear and point features comprising the facility; Coordinate with BIA personnel for accuracy verification; digitizing, proofing and editing stages · Development  of map series for Biological Assessment;  Map production for the Toppenish Creek Corridor Enhancement Project; development of a map series for publication in a plan to be presented to U.S. Dept. of Interior; data development of geomorphological features of the Toppenish Basin; coordination with the Consulting Engineer for development of data for regional flood abatement, planning and mitigation; Diagram production for the National Environmental Hazards and Earthquake Study in association with USGS and Yakama Nation (YN); interpret field diagrams; YN Representative to Intertribal GIS Council · Participation included presentations at national conferences and responsibility as Chairperson of the Education Committee; Member of Integrated Resource Management Team; additionally, participated in policy decision making process, GIS analysis and map.

Related Experience and Skills:

ArcInfo, UNIX operating system, Quark Express, Bookkeeping, Arc View, NT operating system, Adobe

Illustrator · System Administration, GRASS, PC/Mac Systems· Adobe Pagemaker Procurement, GPS data

collection, Large format scanning, Powerpoint Scheduling, GIS data conversion, AML, Photoshop  Budget Management.

Ned Pittman – SSHIAP Operations Co-Manager and Data Delivery (1.5 FTE)

Washington Dept. of Fish and Wildlife, Olympia, WA 98501-1091

Phone: (360) 902-2568; E-mail: pittmnrp@dfw.wa.gov

Education:

B.S. in Salmonid Biology/Ecology/Hydrology. The Evergreen State College, Olympia, WA, 2000.

Biological Work Experience:

- Current: Fish and Wildlife Biologist 2 (Salmonid Habitat Specialist), WA Dept. Fish and Wildlife, Olympia WA, 4/2000 – present.

- Teachers Assistant (Salmonid Ecology: A Field Course), The Evergreen State College, Olympia WA, 9/2000-12/2000.

- Field Technician (intern/volunteer), Department of Natural Resources, Olympia WA, 1/2000-3/2000, 9/1999-12/1999, & 12/1998-3/1999.

- Field Technical Aid, Thurston Conservation District, Olympia WA, 7/1999-9/1999.

Selected Publications:

- Pittman, N., J. A. Heinis, C. J. Cederholm, In prep. Bird, Mammal, and Invertebrate Consumption of Chum Salmon (Oncorhynchus keta) Carcasses at Kennedy Creek, Mason County, Washington, Winter 1998-1999.

- Pittman, N. In prep. An Observation of Cougars Feeding on a Salmon Carcass in Southwest Washington.

- Jauquet, J. M., N. Pittman, J. A. Heinis, S. R. Thompson, N. Tateyama, C. J. Cederholm.  In prep. Observations of Chum Salmon (Oncorchynus keta) Carcass Consumption by Various Wildlife Species, and Spawning-Caused Changes in Water Chemistry and Streambed Microtopography at Kennedy Creek, During 1997-2000.

Professional Expertise:

Possessed knowledge of methods and practices of land management, soil conservation, habitats, food and habits of wildlife; technical habitat processes; elements of habitat for wildlife and fish; fish and wildlife habitat management techniques; environmental regulations; principles and procedures of fish, wildlife or habitat biological research; fish culture, and fish management; standard laboratory and field methods and statistical data processing relating to fisheries work; fish species, their habits, and life histories; factors influencing the capacity of water bodies to sustain fish populations; hatchery operations and treatments for common fish diseases and parasites; fish collection and spawning procedures, and  fishing regulations

Specific job duties include:

Completed a basic watershed analysis and technical paper presenting the results for the Woodland Creek system in Lacey, Washington with the cooperation of two fellow students.  Reviewed the scientific literature, discussing the role of spawning Pacific salmon in terrestrial and freshwater habitats in a technical paper.  Reviewed the scientific literature, discussing the evolution of spring spawning among the genus Oncorhynchus in a technical paper.  Designed and conducted a study examining the interception of precipitation by various stand and tree types on the Evergreen State College campus with the help of two fellow students.

Received training and quality assurance in TFW monitoring protocol from the Northwest Indian Fisheries Commission, Olympia WA.  Authored an in-house informational paper examining the bull trout; it’s biology, life history strategy, and environmental needs.  Collected data concerning salmonid habitat and spawning gravel, LWD, and morphological form according to TFW Responsible for the acquisition, entry, coordination, QA/QC, analysis, and reporting of salmonid habitat data as part of the Salmon and Steelhead Habitat Inventory and Assessment Program (SSHIAP).  Provide salmonid habitat data and distribution information to the Ecosystem Diagnosis and Treatment (EDT) process.  Draft, refine, and/or evaluate methodologies and survey protocols relative to current and historic freshwater salmonid habitats.  Coordinate and track Federal, Tribal, local government and other state agency salmonid recovery, restoration, and protection efforts.  Train inter- and intra-agency staff in current salmonid habitat methodologies related to SSHIAP and EDT.  Conduct fieldwork to verify SSHIAP modeling efforts.

### Eva Wilder – SSHIAP Operations Co-Manager (1 FTE);

Washington Department of Fish and Wildlife, Olympia WA, 98501

(360) 902-2411; gredaelg@dfw.wa.gov

Education:

The Evergreen State College, Olympia, WA, 1995-1996

B.S. in Cell Biology, Western Washington University, Bellingham, WA. 1996.

Biological Work Experience:

- Current: Fish and Wildlife Biologist 2, Department of Fish and Wildlife, Habitat Management Division, Olympia, WA, 1999-present.

- Office Assistance Senior, Office of the Attorney General, Olympia, WA, 1997-1999

- Research Assistant III, Western Washington University, Bellingham, WA, 1996-1997.

- Teaching Assistant, Western Washington University, Bellingham, WA, 1996-1997

Internship: USDA Forest Service Research Station, Tumwater, WA,  April 1993 – July 1993:

Selected Publications:

- Johnson, D.H. and T.A. O'Neil (Manag. Dirs.). 2001. Wildlife-Habitat Relationships in Oregon and

Washington. Oregon State University Press, Corvallis. 736 pp. (Book/CD).

- Cederholm, C.J., D.H. Johnson, R.E. Bilby, L.G. Dominguez, A.M. Garrett, W.H. Graeber, E.L. Greda, M.D. Kunze, B.G. Marcot, J.F. Palmisano, R.W. Plotnikoff, W.G. Pearcy, S.A. Simenstad, and P.C. Trotter.  2000.  Pacific Salmon and Wildlife - Ecological Contexts, Relationships, and Implications for Management.  Special Edition Tech. Rep. WA Department of Fish and Wildlife, Olympia, WA. 138 pp.

- Wilder, E. L., and D. H. Johnson. In prep. Relationship Between Pacific Salmon and 605 Species of Birds, Mammals, Reptiles, and Amphibians in Oregon and Washington.

Professional Expertise:

Possesses knowledge of methods and practices of land management; habitats, food and habits of wildlife; technical habitat processes; elements of habitat for wildlife and fish; fish and wildlife habitat management techniques; principles and procedures of fish, wildlife or habitat biological research, and fish management; standard laboratory and field methods and statistical data processing relating to fisheries and wildlife work; fish and wildlife species, their habits, and life histories.

Specific job duties include:

Assisted in timely completion of data entry, quality assessment/control, and summarization of wildlife and habitat data that was incorporated into the data matrices under the “Wildlife and Species Relationships in Oregon and Washington” (SHP) project. Lead role in development of the index and glossary, finalizing the photographic needs of the SHP, and finalization chapter materials for the final SHP publication – Wildlife-Habitat Relationships in Oregon and Washington, reviewing the format of chapter sections, co-authoring several chapters (marine, habitat descriptions, salmon-wildlife relationships);  Maintenance of WDFW Wildlife Diversity Library at the Habitat office in Olympia.

Lead role in development and finalizing of Key Ecological Functions of Resident Fish in the Columbia Basin, including logistics and organization of expert panel sessions to characterize functions of fresh water fish and their habitat involving close cooperation with other agencies; development of the matrices for the panels; development of Microsoft Access database to store the data from the panels; and quality assessment/quality control and summarization of the subsequent data.

Assisting in the organized expansion of the Salmon and Steelhead Habitat Inventory and Assessment Project (SSHIAP); involved in the development of the SSHIAP Executive Summary brochure for the 2001 legislative session.

Currently involved in the development of a technical report, Monitoring Salmon Habitat in the Pacific Northwest. Directory and Synthesis of ~90 protocols for sponsors and volunteers in Washington, Oregon, Montana, Idaho, British Columbia and Alaska.

Involved in a research leading to a search for sequence homology between caudal gene of Drosophila melanogaster and cDNA of Nasonia vitripensis. Among molecular techniques used were: DNA extraction, purification, and sequencing; PCR reaction; Northern and Southern Blotting; hybridization with radioactive and immunofluorescent probes; culturing stocks of E.coli, bacteriophage , and stocks of Nasonia vitripensis.

Scott E. Anderson – Operations Co-Manager (Field data collection: 1 FTE)

### WA Dept. Fish and Wildlife

2108 Grand Boulevard

Vancouver, WA 98661-4624

## RELEVANT PROFESSIONAL EXPERIENCE

Fish and Wildlife Biologist 2,  Salmon Steelhead Habitat Inventory Assessment Program (SSHIAP) Habitat Science Team, Habitat Program, Washington State Department of Fish and Wildlife, Region 5.  October 2000 to present.  Responsible for acquisition, documentation, coordination, and entry of salmonid habitat data related to recovery efforts in Washington State; lead entity outreach in Water Resource Inventory Area  (WRIA) 28.  Generation of GIS coverages of various habitat criteria; data quality control from outside sources; and data contact with Olympia Staff.  Frequent correspondence and cooperation with state, federal, tribal, private, and local agencies, and area biologists.  Supervisory Position. Computer applications: Arcview 3.2a. Access 2000, Excel.

Environmental Specialist 2,  Washington State Department of Ecology, Environmental Assessment Program.   July 1999 to October 2000.  Supervised crew for biological, chemical, and physical stream surveys for REMAP and EMAP (i.e., EPA protocols).  Quantified physical stream habitat, and fish and amphibian assemblages; sampled and sorted invertebrates; sampled water chemistry; and identified freshwater fish in the field and lab. Correspondence and cooperation with various federal, state, tribal, local, and private agencies.  Public outreach. Computer applications: Access, Excel, Arcview 3.2.

Wetland Monitor, Intern, Washington State Department of Transportation. July-September, 1998.  Formal biological monitoring of WSDOT mitigation sites.  Included formal bird surveys (by sound and sight), vascular species identification using transect-plot method, hydric soil identification with Munsel soil chart, vegetation mapping, benthic macro-invertebrate identification, general site description.

Forest Surveyor, The Evergreen State College. July-October, 1998   Surveyed fir and maple forests using electronic survey scope, and set up research plots for canopy research class.

Researcher, Cook Inlet Aquaculture, Soldotna, AK. July-September 1996; April-September  1997.  Collected research data on adult and juvenile sockeye salmon, Dolly Varden char, coho salmon, and rainbow trout migration escapement.  Data collection methods included: scale samples, length and weight measurement, and smolt otolith removal.  Organized data and kept highly accurate field notes at remote location.  Performed expert fish identification.

Administrative Intern, Washington State Department of Health Division of Drinking Water, Olympia, WA. August-November 1993.  Researched water usage, wrote and reviewed public policy, served as public information source.

## EDUCATION

Master of Environmental Studies,  The Evergreen State College, Olympia, WA, October 1999.

Thesis topic: Freshwater wetland rearing of juvenile chinook salmon and other salmonids: potential for restoration in Puget Sound.

Bachelor of Science, Environmental Policy and Assessment, Huxley College of Environmental Studies, Western Washington University, Bellingham, WA, 1993.

## RELEVENT TRAINING

Data with Arcview,  Spring 2001.  Washington Department of Ecology , Olympia, WA.

Access 2000,  Spring 2001. Washington Department of Fish and Wildlife, Olympia, WA.

Train the Trainers,  Winter, 1999. EPA Rapid Bioassessment Protocols, EPA, Corvalis, OR

Arcview Basics,  Winter 1999. Washington Department of Ecology, Olympia, WA.

Basic First Aid and CPR. 1996-2000 consecutive years.

Cold Water Survival. April 1997.  Cook Inlet Aquaculture, Kenai, AK.

## RELATED SKILLS

 Knowledgeable with ESA listed salmonid species and ESU’s, ESA section 7,10

 Proficient with juvenile and adult salmonid identification.

- Identification of non-salmonid freshwater fish species

- Fluvial in-channel and off-channel habitat formation and identification

 Salmonid population estimation methods; Salmonid redd identification

 Various flow control structures, smolt traps, wiers; Clinometer, Marsh-Mcbirney flow meter, sinuosity; Orion conductivity meter, pH, YSI DO.

 Riparian vegetation coverage estimation, large woody debris tallies and measurements

 Invertebrate identification to family

 Word, Excel, Access, Desktop Publisher, Arcview GIS, GPS

 Experienced with regulatory language of NEPA, SEPA, GMA, ESA, HCP, HPA

 Powerboat operation, large truck, backhoe, chainsaw, forklift.

### Carolyn E. Pearson – Regional Project Manager (1.5 FTE)

124 N. Delaware Av. #2. Wenatchee, WA 9881

Phone: (509) 963-1752; E-mail: pearscep@dfw.wa.gov

Education:

M.S. in Stream Ecology and Rangeland, Oregon State University, Corvallis, OR

Fisheries/Rangelands 1 year of graduate school, Oregon State University, OR

B.S. in Marine Science/Biology, minor in Chemistry, University of Miami, FL

Biological Work Experience:

- Current: SSHIAP Regional Project Manager, WA Dept. of Fish and Wildlife, 11/2000-present

- Fisheries Technician, WA Dept. of Fish and Wildlife, 7/2000-11/2000

- Fisheries Technician, WA Dept. of Fish and Wildlife, 5/1999-7/1999

- Biological Technician: Fish, USDA Forest Service, 3/1996-10/1996

- Fish Biologist, USDA Forest Service, 8/1995-2/1996

- Hydrologic Technician, USDA Forest Service, 5/1995-8/1995

- Experimental Biological Aide, OR Dept. of Fish and Wildlife, 10/1994-2/1995

- Biological Technician: Fish, USDA Forest Service, 5/1994-10/1994

- Biological Technician: Fish, USDA Forest Service, 6/1993-10/1993

- Graduate Teaching Assistant, Oregon State University, 1/1993-6/1993

- Graduate Research Assistant, Oregon State University, 3/1992-1/1993

- Fisheries Biologist Intern, C.R.I.T.F.C., 5/1991-12/1991

- Resident Assistant, University of Miami, 8/1990-5/1991

- Hydrologic Technician, Biscayne National Park, 7/1990-8/1990

- Biology Laboratory Assistant, University of Miami, 9/1987-3/1990

Selected publications:

- Fryer, J. K., C. E. Pearson, and M. Schwartzberg. 1992. Age and Length Composition of Columbia Basin Spring Chinook Salmon at Bonneville Dam in 1991. Technical Report 92-1. Columbia River Inter-Tribal Fish Commission.

- Fryer, J. K., C. E. Pearson, and M. Schwartzberg. 1992. Identification of Columbia Basin Sockeye Salmon Stocks Using Scale Pattern Analyses in 1991. Technical Report 92-2. Columbia River Inter-Tribal Fish Commission.

Professional Expertise:

Assisted landowners in Wahklakum and Cowlitz Counties with the development of resource management systems. Designed and implemented practices that improve management of natural resources. Provided general technical assistance to private landowners in accordance to the Natural Resource Conservation Service, Field Office Technical Guide.

Involved in Conservation Planning including gathering and assembling data to plan resource management systems with landowners, scheduling application of practices, and providing technical assistance necessary to apply practices within the planned systems. This included creation of specific landowner plans for the Conservation Reserve Enhancement Program to increase riparian buffer widths.

Participated in watershed management planning by collecting and using field data, summarizing the findings, and managing the watershed database. Provided assistance in watershed planning efforts based on the principals of Coordinated Resource Management Planning. Assisted with coordinating and facilitating public meetings, helping groups arrive at consensus decisions, compiling and presenting resource data to watershed community groups, and developing plan documents. Represented the District with the Board of Supervisor/Supervisor concurrence at meetings and conferences with County, State, and Federal agencies and landowner groups to assist with providing or exchanging technical information.

EVOS Project leader, responsible for all the aspects of the success of the project including: boat contracting, purchasing, budget administration, field work, data management, personnel supervision including hiring and training, and public relations.

Conducted stream surveys in determination of riffle: glide ratios and general assessment of impacts on streams. Modified and existing /Environmental Assessment to reflect the Existing Conditions of the Marley/Texas Heat Prescribed burn area and comply with NEPA standards. Performed a Timber Sale Environmental Assessment Inventory to determine the intensity of the Boundary wildlife burn, gradient, soil duff layer remaining and tree diameters in several proposed timber sale units.

Martin Hudson – Operations Co-Manager (GIS/Hydrolayer Technology; 0.75 FTE)

Information Technology Application Specialist 4, Washington State Department of Fish and Wildlife, Olympia, WA, 98501; Phone: (360) 902-2487;  E-mail: hudsomgh@dfw.wa.gov

Education:

B.S. in Geography, The University of Wyoming, Casper College, Casper, Wyoming. 1987

M.P. in Watershed Resources Planning w/ GIS emphasis, Univ. of WY, Casper College, Wyoming, 1989.

Professional Work Experience:

- Current: Information Technology Application Specialist 4, WA State Department of Fish and Wildlife, Olympia, WA, 1999 – present.

- Computer Technology Consultant 3, WA State Department of Fish and Wildlife, Olympia, WA, 1995-1999

- Computer Technology Consultant 2, 1992-1995.

Selected Publications:

Ostresh, M. S., Jr., R. A. Marston, and W. M. Hudson. 1990. Wyoming Water Atlas.  A Wyoming Centennial Publication. University of Wyoming, Laramie, Wyoming.

Professional Expertise:

Performs or leads analysis, consulting, design, programming, maintenance, and/or support for major applications, support products, projects, multi-functional databases or database management systems that impact multiple business units or functions. Operates on a senior professional level, where is independently responsible for multiple applications of moderate size/complexity or a large, major application that is vital to program delivery.  Possesses advanced technical skill (e.g. a high degree of expertise in business consulting or modular component software construction, or an understanding of database technology on several platforms) and understands the business from the perspective of a senior business person and are conversant in the customer’s business language.

Specific job duties include:

Development of specifications and codes, tests, and implementation of specifications for major, complex applications as well as support, maintenance of and enhancement of existing large, major applications;

Planning and facilitating application interfaces and application integration; development of complex interfaces for data exchange among diverse transactional applications;  As a project leader of a major project, develops project plan, sets and maintains project schedule, coordinates design/maintenance and testing, assigns and leads staff, ensures standards are met (quality assurance), develops and implements communication strategy, manages budget; Analysis of complex problems; assisting others in de-bugging problems with vendor products; development of  work-arounds and consults with senior technical staff to resolve complex technical problems; Researching issues related to environment, platforms, software and hardware requirements; research and analysis may result in application of new technology requiring new application training; Plans, analyzes, and develops application requirements; develops alternative solutions and makes recommendations; facilitates application approval process; Analyzes business needs, develops requests for proposals, feasibility studies, decision packages, etc. for medium and large projects/issues;

Performs data analysis; develops and maintains logical data models; maintains data repository, including design and development of applications for maintaining and reviewing repository information.; trains and assists staff in use of repository; Design and implementation of physical databases from logical models including request for disk space, development of load procedures, and preparation of data for loading; monitoring database management system and application performance, analysis and documentation of performance problems, implementation of performance improvements and backup processes, and performing recovery as needed; assistance in the testing of disaster recovery process; testing and evaluation of software packages; provision of required security accesses; design, development, and maintenance of common modules of a database management system; Design and development of formal training classes for large groups of users and other technical staff.