# Bonneville Power Administration

# FY 2003 Provincial Project Review

# PART 2. Narrative

Project ID:	31007

Title:	Distribution and seasonal habitat use of ESA-listed salmonids and other fish species in City of Portland tributary streams

# Section 9 of 10. Project description

a. Abstract

This proposal is part of a larger project being conducted by the City of Portland’s Endangered Species Program to:

- inventory aquatic habitat in Portland watersheds;

- determine distribution and seasonal habitat use patterns of ESA-listed salmonids and other fish species in Portland watersheds; and,

- guide development of the city’s recovery plan for listed salmonids.

This proposal seeks funds to continue seasonal sampling to determine the distribution and habitat use of listed salmonids and other fish species.  This activity is an integral and necessary component of the city’s recovery plan for listed salmonids, and will fill critical data gaps for the NMFS technical recovery team.  Neither the city’s nor the ESU’s recovery plan can be fully developed until the current distribution, habitat use, and factors limiting distribution are recognized.  Findings may also serve as a basis for evaluations of specific recovery actions such as erosion control plans, environmental zoning, culvert replacement, etc.

Portland watersheds currently provide or historically provided habitat for a number of ESA-listed and candidate races of salmonids.  Steelhead and chinook salmon utilize a number of streams, and historically utilized many more before access was blocked.  Cutthroat trout also occur in many Portland streams.

If this proposal if funded, we plan to continue conducting seasonal electrofishing in approximately 12 tributary watersheds to the lower Willamette River to determine distribution and seasonal use by listed salmonids.  We will sample in each “reach” designated during habitat surveys (a new reach is identified when landscape changes significantly, a major tributary enters, or a barrier to fish passage is encountered (stream surveys were conducted by ODFW crews using a protocol based on the OWEB Assessment Manual).

Although the primary focus of the project will be on listed salmonids, all species encountered will be enumerated, and an Index of Biotic Integrity (IBI) will be calculated for each reach.  Information about lamprey will be particularly useful for the tribal trustees working on the Superfund listing of Portland Harbor.  Findings will be used to guide development of the City of Portland’s recovery program for listed salmonids and to develop restoration projects for the Natural Resource Damage Assessment component of the Superfund listing.  Information collected will also be useful to the NMFS Technical Recovery Team in its work to establish viable population targets for the Lower Columbia ESU.

b. Technical and/or scientific background

Species at risk include steelhead, chinook salmon, and cutthroat trout.  Preliminary surveys have indicated that steelhead utilize Johnson and Tryon creeks (City of Portland, unpublished data).  The city so far has only sampled other streams during one season and only has funds available for one year’s worth of sampling effort.  The extremely low flows present during this year likely had and will continue to have a significant influence on the one-year effort the city currently is undertaking.  This proposal would allow the city to continue sampling for an additional year to improve the integrity of the data.

Limited sampling by City of Portland ESA Program staff and past research and anecdotal evidence suggest that chinook salmon use the lower reaches of some streams as a refuge from the Willamette River.  The same information also suggests that cutthroat trout are found throughout many streams in the Portland metropolitan area (Ward 1995; Friesen and Ward 1996; Friesen and Zimmerman 1999), and may still be present in many Portland streams.  Another native species that may be a more sensitive indicator of degraded conditions than listed salmonids is the torrent sculpin.  In the greater Portland area, torrent sculpin have been found only in relatively undisturbed reaches of a few streams (Ward 1995; Friesen and Ward 1996; Friesen and Zimmerman 1999).  Again, no comprehensive, multi-season sampling effort has been conducted in the lower Willamette tributaries.  This proposal would remedy that situation.

The imminent risk to these species is continued development within Portland’s watersheds, which may result in further habitat degradation, stream blockages, chemical pollution, etc.  Development of the city’s recovery plan will reduce these risks by limiting activities that have the potential to affect listed species.  The recovery plan can not be fully developed without information collected from this project.  The proposed strategy of surveying habitat, determining fish distribution and seasonal use patterns, and using this information to guide a recovery plan is recognized by the City of Portland, Oregon Department of Fish and Wildlife (ODFW), and National Marine Fisheries Service (NMFS) as achieving direct benefits to Portland’s fish populations.

The project will require coordination between the City of Portland, ODFW, and NMFS.  ODFW has agreed to include this project in its ESA Section 4(d) application to NMFS.  Fieldwork will be subcontracted to ODFW, precluding the need for a state collection permit.  Affected landowners were contacted prior to habitat surveys, and were contacted again prior to implementation of this work.  This proposal seeks to build on that coordination effort by continuing sampling for another year.

c. Rationale and significance to Regional Programs

Completion of the City of Portland’s recovery plan requires knowledge of the distribution and habitat use of ESA-listed salmonids.  The recovery plan will result in incentives and regulations necessary to ensure habitat restoration and protection.  Restored and protected habitat will become self-sustaining due to these regulations.

The objectives of the overall project, which are to (1) inventory aquatic habitat in Portland watersheds, (2) determine distribution and seasonal habitat use patterns of ESA-listed salmonids

in Portland watersheds, and (3) guide development of the city’s recovery plan for listed salmonids, are measurable and quantitative.  Habitat characteristics have been measured through stream surveys, which helped identify areas to be protected and areas that are likely candidates for restoration.  If this proposal is funded, fish assemblages will be identified, and population sizes will be estimated for listed salmonids, providing critical information to refine protection and restoration actions and to document the lower Willamette tributaries’ potential contribution (or lack thereof) to a viable ESU.

Development of the recovery plan has obvious benefits to the long-term survival of listed salmonids in Portland streams and in the larger ESU.  In addition, findings from the proposed work will be used by the city immediately to help guide planning and operational decisions; therefore, benefits to listed species will be immediate.

Although the proposed work will not directly result in extending habitat out from a core area, information collected will be used to prioritize such work in the future.  Some Portland streams contain excellent habitat for steelhead and cutthroat trout, but have limited access because of artificial barriers.  Habitat and fish surveys will indicate priorities for removal of barriers, and confirm the ability of streams to support listed salmonids.  As mentioned above, the Portland recovery plan will result in incentives and regulations necessary to ensure restoration and protection of habitat utilized by ESA-listed species, primarily chinook, steelhead and cutthroat trout.  Protection of this habitat will be enforced by city regulations.

The proposed project provides for significant cost sharing.  The work was dependent on the first phase of the project, the habitat surveys.  These surveys were fully funded by the City of Portland.  Survey costs totaled more than $120,000.

The proposed project is part of a collaborative effort with ODFW, NMFS and USFWS.  The City of Portland funded ODFW to conduct the habitat surveys, and has subcontracted with ODFW to conduct the first year of fish inventories.  If this proposal were funded, the city would continue to contract with ODFW for additional survey work.  The city also is working collaboratively with NMFS, USFWS and ODFW to develop the recovery plan for ESA-listed species.

The proposed project also has a synergistic effect with other actions.  The City of Portland and ODFW are currently collaborating on a project to evaluate habitat use and the effects of development on fish populations (especially juvenile salmonids) in the lower Willamette River.  The mainstem project (a four-year, $1.2 million effort) builds on previous work conducted by ODFW in the lower Willamette River (Farr and Ward 1993; Ward et al.  1994).  Supplementing information about mainstem fish use with information about tributary fish use is a critical component of the city’s recovery planning and of recovery planning for the larger ESU.

The proposed fish inventories will also complete a major body of work conducted to date by ODFW, Clackamas County, the Unified Sewerage Agency of Washington County, and the Washington County Soil and Water Conservation District.  These agencies have completed fish and habitat surveys in streams within or near the Urban Growth Area, but outside of Portland.  Surveys of Portland streams will allow development of a comprehensive summary of the condition of urban streams in the greater Portland area, which will lead to increased protection of ESA-listed species throughout the area and to a more detailed recovery plan for the ESU as a whole.

d. Relationships to other projects

As previously described, this project compliments the collaborative effort between the City of Portland and ODFW to evaluate habitat use and the effects of development on fish populations (especially juvenile salmonids) in the lower Willamette River.  Information garnered from the two projects, combined with information already collected in metropolitan area streams outside of Portland City limits, will significantly aid the recovery of ESA-listed salmonids in the Portland area and contribute important information to ESU recovery planning.

The proposed project also will serve as an important component of the Willamette Restoration Initiative (WRI).  One strategy of the WRI is to protect and restore riparian, terrestrial, and instream habitats and processes sufficient to support self-sustaining levels of associated native fish, aquatic species, and wildlife populations (WRI 2000).  Recommended actions to address this strategy include (1) establish science-based riparian protection guidelines, (2) inventory, map, and conserve priority fish and wildlife habitats in the Willamette Basin, and (3) support basinwide scientific investigations of how to restore floodplain function.

This project is similar in scope and intent to many others currently funded under the Fish and Wildlife Program.  Numerous projects have been or are currently funded that take the approach of (1) collecting information on habitat and distribution of critical fish species in an area, and (2) using this information to guide recovery actions.  This project actually improves upon the design of many funded projects because it will produce comprehensive information on habitat and fish assemblages before our recovery plan is finalized; therefore we will have a basis from which to evaluate recovery actions.  This project will also provide important information to the NMFS Technical Recovery Team and to the Natural Resource Trustees who will evaluate restoration projects as part of the Superfund process for Portland Harbor.

e. Project history (for ongoing projects)

This project has not previously been funded through the Columbia River Basin Fish and Wildlife Program.  However, the City of Portland was able to find funds for one year of effort.  That year began during the summer of 2001.  During the first quarter of Willamette tributary sampling (July 1 -- September 30), the Oregon Department of Fish and Wildlife (ODFW) and the City of Portland Endangered Species Program identified 10 waterways for sampling during the 2001-2002 sampling year.  Eight of the Willamette tributaries identified were sampled for presence/absence data and 100-meter stretches in each reach were sampled for population data.  Doane Creek was identified as a stream to be sampled during the 2001-2002 sampling season but was dry due to drought conditions.  We also were unable to sample the Columbia Slough comprehensively due to staffing and funding constraints.  However, City of Portland ESA staff recently found juvenile chinook and coho in the north portion of the Slough.  Activities completed during the summer of 2001 include:

- Identified, purchased, and prepared sampling supplies

- Developed sampling protocols

- Identified sampling areas

- Contacted landowners for permission to access the creek on their property

- Conducted field sampling:

  - Presence/absence sampling

    - Miller Creek – 2 of 3 reaches sampled

    - Saltzman Creek sampled – 3 of 4 reaches sampled

    - Balch Creek – 2 of 3 reaches sampled

    - Stephens Creek – 3 of 3 reaches sampled

    - Tryon Creek – 4 of 4 reaches sampled

    - Johnson Creek – 7 of 16 reaches sampled

    - Kelley Creek – 1 of 2 reaches sampled

    - Crystal Springs – 1 of 1 reach sampled

  - 100 m reach sampling (identified during presence absence surveys)

    - Miller Creek– 2 of 3 reaches

    - Saltzman Creek– 2 of 4 reaches

    - Balch Creek– 2 of 3 reaches

    - Stephens Creek– 2 of 3 reaches

    - Tryon Creek– 4 of 4 reaches

    - Johnson Creek– 7 of 8 reaches

    - Kelley Creek – 2 of 2 reaches

    - Crystal Springs Creek – 1 of 1 reach

- Entered and verified data collected

# Methods

Presence/Absence sampling:

A single-pass electrofishing method was used to collect fish through out each stream during summer low flows.  All streams sampled were previously surveyed for the aquatic habitat available.  Within each stream, reaches (delineated by significant landscape changes, major tributaries, or passage barriers) were identified, and we sampled approximately 20 percent of the units of each major habitat type (pool, riffle, glide), using independent random starting points for each habitat type in each reach.

100 meter sampling:

A multiple-pass electrofishing method was used to collect fish in a 100-m length of each stream reach.  While conducting extensive summer sampling we selected 100-m lengths within each stream reach to be sampled more intensively.  These lengths are representative of each reach and easily accessible.

# Preliminary Summary of Findings

In the eight Willamette tributaries sampled during the summer 2001 sampling season between zero and eleven species were identified.  No fish were found in Saltzman Creek during presence/absence surveys or 100 meter reach sampling.  The largest diversity was found in Johnson Creek.  Eleven species of fish were identified during presence/absence surveys and 100 meter reach sampling.  In Stephens Creek, fish were only collected in reach one.  Reach two and three of Stephens had no fish present during the summer 2001 sampling period. The attached table provides a summary of surface area sampled during presence/absence surveys as well as a list of species collected by sampling type.

| Table 1. Surface area (m2) electrofished during presence/absence sampling and species collected during presence/absence surveys and 100 meter reach sampling in Willamette tributaries, summer 2001. |  |  |  |
| --- | --- | --- | --- |
|  | # Presence/Absence Sampling |  | 100 m Sampling |
| Tributary | Total Surface Area (m2) | Species Present | Species Present |
| Balch | 432.71 | Cutthroat Trout | Cutthroat Trout |
| Crystal Springs | 104.76 | Cutthroat Trout, Prickly Sculpin, Reticulated Sculpin, Redside Shiner, Speckled Dace | Longnose Dace, Reticulated Sculpin, Redside Shiner, Western Brook Lamprey |
| Johnson | 4,650.16 | Coho, Cutthroat Trout, Largemouth Bass, Longnose Dace, Prickly Sculpin, Rainbow Trout, Reticulated Sculpin, Riffle Sculpin, Redside Shiner, Speckled Dace, Western Brook Lamprey | Coho, Cutthroat Trout, Longnose Dace, Prickly Sculpin, Reticulated Sculpin, Redside Shiners, Speckled Dace, Western Brook Lamprey |
| Kelley | 60.43 | Cutthroat Trout, Reticulated Sculpin | Cutthroat Trout, Reticulated Sculpin, Western Brook Lamprey |
| Miller | 187.81 | Reticulated Sculpin, Three-spine Stickleback | Reticulated Sculpin, Three-spine Stickleback, Western Brook Lamprey |
| Saltzman | 126.35 | No Fish | No Fish |
| Stephens | 132.81 | Chinook, Prickly Sculpin | Chinook, Reticulated Sculpin, Redside Shiner |

f. Proposal objectives, tasks and methods

Objectives

One vision of the City of Portland is to “push past the minimum standards set by the Endangered Species Act to help attain the goal of recovering native fish” (City of Portland 2000).  To this effect, the Portland City Council has adopted a resolution to work with federal, state, regional, and local partners, and with the community to support the recovery of native salmonids.

Objectives specific to the overall project being conducted by the City of Portland’s Endangered Species Act Program directly address the City’s vision: (1) inventory aquatic habitat in Portland watersheds, (2) determine distribution and seasonal habitat use patterns of ESA-listed salmonids in Portland watersheds, and (3) guide development of the city’s recovery plan for listed salmonids.  The final product will be a recovery plan with incentives and regulations developed by the City of Portland necessary to ensure restoration and protection of habitat utilized by ESA-listed species.

Although the three objectives are closely linked, funding is only being requested for sampling to determine distribution and seasonal habitat use patterns of ESA-listed salmonids in Portland watersheds.  Abundance, distribution, and seasonal habitat use will be measured by spring (April-May) 2003.

Tasks and Methods

Objective 1.	Determine distribution and seasonal habitat use patterns of ESA-listed salmonids in Portland watersheds.

Task 1.1.	Conduct seasonal standardized electroshocking for fish in approximately 12 Portland watersheds.

Task 1.2.	Estimate abundance of listed salmonids in summer, and calculate an index of biotic integrity for each stream.

Task 1.3.	Determine seasonal habitat use patterns of listed salmonids in each stream.

###### Task 1.1

We will use a backpack electrofisher to sample each watershed within Portland city limits.  Sampling will be conducted each season for one year, beginning in summer (July-August) 2002.  All streams to be sampled will have been previously surveyed for aquatic habitat by ODFW (Moore et al.  1997).  Within each stream reach (delineated by significant landscape changes, major tributaries, or passage barriers) identified during habitat surveys, we will sample approximately 20 percent of the units of each habitat unit type (pool, riffle, glide), using independent random starting points for each habitat type in each reach (Hankin and Reeves 1988).

We will use the Moran-Zippen removal method estimator (Seber 1982) applied separately to each salmonid species or species age class.  If salmonids are captured during the first electrofishing pass in a unit we will conduct additional passes until no salmonids are observed (maximum of three passes; Armour et al.  1983).

Unlike many salmonid surveys in recent years, we will use electrofishing rather than snorkeling as our primary censusing technique.  Reasons include (1) small size of some streams will preclude effective snorkeling, (2) water quality in some urban streams may preclude safe snorkeling, and (3) although ESA-listed salmonids are the primary focus of sampling, IBI estimates require counts of all fish species, many of which are not easily detected or identified by snorkeling.  Risks of injuring individual fish exposed to electrofishing will be minimized by following NMFS guidelines (NMFS 2000) and by using the field guides of Connolly (1996) to ensure maximum conservancy in the number of habitat units sampled and the number of passes conducted, while achieving reasonable precision in population estimates.

Task 1.2

We will first sample each stream reach in summer (July-August) 2002, and results will be used to estimate abundance of salmonids and calculate an IBI (Karr 1981; Hughes et al. 1998).  Abundance for each salmonid species or age class will be estimated for each habitat unit type in each reach, then individual estimates will be summed to yield total abundance estimates for the entire reach (Hankin and Reeves 1988).  We will first determine if abundance within individual habitat units is significantly correlated (P < 0.05) with unit size (surface area).  If abundance and unit size are correlated, then abundance will be estimated as (abundance in sampled units x total surface area)/surface area in units sampled.  If abundance and unit size are not correlated, then abundance will be estimated as (abundance in sampled units x total number of habitat units)/number of habitat units sampled.

Calculating an IBI for Portland watersheds is important because indicator species or populations may be insufficiently robust indicators (Hughes et al. 1998).  ESA-listed salmonids may not be the only, or even the best indicators of stream health.  Furthermore, data needed to calculate IBI’s are readily collected while electrofishing.  Hughes et al. (1998) developed a method to describe the biotic integrity of small Willamette Valley streams, which is applicable to streams in Portland.  We will calculate an IBI for each stream reach in summer.  The IBI scores will distinguish reaches with acceptable fish assemblages from marginally or severely impaired reaches.  IBI scores will be an additional tool to help identify reaches to be protected or restored.

Task 1.3

When conditions permit, we will re-sample habitat units in autumn (October-November) 2002, winter (January-February) 2003, and spring (April-May) 2003.  Sampling only in summer may be inadequate to relate salmonid production to habitat.  Nickelson et al. (1992) found that production of wild coho salmon was probably limited by availability of adequate winter habitat, and habitat factors such as the amount of woody debris have been strongly correlated to the survival of over-wintering juvenile salmonids (Quinn and Peterson 1996).  It will also be necessary to document the presence or absence of salmonids in all seasons for the City of Portland to include appropriate incentives and regulations in its recovery plan.

We may not be able to effectively sample all reaches each season.  Weather conditions, stream and watershed morphology, etc. may sometimes preclude sampling due to high flow or turbidity.  However, past efforts in the area have indicated that all sites can be sampled in summer, and most sites can be effectively sampled during other seasons (Friesen and Ward 1996; Friesen and Zimmerman 1999).  Sampling during winter and spring will generally be limited to collecting salmonids.  Moderately high flows or turbidity will preclude our ability to collect all species present (e.g., sculpins and lamprey); therefore IBI’s will be calculated for summer only.

g. Facilities and equipment

The facilities to be used for this project include agency offices for the City of Portland Endangered Species Act Program, Portland, OR; and the Oregon Department of Fish and Wildlife, Clackamas, OR.

All capital equipment needed for this project is already in possession of the agencies.  This includes ODFW computers with Pentium processors and all software necessary to analyze data and prepare reports.  Both the City of Portland and ODFW own backpack electrofishing equipment.  Vehicles are available through the state or city motor pools or GSA .

h. References

| Reference (include web address if available online) | Submitted w/form (y/n) |
| --- | --- |
| Armour, C. L., K. P. Burnham, and W. S. Platts. 1983. Field methods and statistical analysis for monitoring small salmonid streams. U. S. Fish and Wildlife Service. FWS/OBS-83/33. |  |
| City of Portland. 2000. Draft framework for an Endangered Species Act recovery plan. | N |
| Connolly, P. J. 1996. Resident cutthroat trout in the central Coast Range of Oregon: logging effects, habitat associations, and sampling protocols. Doctoral dissertation. Oregon state University, Corvallis. | N |
| Farr, R. A., and D. L. Ward. 1993. Fishes of the lower Willamette River, near Portland, Oregon. Northwest Science 67:16-22. | N |
| Friesen, T. A., and D. L. Ward. 1996. Status and condition of fish assemblages in streams of the Tualatin River Basin, Oregon. Northwest Science 70:120-131. | N |
| Friesen, T. A., and M. P. Zimmerman. 1999. Distribution of fish and crayfish, and measurement of available habitat in urban streams of north Clackamas County. Final Report by ODFW to Clackamas County, Clackamas, OR. | N |
| Hankin, D. G., and G. H. Reeves. 1988. Estimating total fish abundance and total habitat area in small streams based on visual estimation methods. Canadian Journal of Fisheries and Aquatic Sciences 45: 834-844. | N |
| Hughes, R. M., P. R. Kaufmann, A. T. Herlihy, T. M. Kincaid, L. Reynolds, and D. P. Larsen. 1998. A process for developing and evaluating indices of fish asemblage integrity. Canadian Journal of Fisheries and Aquatic Sciences 55: 1618-1631. | N |
| Karr, J. R. 1981. Assessment of biotic integrity using fish communities. Fisheries 6:21-27. | N |
| Moore, K. M. S., K. K. Jones, and J. M. Dambacher. 1997. Methods for stream habitat surveys. Oregon Department of Fish and Wildlife Information Report 97-4, Portland. | N |
| NMFS. 2000. Guidelines for electrofishing waters containing salmonids listed under the Endangered Species Act. | N |
| Nickelson, T. E., J. D. Rodgers, S. L. Johnson, and M. F. Solazzi. 1992. Seasonal changes in habitat use by juvenile coho salmon (Oncorhynchus kisutch) in Oregon coastal streams. Canadian Journal of Fisheries and Aquatic Sciences 49:783-789. | N |
| Quinn, T. P., and N. P. Petersen. 1996. The influence of habitat complexity and fish size on over-winter survival and growth of individually marked juvenile coho salmon (Oncorhynchus kisutch) in Big Beef Creek, Washington. Canadian Journal of Fisheries and Aquatic Sciences 53:1555-1564. | N |
| Seber, G. A. F. 1982. The estimation of animal abundance. MacMillan, New York, NY. | N |
| Ward, D. L. 1995. Distribution of fish and crayfish, and measurement of available habitat in the Tualatin River basin. Final Report by ODFW to the Unified Sewerage Agency, Hillsboro, Oregon. | N |
| Ward, D. L., A. A. Nigro, R. A. Farr, and C. J. Knutsen. 1994. Influence of waterway development on migrational characteristics of juvenile salmonids in the lower Willamette River, Oregon. North American Journal of Fisheries Management 14:362-372. | N |
| Willamette Restoration Initiative. 2000. Renewing our commitment: a report to the governor, legistlature and Oregon citizens on restoring the health of the Willamette watershed. | N |
| Ward, J. V. and Stanford, J. A. 1995. The serial discontinuity concept extending the model to floodplain rivers. Regulated Rivers 10: 15-168. | N |

# Section 10 of 10. Key personnel

Mike Reed

Endangered Species Act Program

City of Portland

1900 SW Fourth, Suite 4100

Portland, OR  97201-5350

Education

University of Washington (Seattle, Washington)		M.S.  Wildlife Sciences, 1987

University of Washington (Seattle, Washington)		B.S.  Wildlife Sciences, 1984

Indiana University (Bloomington, Indiana)			B.A.  Psychology, 1976

Employment History

May 1999 – Present:  City of Portland – Endangered Species Act Program

Fisheries Biologist

Member of a core team to assist the City of Portland’s response to the Endangered Species Act.  Duties include drafting a scientifically defensible, integrated citywide approach to fish recovery.  Evaluating City programs and activities that impact salmon and their habitats.  Supervising fisheries and habitat surveys throughout the metropolitan area.  Assisting City Bureaus in negotiations with the National Marine Fisheries Service and other regulatory agencies under Section 7 consultations.  Program Manager for multi-year fish study in the Willamette with the Oregon Department of Fish and Wildlife. Program Manager for an Independent Science Review Team to provide scientific evaluation of updates to City programs.

October 1991 – May 1999:  Jamestown S’Klallam Tribe – Sequim, Washington

Timber, Fish and Wildlife Program Manager

February 1990 – October 1991:  Port Gamble S’Klallam Tribe – Kingston, Washington

Fisheries Habitat Biologist

Expertise

I have over twelve years experience as a fisheries biologist.  My expertise is in the area of habitat inventory and assessment, limiting factors analysis, juvenile salmonid life history research and habitat restoration in rivers and streams in the Pacific Northwest. I have used a variety of survey methodologies (electrofishing, trapping, seining) to determine species presence and seasonal habitat use of federal and state listed salmonid and trout species (chinook, coho, chum, pink, steelhead and cutthroat) in combination with habitat surveys and hydraulic and sediment transport analyses to develop restoration strategies.

Recent Publications and Reports

Hirschi, R.and M.J. Reed.  1998.  Salmon and Trout Life History Study in the Dungeness River.  Jamestown S’Klallam Tribe. Sequim, Washington.

Reed, M.J. et al. 1997.  Recommended Restoration Projects for the Dungeness River: Recommendations from the Dungeness River Restoration Work Group.  Jamestown S’Klallam Tribe.  Blyn, Washington.

David Ward

Oregon Department of Fish and Wildlife

17330 S.E. Evelyn Street

Clackamas, OR  97015

Education

Humboldt State University (Arcata, CA)		M.S. Fisheries, 1985

Humboldt State University (Arcata, CA)		B.A. Zoology, 1978

Experience

1984-Present:	Oregon Department of Fish and Wildlife.

- 1998-Present: Program Leader for Columbia River Investigations Program - Coordinate activities of ongoing departmental and interagency research projects, identify needs for and develop future projects, provide technical oversight to project leaders, and supervise project leaders and other program staff.

- 1991-98: Project Leader for evaluation of the Northern Pikeminnow Management Program.

- 1988-91: Project Leader for evaluation of effects of shoreline development in the lower Willamette River on juvenile salmonids.

- 1984-87: Project Biologist and Technician on various studies.

Expertise

Coordinated and integrated activities of cooperating agencies; hired and supervised staff of project leaders, project biologists, and seasonal workers; designed field and laboratory sampling plans; analyzed wide variety of biological data; authored, edited, and reviewed scientific reports and peer-review articles.  Organized personnel from cooperating agencies to give symposia at fisheries conferences.  Developed and submitted proposals for numerous research projects to various funding sources.  Direct experience with methods and gears associated with habitat and fish surveys in streams, rivers, lakes, and reservoirs.

Recent Publications and Reports

Friesen, T. A., and D. L. Ward.  1999.  Management of northern pikeminnow and implications for juvenile salmonid survival in the lower Columbia and Snake rivers.  North American Journal of Fisheries Management 19:406-420.

Friesen, T. A., and D. L. Ward.  1996.  Status and condition of fish assemblages in streams of the Tualatin River Basin, Oregon.  Northwest Science 70:120-131.

Ward, D. L.  1995.  Distribution of fish and crayfish, and measurement of available habitat in the Tualatin River basin.  Final Report by ODFW to the Unified Sewerage Agency, Hillsboro, Oregon.

Ward, D. L., A. A. Nigro, R. A. Farr, and C. J. Knutsen.  1994.  Influence of waterway development on migrational characteristics of juvenile salmonids in the lower Willamette River, Oregon.  North American Journal of Fisheries Management 14:362-372.

Farr, R. A., and D. L. Ward.  1993.  Fishes of the lower Willamette River, near Portland, Oregon.  Northwest Science 67:16-22.