## COORDINATOR'S WORK PLAN

### July 2001 to June 2003

# ADMINISTRATION

| OBJECTIVES | TASKS | TIMELINE |
| --- | --- | --- |
| Continue watershed council support | - Provide day to day administrative support, - Organize & centralize watershed council information, (utilize website) - Assist in preparing agendas, meeting minutes, mailing & press releases | #### July 2001 to June 2003 |
| Act as liaison and\ or Contact person between watershed councils local government and state resource agencies | - Share information, - Announce funding opportunities, - Organize training events, - Schedule speakers | July 2001 to June 2003 |
| Seek funding for watershed council projects identified in watershed assessments and action plan. | - The coordinator will keep a list of funding opportunities as they become available, and match funding criteria with identified projects | July 2002 to June 2003 |

Watershed Assessment / Action Plan

OBJECTIVES                                             TASKS                                            TIMELINE

| Update Watershed Assessments | - Provide contact information. - Review CREST's data, including GIS and completed comprehensive plans, and available maps. - Schedule meetings with technical review committee as needed, - Assist with data storage, - organize training events or field verification events for data collection, - Assist with landowner outreach and cooperation, and awareness | July 2001 to January 2002 |
| --- | --- | --- |

Watershed Assessment / Action Plan Continued

OBJECTIVES                                             TASKS                                            TIMELINE

| Continue action plan development and implementation | - Assist in the implementation of Action Plans - Maintain list of landowner projects and partners involved - Maintain list of project funding opportunities to support implementation efforts. | July 2001 to June 2003 |
| --- | --- | --- |
| Public outreach efforts | - Provide a series of public comment events, including media coverage (3 total) - Provide display board at Co. fair, place around town like libraries and other events |  |

Watershed Projects

OBJECTIVES                                             TASKS                                            TIMELINE

| Identify projects that will be beneficial to aquatic life, and will also involve private landowner participation, including ODF, and Willamette Industries Inc. | - Organize volunteers - seek funding for projects already identified as a potential benefit to salmonids (riparian planting, bank stabilization, fencing etc) - Develop monitoring strategies to ensure monitoring efforts continue after project completion - Submit project reporting forms upon completion of projects. - Organize and contact the necessary agency support for project consultation, and permit review. | July 2001 to June 2003 |
| --- | --- | --- |

Education & Outreach

OBJECTIVES                                             TASKS                                            TIMELINE

| Increase public awareness Promote watershed council participation | - Organize volunteer watershed activities: field visits, project selection tours, landowner visits, project inspection visits, monitoring training events - Hold 3 public information meetings to announce watershed assessment findings, and project selection results - Maintain the communication with local government to promote more local support and participation - Provide quarterly reports to City of Warrenton, City of Seaside, City of Astoria and Clatsop County Commissioners. | July 2001 to June 2003 January, February and March 2001 July 2001 to June 2003 |
| --- | --- | --- |

Education & Outreach Continued

OBJECTIVES                                             TASKS                                            TIMELINE

| Increase the involvement of students in watershed council activities, especially data collection & monitoring activities. | - Link student curriculum development with watershed council action plans - Provide coordination to plan effective partnerships and to set reasonable goals - Store and maintain data collected by Students at CREST. - Continue providing opportunities to Clatsop Community College students to participate in monitoring events and obtain work-study credits. | September 2001 to June 2003 |
| --- | --- | --- |

Water Quality Monitoring Program

OBJECTIVES                                             TASKS                                            TIMELINE

| Continue developing and implementing Quality Assurance, Quality Control (QA\QC) Water Quality Monitoring Plans Maintain an inventory of water quality monitoring equipment available in the county and available to watershed councils | - Organize a core group of dedicated WC volunteers (from each council) to design, update and implement QA\QC plans - Assist in writing QA\QC Plans - Coordinate with DEQ to offer training events, establish reasonable objectives to obtain the most useful data - Develop a network of water quality monitoring equipment. - Maintain list of available equipment - Coordinate the use of WQ equipment and seek more form DEQ when necessary | July 2001 Update plans as action plans reveal data gaps and priorities areas are selected July 2001 to June 2003 |
| --- | --- | --- |