# FY 2007-2009 F&W Program Project Solicitation

# Section 10. Narrative

Project ID:	199901500

Title: 	Restoring Anadromous Fish Habitat in Big Canyon Watershed

A. Abstract

Big Canyon Creek historically provided quality spawning and rearing habitat for A-run wild summer steelhead in the Clearwater River subbasin (Fuller, 1986).  However, high stream temperatures, excessive sediment and nutrient loads, low summer stream flows, and lack of stream cover caused anadromous fish habitat constraints in the creek. The primary sources of these nonpoint source pollution and habitat degradations are attributed to agricultural, livestock, and forestry practices (NPSWCD, 1995).  Addressing these problems is made more complex due to the large percentage of privately owned lands in the watershed.

The Nez Perce Soil and Water Conservation District (NPSWCD) developed this project to enhance steelhead trout natural production in the Big Canyon watershed by improving salmonid spawning and rearing habitat. The NPSWCD seeks to assist private, tribal, county, and state landowners in implementing Best Management Practices (BMPs) to reduce nonpoint pollutants, repair poorly functioning riparian zones, and increase water retention in the watershed.  The project funds coordination, planning, technical assistance, BMP design and installation, monitoring, and educational outreach to identify and correct problems associated with agricultural and livestock activities impacting water quality and salmonid survival. The project accelerates implementation of the Idaho agricultural water quality management program.  It also addresses specific needs identified in the Clearwater Subbasin Summary 2001 Draft and the 2000 Columbia River Basin Fish and Wildlife Program documents.

The Big Canyon Creek watershed proposal coordinates with other watershed partners including: Natural Resources Conservation Service (NRCS), Lewis County Soil and Water Conservation District, Idaho Fish and Game (IDFG), University of Idaho (UI), Nez Perce County Commissioners, Clearwater Focus Program, Clearwater Basin Weed committee, and Nez Perce Tribe Water Resources (NPTWRP), Fisheries Resource Management, and Land Services Departments.

This proposal’s goals include installation of upland and cropland erosion controls, riparian plantings to lower water temperatures, channel modifications, and  measures to limit rural road runoff. It also describes objectives outlined in the NPSWCD Five Year Resource Conservation Plan.  This plan was developed through a locally led process that uses public input to prioritize resource concerns within the NPSWCD.

B. Technical and/or scientific background

## Problems the project addresses

This proposal addresses the problem of decreased or degraded salmonid spawning and rearing habitat Big Canyon watershed.  Specifically, the proposal addresses the lack of funds to support full implementation of agricultural and livestock BMPs on private, tribal, county, and state lands. The lack of these BMPs has allowed for poorly functioning riparian zones, poor water retention in the watershed, and the continued movement of nonpoint pollutants into the creek.  The project also addresses completing identified gaps in resource inventories in the Big Canyon watershed.

The Draft Clearwater Subbasin Summary, Big Canyon Creek Environmental Assessment- Final Planning Report, and the Big Canyon Aquatic Assessment were the primary guiding documents used in developing this proposal.

## Project goals

- Develop and implement BMPs on agricultural, mining, grazing, timber and urban land uses to protect and/or restore fish and wildlife habitat, streambank stability, watershed hydrology, water quality, and floodplain function.

- Organize, coordinate and lead interagency and locally led conservation efforts.

- Public education and technology transfer.

- Monitor and evaluate BMP effectiveness in improving fisheries habitat.

- Successfully administrate the BPA project.

## Project Location

The project proposal encompasses the entire Big Canyon watershed including the Little Canyon subwatershed.

## Project Sponsor

NPSWCD is a non-profit organization promoting the protection of natural resources on a watershed basis.  The NPSWCD consists of seven locally elected (through a county election process) members.  The NPSWCD boundaries are Nez Perce County, Idaho.  The NPSWCD conducts a public input process to develop its goals and objectives.  From this public input, the NPSWCD produces a Five-Year Resource Conservation Plan, which identifies specific needs and goals to address local resource concerns.  For example, according to a Conservation Needs Assessment Survey, one of the top ten resource concerns within the NPSWCD was the protection of wildlife habitat.

The NPSWCD has over 60 years of experience in resource conservation, design and implementation of BMPs, and working with local landowners to install on-the-ground conservation practices.  As a result of current and past efforts the NPSWCD has an excellent working relationship with local landowners and elected officials.

## Program History

The NPSWCD is submitting this proposal to address a high priority concern within the conservation district boundaries. Due to concerns of local residents regarding habitat and water quality issues the NPSWCD completed the 1989 Big Canyon Creek Idaho Agricultural Water Quality Program- Planning Project Application.  This allowed the development of a watershed plan addressing anadromous fish habitat and water quality resource issues in the Big Canyon Creek watershed.  In 1995, the NPSWCD published its efforts in the Big Canyon Creek Environmental Assessment- Final Planning Report. A portion of the BMPs identified in the Environmental Assessment (NPSWCD, 1995) were funded through the NPSWCD with monies from the Idaho State Agricultural Water Quality Program.   The project sponsors include the NRCS, Nez Perce County Board of Commissioners, Idaho Department of Fish and Game (IDFG), Idaho Soil Conservation Commission (ISCC), Idaho Department of Environmental Quality (IDEQ), Bureau of Land Management (BLM), and the Nez Perce Tribe (NPT).

Although the Environmental Assessment  (NPSWCD, 1995) watershed plan identified the need for several BMPs, only part of these BMPs were actually approved for cost-share funds.  In addition, the maximum cost-share rate established for the funds is 75%.  Due to the high cost of practice installation, low agriculture commodity prices, and mostly off-site benefits, landowners are reluctant to install the needed BMPs.

The NPSWCD is submitting this proposal for developing, designing, and installing BMPs as well as to provide cost-share dollars to landowners for BMPs not funded through other programs.  In addition, the NPSWCD plans to use BPA funds to supplement the Idaho State Agricultural Water Quality Program cost-share funds on erosion reduction and riparian enhancement BMPs.  BMP types and extents have already been identified in the Environmental Assessment Plan (NPSWCD, 1995).

###### Background- Watershed Description

The Big Canyon Creek watershed begins at Mason Butte in Lewis County near the farming community of Craigmont (Figure 1).  It flows in a northerly direction for 31 miles through the Camas Prairie before draining into the Clearwater River approximately two miles north of Peck, Idaho.  Elevation ranges from 4,639 feet at Mason Butte to 950 feet at the town of Peck. Average annual precipitation varies with the elevation, and ranges from 20 to 28 inches per year.

Figure 1. Location of Big Canyon Creek watershed, Nez Perce Indian Reservation, towns and county boundaries

The approximately 144,000 acre watershed is located within Lewis County and Nez Perce County.  Major drainages in the watershed include Little Canyon, Cold Springs Creek, Posthole Canyon, Sixmile Canyon, Nichols Canyon and several unnamed tributaries.

The landownership within the Big Canyon Creek Watershed is broken down as follows:

85% Private, 9% Nez Perce Tribe, 4% BLM, and 2% State of Idaho

Rolling plateaus of non-irrigated cropland typify the watershed’s upland areas. This agricultural land comprises over 60% of the watershed acres. The NPSWCD 1995 Farming Practices Survey Report for Big Canyon Creek Watershed found that winter wheat is the top crop produced in the area, followed by spring barley and legumes.  Most watershed agricultural producers use a three year crop rotation and shank in an average of 100 lbs./ac of anhydrous as their nitrogen fertilizer (NPSWCD, 1995). Overall, only 43% of those surveyed reported soil testing to determine their specific fertilizer requirements (NPSWCD, 1995).  The majority of those who did soil test, did so on a three year sampling frequency (NPSWCD, 1995). Based on sampling data, the NPSWCD’s Big Canyon Creek Water Quality Report Summary (1995) hypothesized that upper Nichols subwatershed may contribute more than its share of nitrates into the Big Canyon system.

After leaving the uplands, drainages then flow through U-shaped canyons with steep walls. Many of these canyon areas are classified as rangelands.  Big Canyon’s rangeland areas and relatively inaccessible canyon floor are moderately to heavily grazed. The 13% of forestland acres in the watershed are usually on the steep canyon slopes and drainages.  These areas have been historically and/or recently logged.  Riparian vegetation is generally sparse in the accessible areas of the watershed.

Table 1. Land use characteristics of each subwatershed within the Big Canyon Creek watershed.

| Subwatershed | Area | Forestry | Forestry | Ag/Range | Ag/Range | Urban | Urban |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Name | (Acres) | Acres | Percent | Acres | Percent | Acres | Percent |
| Big Canyon Mouth | 4,796 | 1,483 | 30.9 | 3,004 | 62.6 | 306 | 6.4 |
| Lower Big Canyon | 11,047 | 1,726 | 15.6 | 9,246 | 83.7 | 73 | 0.7 |
| Nichols Canyon | 6,551 | 844 | 12.9 | 5,657 | 86.3 | 51 | 0.8 |
| Middle Big Canyon | 12,673 | 2,222 | 17.5 | 10,403 | 82.1 | 47 | 0.4 |
| Sixmile Canyon | 6,573 | 941 | 14.3 | 5,583 | 84.9 | 51 | 0.8 |
| Posthole Canyon | 12,697 | 3,187 | 25.1 | 9,484 | 74.7 | 25 | 0.2 |
| Fletcher | 5,145 | 563 | 10.9 | 4,566 | 88.7 | 14 | 0.3 |
| Upper Big Canyon | 11,627 | 2,917 | 25.1 | 8,497 | 73.1 | 219 | 1.9 |
| Upper Big Canyon/Coldsprings | 13,714 | 2,856 | 20.8 | 10,781 | 78.6 | 75 | 0.5 |
| Lower Little Canyon | 10,801 | 2,778 | 25.7 | 7,879 | 72.9 | 147 | 1.4 |
| Upper Little Canyon | 17,062 | 2,426 | 14.2 | 14,523 | 85.1 | 113 | 0.7 |
| Lower Long Hollow | 8,540 | 44 | 0.5 | 8,061 | 94.4 | 434 | 5.1 |
| Upper Long Hollow | 9,818 | 0 | 0.0 | 9,766 | 99.5 | 51 | 0.5 |
| Holes Creek | 13,949 | 57 | 0.4 | 13,799 | 98.9 | 94 | 0.7 |
| Total Watershed | 144,994 | 22,045 | 15.2 | 121,249 | 83.6 | 1,699 | 1.2 |

###### Slopes from cropland in the watershed range from 3-25%. Cropland soils on the upland areas include Nez Perce Soil and Water Conservation District Perce, Uhlorn, and Powwahkee which were formed under prairie conditions and Taney, Setters, and Southwick loams which were originally forested, but cleared of timber to allow for cultivation (Hahn, unpub).  The prairie soils are moderately well drained, however, the subsoil clay reduces permeability which results in springtime saturated soils and subsequent increased soil erosion.

###### Cut-over soils, specifically the Taney soils, also have a fragipan subsoil characteristic which restricts water and root movement into the subsoil. Setters subsoils have a high clay content which also results in low water permeability.  During wet periods, perched water tables in these soils move water laterally down slope, thereby producing sidehill seeps.  Often, the naturally low pH of the cut-over soils is further depressed by the application of acidifying nitrogen fertilizers.  For pH below 5.5, soil aggregation may also be decreased, leading to increased soil losses and sediment delivery.

Gwin, Kettenbach, Meland, and Riggins, the major rangeland soils, are well drained and contain large amounts of rock fragments which limit their cropland and grazingland use.  Lack of grazing management during the wet periods can result in compaction and downslope soil movement on steep slopes.

Forestland soils in the watershed include Klickson and Keuterville with Agatha inclusions.  The soils are well drained and found on steep north and east canyon sideslope aspects.  These soils have severe sedimentation potential when disturbed.  Primary soil disturbance is generally due to logging activities.

The Big Canyon Creek watershed provides important habitat for both anadromous and resident fish.  Anadromous fish species identified in the watershed include wild Snake River Basin A-run steelhead, Snake River fall chinook salmon, and possibly the recently reintroduced coho salmon. Resident fish include rainbow trout, brook trout, speckled dace, chiselmouth, northern squawfish, redside shiner, bridgelip sucker, and paiute sculpin (Fuller etal, 1986).   As with many anadromous streams in the Columbia River Basin, salmon and steelhead populations have declined significantly from historic levels (Idaho Department of Fish and Game et al.2000).

Both the steelhead and fall chinook salmon are listed as “threatened” by the National Marine Fisheries Service (NMFS) under the Endangered Species Act (ESA).  The ESA considers both the fall chinook salmon and the steelhead within the Clearwater subbasin to be part of the Snake River evolutionary significant unit (ESU). Since chinook primarily spawn below the North Fork Clearwater confluence (Garcia et al, 1999), Big Canyon Creek’s habitat and water quality play a significant role in the overall long-term success.  Considerable potential exists for improving anadromous fish populations in Big Canyon Creek (Kucera et al. 1983).

Problem History

Clearwater Subbasin Summary Draft (2000) states one subbasin wide primary limiting factor for resident salmonid populations is the impact of land management activities on hydrology, sedimentation, habitat distribution and complexity, and water quality (Columbia Basin Fish and Wildlife Authority, 1999).   For the lower Clearwater Assessment unit, the identified limiting factors are temperature, base flow, flow variation, sediment, watershed disturbances, habitat degradation, exotics, and connectivity/passage.  In the Big Canyon watershed, low stream flows and a lack of adequate multi-layered riparian vegetation have reduced the suitability of the creek and its tributaries as quality spawning and rearing habitat. In addition, sediment, nutrients, and bacteria from existing land-use practices are adversely impacting water quality.  The proposed actions within this proposal are a direct result of the watershed’s limiting factors and the watershed partners’ goals and objectives.

## Agriculture

Agricultural related nonpoint source pollution is caused by (USDA, 2000):

- Conventional tillage practices which pulverize the soil surface, leaving inadequate crop residues.

- Lack of enduring land treatment practices to control or reduce sheet, rill, concentrated flow, and gully erosion.

- Inversion tillage, such as plowing, which tends to create a moisture-restrictive barrier at a depth of 8-10 inches.

- Continued use of excessively steep and erodible lands for crop production.

- Lack of riparian cover and protection due to farming and spraying near riparian areas.

- Agronomic practices which result in degraded soil quality and health.

- Improper road construction for haul roads.

Soil erosion rates on conventionally tilled cropland soils average 25 tons per acre per year. With an average of 20% of the soil moving off of agricultural lands, the Big Canyon watershed is estimated to yearly deliver over one quarter of a million tons of sediment to Big Canyon creek (NPSWCD, 1989).   Fisheries is the first resource to be impacted by this excessive sedimentation by causing spawning gravel embeddedness.

### Livestock

Livestock related nonpoint source pollution is caused by (USDA, 2000):

- Improper livestock grazing practices.

- Overgrazing.

- Direct livestock watering access to stream.

- Grazing in riparian areas.

- Animal Feeding Operation (AFO) nutrient runoff.

A 1998 Confined Animal Feeding Operations Inventory and Analysis (NPSWCD, 1998) ranked the Big Canyon Creek’s water quality as being at “medium risk” from livestock operations.  The high amount of cropland and difficult canyon access moderated the score. This proposal also addresses BMP implementation on AFO problems in anadromous fish habitat areas in the Big Canyon watershed.

## BMPs

BMPs allow for the treatments necessary for agricultural non-point sources to move toward attainment of water quality standards and beneficial uses and remove Big Canyon Creek from the Idaho 303(d) list.

NPSWCD provides technical assistance to the landowner by completing field inventories to determine resource problems and then developing reasonable and prudent alternatives to solving the problems.  The NRCS Field Office Technical Guide (FOTG) is the guiding document in determining the BMP alternatives and their positive and negative effects on the land, water, air, and wildlife resources.

Due to consecutive years of poor agricultural prices, agricultural and livestock producers have limited financial resources for the installation of BMPs.  Conservation programs available through federal and state resources provide cost-share for a portion of selected BMP installation.  However, cost-share is not available for all of the BMPs needed to improve fisheries habitat.  In addition, landowners do not have the financial resources to provide their part of the installation contribution. This proposal allows for accelerated land treatment implementation on non-irrigated cropland, Animal Feeding Operations (AFOs), forestland, and riparian areas with an expanded area.  This adds to ongoing work to provide resource protection throughout the entire watershed.  NPSWCD proposes to use BPA funds to install BMP practices in cooperation with private landowners.  Other cost-share programs will be utilized first with BPA funds providing an additional incentive to install the BMPs which have mostly off-site benefits.

## BMP Installation

This proposal installs BMPs on agricultural and livestock lands which address identified resource concerns on that land. Individual landowners maintain and operate applied land treatments at their own cost throughout the life of the long-term contract.  Landowner conservation plans and resulting contracts explains the operation and maintenance required for each BMP thorough the NRCS standards, specifications, and designs.  Annual BMP inspections during the contract length allow for technical assistance for the landowner if any problems occur.

Agricultural BMPs include:

Tillage Practices- No-till or Direct Seeding, Residue Management, Pest Management, Nutrient Management, Stripcropping.

Structural Practices- Grade Stabilization Structures, Sediment Basins, Ponds, Grassed Waterways, Access Roads, Buffer Strips, Filter Strips, Field Borders, Diversion Terraces, Water and Sediment Control Basins

The purposes of these practices include:

- Reducing off-site sediment.

- Decreasing water temperature.

- Reducing nutrients, pesticides, and bacteria to surface waters.

- Lowering nutrients and pesticide levels in ground water (Kucera et al., 1983).

Riparian BMPs include:

Stream or Pond Bank Improvement Practices- Channel Vegetation, Fish Stream Improvement, Critical Area Planting, Riparian Forest Buffers, Streambank/Shoreline Protection, Tree/Shrub Establishment, Constructed Wetlands

The purposes of these practices include:

## Reducing stream temperatures.

## Allowing re-introduction of large woody debris into the stream system.

## Stabilizing streambanks.

## Enhancing overhanging vegetation.

- Establishing multi-layered riparian vegetation.

## With their large, extensive root systems, riparian plants play a major role in stabilizing streambanks, shading the stream, and providing hiding cover for fish. In addition, the plants provide habitat for terrestrial insects that fall into the stream to become food for juvenile salmonids (USDA. 2000).  Research has consistently shown that the maintenance or reestablishment of streamside vegetation is a major part of successful stream management for anadromous salmonids (USDA. 2000).

Livestock BMPs include:

AFO Practices – Waste Management Systems, Roof Runoff Management Systems, Off-site Watering Facilities, Nutrient Management

Grazing Practices- Fencing for use exclusion, Off-site Watering Facilities, Heavy Use Area Protection, Pasture/Hayland Planting, Range Planting

The purposes of these practices include:

- Reducing off-site sediment.

- Stabilizing streambanks.

- Establishing multi-layered riparian vegetation.

- Decreasing water temperature.

- Reducing nutrients and bacteria to surface waters.

- Lowering nutrients levels in ground waters.

#### Conservation Plans

Conservation Plans are developed by NPSWCD Conservation Planners.  Planners work directly and closely with the landowners in order to address resources problems.   The conservation plans then guide the development of landowner contracts for the installation of BMPs. The development of conservation plans on private, tribal, and state lands allows for needed restoration and protection actions to meet desired goals for improving fish habitat in the watershed protection plan.  Conservation plan development efforts in the watershed proposal area will be selected by a priority ranking system which focuses on areas determined to be most critical to fish.  Developing conservation plans will follow NRCS FOTG protocols and involves a nine step process:

- Identify resource problems

- Identify objectives regarding use, treatment, and management of land

- Inventory natural resources and their conditions

- Analyze resource information and identify causes of resource problems

- Develop alternative treatments

- Evaluate alternatives

- Select alternative

- Implement alternative

- Monitoring and evaluation of implemented alternative

The NPSWCD and the NPT (#199901600) coordinated to develop both of their BPA project proposals.  The two separate project proposals work together to address fish habitat issues throughout the Big Canyon Creek watershed. This coordination assures that no duplication of efforts and finances exists.

C. Rationale and significance to regional programs

The “Restoring Anadomous Fish Habitat in the Big Canyon Creek Watershed” project is needed to facilitate the restoration of habitat within the watershed and also to implement on the ground projects.  The NPSWCD has been working in the watershed to restore fish habitat since 1999.  The NPSWCD historic efforts have resulted in 8 miles of habitat restored and a reduction in sediment delivered to the stream of 48,000 tons per year.

Justification of Watershed Restoration

The Big Canyon Creek Watershed is a high priority for restoration and protection for the following reasons:

- Presence of at-risk species: wild A-run steelhead

- Potential to increase success of Coho outplants

- Assessment completed in the watershed for passage barriers, watershed resources

- High amounts of watershed restoration efforts by other groups

- Landowner involvement

- Reducing water temperatures and sediment delivery to the Clearwater River will improve Chinook salmon rearing habitat

- Watershed identified by NOAA Biop as high potential in Clearwater

Restoration efforts in the Big Canyon Creek watershed focus on providing healthy spawning and rearing habitat for anadromous and resident fish.  This proposal specifically relates to objectives and goals in the 2000 Fish and Wildlife Program.

Clearwater Subbasin Summary

The vision for the Clearwater Subbasin is a healthy ecosystem with abundant, productive, and diverse aquatic and terrestrial species, which will support sustainable resource-based activities.  There are several guiding principles within the Management Plan, all of which are directly addressed by this project proposal.  This project is essential to address the problems and to accomplish many of the objectives identified in the 2003 Clearwater Subbasin Management Plan (Draft).

The Draft Clearwater Subbasin Management Plan, Nov. 2003, compiles problem statements, objectives and strategies for the subbasin.  The Big Canyon Creek Watershed is comprised of 3 PMU’s; PMU-6, PMU-7 and PMU-8 of the subbasin plan.  The proposed restoration and protection efforts within this project proposal meet many of the stated objectives within the Clearwater Subbasin Management Plan.  The specific problems, objectives and strategies addressed by this proposal include:

Problem 2: Anadromous fish production is limited by habitat quality, quantity and connectivity in portions of the subbasin.

B.  Objective: Increase anadromous fish productivity and production, and life stage specific survival through habitat improvement. (page 18)

Proposal Relationship:   The stream habitat inventory is a component of this proposal.  An additional component is completed through the Nez Perce Tribe’s proposal #199901700 for the completion of fish abundance and distribution within the Big Canyon Creek watershed.  This information is scheduled for completion in 2006.  The NPT and NPSWCD plan to use both components to refine fish limiting factors identified in the Clearwater Subbasin Management Plan and then prioritize limiting factors within the Big Canyon Creek watershed.

Problem 7: Water quantity and quality, connectivity, and habitat complexity are key environmental factors that limit the production of anadromous and resident fish species and aquatic wildlife.

O.    Objective: Complete adequate flow designations for all anadromous fish bearing waterways by 2010. (page 31)

Proposal Relationship:  Restoring natural flow timing will be accomplished through the installation of erosion control structures, planting of vegetation, and restoration of forest habitats.  Implementation of forest and agricultural BMPs will be prioritized.  Specific practices scheduled for implementation through this proposal which will address flow timing and base flows include upland vegetative plantings (grass and trees), upland erosion and water control structures, wetland enhancement, creation, and restoration, and riparian and buffer plantings.

P.    Objective: Reduce number of artificially blocked streams by 2017.  (page 32)

Proposal Relationship:  The NPT completed a fish passage barrier inventory and prioritization for replacement in 2005.  This prioritization is the basis for selecting fish passage barriers for removal.  This proposal addresses barriers on two levels.  The first is the removal of barriers identified in the passage barrier assessment – focusing on those in private lands and not on public transportation systems.  The second is the installation of low flow crossings which allow equipment access and maintain minimum flows required for fish migration in summer months.  Several alternatives were identified through an interdisciplinary team (IDFG, NPT, NOAA, NRCS) in 2005. Two of these alternatives will be installed through this proposal.

Q.    Objective: Reduce water temperatures to levels meeting applicable water quality standards for life stage specific needs of anadromous and native resident fish, with an established upward trend in the number of stream miles meeting standards by 2017. (page 33)

Proposal Relationship:  This proposal collects water temperature data within the watershed in order to develop a comprehensive water temperature database and provide a baseline to evaluate the effectiveness of restoration activities in reducing stream temperatures.  In addition the stream habitat survey will identify and prioritize the need for temperature reduction projects.

S.    Objective: Reduce in-stream sedimentation to levels meeting applicable water quality standards and measures, with an established upward trend in the number of stream miles meeting such criterion by 2017. (page 35)

Proposal Relationship:  Problems and opportunities will be identified through the completion of the stream habitat inventory and development of habitat restoration plans.  Sixty miles are slated to be completed through this proposal.  This proposal completes this strategy as the prioritization process will identify areas for protection as well as restoration.Stream inventory data collection will inventory the erosion sources along streams within the Big Canyon Creek watershed.  Areas for treatment will be prioritized through an ITD team including the NPT, IDFG and NPSWCD. Reduction of sediment inputs will be accomplished through the installation of erosion control structures, planting of vegetation, installation of sediment basins, establishment of buffers in feedlot areas, installation of bioengineering techniques on eroding streambanks, fencing, riparian restoration, direct seeding, and installation of alternative livestock water systems.

U.    Objective: Improve aquatic habitat diversity and complexity to levels consistent with other objectives outlined in this document, with particular emphasis on recovery of anadromous and fluvial stocks. (page 37)

Proposal Relationship:  This proposal coordinates with other groups within the Big Canyon Creek watershed.  In addition, this proposal implements BMPs identified in the Big Canyon Water Quality Program for Agricultural Project.  The NPSWCD will follow habitat restoration plans developed for site specific restoration activities.  Eight plans were developed through the 2002 “Restoring Anadromous Fish Habitat to the Big Canyon Creek Watershed” proposal number 2002-015-00.  These plans identify specific aquatic habitat improvements needed to restore and enhance steelhead spawning and rearing habitat.  Instream habitat complexity projects are planned within the proposal.  Projects will be installed within high priority areas as identified through the stream inventory and habitat restoration planning process.  Specific practices include bio-engineering treatments, riparian plantings, and placement of instream cover.

Problem 10: The loss of wetland and riparian habitats particularly in the Lower Clearwater AU, Lolo-Middle Fork, and South Fork AU has negatively impacted the numerous wildlife species that utilize these habitats.

Z.    Objective: Protect all currently functioning wetlands. (page 41)

Proposal Relationship:  Wetland creation, enhancement and restoration are components of the proposal.  In addition, the installation of livestock water developments and completion of grazing management plans are identified.  Education occurs through district newsletters and development of fact sheets.  Our priority installation BMPs include the installation of biologs and wetland sod.  The NPSWCD demonstrated great success with these techniques in 2005.  Through the 2002 “Restoring Anadromous Fish Habitat” proposal the NPSWCD developed growing tanks and procedures for wetland biologs.  This project was a collaborative effort between NPT, NRCS and the NPSWCD.  This unique method will continue to be implemented throughout the watershed.

AA.    Objective: Restore 500 acres of historic wetlands to proper functioning condition by 2017. (page 42)

Proposal Relationship:  Wetland creation, enhancement and restoration are components of the proposal.  Areas are identified and prioritized through the stream habitat survey, hydric soil analysis, and development of habitat restoration plans.  Special emphasis will be placed on the Reubens area as it was identified in the Clearwater subbasin plan as an important area for historic herbaceous wetlands.

BB.     Objective: Protect and restore an additional 300 miles of riparian habitats by 2017. (page 42)

Proposal Relationship:  Riparian habitats will be protected and restored through the installation of livestock watering systems, development of grazing plans, installing fence, removal of exotic vegetation, installation of native vegetation, educational activities, and the promotion of additional BMPs.NPSWCD staff will actively promote the CCRP program and work with USDA and IDFG staff to identify, plan, and implement CCRP program within the Big Canyon Creek watershed.  Landowner education activities will also be completed for this activity.

Problem 11: The introduction of noxious weeds and nonnative plant species into the Clearwater subbasin has negatively impacted native terrestrial focal species.

CC.     Objective: Protect the existing quality, quantity and diversity of native plant communities providing habitat to native wildlife species by preventing the introduction, reproduction, and spread of noxious weeds and invasive exotic plants into and within the subbasin. (page 44)

Proposal Relationship:  Plantings completed through this proposal will only use weed free seeds.  Educational announcements will be distributed to local seed suppliers as well as through the NPSWCD newsletter. Educational activities include weed identification workshops, development of weed plans, and brochures targeting the recreational vehicle users within the watershed.

DD.    Objective:  Reduce the extent and density of established noxious weeds. (page 45)

Proposal Relationship:  In collaboration with the CRBWMACC, prioritized weed infestations will be treated in the most economical manner feasible.

Problem 12: Historic and current livestock grazing adversely impacted fish and wildlife habitats and populations in some portions of the subbasin.

EE.     Objective:  Reduce the negative impacts of livestock grazing on the fish, wildlife and plant populations in the subbasin. Focus efforts on riparian and wet meadow habitats. (page 46)

Proposal Relationship:  Data is collected through the development of habitat restoration plans and the completion of the stream habitat inventory.  Animal feeding operation impacts on water quality and fish habitat will be reduced through the installation of feedlot nutrient management plans, development of alternative watering facilities, streambank restoration, runoff management plans, grazing management plans, and vegetative filters.  The NPSWCD completed an Animal Feeding Operation inventory in 1999.  This survey identified high priority operations for water quality improvements.  Two animal feeding operations were improved using funds from the 2002-2005 project.  These projects are extremely successful and have resulted in an increased landowner request for assistance.

Problem 16: Road construction, timber harvest and/or fire suppression have altered the size, quality, distribution and juxtapositions in and between habitat patches in the subbasin.

JJ.      Objective: Reduce the impact of the transportation system on wildlife and fish populations and habitats.  (page 50)

Proposal Relationship:  In 2005 the NPSWCD identified the need to develop transportation plans for forest, cropland, and grazing land access roads.  The majority of these roads are dirt surfaces and poorly maintained.  In addition, many of the roads are located adjacent to water courses and transport sediment to the stream.  Transportation planning on these roads will be completed through the habitat restoration plan development component of this proposal.  Technical assistance for planning will be obtained from the Nez Perce Tribe through proposal number 1999-01700.  The transportation plan will identify existing field access roads, their condition, and treatment needs.  Specific road treatments will be identified through the transportation planning process.  Specific implementation items will vary depending on the site specific recommendations made through the plan.

Problem 18: As reflected in the inventory, numerous agencies and entities are implementing programs and projects in the subbasin. Lack of coordination and integration limit the economic, social, cultural and biological benefits of aquatic and terrestrial protection and restoration in the subbasin.

LL.    Objective: Develop programs and project proposals compatible with existing community needs and that integrate with local watershed protection, restoration and management objectives and activities. (page 52)

Proposal Relationship:  The NPSWCD completed a Big Canyon Creek Marketing Plan in 2006.  This plan includes public involvement strategies for planning and decision making.  Activities identified in the plan will be implemented through this proposal.  Activities include public meetings, public comment periods, and focus group meetings.  Coordination with agencies is critical to the success of this project.  The NPSWCD works closely with the NPT to achieve fish habitat improvement success.  This proposal was closely linked to the NPT proposal #1999-016-00.  The NPT activities focus on tribal lands while the NPSWCD proposal focuses on private lands within the watershed.  In addition, coordination occurs with the IDFG, NRCS, and NPC to implement habitat improvement projects.

Problem 21: In the past, projects have not been successful in conditions where the local groups are not supportive. Long-term program implementation is more successful where projects are locally developed and implemented.

PP.   Objective: Participate in existing, and contribute to the further development of, local watershed and technical advisory groups. (page 58)

Proposal Relationship:  Completion of the inventory, analysis and recommendations from this proposal will assist the NPSWCD in identifying the future habitat restoration efforts needed as well as providing a prioritization and focus for specific watershed goals.  Part of the Big Canyon Creek watershed is located within the Lewis Soil Conservation District boundaries.  Information developed through this proposal will assist the Lewis Soil Conservation District in implementing their long range conservation goals.

QQ.    Objective: Maximize social and economic benefits as much as possible while implementing the Clearwater Subbasin Plan. (page 59)

Proposal Relationship:  Local labor forces and contractors will be used for installation of projects.

RR. Objective: Increase resource information and education delivery in the subbasin. (page 59)

Proposal Relationship:  This proposal is based upon a watershed approach to solving the identified resource issues.  In addition, the NPSWCD embraces a watershed approach in comprehensive planning efforts.  Information and education activities will be implemented according to the Big Canyon Creek Marketing Plan.  This plan was developed in 2006 and includes strategies to increase public awareness and to encourage adoption of fish habitat management practices.

The Big Canyon Creek Watershed consists of PMU-6, Pmu-7 and PMU-8 of the subbasin plan and amendment recommendation.

Table 4 is derived from the Clearwater Subbasin Management Plan and shows restoration issues and priorities by PMU.  Colors shown in the following data matrices show the priority assigned to the restoration issue assigned by the management plan: yellow = highest, red = high, green = medium, and blue = low.

Table 4:  Restoration Issues and Priority

| Restoration Issue | PMU-6 | PMU-7 | PMU-8 |
| --- | --- | --- | --- |
| Surface Erosion | X | X | X |
| Water Temperature |  | X | X |
| Hydrology | X |  |  |
| Grazing Impacts |  | X | X |
| In-stream Work |  | X | X |

Private Lands Prioritization Discussion

Based on a cursory evaluation of Table 4, the highest priority dealing with the widespread risks of erosion and increased water temperatures. The risk of surface erosion is a high priority concern in PMU’s 6, 7 & 8, coupled with apparent impacts from grazing, landslides, and sediment load.  This proposal includes road improvement projects that specifically address surface erosion. The need for riparian protection and in-stream habitat work appears common to many of the private land ownership PMUs, but of lower priority, and is also addressed by this proposal.

NPPC 2000 Fish and Wildlife Program

The program is habitat based focused on rebuilding healthy, naturally producing fish and wildlife populations by protecting, mitigating, and restoring habitats and the biological systems within them.  This project proposal works towards accomplishing the vision and objectives of the program by protecting and restoring the ecological functions, and habitats of the Big Canyon Creek watershed.  This project proposal directly addresses the following RPA actions: 149, 150, 152, and 153.

Clearwater Basin Noxious Weed Committee

This proposal supports and implements the goals of the Noxious Weed Committee to control and eradicate noxious weeds in the county.  One of the objectives of this proposal is to work with the Committee to develop a GIS overlay on noxious weeds for the watershed.

USDA- Natural Resources Conservation Service Strategic Plan 2000 – 2005

Goals identified in the NRCS’s Strategic Plan and which are addressed by the NPSWCD’s Big Canyon Creek watershed proposal include:

- Enhance natural resource productivity to enable a strong agricultural and natural resource sector by maintaining, restoring, and enhancing cropland, grazing land, and forestland productivity.

- Reduce unintended adverse effects of natural resource development and use to ensure a high quality environment by protecting water and air resources from agricultural non-point sources of impairment, enhancing animal feeding operations to protect the environment, and maintaining, restoring, or enhancing wetland ecosystems and fish and wildlife habitat.

- Deliver high quality services to the public to enable natural resource stewardship by delivering services fairly and equitably, strengthening the conservation delivery system, and ensuring timely, science-based information and technologies.

NMFS Biological Opinion

The proposed project complies with the following BiOp objectives:

- This project will help restore watershed health and degraded habitat.

- This project is designed to help recover the ESU of Snake River summer steelhead.

- This project helps avoid the jeopardy standard for the steelhead ESU.

- This project complies with the Reasonable and Prudent Alternative selected by NMFS to avoid the jeopardy standard.

- This project will help eliminate future road failures/landslides and protect the watershed from future degradation.

- This project will help to meet water quality standards and comply with the Clean Water Act.

- This project will be cost-shared through federal, state and private sources using programs such as the NRCS administrated PL-566, Environmental Quality Incentives Program (EQIP), Wetland Reserve Program (WRP), and Wildlife Habitat Improvement Program (WHIP).

- Restoring riparian habitats—re-vegetation of riparian areas and removal of streamside roads.

Salmon Recovery Strategy

The SRS habitat plan includes 1) immediate actions – restore water quality, remove passage barriers, secure high quality habitat, 2) Manage federal lands to protect fish, 3) Protect and improve tributary habitat (Federal Caucus 2000).

This project proposal fits into this plan by implementing immediate actions in erosion reduction, sediment reduction, stream temperature reduction, bacteria and nutrient reductions which will restore water quality and return quality habitat to key fisheries species.  All aspects of this project are coordinated with NRCS, NPT, IDFG, DEQ, Nez Perce County, and private landowners.

D. Relationships to other projects

In the Big Canyon Creek watershed, several federal, state and tribal programs may assist with anadromous fish habitat and riparian area restoration activities. This interest allows for many collaborative efforts and cost-share opportunities.  The proposal works with on-going restoration and monitoring projects within the watershed, which include the Clearwater Basin Noxious Weed Committee, NRCS, and NPTWRP.

This proposal complements BPA Project Number 199901600 which will complete resource inventory and implementation needs identified in the NPSWCD Big Canyon Creek Environmental Assessment (1995). This proposal is an expansion of NPSWCD BPA Project Number 199901500.

Other projects within the Big Canyon Creek watershed include:

BPA Project Number 199901600. NPTFWP.  Protect and Restore Big Canyon Creek Watershed. On-the-ground project M&E has been developed for the following on-going BPA projects.  An ongoing monitoring and evaluation plan to determine the overall health of the ecosystem and feedback for future project development.

FEMA- Flood mitigation. Lower Big Canyon FEMA Project. Land purchased in critical flood plain areas in 1998.   Extensive floodplain creation and streambank stabilization work to allow the creek to function closer to its normal hydrology.  Installation of instream streambank and fish structures and riparian vegetation. Work completed 2000.

Nez Perce Soil and Water Conservation District. Big Canyon Water Quality Program for Agriculture. Provides up to 75% cost share on agricultural and livestock BMPs with an emphasis on improving water quality in the creek. Addresses BMPs on private lands.  Landowners often have a hard time coming up with the remaining payment obligations

E. Project history (for ongoing projects)

Table 1. NPSWCD Accomplishments within the Big Canyon Creek Watershed

| Metric | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Road miles improved in upland area | .66 |  |  |  |  |  | 1.1 |
| Fence miles installed in riparian area |  |  | .33 | .95 |  |  | 1.28 |
| Fence miles installed in upland area |  | .35 | .09 |  |  |  | 1.1 |
| Instream habitat complexity stream miles improved | 0.66 |  |  |  |  |  | 0.66 |
| Structures installed for instream habitat complexity. | 5 |  |  |  |  |  | 5 |
| Wetland Acres Treated | .33 | .02 | .77 | 3 | 2 | 2 | 6.37 |
| Riparian Miles Treated | .13 | .5 | .71 | .57 | 2.7 | 1.25 | 5.86 |
| Upland acres treated | 95.95 | 1943.2 | 1756.8 | 2665 | 5263.3 | 4,100.1 | 15,863.23 |
| Riparian acres treated | 9.48 | 1.61 | 2.55 | 1.72 | 106.5 | 45.4 | 167.26 |

F. Proposal biological objectives, work elements, and methods

The proposed restoration and protection of the Big Canyon Creek Watershed follows the watershed restoration approach promoted by the NPSWCD.

All aspects of this proposal have been coordinated and developed with the Nez Perce Tribe (NPT) , using the Clearwater Subbasin Management Plan (Draft) and several other guiding documents as listed in section “C” above.

## Project

## Objective 1:  Successfully implement the “Restore Anadromous Fish Habitat in the Big Canyon Creek Watershed” project.

## Successful is defined as the timely completion of identified work elements and tasks.

Clearwater Subbasin Plan Relationship: The following objectives are linked to this project: CC (pg. 44), LL (pg. 52), MM (pg. 52), PP (pg. 52), and RR (pg. 59)

Work Element #1a:  Manage and Administer Projects (WE 119)

Work Element Title:  Manage and Administer Project

Discussion: Coordinate and communicate project administration, planning, technical, reporting, and implementation activities with BPA, regional partners, and regulatory agencies to ensure project goals, objectives, and expectations are being met and to comply with environmental regulations.  Includes management of on the ground efforts, subcontractors, metric reporting, financial reporting, and development of statement of work (SOW) packages.

Methodology: Meetings and phone calls to discuss schedules, responsibilities, and logistics.  Prepare SOW, budget, and equipment inventory, calendar of monthly spending, and submit to COTR 90 days prior to contract end. Subcontracts are developed using established NPSWCD contracting procedures and contract formats.  BPA invoicing process, accrual estimates and metrics reporting follows established BPA procedures and guidance.

Timeframe:   3/1/2007 through 2/28/2010

Deliverable:  3 SOW packages, 9 meetings.

Work Element #1b:  Coordination (WE 118)

Work Element Title:  Coordinate project implementation to reduce duplication and improve project delivery.

Discussion: Coordination includes activities with agencies as well as private landowners.

Methodology: Coordinate project activities with Nez Perce Tribe (NPT), Idaho Department of Fish and Game (IDFG), Lewis County, and Nez Perce County (NPC) through meetings, correspondence and phone calls.  Attend meetings related to BPA proposals and seek additional funding for project implementation.  With the assistance of the Clearwater Focus watershed coordinators, organize and participate in a one-day interagency coordination meeting (meeting held annually) to include the Nez Perce Tribe, Idaho Department of Fish and Game, Idaho Department of Environmental Quality (DEQ), USDA-Natural Resources Conservation Service (NRCS), Nez Perce County, Lewis Soil Conservation District, and Idaho Department of Transportation (IDT).  Participants will share information on specific watershed activities.  The goal of the meeting is to facilitate information sharing and to coordinate monitoring and inventory activities in order to avoid duplication and reduce expenses.

Timeframe:   3/1/2007 through 2/28/2010

Deliverable:  3 meetings per year in 2007, 2008, and 2009 meetings.

Work Element #1c:  Provide Technical Review (WE 122)

Work Element Title:  Provide technical assistance to agencies within the watershed in order to share technical expertise and reduce project costs.

Discussion: None.

Methodology: Technical assistance is provided to the NPT, IDFG, NRCS, SCC and NPC for designs, site inventory, and development of recommendations for projects occurring within the watershed and impacting fish habitat.

Timeframe:   3/1/07-2/28/2010

Deliverable:  Technical assistance provided on 3 projects per year in 2007, 2008, 2009.

Work Element #1d:  Create/Manage/Maintain Database (WE 160)

Work Element Title:  Develop a project database to facilitate information sharing and improve efficiency in BPA metrics reporting.

Discussion: A project installation database was developed by the NPSWCD to track projects, to development maintenance lists, provide RPA and metrics reporting to BPA and to facilitate the sharing of information with other groups.  The existing database was started in 2003 and contains project information for the years 199 through 2005.  2006 data will be added in January 2007.  Due to the high number and large success of shared projects between the NPT and NPSWCD, the group identified the need for a shared database to assist with project coordination, planning and reporting.  The database format will be revised and linked to a spatial GIS layer and include projects from the NPSWCD and NPT.

Methodology: Develop and update database and GIS layers to track project installation location and project specific information over time. This database will be developed in coordination with the Nez Perce Tribe and shared with other agencies as well as BPA annual reporting.

Timeframe:   Development:  November – March, 2008;  Project updating occurs annually in 2007, 2008, and 2009.

Deliverable:  Project tracking database and GIS infrastructure

Work Element #1e:  Produce Environmental Compliance Documentation (WE 165)

Work Element Title:  Complete environmental compliance documentation.

Discussion: None.

Methodology: Work with BPA ESA coordinator to determine environmental compliance documentation needs and receive a summary of HIP BiOp information for selected categories of action.  Includes activities for completing NEPA checklists.  Work will be completed by the NPSWCD.

Timeframe:   3/2007-6/1/2007;3/1/08-6/1/08;3/1/09-6/1/09

Deliverable:  NEPA checklist, summary of HIP BiOp information

Work Element # unnumbered – Produce Annual Report (WE 132)

Work Element Title:  Produce annual project report.

Discussion: None.

Methodology: Prepare an annual accomplishment report and submit to BPA for publication on web site.

Timeframe:   once per year in 2007, 2008, 2009

Deliverable:  3 reports

Work Element # unnumbered – Produce PISCES Status Report (WE 185)

Work Element Title:  Produce PISCES Status Report.

Discussion: None.

Methodology: Using BPA’s PISCES system report milestone status for deliverables in the contract

Timeframe:   4 times per year in 2007, 2008, 2009

Deliverable:  12 reports

## Project

## Objective 2:  Identify fish habitat limiting factors and prioritize treatment needs for the restoration, protection and enhancement of steelhead spawning and rearing habitat within the Big Canyon Creek watershed.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: B (pg.18), O (pg.31), Q (pg.33), S (pg.36), U (pg.37), Z (pg.40), AA (pg.42), BB (pg.42), CC (pg.44), DD (pg.45), EE (pg.45), JJ (pg.50), and MM(pg.52).

Work Element #2a:  Produce Inventory or Assessment (WE 115)

Work Element Title:  Collect stream inventory data on 60 miles of Big Canyon Creek.

Discussion: This work element requires several steps which are listed by milestone.  The methodology, timeframe, and deliverables are listed for each milestone.

Milestone A. Obtain landowner permission.

Methodology: Personally contact landowners at selected assessment sites and obtain access permission.   Work will be completed by the NPSWCD.

Timeframe:  June 2007, June 2008, and June 2009.

Deliverable:  Landowner permission obtained.

Milestone B. Compile maps and determine access needs.

Methodology: Obtain aerial photography and USGS topographic maps for use in completing assessments.  Determine access needs by reviewing maps and talking to landowners.  Produce maps by reach number.  Work will be completed by a subcontractor or existing NPSWCD resources depending upon the number of maps needed.

Timeframe:  May 2007

Deliverable:  Access needs identified.  Maps created by inventory reach.

Milestone C. Collect field data.

Methodology: Collect field data using the protocol established through the 2002 BPA project # 2002-015-00 “Restoring Anadromous Fish Habitat in the Big Canyon Creek Watershed”.  GPS locate assessment sites in the field.  Develop a GIS layer showing evaluation sites

Timeframe:  May – September 2007, May-September 2008, and May – September 2009 (if needed).

Deliverable:  Data collected on 120 miles

Work Element # 2b:  Create/Manage/Maintain Database (WE 160)

Work Element Title:  Maintain stream inventory database in order to capture data and  facilitate analysis.

Discussion: None.

Methodology: Maintain a database and the associated spatial layer used to manage and analyze the stream inventory and assessment data.  Data entry components will be completed by the NPSWCD and GIS components by a subcontractor.

Timeframe:  12/1/2007 through 2/28/2009

Deliverable:  Database and GIS coverage

Work Element #2c:  Analyze/Interpret Data (WE 162)

Work Element Title:  Analyze Big Canyon Creek Stream Inventory Data in order to identify fish limiting factors and prioritize treatment needs.

Discussion: This work element requires several steps which are listed by milestone.  The methodology, timeframe, and deliverables are listed for each milestone.

Methodology: Analyze and interpret data to identify major limiting factors and list recommended treatment alternatives.  Data analysis shall include items specified in Section C “Rationale and relationship to regional programs”.  These include but are not limited to identification of stream temperature problem areas, identification of floodplains and wetlands, identification of sediment sources and problems, identification of nutrient input sources, prairie remnants, mature ponderosa pine stands, weed infestations and livestock impacts.

Timeframe:  December 2007, December 2008 and October – December 2009.

Deliverable:  Data analyzed.

## Project

## Objective 3:  Establish baseline temperature database, identify and prioritize stream temperature problems, and evaluate project implementation effectiveness.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: B (pg.18), Q (pg.33), LL (pg.52), and RR (pg.59).

Work Element #3a:  Collect/Generate/Validate Field and Lab Data (WE 157)

Work Element Title:  Stream temperature data collection in the Big Canyon Creek watershed.

Discussion: The Lower Clearwater TMDL is in progress and planned for completion by 2007.  Temperature data on the small tributaries is a data gap identified for TMDL as well as within the Clearwater River subbasin.

Methodology: Collect stream temperature data at 6 sites within the watershed.  The sites are selected through a coordinated effort with Nez Perce Tribe and Idaho Department of Environmental Quality.  Location selection and deployment will follow Idaho Department of Environmental Quality protocols.  Loggers are placed in March and collected in November of each year.  Work will be completed by NPSWCD staff.

Timeframe:  March – November for each year 2007, 2008, and 2009

Deliverable:  Loggers deployed and raw data collected.

Work Element #3b:  Collect/Generate/Validate Field and Lab Data (WE 157)

Work Element Title:  Evaluate effectiveness of stream temperature reduction practices.

Discussion:  Practices were installed from 2003-2006 for the purpose of stream temperature reduction.  The majority of these practices were riparian vegetation plantings.  In order to evaluate the effectiveness of these projects in reducing stream temperatures, data needs to be collected.

Methodology: Collect stream temperature data at 4 sites where riparian vegetation has been planted.  The monitoring sites will be located at strategic locations within the watershed.  HOBO temperature loggers will be deployed at the upstream and downstream ends of projects.  Deployment, data collection, quality assurance, and data management will follow Idaho DEQ protocols.  Loggers are placed in March and collected in November of each year.  Work will be completed by NPSWCD staff.

Timeframe:  March – November for each year 2007, 2008, and 2009

Deliverable:  Loggers deployed and raw data collected.

Project

Objective 4:  Inventory, assess, identify projects and produce watershed/stream restoration plans on specific lands within the Big Canyon Creek Watershed.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: B (pg.18), M (pg.29), Q (pg.33), S (pg.36), U (pg.37), V(pg.38), W (pg.38,39),

X (pg.39), Y (pg.40,41), Z (pg.41), BB (pg.42,43), CC (pg.44), EE (pg.45,46), and

JJ (pg.50).

Work Element #4a:  Identify and Select Projects (WE 114)

Work Element Title:  Identify and select projects for restoration plan development, site specific inventories, and project designs.

Discussion: This work element requires several steps which are listed by milestone.  The methodology, timeframe, and deliverables are listed for each milestone.

Milestone A.  Accept applications for project participation.

Methodology: Applications for project participation will be collected by using the project application format developed for the.  Applications will be accepted by mail, fax, or phone following established NPSWCD guidelines

Timeframe:  May through July of each year in 2007, 2008 and 2009

Deliverable:  8 applications received each year in 2007, 2008, and 2009

Milestone B. Meet one-on-one with landowners in the watershed

Methodology: Meet with landowners on their property to discuss project goals, fish habitat resource needs, and discuss opportunities for habitat improvement on their land.  The NPSWCD staff has been using this method of landowner education for over 60 years and has established a trust relationship with landowners in the watershed.

Timeframe:  May – September 2007, May-September 2008, and May – September 2009 (if needed).

Deliverable:  8 landowner meetings per year in 2007, 2008, and 2009

Milestone C. Complete initial site reviews and collect resource data

Methodology: Visit project sites and complete inventory data for approved project applications. Site inventory will follow NRCS FOTG procedures and methods.

Timeframe:  May through July of each year in 2007, 2008 and 2009

Deliverable:  6 initial site reviews completed each year in 2007, 2008, and 2009

Milestone D.  Rank and prioritize applications from landowners

Methodology: Rank project applications using an established ranking protocol.  This criterion will ensure that the applications with the most impact on fish habitat are selected and processed

Timeframe:  May through July of each year in 2007, 2008 and 2009

Deliverable:  List of prioritized applications each year in 2007, 2008 and 2009

Work Element #4b:  Produce Plan (WE 174)

Work Element Title:  Develop Habitat restoration plans.

Discussion: This work element is critical to the identification and implementation of restoration projects within the Big Canyon Creek Watershed.  The NPSWCD uses a conservation planning process to develop habitat restoration plans.  After a potential project is identified in Task D, then an initial site inventory is conducted to identify natural resource concerns.  Depending upon the size and complexity of the site, the inventory is completed by an interdisciplinary team of resource professionals who provide technical assistance in identification of problems and selection of alternatives.  After an inventory and assessment/quantification of resource concerns, a list of alternatives to treat the identified problems is developed.  The next step is to develop the habitat restoration plan which identifies the concerns, treatment goal/standard, the selected alternative for treatment, implementation schedule and costs.  This plan is the basis for implementation of all projects.

Methodology:  Inventory, assess, identify, and select alternatives to treat fish habitat related resource concerns.  This is completed by on-site inspections and inventory protocols established by the NPSWCD.

Timeframe:   3/1/2007 – 2/28/2010

Deliverable:  4 habitat restoration plans per year in 2007, 2008, 2009

Work Element #4c:  Produce Design and /or specifications (WE 175)

Work Element Title:  Complete designs identified in habitat restoration plans.

Discussion: Depending upon the complexity of the design, NPSWCD staff complete designs.  Technical assistance for complex designs is obtained from the NPT, Idaho Department of Agriculture, and Natural Resources Conservation Service.

Methodology:  Designs are prepared for projects identified in the habitat restoration plans developed under the produce plan work element. Complete surveys to obtain site specific data for the completion of engineering and technical designs. This work includes, but is not limited to, cross-sections, benchmark elevation determination, topographic and photometric surveys. Design package includes surveys, engineering or technical drawings, site maps, construction or installation specifications and material specifications, and cost-estimates. Site locations for designs are determined from the annual prioritization of projects submitted by landowners. A list of projects is developed each fall and then designs are prepared for the highest priority projects. Designs are completed through a coordinated team of professionals including Nez Perce Tribe, Nez Perce County, USDA-Natural Resources Conservation Service, Idaho Department of Agriculture, and subcontractors.

Timeframe:   3/1/2007 – 2/28/2010

Deliverable:  15 designs completed each year in 2007, 2008, 2009

## Project

## Objective 5: Implement agricultural, livestock and riparian structural and management practices to restore, enhance, and protect anadromous fish habitat, streambank stability, watershed hydrology, water quality, and floodplain function within the Big Canyon Creek watershed.

Tasks completed under this objective include those relating to land improvement projects.  All projects installed through this objective have been identified as a high priority through the conservation planning process.  When a project reaches this phase, all designs and environmental compliance activities are completed.  Tasks include the layout, inspection, and physical installation of the projects listed.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: M (pg.29), Q (pg.33), S (pg.36), U (pg.37), W (pg.38,39), Y (pg.40,41), Z (pg.41), AA (pg. 42), BB (pg.42,43), CC (pg.44), DD (pg. 45), EE (pg.45,46), JJ (pg.50), and QQ (pg. 59).

Work Element #5a:  Develop alternative water source (WE 34)

Work Element Title:  Develop alternative livestock water sources.

Discussion: Alternative water sources are needed to remove livestock from riparian, wetlands, and other sensitive resource areas.  Selecting a livestock watering alternative includes consideration of site specific water sources, impacts on other resources from development of a new water source, economics, and system limitations.  The steep topography and limited access to canyonlands prevents unique challenges in the selection of a water source.  Alternative energy systems are needed in these areas due to a lack of reliable power sources.  The NPSWCD is demonstrating wind and solar technologies through the existing watershed project.  These technologies appear promising for canyonland installations.

Methodology:  Install alternative water developments in areas identified through the stream inventory and conservation planning process. Where livestock water directly from stream sources or springs, alternative water sources will be developed. These water sources include wind, solar and gravity fed systems. Typical components of a water system include a trough, collector and pipeline.  Subcontracts will be developed for installation of systems.

Timeframe:   June – October each year in 2007, 2008 and 2009

Deliverable:  3 alternative watering facilities per year in 2007, 2008, and 2009.

Work Element #5b:  Install Fence (WE 40)

Work Element Title:  Install fence to protect wetlands/riparian areas.

Discussion: None.

Methodology:  Install fence in areas identified through the stream inventory and conservation planning process. Work items include obtaining materials identified in fence designs and installation. Fence will be installed by landowners or by the Nez Perce Tribe Fence Crew.

Timeframe:  May through November of each year.

Deliverable:  1 miles of fence per year in 2007, 2008, and 2009.

Work Element #5c:  Upland Erosion and Sedimentation Control (WE 55)

Work Element Title:  Install erosion control practices.

Discussion: None.

Methodology: Install erosion control measures such as grassed waterways, terraces, grade control structures, sediment basins, diversions, water and sediment control structures and buffers as recommended through the stream inventory process and habitat plan development on specific land owner properties.

Timeframe:  May to November of each year.

Deliverable:  8 erosion control practices per year in 2007, 2008, and 2009.

Work Element #5d:  Create, Restore, and/or Enhance Wetland (WE 181)

Work Element Title:  Restore and enhance wetlands.

Discussion: None.

Methodology: Implement wetland restoration and enhance measures as recommended through the stream inventory and habitat planning process.   These methods include the development of shallow water areas, wetland plantings, wetland sod installation, and wetland biolog installation.

Timeframe:  May to November of each year.

Deliverable:  0.5 acres of restored and/or enhanced wetland per year in 2007, 2008, and 2009.

Work Element #5e:  Improve/Relocate Road (WE 38)

Work Element Title:  Improve forestry, agriculture and rangeland access roads.

Discussion:  None.

Methodology: Road improvements consist of upgrading cross-sections and ditch, addition of base and surface aggregates, and upgrading inadequate cross-drains to reduce sediment delivery to the stream. Work inspection will occur during installation to ensure design parameters and material specifications are followed.

Timeframe:  May to November of each year.

Deliverable:  1 mile of improved road per year in 2007, 2008, and 2009.

Work Element #5f:  Increase Habitat Complexity (WE 29)

Work Element Title:  Restore instream habitat complexity within the Big Canyon Creek Watershed.

Discussion:   None.

Methodology: Restore instream habitat complexity through the installation of LWD in areas recommended by the stream inventory.

Timeframe:  May to November of each year.

Deliverable:  1 mile of stream with increased habitat complexity per year in 2007, 2008, and 2009.

Work Element #5g:  Remove Vegetation (WE 53)

Work Element Title:  Control weeds to assist in establishment of riparian vegetation.

Discussion: The control of weed competition is critical in the first two to three years after a riparian planting.

Methodology:  Implement invasive weed treatment prior to planting vegetation. Weed control will be performed using mechanical and chemical control methods to assist in the establishment of riparian vegetation. Mechanical weed control is performed with weed eaters and mowers. Chemical weed control is performed using hand sprayers with herbicide application occurring in spot treatment areas. Weed control will be performed in late spring and early fall depending upon weed growth during the year. Work will be completed by NPSWCD staff, Idaho department of Correction Inmate Labor, and subcontractors.

Timeframe:  April-October annually

Deliverable:  8 acres weed control per year in 2007, 2008, and 2009

Work Element #5h:  Plant Vegetation (WE 47)

Work Element Title:  Plant riparian and upland grass plantings to reduce sediment delivery, improve base flows, increase stream habitat shading and improve habitat complexity.

Discussion:  None.

Methodology:  Plant vegetation to reduce sediment delivery to Big Canyon Creek, restore base flows, increase stream shading and improve habitat diversity and complexity. Locations are determined from recommendations in the stream inventory and habitat planning processes. Native species will be used where appropriate and feasible. All seed used will be certified weed free seed.

Timeframe:  April-October annually

Deliverable:  7 acres riparian plantings and 20 acres upland plantings per year in 2007, 2008, and 2009

## Project

## Objective 6: All historical fish habitat within the Big Canyon Creek watershed is accessible and connectivity is re-established.

Clearwater Subbasin Plan Relationship: The following objective applies to this project: P (pg.32).

Work Element #6a:  Remove/Modify Dam (WE 85)

Work Element Title:  Maintain connectivity within the Big Canyon Creek watershed in low-flow months.

Discussion:   None.

Methodology: Install 2 low flow crossing barrier improvements. A different technique will be used at each site to demonstrate to land owners and users alternatives for low flow condition stream crossings. Stream inventory data collected in the 2002-2005 proposal identified fish passage barriers during low flow summer months. These barriers typically occur where the stream is used for agricultural equipment crossings. The need for low cost, low maintenance alternatives was identified. Crossing types will be identified in the FY06 Restoring Anadromous Fish Habitat Proposal. These alternatives will be applied through this proposal and used as demonstration sites to assist in land owner/manager adoption.

Timeframe:  May to November of 2008

Deliverable:  2 stream crossings installed

Work Element #6b:  Install Fish Passage Structures (WE 184)

Work Element Title:  Restore connectivity.

Discussion:   None.

Methodology: Replace barrier culverts with fish friendly structures as recommended and prioritized by IDT team and SVAP. Implementation items include bid advertisement, site inspection, bid award, final inspection.  Replace fish passage barriers on private lands identified within the Fish Passage Barrier Assessment.  Work is in cooperation with the NPT and NPC.  Focus will be along stream reaches identified for road improvements by NPC.  The target is to replace barriers along an entire stream reach, where the NPC is replacing NPC owned and operated culverts to meet fish passage criteria and the NPSWC and NPT replace private culverts within these same reaches.  The coordinated effort will result in a reduction of costs due to labor and equipment availability within the identified reaches.

Timeframe:  May to November of each year.

Deliverable:  Replace 1 structures per year in 2008 and 2009

## Project

## Objective 7: Continue Marketing the Project to Watershed Stakeholders.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: BB (pg.42,43), CC (pg.44), DD (pg. 45), LL (pg. 52), PP (pg. 58), and RR (pg.59).

Work Element #7a:  Outreach and Education (WE 99)

Work Element Title:  Inform public about fish habitat needs within the watershed.

Discussion: This work element requires several steps which are listed by milestone.  The methodology, timeframe, and deliverables are listed for each milestone.

Milestone A. Develop and distribute Forever Soil and Water newsletter to identified landowners in watershed survey areas.

Methodology:  Update newsletter mailing list to include landowners within identified watersheds.  Publish a newsletter 2 times per year to provide project specific and habitat restoration educational information.  Specific articles relate to CCRP program relationship to project areas, weed identification, biocontrol availability for yellow starthistle.

Timeframe:  February and October of each year in 2007, 2008, and 2009

Deliverable:  6 newsletters

Milestone B. Conduct public information meetings.

Methodology:  Using mass mailing and television techniques inform the Big Canyon Creek watershed landowners about the project and meeting specifics.  The agenda will include other agencies that have activities within the watershed.

Timeframe:  January 2008

Deliverable:  One public meeting

Milestone C. Develop information materials to explain project goals and specific fisheries needs.

Methodology:  Work with the IDFG and NPT to develop one-page informational fact sheets on the fish species present and habitat needs. Provide an initial project media overview by presenting information to KOZE radio show, and Lewiston Morning Tribune.  Develop fact sheets for new weed invaders, weed free seed benefits, ATV weed spreading, and native species information.  Efforts are with the Palouse Prairie Foundation and IDA.  Work will be completed by a subcontractor.

Timeframe:  December 2007 through December 2008

Deliverable:  2 PSAs, 4 fact sheets

Milestone D. Conduct two noxious weed educational workshops for watershed landowners.

Methodology:  Coordinate with the Nez Perce Tribe Bio-control Center and the Clearwater Basin Weed Advisory Committee to conduct the workshop.  Inform landowners by newsletters, newspaper, and newsletter advertisements.  Based on high landowner interest, we estimate 50 landowners will receive direct educational benefits.

Timeframe:  June 2007 and June 2009

Deliverable:  Two Educational workshops

Milestone E. Conduct Technology transfer tour.

Methodology:  Following NRCS social Science protocol for conducting watershed tours, the NPSWCD will advertise a project results tour.  The tour will show implemented BMPs to address fish habitat.  The NPSWCD will arrange transportation, speakers, and obtain all agreements to conduct the tour.

Timeframe:  June 2008

Deliverable:  One tour

## Project

## Objective 8: Ensure project installation compliance and revise implementation strategies based on monitoring installed practices.

Tasks completed under this objective include those relating to project maintenance activities.

Clearwater Subbasin Plan Relationship: The following objectives apply to this project: B (pg. 18), O (pg. 31), P (pg. 32), Q (pg. 33), S (pg. 36), U (pg. 37), W (pg. 38,39), X (pg. 41), Y (pg. 41), Z (pg. 41), AA (pg. 42), BB (pg. 43), CC (pg. 44), DD (pg. 45), EE (pg. 46), and JJ (pg. 50).

Work Element #8a:  Maintain Vegetation (WE 22)

Work Element Title:  Maintain riparian vegetation.

Discussion: Maintenance of riparian planting vegetation is critical to establishment success for the first 3 years following a planting.  Plantings completed in the previous BPA project for the years 2004-2006 will be maintained as well as plantings installed in 2007-2009.  The NPSWCD develops subcontracts with landowners.  One item in these contracts is the long-term maintenance of plantings.  Under these subcontracts, the landowner is responsible for vegetative planting maintenance after the initial establishment years.  All costs associated with long-term maintenance are the responsibility of the subcontract participant.  Maintenance needs during establishment will vary depending upon plant species, annual precipitation, and original site conditions.  The NPSWCD staff will periodically inspect plantings in the long-term maintenance phase to ensure that landowners are properly maintaining the practices.

Methodology:  Maintenance of previously installed riparian vegetation includes an annual site review to monitor establishment and determine if weed control is needed. If weed control is determined as needed, then the weed control will be performed. Weed control methods include mechanical (mowing) and herbicide (spot spraying).

Timeframe:  March-October annually

Deliverable:  40 acres vegetation maintained

Work Element #8b:  Collect/Generate/Validate Field and Lab Data (WE 157)

Work Element Title:  Project compliance and implementation monitoring.

Discussion: Implementation monitoring is needed on projects installed in 2003 through 2009 to ensure the projects are functioning as intended.  Monitoring may include practice effectiveness data relating to sediment reductions, stream temperature, riparian restoration, erosion control, and stream morphology changes as appropriate.

Methodology:  Post project monitoring to ensure project specifications were completed. Set up and collect data to evaluate restoration projects to ensure desired outcomes are met. Data collection may include photo points, vegetation plots, cross-sections, bank erosion monitoring and post year site inspections.

Timeframe:  September-November annually

Deliverable:  Implementation monitoring completed on 10 sites.

G. Facilities and equipment

Activities for this project will be based out of the Nez Perce Soil and Water Conservation District office in Culdesac, Idaho.  Space and field survey equipment exists to complete identified project tasks.  However, the following items are needed to complete the tasks outlined in this proposal:

1)	GPS unit

2)	Lap Top Computer

3)	ArcView Software Extensions for 3-D mapper and spatial analyst

4)   GIS computer upgrade (additional hard drive storage)

H. References

Reference (include web address if available online)

Columbia Basin Fish and Wildlife Authority. 1999. FY 2000 Draft Annual Implementation Work Plan. Submitted to the Northwest Power Planning Council.

Columbia River Inter Tribal Fish Commisssion. 1996. Spirit of the Salmon- The Columbia River Anadromous Fish Restoration Plan of the Nez Perce, Umatilla, Warm Springs and Yakama Tribes

(Replace this text with your response; use regular Word commands to add/del/move rows)

(Replace this text with your response; use regular Word commands to add/del/move rows)

(Replace this text with your response; use regular Word commands to add/del/move rows)

I. Key personnel

Name:  Lynn Rasmussen

Title:  Project Manager

Agency: Nez Perce Soil and Water Conservation District

Hours:  FTE

Project Duties: Project manager, lead technical contact, budget management, cropland erosion control planning and design, training staff, quality assurance.

Current Responsibilities: Responsible for watershed planning for District programs in Nez Perce County, liaison with the Nez Perce Tribe, Contracting officer for District programs, watershed and area-wide planning, coordination with state, tribe and local governments on priority conservation issues, supervise and train staff, develop and design conservation BMPs.

Education: 	B.S. Crop Science, University of Idaho

Range, chemistry credits, New Mexico State University

M.S. Soils, University of Idaho

Relevant Training:

Pesticide Consultant License in Idaho, area-wide planning, hydrology, stream morphology, water quality indicators, soil quality, forest water quality, confined animal feeding operation design, livestock waste and crop fertilizer nutrient management planning, range inventory, plant identification, stream corridor restoration, conservation practice engineering design, construction inspection, nutrient management, bio-engineering applications, NEPA and ESA documentation, soil physics, stream visual assessment evaluation, BMP effectiveness evaluation, statistics, conservation program management, personnel management, locally led conservation and public involvement, conservation salesmanship, project management, greenhouse production, agronomy, soil classification, soil chemistry

Previous Employment:

- July 2003 to present	Nez Perce Soil and Water Conservation District

Project Manager

- October 1995 – July 2003	Natural Resources Conservation Service

District Conservationist

- August 1993-September 1995	Natural Resources Conservation Service/Watershed

Enhancement Team

Resource Conservationist

- July 1990 – July 1993	Natural Resources Conservation Service

Soil Conservationist, St. Maries Field Office

- June 1988 – June 1990	Natural Resources Conservation Service

Soil Conservationist, Moscow field office

- June 1986-May 1988	University of Idaho

Research Assistant

Expertise: Ms Rasmussen’s background encompasses water quality planning, watershed planning, erosion calculation and analysis, conservation practices design, and project management.

Relevant Job Completions: (5 max) – 1)  Developed, coordinated and principle author on the Big Canyon Creek Environmental Assessment.  2)  Conducted a 5 year BMP effectiveness study evaluating the erosion reduction from grass waterways and sediment control structures. 3)  Responsible for resource inventory collection, data analysis, alternative development, NEPA compliance for the Lapwai Creek PL566 watershed project. 4)  Completed 20 habitat restoration plans from 2003-2005 5)  Completed the inventory and analysis for watershed resource assessments on Cottonwood Creek, Hatwai Creek, and Lindsay Creek.

Name: Amanda Hendrix

Title: Resource Conservationist

Agency: Nez Perce Soil and Water Conservation District

Hours:  FTE

# Education:  B.S. Plant Science, Montana State University, Bozeman, MT, 2001

Current Responsibilities: Work with agricultural and rural landowners to promote conservation of natural resources.  Develop and administer contracts based on conservation needs and implement best management practices to improve water quality and mitigate other resource concerns.

Relevant Trainings:

  RUSLE Training (NRCS 10/05)

  Biological Control Agents Training (NPT 5/05)

  Certified Plant Professional, Idaho and Montana Nurseryman Association

  Wetland Delineation and Management, Wetland Training Institute (9/05)

Duties on project: Work with agricultural and rural landowners to address resource concerns.  Provide technical assistance to implement resource management practices that will improve water quality and wildlife habitat.  Inventory resources and prioritize projects.  Participate in monitoring best management practices to determine their efficacy.

Previous Employment:

 May 2005-Present, Resource Conservationist, Nez Perce SWCD, ID

 April- May 2005, Biological Science Technician, Lower Granite Dam, WA

 May 2004- October 2004, Botanical Inventory Technician, BLM Cottonwood Field Office, ID

 September 2003- April 2004, Assistant Grower, Cashman Nursery, MT

 May 2003 – August 2003, Environmental Technician, Wyo-Ben Inc., WY

 September 2002 – May 2003, Environmental Technician, Wetlands West, MT

 June 2002 – August 2002, Scientist, TREC, MT

 October 2001 – May 2002, Associate Scientist, North Wind Environmental, Inc., WY/ID

 May 2001 - September 2001, Environmental Technician, Wyo-Ben Inc., WY

Expertise: Ms. Hendrix’s background encompasses various environmental concerns and tasks.  Her experience includes vegetation monitoring and assessment; selection and installation of native plant materials for riparian restoration projects; conservation planning; wetland delineation; reclamation planning and implementation of mined lands; debitage analysis; well monitoring; rare plant surveys; surgical pit/radio tagging of juvenile Chinook and steelhead; and native plant propagation.

Name: Dash Dieringer

Title: Field Technician

Agency: Nez Perce Soil and Water Conservation District

Hours:  FTE

Current Responsibilities: Work with agricultural and rural landowners to promote conservation of natural resources.  Develop and design BMP’s, conduct monitoring and evaluation activities in the watershed and the county, develop GIS products.

Relevant Trainings:

  Pesticide applicator license- University of Idaho Agriculture Dept.

Duties on project: Work with agricultural and rural landowners to address resource concerns.  Provide technical assistance to implement resource management practices that will improve water quality and wildlife habitat.  Inventory resources and prioritize projects.  Participate in monitoring best management practices to determine their efficacy. Develop and design BMP’s,  conduct monitoring and evaluation activities, conduct resource inventories, develop GIS products.

Previous Employment:

 2002-Present, Field Technician, Nez Perce SWCD, ID

 2000-2002, Squad Boss, Nez Perce Tribal Fire Management Emergency Wildland Firefigher

Crew, ID

 1998-2000, Squad Leader, Nez Perce Salmon Corps (Americorps), ID

Expertise: Mr. Dieringer’s background encompasses various environmental concerns and tasks.  His experience includes riparian vegetation installation, monitoring and assessment; conservation planning; utilizing GIS technology and systems to produce GIS products, utilizing bioengineer techniques in riparian restoration.

Name: Justin Peterson

Title: Fish Biologist

Agency: Nez Perce Soil and Water Conservation District

Hours:  FTE

Current Responsibilities: Project inventorying restoration needs and assisting with developing restoration projects within the Lapwai and Big Canyon Creek watersheds.

- Relevant Trainings: Course study fisheries management, ichthyology, mamology, onithology, zoolology, biodiversity, field botany, geographic information systems, environmental ethics, chemistry, and biometry.

Duties on project: Inventorying stream reaches based on stream morphology, substrate, erosion extent, anthropogenic impacts, and plant species presence. Assists in completing annual reports. Enter data, compete analysis, and reports utilizing: Excell, Word, Access, and ArcMap.

Previous Employment:

- 1/2006-Present, Fish Biologist, Nez Perce SWCD, ID

- 6/2005 – 1/2006, Biologist, Nez Perce Tribe, Department of Fisheries Research    Management (Watershed)

- 2/2005 – 5/2005, Senior Fishery Technician, Idaho Dept. of Fish and Game

- 5/2001 – 2/2005, Fishery Technician, Idaho Dept. of Fish and Game

- 5/2000 – 1/2001, Fishery Biological Aide, Idaho Dept. of Fish and Game

- 7/1999 – 11/1999, Biological Aide, Lewis Clark State College

Expertise: Mr. Peterson has a solid background in Fisheries research and management. He is knowledgeable in the anadromous fish species of the region and is the District’s authority on fish biology for matters.

Name: Mike Hoffman

Title: Water Quality Resource Conservationist

Agency: Soil Conservation Commission

Current Responsibilities: Provide technical assistance for BMP installation.

Name: Bill Lillibridge

Title: Engineer

Agency: Idaho Department of Agriculture

Current Responsibilities: Provide technical assistance for BMP installation.

Name: Clint Chandler, Fisheries Biologist II

Title Fisheries Biologist II

Agency: Nez Perce Tribe Fisheries/Watershed Division

Hours: 1.0 FTE

Education:  B.S. Biology, Eastern Oregon State University, La Grande, OR 1991

Current Responsibilities:

Responsible for budget preparation, subcontract preparation and management, equipment selection and procurement, personnel interviews, training and supervision, data collection and analysis, database management, report writing and proposal development.

Previous Employment:

2002-Present: Nez Perce Tribe Fisheries/Watershed Division

Fisheries Biologist II/Project Leader

1999-2002: Nez Perce Tribe Fisheries/Research Division

Fisheries Technician II

1998: Science Application International Corporation

Terrestrial Ecologist

1997: USGS Columbia River Research Lab (subcontracted by Johnson Controls Inc.)

Fisheries Biologist

Relevant Training:

Thirteen years fisheries experience, eight of which juvenile salmonid research.

Experience with snorkel, screw-trap, gee-trap, weir, trawl, seine, gill-net, long-line, hook and line and electrofishing surveys.

Five years experience with habitat assessment, four of which stream aquatic.

Five years experience training and supervising fisheries aides, technicians and biologists.