# FY 2007-2009 F&W Program Project Solicitation

# Section 10. Narrative

Project ID:	2007222000

Title: 	Genetic Characteristics and movement patterns of bull trout populations between Chief Joseph and McNary Dams within the Columbia Cascade and Columbia Plateau Provinces

A. Abstract

Uncertainty about genetic structure, abundance, distribution, and habitat use of bull trout populations constrains effective management and contributes to regulatory uncertainty.  The status of bull trout populations is difficult to assess because bull trout are rare and they exhibit a diversity of life history strategies within populations.  Consequently, accurate population assessments require long-term monitoring using a variety of techniques.  The objectives of this project are to evaluate the status of the Columbia River Distinct Population Segment of bull trout within the Columbia Cascade and Columbia Plateau Provinces, between Chief Joseph and McNary Dams.  We, propose to use two approaches to enhance ongoing assessments of population status: (1) determine population genetic structure, and assess brook trout hybridization, using non-lethal tissue sampling and (2) evaluate connectivity, locate spawning and wintering areas, and identify migratory patterns using radio telemetry and genetics data.  New data gathered together with completed and ongoing studies will result in a comprehensive view of bull trout populations in four sub-basins and the mainstem Columbia River and will provide the methodological framework necessary for improving the reliability of bull trout population assessments.

This multi-agency effort will address information needs identified in biological opinions, sub-basin plans, Washington State watershed plans, US Forest Service (USFS) watershed assessments, state and federal recovery plans, habitat conservation plans, and Columbia basin fish and wildlife plans.  It could be used to relate population status to current management strategies and to identify relevant watershed restoration needs. Our efforts to analyze data and use of coordinated methods will have relevance at multiple scales across the range of bull trout. We will present results of this work in guidance to fisheries managers, annual reports, presentations at professional and public meetings, and publications in peer-reviewed journals.

B. Technical and/or scientific background

The general problem addressed by this proposed project is widespread uncertainty about the population structure, distribution, abundance, and habitat use of bull trout.  We will address this problem at a variety of scales ranging from individual spawning tributaries, to the core areas identified in the 2002 USFWS Draft Bull Trout Recovery Plan, to the migratory connective corridors among four sub-basins (Methow, Entiat, Wenatchee, and Yakima) and their connection through the mainstem Columbia River, and to the Columbia River Distinct Population Segment of bull trout.

The biological basis of this problem stems from the rarity and life history diversity of bull trout.  The abundance of bull trout have been reduced by the combined effects of habitat degradation, blockage of migratory corridors, poor water quality, incidental catch by anglers, entrainment, and introduced non-native species (USDI 1998).  All of these factors have contributed to declining abundance in the Columbia Cascade and Columbia Plateau Provinces.  Low abundance reduces probability of detection per unit of survey effort (Dunham and Chandler, 2001).  Life-history diversity is expressed as resident and migratory forms, with migratory forms expressing further diversity as either fluvial or adfluvial migrants (Rieman and McIntyre 1993).  Expression of these different life-history forms is probably associated with genetic diversity (Rieman and McIntyre 1993).  Simulations suggest that average annual spawning populations of at least 1,000 individuals represent a cautious goal for preserving this genetic diversity (Reiman and Allendorf 2001). Variation in the proportions of the population exhibiting each strategy, the potential for elimination of some life-history forms (e.g., by barriers to migration), irregular spawning timing, and apparently opportunistic use of different spawning areas (Reiman and McIntyre 1995), all contribute to the difficulty of accurately determining population status, migration patterns, and habitat use.

A second biological issue is that bull trout have different habitat requirements and life-history strategies than anadromous salmonids (USFWS 1998b).  Analyses that focus on limiting factors for anadromous salmonids may not adequately account for the different, and sometimes more stringent habitat requirements of bull trout.  This may be especially true of the migratory pathways and timing of adult bull trout.

The administrative component of this problem stems from the USFWS listing bull trout as a threatened species in the Columbia Basin in 1998 (USDI 1998) and throughout their range in the coterminous United States in 1999 (USDI 1999).   Incomplete information about the distribution and abundance of bull trout leads to regulatory uncertainty and sub-optimal management, including difficulties in developing adequate conservation and recovery plans, and risk analysis’.

In the specific sub-basins (Methow, Entiat, Wenatchee, Upper Middle Columbia mainstem Yakima, and lower Middle Columbia),  where we will implement this project, sub-basin summaries, draft salmon recovery plans, biological opinions, habitat conservation plans, and watershed assessments are consistent in identifying the need for additional information about the distribution, abundance, population structure, and habitat use patterns of bull trout.  The  approaches described below will address the USFWS FCRPS BO, Reasonable Prudent Measure #8 and Conservation Measures # 1, 2, and 3, at the least.  It also addresses the following USFWS Draft Recovery Plan Tasks:  Chapter 21 – Task # 4.1.1, 2.5.3, 4.2.1, 5.3, and 6.1.1; Chapter 22:  Task # 2.5.1, 3.2.4, 4.3.2, 5.5.1, 5.5.4, and 6.2.1See Section D above and the online form Section 5 for relationships to other projects.

The bull trout recovery teams and Washington State Salmon Recovery teams, within the Columbia Cascade Province and Columbia Plateau Provinces, identified the need to adequately assign bull trout into populations and further develop information to accurately assess population distributions and trends. Much of this proposal work can be accomplished using non lethal genetic sampling and microsatelite analysis; using telemetry and pit tagging to identify connectivity between populations while cross referencing to the genetics analysis; and by conducting spawning surveys and snorkel surveys at the same time to verify locations of tagged fish, collect genetic samples, and gather additional distribution data.

The necessity of this expanded work for bull trout will fill in the data gaps and collate information previously gathered to help tell the story for bull trout in this area.  We expect to use the information to inform our recovery and restoration efforts.  Without the new information from the Methow and the full genetics analysis we can not adequately tell the story of how the bull trout populations fit together or are affected. We propose to compile existing information, coordinate and develop and use standardized ongoing data collection efforts, and collect new information using two approaches and combining data from each to assist with the analysis.  These efforts are all directed toward increasing reliability and practicality of bull trout population assessments and achieving a better understanding of habitat limiting factors for bull trout.  Each approach will employ established protocols as described in the methods section.  The information gained from the work in this proposal will reduce uncertainty in effects analysis on federal projects and lead to more complete management assessments once the migratory history is known and the genetics analysis completed.  We will be able to tell more accurately that a federal project or management strategy may affect a certain population or core area for bull trout with a phylogenic tree and knowing where the migratory form moves.

Approach 1:  Determine population genetic structure, and assess brook trout hybridization, using non-lethal tissue sampling.

Currently, four laboratories in North America provide DNA analysis of bull trout: University of British Columbia, USFWS – Abernathy, WA, Washington State Department of Fish and Wildlife, and the University of Montana.  The Wild Trout and Salmon Genetics Lab at the University of Montana has completed the majority of DNA analysis of bull trout and has the largest database of allele frequencies at nuclear markers for native char.  Recently, the labs agreed to develop one database to store pertinent information regarding bull trout tissue samples, including the location where the sample was collected, the location where the sample is stored, and if an analysis has been completed on the sample, what type it was.  This agreement will coordinate management of bull trout genetic information and will reduce unnecessary harm to bull trout resulting from duplication of sampling effort.   In 2005, a joint effort among the four laboratories involved in genetic analysis of bull trout (US Fish and Wildlife Service (USFWS), Washington Department of Fish and Wildlife (WDFW), Idaho Department of Fish and Game (IDFG), and University of British Columbia - UBC) identified a standardized suite of 12 microsatellite loci to be used by all labs in subsequent studies, an additional 4 loci were identified as reserve loci to be used in some studies.  This standardization allows data collected in the different labs to be shared, and facilitates the creation of a genetic baseline that can be used in new studies.  Additionally, the use of a standardized suite of microsatellites allows the various labs to collect and archive data over many years to accomplish the goal of a comprehensive bull trout baseline across the range of the species.

The US Forest Service Genetics Lab in Olympia assisted with the coordination of information and database development for bull trout.  They developed a Study Plan for Genetic Analysis of Bull Trout in Washington State (Aubry, 2005) in which emphasis and priorities are outlined for genetic studies in Washington.  This project follows guidance in that plan.

The Wild Trout and Salmon Genetics Lab at the University of Montana analyzed tissue samples from across the range of the bull trout with the older loci.  At the regional scale, analyses show at least three genetically distinct groups of bull trout: (1) A coastal bull trout population, (2) A lower Columbia basin or Snake River  population (this group includes  the John Day, Umatilla, and Walla Walla Rivers assemblages), and, (3)  A Clark Fork  population (Spruell et al. 2000).  Within major assemblages, populations are further subdivided, primarily at the local drainage level (Spruell, et al. 2000).

Genetic work done in the Yakima (Reiss, 2003) identifies populations using the original loci. Current work by WDFW (pers. comm. D. Hawkins, WDFW, 2005) will use the new standardized loci to rerun some samples in the Yakima.  This project will tier to that work and use existing and collect new samples for a full basin population analysis including some brook trout hybridization assessments

Also, some tissue samples exist in the upper Middle Columbia collected from telemetry work and other population sampling work.  This project will utilize those existing samples and collect additional samples to run using the new standardized loci.  Some radio telemetry samples were analyzed by the Univ. of Montanta Wild Trout and Salmon Genetics Lab (Pers. comm. Paul Spruell, Univ. of MT, 2001). And appear to be most similar genetically to the Flathead Lake and Clark Fork River bull trout in Montana (P. Spruell, pers. com.).  Tests for assigning populations in the Upper Middle Columbia have not been done.  As well, tests at finer geographic scales (i.e. at local populations) are not currently available for the Wenatchee and Methow core areas. This project will attempt to define populations at multiple scales.

The proposed genetic sampling will entail the collection of approximately 30 tissue samples from each of the known spawning tributaries within the 4 sub-basins (Wenatchee, Entiat, Methow, and Yakima).  Genetic samples will be gathered in coordination with the multiple lab data management effort described above.  A large proportion of the samples are already collected from the field and new samples will be added as needed.  Analysis methods will follow those in Spruell et al. (2003) and Neraas and Spruell (2001).

The number of microsatellite loci needed to provide accurate assignment of individuals to their tributaries of origin will be determined by the amount and distribution of genetic diversity observed among the populations analyzed under Objective 1.  A solid theoretical framework exists in the genetics literature for assigning individuals to populations (Manel et al 2005).   We will use the methods of Banks et al (2003) and Rosenberg. (2005) to assess the power of each locus and all loci combined to assign fish to tributary of origin.  These analyses will include the 12 microsatellite loci described previously plus additional loci developed by DeHaan and Ardren (2005) if needed. We will assess the overall power of correct assignment by deleting an individual fish from the dataset, recalculating the allele frequencies for the source population of that individual, and then assigning that fish to one of the sampled populations (Banks and Eichert 2000).   This procedure will be repeated for each individual fish in the data set.  The percent of fish assigned correctly to their tributary of origin will represent the statistical power of the analysis.  Ardren et. al (2005) have already successfully implemented a genetic based assignment procedure for 27 bull trout populations in the Clark Fork River System of Montana and Idaho using 11 microsatellite loci.

Analyses of the existing and new genetic samples address whether genetic differences within and among local populations, core areas, and sub-basins in the mid Columbia River area.  This information can be used to determine the appropriate geographic scale for bull trout population management.  The results of population genetic analyses can also be compared with telemetry results, which provide an independent measure of the potential for gene flow.  Recent bull trout telemetry studies in the Wenatchee and Entiat sub-basins by the USFWS (USFWS 2004 draft) and in the upper Columbia River by county Public Utilities Districts (PUD’s) have demonstrated that fish observed at Rocky Reach Dam move up to the upper Chiwawa River in the Wenatchee Basin and up to the upper Methow River and its tributaries. Also some fish from these core areas overwinter together in the mainstem Columbia River.  Genetic analysis alone can not tell you where the populations maybe when foraging, migrating, or overwintering.  Past telemetry work  (Kelly Ringel and De La Vergne 2001) indicates that multiple populations overwinter together for half of the year.  Without the genetics we can not tell if these fish are from a single or many populations.   Since migratory bull trout spend half of their life in other areas than the spawning area, telemetry is an established method that is used to determine movement patterns into these areas, as well as how populations may mix within the basin/Core Area.  Telemetry helps to flush out the metapopulation structure being used in each area.

The Univ. of MT, Wild Trout and Salmon Genetics Lab, continues to work on projects at the local population or drainage scale in the Clark Fork and Lake Pend Oreille drainages in Idaho, in the Yakima subbasin in Washington, and in the Deschutes and Joh Day drainages in Oregon.  WDFW and the USFWS Abernathy lab have ongoing projects in the Yakima, Entiat, Wenatchee, and other sub basins (Pers com W. Ardren, USFWS and D Hawkins, WDFW, 2006). Paul Spruell et al., the USFWS Bull trout Science Team in 2004, Aubry (2005), and the USFWS Abernathy genetics lab (during the bull trout 5 year review) have identified a data gap in population specific genetic data for the Middle Columbia River area. Data generated by this proposal for the Wenatchee, Entiat, Methow, and Yakima sub basins largely fill this data gap. Use of the standardized suite of microsatellite markers will allow newly generated data from this study to be added to the larger data set compiled when analyses of existing samples from the Columbia River are completed. This comprehensive combined data set provides opportunities to investigate phylogenetic and biogeographic relationships among bull trout populations within the entire Columbia Basin.

Interspecific hybridization with non-native brook trout has been identified as one of the key threats to the recovery of bull trout (Kanda et al. 2002), and further identified as a prioritized research area by Aubry (2005) in both the Upper and Middle Columbia Recovery Units within the Columbia Cascade and Columbia Plateau Provinces respectively.  This Project will also determine the occurrence and explore the dynamics of hybridization between bull trout and brook trout in the Twisp River (Methow Core Area/sub-basin, Columbia Cascade Province) and Bumping/American Rivers (Yakima Core area/sub-basin, Columbia Plateau).  Brook trout invasions have been linked to changes in habitats such as temperature increases, slower waters, etc.  Determination of the impact of hybridization is a high priority for WDFW bull trout recovery and a necessary component for assessing threats in each population. Furthermore, the presence of unidentified hybrid individuals in collections can obscure the results of population structure analyses. Bidirectional, introgressive hybridization between these two species has been documented by DeHaan et al. (2005) in the Malheur River Basin, OR and by Kanda et al. (2002) in five streams in western Montana.  Fish with intermediate morphological characteristics have been collected in both the Twisp and American Rivers (two rivers included in this project’s proposed research area specifically identified as areas of concern for hybridization).  However, their ancestry has not been genetically determined, nor have the dynamics of hybridization been studied in these rivers.

Six of the microsatellite markers included in the standardized suite described in Objective 1 above exhibit non-overlapping allelic ranges between bull and brook trout and can be used to definitively identify the species of pure individuals as well as to identify hybrids. Thus, we can screen the samples collected for analysis of population structure and remove hybrid individuals, as well as demonstrating the occurrence of hybridization in particular populations.

Mitochondrial DNA (mtDNA) is maternally inherited and each individual has only one haplotype, therefore, the species identity of the mother can be determined.  DeHaan et al. (2005) demonstrated that the cytochrome B gene region of mtDNA produces different sized fragments for bull and brook trout when digested with the restriction enzyme Rsa-1. The combination of genetic identification of hybrid status by nuclear microsatellites and identification of the species of the maternal line can yield insights in to how hybridization is occurring between bull and brook trout.

Previous samples collected for the analysis of genetic structure of bull trout in the Twisp and American have targeted fish that were morphologically bull trout.  Therefore, to better assess the impact of interspecific hybridization (whether introgressive hybridization is occurring, and whether females of both species are involved), 50 fish will be randomly collected from each river. Using nuclear microsatellites we will identify the species category of each sample (pure bull, pure brook, F1 hybrid, introgressed hybrid), and using mtDNA markers we will identify the species of the maternal line. The program NEWHYBRIDS and the methods described by Anderson and Thompson (2002) will be used for hybrid analyses. This information will allow us to better understand the impact interspecific hybridization has on bull trout populations.  Introgressive hybridization and the subsequent loss of genetic integrity can result in the complete loss of a species, whereas interspecific hybridization has much less impact if it occurs infrequently with limited reproduction by hybrid individuals.

The results of this analysis of hybridization in the Twisp and American Rivers can be used to direct further research in other areas of the Upper and Middle Columbia Recovery Units where hybridization occurs or is suspected.

The Project gathers information to focus offsite mitigation for bull trout, and adds to future genetic and population data management. The Project will provide information on how the populations are related genetically, and how future surveys can continue to provide information for future management and recovery.

The USFWS is currently developing a bull trout recovery plan which includes a chapter for the Upper Columbia River Basin in Washington.  The draft recovery plan includes information for the four core areas, the Wenatchee, Entiat, Methow, and Yakima River basins and to some extent the mainstem Columbia River.  The draft recovery plan for the bull trout will request investigations into the genetics of local populations of bull trout and brook trout introgression.  Implementation and monitoring of specific projects for recovery may include the mainstems of the Columbia River and its tributaries. The Bull Trout RM & E Team developed to assist in protocol development will be working on genetics as a research issue in the future.

Approach 2.   Evaluate connectivity, locate spawning and wintering areas, and identify migratory patterns using radio telemetry, pit tagging, and genetic based population assignments

Telemetry and pit tagging provides insights into specific habitat elements used during different time periods and life-cycle stages including migratory routes, timing of migration, holding areas, overwintering, spawning habitat, and connectivity.  Information gained from telemetry in the subbasins of the Columbia Cascade and Columbia Plateau Provinces will provide additional information for limiting factors outlined in each of the subbasin summaries.  For example, in the Methow information is lacking about how temperatures affect bull trout and where connectivity problems exist.

Telemetry projects are currently ongoing in the Entiat and Yakima sub basins.  A draft report for the telemetry results in the Wenatchee sub basin (Pers. com. J. De La Vergne, USFWS, 2006).  Results from these projects have shown bull trout moving down from tagging locations in the upper sub-basins in the Entiat and Wenatchee all the way to the Columbia River, overwintering in the mainstem Columbia River, and returning to spawn in the headwaters of the Chiwawa River as identified in USFWS, 2001.  Personal communication with WDFW (Eric Anderson) in 2004 about result of the Yakima sub-basin onging bull trout telemetry study shows that bull trout move and between the Naches River and upper Yakima River but that most movement has occurred within the mainstem Naches and its tributaries.  Information gained on bull trout use of specific mainstem habitats and the temperature or flow regimes encountered in those habitats will help to describe overwintering habitat and to assess factors that may influence the quality of this habitat (e.g., hydro operations).

Currently, the Chelan and Douglas County PUD as part of their Bull Trout Management Plan (www.chelanpud.org) are implementing radio telemetry study within the mainstem Columbia River.  They have also collected data in the past in the Columbia River mainstem (BioAnalysts, Inc. 2002 and 2004).  The USFWS-Mid Columbia River Fisheries Resource Office (MCFRO) will be beginning a small bull trout telemetry study in the Methow, focusing on similar approaches identified in this proposal.  The work identified in this project will expand on the MCFRO work to allow a full basin approach.

US Geological Survey (USGS) is working within the Methow sub-basin on a Bureau of Reclamation (BOR) project trapping and pit tagging bull trout (Martens and Connolly, 2005).  This BOR project addresses the need about the effectiveness of restructuring existing water diversions to enhance fish passage in the Lower Methow River subwatershed.  Pit tagging detectors are installed and monitored in the lower Methow sub basin.  The BOR project provides and opportunity for this project to coordinate with the existing pit tagging project by using existing data, pit tag detectors, personnel, and facilities, and expand detection sites and provide additional support to analyze existing and new pit tag data gathered on the radio tagged bull trout in additional tributaries.  The Project will provide the opportunity for BOR to gather additional bull trout data.

Overlaying or cross calibration of information from telemetry and pit tag tracking with genetics based analysis will allow us to determine spatial structure and population size. Movement data also will provide information on the rate, extent, and timing of interchange of individuals among sub-basins (see item (1) above).  Information about migration patterns will provide insights into important habitat elements on migratory pathways (i.e., thermal refugia). Telemetry data (locations and migration patterns) will be analyzed using spreadsheets, statistics packages, and Geographical Information System mapping. Pit tag data will follow pit tagging data reporting protocols similar to salmon and steelhead and submit data to PTAGS.

Generating a genetic baseline for all of the middle Columbia River Basin populations allows us to use genetic assignment tests to identify the geographic origins of fish collected in the mainstem Columbia River.  This information will be important for understanding migration patterns and identifying key habitat for migratory bull trout.  It also provides the opportunity to identify the most likely origins of all fish captured, not just physically tagged fish.  This ability to assign all bull trout encountered, including fish too small to tag, in the field back to a population of origin would greatly increase our knowledge of bull trout movement in the middle Columbia River Basin.

C. Rationale and significance to regional programs

Bull trout (Salvelinus confluentus) have been listed by the Fish and Wildlife Service (FWS) as Threatened in the Columbia River Distinct Population Segment (DPS) since 1998 (USDI).   This DPS is represented by widespread subpopulations that have declined in overall range and numbers.  The majority of Columbia River bull trout occur in isolated, fragmented habitats that support low numbers of which fish are inaccessible to migratory bull trout.  The decline of bull trout, as described in the bull trout Final Rule, dated June 12, 1998 (USDI, 1998), is primarily due to habitat degradation and fragmentation, blockage of migratory corridors, poor water quality, past fisheries management practices, and the introduction of non-native species.

Information about migratory and life history patterns of bull trout within the Upper and Middle Columbia River Bull Trout Recovery areas is still lacking due to the lack of population assignment information.  Additionally, information about the degree to which the fish in the upper and middle Columbia River are genetically connected to the other populations in the Columbia River basin is also lacking.  Adfluvial, fluvial, and resident life forms exist within the basin and knowledge of connectivity between the three is uncertain.  In addition, information about adfluvial/fluvial and resident bull trout migrations and spawning is also incomplete.  This Project would assign populations so that distribution and abundance can be adequately developed for recovery and mitigation efforts.  In the Methow, information is lacking about distribution, spawning, hybridization, connectivity, and how temperatures affect bull trout, particularly where barriers or partial barriers to migration problems exist.  In the Entiat, the effects on bull trout of an apparent scarcity of overwinter habitat and formation of anchor ice and the use of the Columbia River are not well understood.  In the Wenatchee, connectivity occurs between spawning habitat, upper tributaries, the Columbia River and other subbasins, the timing of use and interconnectivity between populations is unclear.  In the mainstem, bull trout overwinter habitat and year round migratory habitat exists but is poorly understood.  In the Yakima, the distribution and relationships among the local populations, including the resident populations, and the impact of hybridization with brook trout are not well understood. Most subbasin plans in the upper and mid Columbia area point out the need to analyze bull trout life history and reduce the threat from brook trout hybridization.  Adequate population assignments are lacking in all sub-basins for bull trout that use the mainstem and it is unclear which populations are affected by management of the Columbia River mainstem.

Current bull trout local population assignments are inadequate for Section 7 Endangered Species Act (ESA) consultation and recovery purposes in the mid and upper Columbia River.  Current ESA effects and Jeaopardy analyses on bull trout populations, affected by mainstem Columbia River dams and other projects, can not be assigned to populations or sub basins within the Columbia River. Knowing which populations are affected by projects in the Columbia River could reduce costs associated with analyses and further refine “Take” given for bull trout.

The Project is tied to the NMFS biological opinion (BO), the USFWS BO, the USFWS Recovery Plan, the sub basin plans, draft salmon recovery plans, and current genetic analysis ongoing for bull trout.  The relationships to the NMFS BO occur through  Reasonable and Prudent Alternatives 1, 7, 155, 167, 193, and 198 in the 2000 BO. The Project gathers information necessary to further implement the BOs as well as meet data needs identified within them. The Project also gathers information to focus efforts for offsite mitigation for bull trout, gathers data for refining future sampling methods for bull trout, gathers data regarding where incidental mortality of bull trout might occur, develops methods for future fish tagging and detection methods, and adds to future genetic and population data management. The USFWS BO requires commitments from the Bonneville Power Administration to minimize effects to bull trout and incorporate bull trout in planning and management efforts, specifically Reasonable and Prudent Measure #8 and other conservation measure.  The proposal provides information that can  be used for adaptive management as well as information about bull trout in the area of both federal and other dams located in the Columbia River basin.  The Project identifies connectivity necessary to maintain bull trout population assemblages in the middle Columbia area. The  Project will provide information on where the populations of bull trout are in the Columbia Cascade and Columbia Plateau Provinces and the how they are related genetically, and how future surveys can continue to provide information for future management and recovery.  The Project also attempts to address sub-basin summaries which identify limiting factors as lack of connectivity, high and low stream temperatures, and reduced tributary connectivity. These same parameters were identified as limiting factors for bull trout populations in the bull trout listing (USDI, 1999).

Information gained from the location of bull trout in the sub-basins, the identification of migratory patterns, and the genetic analysis of local assemblages of bull trout will further focus management and efforts to conserving populations of bull trout.  New information gained about the bull trout populations will help form the basis to implement measures in the NMFS and USFWS .  The Proposal will assist in filling information gaps for bull trout identified in each sub-basin plan.  Current efforts underway with the range of the bull trout (for example; development of temperature models, designed to be used to meet EPA temperature criteria for bull trout) will incorporate the information gained from this Project.  In addition, migratory information from bull trout movements will provide valuable data about where bull trout are overwintering and habitat bull trout are using.

D. Relationships to other projects

The USFWS is currently developing a bull trout recovery plan which includes chapters for the Upper Columbia River and the Middle Columbia River recovery units in Washington.  The draft version (USFWS, 2002) includes information for each of the four core areas, the Wenatchee, Entiat, Methow, and Yakima River basins and to some extent the mainstem Columbia River.  The recovery plan for the bull trout requests investigations into the use of all habitats used in order to determine the needs of bull trout.  Implementation and monitoring of specific projects for recovery will include the mainstems of the Columbia River and its tributaries.

Sub basin plan and draft Washington State Salmon Recovery plans link to the USFWS Draft Recovery plans and have similar data gaps for bull trout. See section D for further relationships.

Current telemetry efforts are showing patterns of long distance migrations (>140 miles round trip) and extended overwintering use (>6 months) in the mainstem Columbia River for (USFWS, 2001).  Telemetry studies have found fish tagged in the mainstem Columbia River (Kreiter, 2001, BioAnalysts, Inc 2002 & 2004)) near the mouth of the Wenatchee River moving into tributaries in the Methow and Entiat Rivers.  A large number of migratory adults have been located for the past three years moving through Rock Island, Rocky Reach, Wells Dams on the Columbia River, through Tumwater dam on the Wenatchee River, through Rosa Dam on the Yakima, and through weirs in both the Twisp and Chiwawa Rivers.  Past steelhead creel surveys have caught  spawned out migratory bull trout (pers. comm. L. Brown, WDFW 1998). Bull trout have also been sighted moving through Rosa Dam on the Yakima (pers com Eric Anderson, WDFW, 2004). Currently, radio telemetry projects ongoing in the Wenatchee, Entiat, and Yakima Rivers will be completed by 2006 and 2007.   In 2005, the USFWS started tracking bull trout tagged by the PUD from the Columbia River into the Methow when they migrated into the system. This will occur through 2007.

To fully understand the basin wide bull trout population movements further tagging and tracking work is necessary.  This project will be closely tied to the current tracking work in the Methow.  Bull trout have been observed in the lower Methow, the Twisp River, Wolf Creek, the Upper Methow River, the lower Lost River, and Libby Creek, indicating many populations may use the Columbia River for overwintering or forage habitat.  These fish could likely migrate up to Chief Joesph Dam and have been observed migrating down to Rock Island Dam.  Telemetry work done in the Yakima, Wenatchee, Entiat, and upper mainstem Columbia River will assist in the work this project will be implementing.   The Chelan and Douglas PUD will be tagging and tracking fish until 2008 and providing an opportunity to share resources and data.

Within the proposal, the genetic approach is formulated after similar bull trout work being completed in Lake Pend O’rielle and the Clark Fork River in Idaho by multiple agencies. The Yakima Basin in Central Washington is currently involved in similar genetics work through Central Washington University and the US Forest Service.  The University of Montana, the USFWS, WDFW are currently working with each of the projects mentioned above and is involved in a continuing effort to develop a baseline of bull trout genetics information.  These labs suggests that this type of an effort in the Wenatchee, Entiat,  Methow, and Yakima sub basins would add a large data set of information where currently there is a large data gap.

Additional research, using the protocol methodology for determining bull trout presence (Peterson et al, 2001), has  been conducted in the Wenatchee, Methow, and Yakima River sub basins.  Ongoing bull trout habitat data collection will assist the USFS Rocky Mountain Research lab in developing patches of bull trout habitat, which will assist in recovery. As a part of the habitat evaluation portion of the bull trout presence protocol, in stream thermographs were been placed every two kilometers in association with habitat surveys and snorkel surveys in the Chiwawa and Twisp Rivers.  Additional thermographs have been  placed by the USFWS, USFS, tribes, and DOE in these and other watersheds within these sub-basins. Winter temperatures have been collected by some of these same instream thermographs in the Wenatchee and Methow areas by the FWS.

Additional stream temperature research by the USFWS, the Pacific Watershed Institute, and USFS, is ongoing using Forward Looking Infrared (FLIR) technology.  FLIR entails the use of infrared aerial photos within an aquatic system. Stream temperatures collected from instream thermographs are mapped across entire stream networks at the time of surveys.  The FLIR images  are correlated to known temperatures and then reviewed to  find thermal changes.  These thermal changes depict  springs and thermal upwelling areas.  These  flights were flown in the Chewuch and Twisp Rivers in the Methow; in all the major tributaries in the Wenatchee and the mainstem above Leavenworth; and in the Mad River in the Entiat by Watershed Sciences, LLC in Corvalis Oregon.  Results from these flights were available in spring of 2002.

Within the Columbia Cascades and Columbia Plateau Province, the Northwest Forest Plan requires the USFS to address its  Aquatic Conservation Strategy.  In addition, under  Section 7 of the Endangered Species Act, consultations for bull trout require adequate project analysis in order to determine any potential affects to bull trout.  In order to meet this obligation the USFWS and USFS has been completing watershed baselines for the bull trout in order to look at known population information, potential management threats, and cumulative effects of management.  Bull trout spawning surveys on National Forest land are conducted collaboratively and include personnel from USFWS Central Washington Field Office and the USFWS Leavenworth Mid Columbia River Fisheries Resource Office, the USFS, and Washington State Department of Fish and Wildlife (WDFW).  This information is used to update the bull trout appendix of the Salmonid Stock Inventory by WDFW.

Management among the hydro projects located on the mainstem Columbia River within the Upper Columbia River and adjacent to the Middle Columbia Bull Trout Recovery Units should be based on the best scientific information available regarding the effects of their activities on the bull trout. The Proposal provides the opportunity to address some of the unanswered questions that exist regarding bull trout’s use of the mainstem Columbia and what that means to hydro project management.

Coordination is a key element in the success of this project and the ongoing telemetry studies. The US Forest Service, U.S. Fish and Wildlife Service, BRD in Cook, Washington, WDFW, Chelan and Douglas Public Utility Districts (PUD), Tribes, and other agencies and entities are all interested in obtaining information about bull trout migratory patterns and habitat use in the area. As the lead on this Project, the USFWS coordinated bull trout collections, data downloading, and tracking efforts with WDFW, the tribes, and the PUD.  USFWS staff continues efforts to coordinate with all of the parties in the upper middle Columbia River area, as well as our partners within and outside of the state.  We do so in order to make sure that Projects we conduct are based on sound science and do not overlap existing project work elsewhere.

E. Project history (for ongoing projects)

This Proposal has not been funded in the past by BPA.  With non-BPA funding,  three radio telemetry studies are ongoing: the previously discussed USFWS Wenatchee River radio telemetry study, the PUD mainstem Columbia River telemetry study, the Entiat bull trout telemetry study, and the Yakima bull trout telemetry study.  All should be finalized in 2006-2007 and have been coordinated to maintain a consistent effort.   Spawning surveys are also ongoing and implemented annually by the USFS, USFWS, and WDFW in each of the core areas.  Snorkel surveys by the USFS, PUD and USFWS are ongoing efforts for determining population estimates and habitat suitability for salmonids and bull trout and are coordinated with. Placement of thermographs, have been coordinated with USFS, tribes, and DOE, where possible in bull trout habitat.

F. Proposal biological objectives, work elements, and methods

Objectives

The objective of this Project is to evaluate bull trout populations in the Methow, Entiat, Wenatchee and Yakima Sub-basins and mainstem Columbia River within the Columbia Cascade and Columbia Plateau Provinces.

In order to meet this objective the following approaches will be completed: (1) determine population genetic structure, including analysis for brook trout hybridization, using non-lethal tissue sampling, (2) evaluate connectivity, locate spawning and wintering areas, and identify migratory patterns using radio telemetry, pit tagging, and genetic based population assignments

Tasks and Work Elements

The following is a specific list of Work Elements/Tasks for each approach of the objective outlined both above and in the budget.

Approach 1:  Determine population genetic structure, including analysis for brook trout hybridization, using non-lethal tissue sampling,

Hypothesis 1:  Bull trout within the Columbia Cascade and Columbia Plateau Provinces are significantly differentiated into one or more core areas and multiple local populations, and are significantly different from populations upstream of Chief Joeseph and downstream of  McNary Dams.

Hypothesis 2:  Bull trout in the Columbia Cascade and Columbia Plateau Provinces have some degree of hybridization with brook trout.

Hypothesis 3:  Bull trout in the Twisp River within the Columbia Cascade Province and within the American River, within the Columbia Plateau Province have high percentage of introgression with brook trout.

Work Elements

- Collect/Generate/Validate Field and Lab data

A.  Collect and run new bull trout samples

B.  Collect and run existing bull trout and brook trout samples

C.  Collect and run brook trout samples and bull trout samples

2.   Analyze/Interpret Data including develop data base and conduct assignment tests 	and determine introgression of brook trout.

3.   Disseminate Raw/Summary Data and Results in required report format, cd, etc.

4.   Produce Environmental Compliance Documentation

5.   Manage and Administer Project

Approach 2: Evaluate distribution, connectivity, locate spawning and wintering areas, and identify migratory patterns using radio telemetry, pit tagging, and genetic based population assignments

Hypothesis 1:  Bull trout in the Methow River spawn in multiple tributaries and

overwinter in the Columbia River, lower Methow River, Twisp River, lower

Chewuch River.

Hypothesis 2:  Migratory bull trout travel large distances and multiple populations

intermingle in the Columbia River.

Hypothesis 3:  Adult migratory bull trout begin spawning migrations in the spring

and reside in spawning tributaries for both extended and short duration prior to 	spawning.

Hypothesis 4: Bull trout travel in the hours of darkness

Hypothesis 5:  Movements of bull trout depict how they are assigned using

genetic assignment tests.

Hypothesis 6:  There are additional unknown spawning areas in the Methow sub-	basin for bull trout

Hypothesis 7:  There are habitat limiting factors that impede connectivity for migratory bull trout

1.   Collect/Generate/Validate Field and Lab data

A.  Surgically implant radio and pit tags

B.  Set up telemetry and pit tag stationary detection sites

C.  Track fish using mobile, aerial, and snorkeling

D.  Conduct spawning surveys and snorkel surveys to verify and identify

locations, conditions of fish, locate populations, and examine habitat

2.   Analyze/Interpret Data including develop data base

3.   Disseminate Raw/Summary Data and Results in required report format, cd, etc

4.   Submit//Aquire Data to PTAGIS for the pit tags and to larger regional telemetry 	data sets

5.   Produce Environmental Compliance Documentation

6.   Manage and Administer Project

Fiscal year 2007.   Project Management - Equipment purchases, agreements/contracts, permits/NEPA, and coordination will occur through the USFWS Central Washington Field Office/ USFWS Mid Columbia Fisheries Resource Office.  Collect/generate/validate data - Tissue samples for the genetics analysis will be collected from the field, fish tagging and pit tagging and some tracking.  Analyze/interpret – interim reports, databases.  Disseminate – Disseminate current information in interim reports

Fiscal year 2008.   Project Management - Equipment purchases, agreements/contracts, permits/NEPA, and coordination will occur through the USFWS Central Washington Field Office/ USFWS Mid Columbia Fisheries Resource Office.  Collect/generate/validate data - Tissue samples for the genetics analysis will be collected from the field, fish tagging and pit tagging and some tracking.  Analyze/interpret – interim reports, databases.  Disseminate – Disseminate current information in interim reports

Fiscal year 2009. Fiscal year 2007.   Project Management - Equipment purchases, agreements/contracts, permits/NEPA, and coordination will occur through the USFWS Central Washington Field Office/ USFWS Mid Columbia Fisheries Resource Office.  Collect/generate/validate data - Tissue samples for the genetics analysis will be collected from the field, fish tagging and pit tagging and some tracking.  Analyze/interpret – interim reports, databases.  Disseminate – Disseminate current information in interim reports, and Final report,

We will present results of this work in guidance to fisheries managers, annual reports, presentations at professional and public meetings, and publications in peer-reviewed journals.

Methods

Genetics:  Non-lethal tissue sampling in order to determine population genetic structure.

Fish will be captured by hook and line, hand netting, or as fish are handled at weirs, smolt traps, or ladders.  A paper punch size piece of tissue will be taken from a fin (typically the caudal fin) and placed into labeled vials of 100 % non-denatured ethanol and sent to the lab for analysis.  A standardized analysis will be used to identify populations.  This standardization allows data collected in the different labs to be shared, and facilitates the creation of a genetic baseline that can be used in new studies.  See the discussion in Section B (Technical and/or Scientific Background) for futher detail on this analysis. Also, the US Forest Service Genetics Lab in Olympia assisted with the coordination of information and database development for bull trout.  They developed a Study Plan for Genetic Analysis of Bull Trout in Washington State (Aubry, 2005) in which emphasis and priorities are outlined for genetic studies in Washington.  This project follows guidance in that plan.

Also, some tissue samples exist in the upper Middle Columbia collected from telemetry work and other population sampling work.  This project will utilize those existing samples and collect additional samples to run using the new standardized loci.  Some radio telemetry samples were analyzed by the Univ. of Montanta Wild Trout and Salmon Genetics Lab (Pers. comm. Paul Spruell, Univ. of MT, 2001). And appear to be most similar genetically to the Flathead Lake and Clark Fork River bull trout in Montana (P. Spruell, pers. com.).  Tests for assigning populations in the Upper Middle Columbia have not been done.  As well, tests at finer geographic scales (i.e. at local populations) are not currently available for the Wenatchee and Methow core areas. This project will attempt to define populations at multiple scales.

The proposed genetic sampling will entail the collection of approximately 30 tissue samples from each of the known spawning tributaries within the 4 sub-basins (Wenatchee, Entiat, Methow, and Yakima) which do not have samples.  Genetic samples will be gathered in coordination with the multiple lab data management effort described above.  A large proportion of the samples are already collected from the field and new samples will be added as needed.  Analysis methods will follow those in Spruell et al. (2003) and Neraas and Spruell (2001). See the Table attached which shows where samples have been collected.

The number of microsatellite loci needed to provide accurate assignment of individuals to their tributaries of origin will be determined by the amount and distribution of genetic diversity observed among the populations analyzed under Objective 1.  A solid theoretical framework exists in the genetics literature for assigning individuals to populations (Manel et al 2005).   We will use the methods of Banks et al (2003) and Rosenberg. (2005) to assess the power of each locus and all loci combined to assign fish to tributary of origin.  These analyses will include the 12 microsatellite loci described previously plus additional loci developed by DeHaan and Ardren (2005) if needed. We will assess the overall power of correct assignment by deleting an individual fish from the dataset, recalculating the allele frequencies for the source population of that individual, and then assigning that fish to one of the sampled populations (Banks and Eichert 2000).   This procedure will be repeated for each individual fish in the data set.  The percent of fish assigned correctly to their tributary of origin will represent the statistical power of the analysis.  Ardren et. al (2005) have already successfully implemented a genetic based assignment procedure for 27 bull trout populations in the Clark Fork River System of Montana and Idaho using 11 microsatellite loci.

Telemetry:  Using radio telemetry to evaluate connectivity, locate spawning and wintering areas, and identify migratory patterns.

In order to gain needed information in the Methow basin we will need to do additional telemetry and tag additional fish in the Methow due to the large distance between bull trout populations.  We will attach telemetry ~60 transmitters to bull trout, they will be captured by a variety of methods including hook and line, seining, hand netting at night (all under a FWS permit), or trapping at weirs operated by Washington Department of Fish and Wildlife (WDFW) under their permits.  Surgical implantation of the telemetry tags will follow methods used in the Wenatchee Telemetry project and described in USFWS, 2001, and methods used in both the Entiat and Yakima Telemetry projects. Radio telemetry tracking will occur using three methods; stationary sites, non-stationary ground based receivers, and non-stationary airplane mounted receivers (Kelly Ringel and De La Vergne 2001).  Radio tracking will occur for approximately two years (the approximate lifespan of the transmitter batteries).  Fish will be captured by hook and line, hand netting, or as fish are handled at weirs, smolt traps, or ladders.

Approximately 30-40 bull trout will be surgically implanted with radio tags in the Methow basin.

Radio-tag Surgery.  Holding tanks and surgical equipment are set up prior to capturing bull trout. The radio-tag is thoroughly cleaned of all tape residue. Surgical tools and the radio-tag are placed in a 30 ml/L Nolvason solution and rinsed in a 0.1% saline solution. Distilled water is used to make the solutions. Everyone handling the fish washes their hands in Nolvason before surgery on each fish. The bull trout is placed in a holding tank containing an 80 mg/L concentration of tricane methane sulfonate (MS 222), buffered with 160 mg/L of sodium bicarbonate (baking soda) to neutralize the pH. In our Wenatchee study we occasionally tested the pH=s of the river or lake water and the solutions to determine if we were adequately buffering.  With our testing we determined that after the addition of the MS 222, the pH changes from~ 6.5 to 4.5 and buffering brings the water back up to the original pH.  While the bull trout are being anaesthetized, we take a fin clip and place it in 100% ethanol with a label. When close to being fully anaesthetized, the fish are placed in a sturdy nylon bag and weighed with a spring scale. The fish is held in the anesthetic again to insure it is fully anaesthetized until surgery time. We record the time in anesthetic. The bull trout is placed on a wet, foam lined V-shaped trough that we coat with PolyAqua. To keep the fish anesthetized during the surgical procedure, a 40 mg/L concentration of  MS-222 is used, buffered with 80 mg/L of sodium bicarbonate and the fish=s gills are continually flushed with this solution using a large syringe (turkey baster). We are careful not to allow any of the MS-222 to get into the incision site.

Betadine is used to disinfect the fish prior to making an incision. Using a #12 stainless steel scalpel blade an approximate 2-3 cm incision is cut laterally of the mid-ventral line and anterior to the pelvic girdle. We use a 1x2 tooth tissue grabbing forceps to pull the skin away from internal organs and take care not to nick or cut any internal organs. We visually assess inside the fish to determine the fish=s gender. A hollow needle (catheter) is used to make the lateral antennae exit site which is angled to above and posterior of the pelvic fins. The antenna is threaded through the catheter and the catheter removed. The tag is then inserted and positioned in the body cavity. The incision is sutured using absorbable suturing material (Vicryl 3-0) with an FS-1 3/8 24 mm needle and 3-4  independent sutures with a 3-2-2 surgeon=s knot wrap pattern. The surgical needle and thread are rinsed in a 0.1% saline solution between each stitch as is other equipment as needed to prevent the introduction of MS-222 or other substances into the wound. After the suturing is complete, an external topical antibiotic (betadine) is applied and swabbed. A veterinarian=s glue (Vetbond) is used over all sutures and the incision to help bond tissues, hold the knots, and keep water out of the incision. We measure the time to complete the surgeries and so far, all have been completed between 4:31 and 8:08 (minutes:seconds).  At the discretion of the surgeon and assistant, sometimes during the last stitch, freshwater is given to the fish over its gills with the syringe, which seems to reduce the recovery time. After each surgery, tools are thoroughly cleaned and disinfected again. After surgery is complete the bull trout are placed in a holding container with an oxygen bubbler and if needed with ice packs for recovery.  Sometimes they are placed into a fish tote (5"-15" diameter PVC pipe with holes, closed with pieces of wood on the ends, with rope to secure the wood end and for carrying) and placed into the river or holding container to be able to transport them after recovery.  Temperatures are monitored in all water containers and ice packs added if needed. These fish are usually monitored and released in approximately 15 minutes.  Fish are usually released near the site of capture unless conditions are considered harmful.  If they need to be trucked to a more suitable release site, they are placed in a large container of oxygenated freshwater in the back of a truck. At the release site the water in the holding container was tempered until its temperature was at or within one degree of the temperature in the river. The totes are then placed in slow water near the stream’s edge. Genetic samples will also be taken. A paper punch size piece of tissue will be taken from a fin (typically the caudal fin) and placed into labeled vials of 95% ethanol and sent to the lab for analysis.

Telemetry Tracking.  Telemetry tracking occurs using three methods; stationary sites, non-stationary ground based receivers and non-stationary aero mounted receivers. Stationary sites are positioned  throughout the sub basins at major tributaries, primarily near the mouths of known spawning streams and at other points to strategically monitor bull trout movement.  Sites with stationary sites in the Methow River are likely to be located at the Twisp River, Beaver Creek, Wolf Creek, the confluence with the Chewuch River, Lake Creek, Early Winters Creek, and the Lost River. Fixed stations record information 24-hours per day.  Non-stationary ground based receivers will be hand-held or vehicle mounted and used during times of the year when most areas are accessible by roads or trails.  Aero mounted receivers will be used mostly during the winter when ground access is limited and when quick movments are observed (i.e. during spawning).

Information from these sites allow us to detect the times that bull trout were passing these stations and direction of travel. Information from these stations was downloaded on a regular basis. The stations were checked to see if they were operating properly, and batteries were replaced as needed.  Mobile tracking of bull trout occurs from vehicle and on foot.  With the Wenatchee project, mobile and aerial tracking was limited and not conducted on a regular basis due to limited funding.  However, we have accounted for funding in this grant to maintain a regular schedule.  Aerial flights from a fixed-wing aircraft likely will focus on the known spawning and adult holding streams. Tributary flights may be limited, however, to only flying to the Wilderness Area boundaries because of flight restrictions in wilderness and because of hazardous weather conditions in the winter.  Information is/will be analyzed using spreadsheets, statistics packages, and Geographical Information System mapping.

Pit tagging:  Pit tagging will be preformed similary to techniques used on salmon by the USGS staff.  Radio tagged fish will have the pit tag implanted in the incision to reduce stress to the fish from multiple procedures. Data will be submitted to PTAGIS for tracking.

G. Facilities and equipment

Crews necessary to collect genetic samples and do population/telemetry work will  be supervised out of the USFWS offices located at 215 Melody Lane  in Wenatchee, WA.  Space is currently available to accommodate a computer station for data entry at the USFWS office located at 215 Melody Lane in Wenatchee, WA.  The USFS can house an employee to conduct surveys and tracking. Campgrounds and trails are in the locations of areas where the sampling may occur.  Where available, campgrounds will be used as remote lodging sites.  The USFWS has camping gear available.  There is a heated, locked storage area for equipment storage at the USFWS office in Wenatchee, Leavenworth; at the USFS in the Methow, and at the USGS and WDFW offices in Twisp.  Vehicles can be stored in the parking area at the USFWS office or other federal offices.  A GIS workstation is available at the USFWS office in Wenatchee for the development of reports.  USFS topographic maps are also available in the building.  Copy and fax machines are available for use. Where available, other agencies will coordinate to collect genetic samples and conduct spawning surveys or snorkel surveys (i.e smolt trapps and weirs already established)

H. References

References

Anderson, E.C. and E.A. Thompson. 2002. A model-based method for identifying species hybrids using multilocus genetic data. Genetics 160: 1217-1229. Ardren, W.R., P. DeHaan, and D. Campton. 2005. Genetic analyses of bull trout from the Clark Fork River: A two-phased project to identify region of origin of fish captured below mainstem dams. USFWS Final Report [April 21, 2005]. 74pp. Aubry, C.A. 2005. A Study Plan for Genetic Analysis of Bull Trout in Five Recovery Areas in Washington State. U.S. Fish and Wildlife Service Report. 43 p. plus appendices. Banks MA, and Eichert W. 2000. WHICHRUN (version 3.2): A computer program for population assignment of individuals based on multilocus genotype data. JOURNAL OF HEREDITY 91 (1): 87-89. Banks MA, Eichert W, Olsen JB. 2003. Which genetic loci have greater population assignment power? BIOINFORMATICS 19 (11): 1436-1438. Baxter, C.V. 2002. Fish movement and assemblage dynamics in a Pacific Northwest riverscape. Doctoral Dissertation. Oregon State University, Corvallis. BioAnalysts, Inc. 2002. Movement of bull trout within the Mid-Columbia River and tributaries, 2001-2002-Final. Chelan, Douglas, and Grand County Public Utility Districts, Wenatchee, Washington. BioAnalysts, Inc. 2004. Movement of bull trout within the Mid-Columbia River and tributaries, 2001-2004. Chelan, Douglas, and Grand County Public Utility Districts, Wenatchee, Washington. Brown, L. G. 1992. Draft management guide for the bull trout Salvelinus confluentus (Suckley) on the Wenatchee National Forest. Washington Department of Wildlife. Wenatchee, Washington. Cappellini, M. M. J. 2001. Movements of bull trout (Salvelinus confluentus), spring Chinook (Oncorhynchus tshawtscha), and steelhead (Oncorhynchus mykiss) in Icicle Creek, Washington. U. S. Fish and Wildlife Service, Mid-Columbia River Fishery Resource Office, Leavenworth, Washington. 27 p. CCPUD. 1998. Aquatic Species and Habitat Assessment: Wenatchee, Entiat, Methow, and Okanogan Watersheds, Mid-Columbia Mainstem Conservation Plan. Chelan County Public Utilities Department, Wenatchee, WA. Connolly, P.J., I.G. Jezorek, and E.F. Prentice. 2005. Development and use of in-stream PIT-tag detection systems to assess movement behavior of fish in tributaries of the Columbia River Basin, USA. Proceedings of the Measuring Behavior 2005 Conference, Noldus Information Technology, Wageningen, Netherlands, Sep 2005. http://www.noldus.webaxxs.net/mb2005/ Costello, A. B., T. E. Down, S. M. Pollard, C. J. Pacas, and E. B. Taylor. 2003. The influence of history and contemporary stream hydrology on the evolution of genetic diversity within species: An examination of microsatellite DNA variation in bull trout, Salvelinus confluentus (Pisces: Salmonidae). Evolution 57:328-344. DeHaan, P., D. Campton, and W. Ardren. 2005. Genetic Analysis of Hybridization between Bull Trout and Brook Trout in the Upper Malheur River Basin, Oregon. USFWS Report. Dunham, J.B. and B.E. Rieman. 1999. Metapopulation Structure of Bull Trout: Influences of Physical, Biotic, and Geometrical Landscape Characteristics. Ecological Applications 9:642-655. Dunham, J. and B. Rieman. 2001. Sources and Magnitude of Sampling Error in Redd Counts for Bull Trout. North American Journal of Fisheries Management 21:343-352 Dunham, J. and G.L. Chandler. 2001. Models to Predict Suitable Habitat for Juvenile Bull Trout in Washington State. Final Report. U.S. Forest Service, Rocky Mountain Research Stattion, Boise, ID. Report to USFWS, Lacey WA. 74pp. Contact: joe_Polos@fws.gov. Fredenberg, W. 2003. Informal survey of adfluvial bull trout waters of the Columbia River Basin. U.S. Fish and Wildlife Service, Creston, Montana 10 p. Gunckel, S. L., A. R. Hemmingsen, and J. L. Li. 2002. Effect of bull trout and brook trout interactions on foraging habitat, feeding behavior, and growth. Transactions of the American Fisheries Society 131:1119-1130. Kanda N., and F. W. Allendorf. 2001. Genetic population structure of bull trout from the Flathead River Basin as shown by microsatellite and mitochondrial DNA markers. Transactions of the American Fisheries Society 130(1):92-106. Kanda, N., R.F. Leary, and F.W. Allendorf. 2002. Evidence of introgressive hybridization between bull trout and brook trout. Transactions of the American Fisheries society 131: 772-782. Kelly Ringel, B. and J. DeLaVergne. 2001. Wenatchee Basin Bull Trout Radio Telemetry Study 2000 Progress Report. U.S. Fish and Wildlife Service, Leavenworth, Washington. Kelly Ringel, B. M. 1997. Analysis of fish populations in Icicle Creek, Trout Creek, Jack Creek, Peshastin Creek, Ingalls Creek, and Negro Creek, Washington 1994 and 1995. U.S. Fish and Wildlife Service. Mid-Columbia River Fishery Resource Office, Leavenworth, Washington. 49 p. Leary, R. G., F. W. Allendorf, S. H. Forbes. 1993. Conservation genetics of bull trout in the Columbia and Klamath River drainages. Conservation Biology 7(4):856-865. Lohr, S., T. Cummings, W. Fredenberg, S. Duke. 2001. Listing and Recovery Planning for Bull Trout. U.S. Fish and Wildlife Service, Snake River Basin Field Office, Boise, ID. 9 p. Manel, S., O. Gaggiotti, R. S. Waples. 2005. Assignment methods: matching biological questions with appropriate techniques. Trends in Ecology and Evolution, 20:136-142. Marotz, B., B. Hansen, and S. Tralles. 1988. Instream flows needed for successful migration, spawning, and rearing of rainbow and westslope cutthroat trout in selected tributaries of the Kooenai River. Prepared for Bonneville Power Administration by Montana Department of Fish, Wildlife, and Parks, Kalispell, Montana. 181 p. Martin, S. W., J. A. Long, and T. N. Pearsons. 1995. Comparison of survival, gonad development, and growth between rainbow trout with and without surgically implanted dummy radio transmitters. North American Journal of Fisheries Management 15:494-498. Martens, K. and Connolly, P.J. 2005. Lower Methow Tributaries Intensive Effectiveness Monitoring Study, Draft Progress Report to BOR; For the Period: Nov 2004-Oct 2005. USGS, Western Fisheries Research Center, Columbia River Research Laboratory, Cook, WA. Dec.2005.10p Mendel, G., C. Fulton, and R. Weldert. 2003. An investigation into the migratory behavior of bull trout (Salvelinus confluentus) in the Touchet River Basin. Washington Department of Fish and Wildlife, Olympia, Washington. 33 p. McElhany, P., M.H. Rechleshaus, J.J. Ford, T.C. Wainwright, and E.P. Bjorkstedt. 2000. Viable Salmonid Populations and the Recovery of Evolutionarily Significant Unit. U.S. Department of Commerce, NOAA Tech. Memo. NMFS-NWFSC-42, 156 pp. Mongillo, P. 1992. Distribution and Status of Bull Trout/Dolly Varden in Washington State. Bull Trout/Dolly Varden Management and Recovery Plan. Washington Department of Wildlife, Fisheries Managemetn Division Report 92-22, Olympia, WA. Mullan, J. W., K. R. Williams, G. Rhodus, T. W. Hillman, and J. D. McIntyre. 1992. Production and habitat of salmonids in Mid-Columbia River tributary streams. U.S. Fish and Wildlife Service, Report No. FRI/FAO-86-15, Leavenworth, Washington. 68p. Neraas, L., and P. Spruell. 2000. Fragmentation of Riverine Systems: The Origins of Bull Trout (Salvelinus confluentus) At The Base Of Cabinet Gorge Dam, Montana. Submitted to Molecular Ecology. Ogg, L. W., and M. R. Stutsman. 2002. Summary report of the Olympic National Forest bull trout recovery project 1995-2001. U.S. Forest Service, Olympia, Washington. 54 pages. Peterson, J., J. Dunham, P. Howell, R. Thurow, and S. Bonar. 2001. Protocol for Detecting Bull Trout Presence. Report to Western Division of American Fisheries Society. Contact: shelly_spalding@fws.gov. Pillipow, R., and C. Williamson. 2004. Goat River bull trout (Salvelinus confluentus) biotelemetry and spawning assessments 2002-03. BC Journal of Ecosystems and Management Volume 4, Number 2:1-10. http://www.forrex.org/jem/2004/vol4/no2/art6.pdf Pratt, K. L. 1992. A review of bull trout life history. Pages 5-9 in: P.J. Howell and D.V. Buchanan editors, Proceedings of the Gearhart Mountain Bull Trout Workshop, Oregon Chapter of the American Fisheries Society, Corvallis, Oregon. Proebstel, D. S., R. J. Behnke, S. M. Noble. 1998. Identification of salmonid fishes from tributary streams and lakes of the mid-Columbia basin. Joint publication by U.S. Fish and Wildlife Service, Leavenworth, Washington, and World Salmonid Research Institute, Colorado State University, Fort Collins, Colorado. 165 p. Quigley, T. M., and S. J. Arbelide, tech. Eds. 1997. An assessment of ecosystem components in the interior Columbia basin and portions of the Klamath and Great Basins: volume 3. General Technical Report PNW-GTR-405. Rieman, B.E., F.W. Allendorf. 2001. Effective population size and genetic conservation criteria for bull trout. North American Journal of Fisheries Management. 21:756-764 Rieman, B. E., and J. B. Dunham. 2000. Metapopulations and salmonids: a synthesis of life history patterns and empirical observations. Ecology of freshwater fish 9:51-64. Rieman, B. E., and J. D. McIntyre. 1996. Spatial and temporal variability in bull trout redd counts. North American Journal of Fisheries Management 16:132-141.Rieman, B.E., D.C. Lee, and R. Thurow. 1997. Distribution, Status, and Likely Future Trends fo Bull Trout Within the Columbia River and Klamath River Basins. North American Journal of Fisheries Management 17:111-125. Rieman, B. E., and J. D. McIntyre. 1995. Occurrence of bull trout in naturally fragmented habitat patches of varied size. Transactions of the American Fisheries Society 124:285-296. Reiman, B.E., and J.D. McIntyre. 1993. Demographic and Habitat Requirements for Conservation of Bull Trout. General Technical Report INT-302. Ogden, Utah: U.S. Forest Service, Intermountain Research Station, 38 pp. Reiss, K.J. 2003. GENETIC VARIABILITY WITHIN BULL TROUT (Salvelinus confluentus) POPULATIONS IN THE YAKIMA RIVER BASIN. M.S. Thesis. Central Washington University. Rosenberg NA. 2005. Algorithms for selecting informative marker panels for population assignment. JOURNAL OF COMPUTATIONAL BIOLOGY 12 (9): 1183-1201. Salow, T., L. Hostettler. 2004. Movement and mortality patters of adult adfluvial bull trout (Salvelinus confluentus) in the Boise River Basin Idaho. U.S. Bureau of Reclamation. Boise, Idaho. 40 p. Schill, D., R. Thurow, P. Kline. 1994. Seasonal movement and spawning mortality of fluvial bull trout in Rapid River, Idaho. Job performance report IDFG 94-13. 38 p. Scholz, A. T., H. J. McLellan, D. R. Geist, and R. S. Brown. 2005. Investigations of migratory bull trout (Salvelinus confluentus) in relation to fish passage at Albeni Falls Dam. Battelle Pacific Northwest Division, Richland, Washington and Eastern Washington University, Department of Biology, Cheney, Washington. Final report submitted to United States Army Corps of Engineers, Seattle, Washington. Contract DACW68-02-D_0001. Delivery Order EC01. 183 p. Spruell P., B.E. Reiman, K. Knudsen, F.M. Utter, and F.W. Allendorf. 1999. Genetic Population Structure Within Streams: Microsatellite analysis of bull trout populations. Ecology of Freshwater Fish 8:114-121. Spruell P, Hemmingsen AR, Howell PJ, Kanda N and Allendorf FW. 2003. Conservation genetics of bull trout: Geographic distribution of variation at microsatellite loci. Conservation Genetics, 4, 17-29. Summerfelt, R. C., and L. S. Smith. 1990. Anesthesia, surgery, and related techniques. Pages 213-272 in C.B. Schreck and P.B. Moyle, editors. Methods for fish biology. American Fisheries Society, Bethesda, Maryland. Swanberg, T. 1996. The Movement and Habitat Use of Fluvial Bull Trout in the Upper Clark Fork River Drainage. Master’s Thesis, University of Montana, Missoula. Thurow, R. F. 1994. Underwater Methods For Study of Salmonids in the Intermountain West. U.S. Department of Agriculture, Forest Service, Intermountain Research Station. General Technical Report INT-GTR-307. Ogden, UT. USFWS 1999 Plants; Determination of Threatened Status for Bull Trout in the Coterminous United States; Final Rule. November 1, 1999. Federal Register 64 (202):58909-58933. USFWS 1998a. Endangered and Threatened Wildlife and Plants; Determination of Threatened Status for the Klamath River and Columbia River Distinct Population Segments of Bull Trout. June 10, 1998. Federal Register 63(111):31647-31674. USFWS 1998b. Bull Trout Interim Conservation Guidance. US Fish and Wildlife Service, Lacey, WA. White paper. 47p. Contact: Shelly_Spalding@fws.gov. USFWS. 2001. Draft Bull Trout Recovery Plan, Chapter One. U. S. Fish and Wildlife Service, Boise, ID. Contact: sam_lohr@fws.gov. Kelly Ringel, B. and J. DeLaVergne. 2001. Wenatchee Basin Bull Trout Radio Telemetry Study 2000 Progress Report. U.S. Fish and Wildlife Service, Leavenworth, Washington. USFWS. 2002. Chapter 1, Introduction. 136 p. In: U.S. Fish and Wildlife Service. Bull Trout (Salvelinus Confluentus) Draft Recovery Plan. Portland, Oregon USFWS. 2002. Upper Columbia Recovery Unit #21&22 , Washington. U.S. Fish and Wildlife Service. Bull Trout (Salvelinus confluentus) Draft Recovery Plan. Portland, Oregon WDFW. 1998. Washington State Salmonid Stock Inventory: Bull Trout/Dolly Varden. Washington Dept. of Fish and Wildlife, Fish Program. Olympia, WA. 437 p. WDFW. 2004. Chiwawa River weir records of bull trout captured. Records received from Rick Stilwater (WDFW). Wenatchee, Washington. WDFW 2005. Tumwater Dam counts of bull trout moving upstream in the fish ladder recorded by video camera of window in the ladder with video operated 24-hr per day and typically March to December. Electronic records received from Mike Tonseth (WDFW) January 24, 2005. Wenatchee, Washington.

I. Key personnel (see resumes following)

Judith A. De La Vergne -	Project manager; will also assist with data collection and

tagging efforts

William Ardren -		USFWS regional geneticist; will conduct some of the

genetics work and provide coordination between other labs

Denise Hawkins -		WDFW research bull trout geneticist; will contract with for 				some of the genetics work

Paul Spruell- 			Research geneticist;  largest bull trout genetics tissue 					dataset and potential contractor

RD Nelle -			USFWS fisheries biologist; will conduct much of the

Radio telemetry work

Patrick Connolly -  		USGS researcher; will conduct much of the pit tagging 					work and assist with tracking fish.

Judith A.  De La Vergne

Resume

Contact:  US Fish and Wildlife, Central Washington Field Office, 215 Melody Lane, Suite 119, Wenatchee, WA 98801Phone:  509-665-3508, ext. 21; Fax: 509-665-3509;

Email: judy_delavergne@fws.gov

Education

BS in Marine Biology, Minor In Chemistry, 1983-1988

Western Washington University, Bellingham, WA

Associates Degree in General studies, 1981-1983

Everett Community College, Everett, WA

Employment

Fish and Wildlife biologist, 1997- Present (FTE)

US Fish & Wildlife Service, Wenatchee, WA

Fish Biologist, 1989-1997 (FTE)

US Forest Service, Leavenworth, WA

Current Responsibilities:

I am employed as a fish and wildlife biologist within the area of the President’s Northwest Forest Plan in Central Washington.  I review both plan and project evaluations for their impacts on the aquatic resource, review and provide input for project development and analysis, conduct wildlife and aquatic monitoring, and implement fisheries surveys. In the past I reviewed assessments developed for section 7 consultations and Section 10 permits. With assistance from the Leavenworth Fish and Wildlife Service Fisheries Resource Office, I am currently conducting a radio telemetry project in the Wenatchee basin to determine adult bull trout migratory patterns. I have acquired funding for the Yakima BT Radio Telemetry Interagency agreement with WDFW for the Yakima Telemetry Project.  I assisted in acquiring finding, provided technical expertise for the Entiat and Chelan and Douglas PUD Columbia River BT Telemetry projects.   I am the Team Leader for the Upper Columbia and Yakima Bull Trout Recovery Unit Teams and have provided significant portions of information for the draft recovery plans for the Wenatchee, Yakima, Entiat, and Methow Basins.  I annually conduct bull trout spawning ground surveys on several streams and complete an annual report.  I co-organized the annual Salvelinus Confluentus Curiosity Society Workshop in 2001 and Central Washington Bull Trout Monitoring Meeting in 2004. During the SCCS workshop, I organized five field projects completed by 55 biologists in one day.  I actively coordinate both externally and internally, for the benefit of aquatic species and to reduce cost and effort. CoAuthored the USFWS Bull Trout Science Team document:  Bull Trout Recovery Planning: A review of the science associated with population structure and size. Provide technical help to the bull trout recovery RM&E team.

Relevant Skills

Skilled in data collection, fish identification and biology, fish habitat surveys and identification, aquatic restoration, electro-fishing and snorkeling for population surveys and presence absence surveys, radio telemetry research, surgical implantation of radio tags and aerial tacking, and computer skills to effectively analyze data

Relevant Accomplishments/Job Completions

Coordinated monitoring reports for bull trout redd surveys and snorkel surveys

Developed USFS Watershed analysis documents and Biological Baselines now used in Limiting Factor Analysis and Subbasin and recovery plans

Assisted in the completion of the Bull Trout 5 year review and participate with the USFWS BT to develop a ESA “Take” Tracking database.

Developed Interim and Draft final reports and presentations for the Wenatchee River Bull Trout Telemetry Project

- William R. Ardren

- Resume

- Contact: 		U.S. Fish & Wildlife Service, 1440 Abernathy Creek Road  Longview, WA 98632.

- TEL:  360-425-6072;   FAX:  360-636-1855;   E-mail: William_Ardren@fws.gov

- EDUCATION

Ph.D. (Fisheries Science):  June, 1999.  University of Minnesota, Department of Fisheries, Wildlife and Conservation Biology, St. Paul, MN.

Advisor: Anne Kapuscinski.

B.A. (Biology): May, 1993.  St. John's University, Department of Biology, Collegeville, MN.

- EMPLOYMENT

2004-present:	Regional Fish Geneticist (FTE), USFWS, Abernathy Fish Technology Center, Longview, WA.

2002-2004:  	Molecular Population Geneticist, USFWS, Abernathy Fish Technology Center, Longview, WA.

2001-2002: Post-Doctoral Research Associate, Department of Zoology, Oregon State University, Corvallis OR.

1999-2001: Assistant Professor, Department of Biology, Luther College 700 College Dr., Decorah IA.

- RELEVANT  GRANTS

Avista Power Corp Contract R-20413: $64,700/yr. Genetic and Geographic Origins of Threatened Bull Trout Trapped at Dams in the Clark Fork River, MT. 2003-present.

Burns-Paiute Tribe Contract T-10017: $14,995/yr.  Genetic Analysis of Hybridization between Bull Trout and Brook Trout in the Malheur River, OR. 2003-present.

Bonneville Power Administration project # 2003-063-00: $398,315/yr.  Natural Reproductive Success and Demographic Effects of Hatchery-Origin Steelhead in Abernathy Creek, Washington: Can newly-developed, native broodstocks of steelhead derived from captively-reared parr potentially contribute to recovery of naturally spawning populations? 2003-present.

RELEVANT  PUBLICATIONS / REPORTS

DeHaan, P.D. and W.R. Ardren. 2005. Characterization of 20 highly variable tetranucleotide microsatellite loci for bull trout (Salvelinus confluentus) and cross-amplification in other Salvelinus species. Molecular Ecology Notes 5: 582–585.

Ardren, W.R., P. DeHaan, and D. Campton.  2005. Genetic analyses of bull trout from the Clark Fork River:  A two-phased project to identify region of origin of fish captured below mainstem dams. USFWS Final Report [April 21, 2005]. 74pp.

Ardren, W.R. and A.R. Kapuscinski. 2003. Demographic and genetic estimates of effective population size (Ne) reveals genetic compensation in steelhead trout. Molecular Ecology, 12:35-49.

Jones, A.G. and W.R. Ardren. 2003. Invited Review: Methods of parentage analysis in natural populations. Molecular Ecology 12: 2511-2523.

Denise K. (Hendren) Hawkins

Resume

Contact: phone: (360) 902-2749;  FAX: 360-902-2944;  e-mail: hawkidkh@dfw.wa.gov

Current Employment: 	Washington State Dept. Of Fish and Wildlife, Olympia, WA

#### Fish and Wildlife Biologist-4  (FTE)

EDUCATION

B.S. Biochemistry (1986) University of California, Davis

Ph.D. Fisheries (1997) University of Washington, School of Fisheries

PROFESSIONAL EXPERIENCE

July 2005 – present:  Fish and Wildlife Biologist-4, Washington Department of Fish and Wildlife

March 2004 – July 2005:  Fish and Wildlife Biologist-3, Washington Department of Fish and Wildlife

February 1991 – September 1991:  Research Assistant II, Immunex Corp. Seattle, WA

July 1988 – December 1990: Research Specialist II, Emory University, Atlanta, GA

March 1987 – March 1988: Research Assistant, Wayne State University, Detroit, MI

March 1982 – December 1986: Biomedical Scientist, Lawrence Livermore National Laboratory, CA

SELECTED PUBLICATIONS

Hawkins, D.K. and T.P. Quinn. 1995. Critical swimming velocity and associated morphology of juvenile coastal cutthroat (Oncorhynchus clarki clarki), steelhead (O. mykiss) and their hybrids. Can. J. Fish. Aquat. Sci. 53:1487-1496.

Hawkins, D.K. 1997. The effects of interspecific interactions and hybridization on coastal cutthroat trout. In: Sea-Run Cutthroat Trout: Biology, Management and Future Conservation (eds. Hall, J.D., P. Bisson, and R. Gresswell). pp. 18-19. American Fisheries Society, Corvalis OR.

Hawkins, D.K. 1997. Hybridization between coastal cutthroat trout (Oncorhynchus clarki clarki) and steelhead (O. mykiss). Ph.D. Dissertation, University of Washington, Seattle, WA.

Hawkins, D.K. and C.J. Foote. 1998. Early survival and development of coastal cutthroat trout (Oncorhynchus clarki clarki), steelhead (O. mykiss) and reciprocal hybrids. Can. J. Fish. Aquat. Sci. 55:2097-2104.

Hawkins, D.K. 2004. Microsatellite DNA Analysis of sockeye and kokanee (Oncorhynchus nerka) from Lake Ozette, Washington. WDFW Genetics Laboratory Report. 29p.

Current Responsibilities, Skills and Project Duties

Supervise biologists and scientific technicians working in the WDFW genetics Lab and day-to-day lab operations including scheduling and coordination of projects, work efforts, and instrument use.  Design, lead, and participate in DNA-based studies to address conservation and management concerns for priority species of salmonids.  Consult and interact with the Lab Director regarding lab-wide: troubleshooting needs; implementation of new genetic markers, methodologies, procedures, and data collection and analysis methods; and QA/QC needs and processes.  Previous experience with designing and execution of salmonid interspecific hybridization studies including habitat use, field identification, and genetic identification.  Duties for this project will include cooperative collection and analysis of genetic data in conjunction with USFWS Conservation Genetics Lab, Abernathy Fish Technology Center.

Paul Spruell

Resume

Contact:  University of Montana, Division of Biological Sciences, Wild Trout and Salmonid Gentics Lab, Missoula, MT; Phone: 406-243-5771  ; Fax: 406-243-4184; Email: paul.spruell@umontana.edu

Education:  	Ph.D.  Zoology; Washington State University 1994

B.S. Ecology, Ethology, and Evolution; University of Illinois 1987

M.S. Fisheries and Wildlife; Michigan State University 1989

Current Employment:

Faculty and Researcher (FTE)

University of Montana, Division of Biological Sciences, Wild Trout and Salmonid Genetics Lab

Current Responsibilities

University Faculty: Teaching Genetics and Evolution Courses on the campus of Univ. of  MT

Research Professor:  Work is in collaboration with done in collaboration with Fred Allendorf, Kathy Knudsen, Robb Leary, and Bruce Rieman

Research areas: 1)Working Bruce Rieman working on bull trout in Lake Pend Oreille, Idaho for the past five years.  Researching the primary question of how can small populations persist in very dynamic habitats.  To answer this question we are using various techniques including genetic analysis, mark-recapture population estimates, and demographic modeling.  2) Working in hybridization.  Hybridization among salmonids is relatively common and can be a major conservation issue.  We are currently examining both the spread of invasive aquatic species through local systems and the management implications of these introgressed populations. 3) Working on how different life histories might give rise to different patterns in the distribution of genetic variation across the same landscape.  Examining fishes such as sculpin, bull trout and mountain whitefish from the same system is one approach to address this issue.  We are currently working with my graduate student, Andrew Whiteley, to describe both broad and fine-scale genetic patterns in mountain whitefish. Also working on regional technical teams for bull trout and other salmonids to develop fish management plans and protocols.

Coordination: Presentations and Fisheries meetings and workshops; Working with the USFWS, USFS, UBC and WDFW, to set up a data management system for bull trout tissue samples and genetic information

Relevant Publications

Spruell P, Hemmingsen AR, Howell PJ, Kanda N, Allendorf FW (2003) Conservation genetics of bull trout: geographic distribution of variation at microsatellite loci.  Conservation Genetics 4: 17-29.

Weigel DE, Peterson JT, Spruell P (in press) The distribution of introgressive hybridization between westslope cutthroat trout and rainbow trout in the Clearwater basin, Idaho. Ecological Applications.

Spruell P, Bartron ML, Kanda N, Allendorf FW (2001) Detection of hybrids between bull trout (Salvelinus confluentus) and brook trout (Salvelinus fontinalis) using PCR primers complementary to interspersed nuclear elements.  Copeia 2001: 1093-1099.

Allendorf FW, Leary RF, Spruell P & Wenberg JK (2001) The problem with hybrids: setting conservation guidelines.  Trends in Ecology and Evolution  16: 613-622.

Neraas LP & Spruell P (2001) Fragmentation of riverine systems: the origins of bull trout (Salvelinus confluentus) collected at the base of Cabinet Gorge Dam, Montana.  Molecular Ecology 10: 1153-1164.

Spruell P, Rieman BE, Knudsen KL, Utter FM, Allendorf FW (1999) Genetic population structure within streams: microsatellite analysis of bull trout populations.  Ecology of  Freshwater Fish. 8: 114-121.

Patrick J. Connolly

Resume

Contact: U.S. Geological Survey, Western Fisheries Research Center, Columbia River Research Laboratory, Cook, WA

Education:

School						    Degree and Date Received

Oregon State University, Corvallis		    Ph.D.  Fisheries Science, 1996

University of Idaho, Moscow			    M.S.   Zoology, 1983

Centre College of Kentucky, Danville		    B.S.    Biology, 1977

Current Employment

1997-Present	Lead Research Fish Biologist,.

U.S. Geological Survey, Western Fisheries Research Center, Columbia River Research Laboratory, Cook, WA

Current responsibilities:  Principle Investigator on several research projects including determining life history aspects and limiting factors to production for juvenile steelhead in the Wind River watershed (WA) and determining effectiveness of restoration actions in the Methow watershed (WA).

Past Employment

1994-1997	Consultant to Wind River Restoration Team, WA.

1990-1996	Research Assistant, Oregon State University, Corvallis.

1988-1991	Fish Biologist--Subbasin Planner, Oregon Dept. Fish & Wildlife, Corvallis.

1987-1988	Fish Biologist--Research, Oregon Dept. Fish & Wildlife, Columbia River Research, Clackamas, OR.

1985-1987	Fish Biologist, Beak Consultants Inc., Portland, OR.

1984-1985	Fishery Biologist, U.S. Fish and Wildlife Service, National Fisheries Research Center, Columbia River Field Station, Cook, WA.

1983-1983	Fish Habitat Surveyor, Idaho Transportation Dept., Coeur d’Alene, ID.

Expertise:  My expertise is in stream fish ecology and population dynamics.  I have contributed to numerous studies involving anadromous and resident salmonids as well as non-salmonids of the Pacific Northwest.

Publications and Reports (five most relevant)

Connolly, P.J., I.G. Jezorek, and E.F. Prentice.  2005.  Development and use of in-stream PIT-tag detection systems to assess movement behavior of fish in tributaries of the Columbia River Basin, USA.  Proceedings of the Measuring Behavior 2005 Conference, Noldus Information Technology, Wageningen, Netherlands, Sep 2005. http://www.noldus.webaxxs.net/mb2005/

Gresswell, R.L., and P.J. Connolly.  2005. Geo-referenced database for coastal cutthroat trout Oncorhynchus clarki clarki of Washington and Oregon. U.S. Geological Survey. A web-based product: http://ocid.nacse.org/nbii/cutbib/index.php

Connolly, P.J., and J.H. Petersen.  2003.  Bigger is not always better for overwintering young-of-year steelhead.  Trans. of the American Fisheries Society 131:262-274.

Connolly, P.J., and B. Bair.  2002.  Watershed restoration for anadromous rainbow trout in Washington's Wind River, USA.  Pages 194-208 in Central Fisheries Board of Ireland.  Proceedings of the 13th International Salmonid Habitat Enhancement Workshop.  ISSN 1649-256X, Dublin, Ireland.

Connolly, P.J., and J.D. Hall.  1999.  Biomass of coastal cutthroat trout in unlogged and previously clear-cut basins in the central Coast Range of Oregon.  Trans. of the American Fisheries Society 128:890-899.

R.D. Nelle

Resume

Richard D. (R.D.) Nelle

Contact: USFWS, 7501 Icicle Road, Leavenworth, WA 98826

Tel: 509-548-7573,  E-mail: RD_Nelle@fws.gov

EDUCATION

B.S. Zoology (1987) Southern Illinois University, Carbondale

M.S. Fishery Resources (1999) University of Idaho, Moscow

PROFESSIONAL EXPERIENCE

2002–present:	Fishery Biologist GS-11, U.S. Fish and Wildlife Service, Mid-Columbia River Fishery Recourse Office, Leavenworth, WA

1999–2002:	Fishery Biologist GS-9, U.S. Fish and Wildlife Service, Togiak National Wildlife Refuge, Dillingham, AK

1993–1999:	Fishery Biologist GS-9, USGS Biological Resource Division, Ahsahka, ID

1993–1993:	Fishery Biologist, Washington Department of Fish and Wildlife, Leavenworth, WA

1987–1992:	Fishery Biologist GS-5,GS-7,GS-9, U.S. Fish and Wildlife Service, Columbia River Field Station, Cook, WA

CURRENT RESPONSIBILITIES AND PROJECT DUTIES

Lead of the Native Fish Assessment / Recovery Section of the USFWS Mid-Columbia River Fishery Recourse Office supervising biologist and technicians conducting monitoring and research projects within the Columbia Cascade Province. Principle investigator on several studies including assessment of adult steelhead spawning success in the Entiat River, effectiveness monitoring of restoration actions in the Entiat River, and bull trout life history attributes in Entiat and Methow rivers using radio telemetry.

SELECTED REPORTS

Nelle, R.D. 2002.  Seasonal movement and distribution of rainbow trout in the Togiak River watershed, Togiak National Wildlife Refuge. Togiak National Wildlife Refuge Report, Dillingham, Alaska

Nelle, R.D. 2002.  Life history attributes of rainbow smelt Osmerus mordax dentexfrom the Togiak River, Togiak National Wildlife Refuge, 2002. Togiak National Wildlife Refuge Report, Dillingham, Alaska.

Nelle, R. D. 2002.  Species occurrence and length frequency distribution of fish in six lakes and five streams of the Togiak National Wildlife Refuge, Alaska, 2000-2002. Togiak National Wildlife Refuge Report, Dillingham, Alaska.

Nelle, R. D. 2002.  Collection of rainbow trout Onchorynchus mykiss genetic tissue samples from the Osviak River, Togiak National Wildlife Refuge. Togiak National Wildlife Refuge Report, Dillingham, Alaska.

Nelle, R.D. 1999.  Smallmouth bass predation on juvenile fall chinook in the Hells Canyon Reach of the Snake River, Idaho.  Master’s Thesis. University of Idaho, Moscow